## Cover
MISSOURI DEPARTMENT OF TRANSPORTATION
Standard Inspection and Testing Plan (ITP): |  |  |  |  | Date Version: | April 2021
| Section 200 | Section 300 | Section 400 | Section 500 |  | Section 600 | Section 700
| Section 800 | Section 900 | Help and Instructions |  |  | Print Sec 200-900

## Help and Instructions
Go Back to Front
DIVISION 000:
Spec. |  | Item Description | Parameter or Procedure | Additional Reference |  | Acceptance Criteria
Spec. |  | Where the governing specifications are found.
Item Description |  | Most basic description of the element of work.
Parameter or Procedure |  | Describes which portion of the work item being discussed on this line of the ITP. It is common for a specification or item to have several parameters or procedures.
Additional Reference |  | contains useful information such as other specification sections that may be integral to inspection of the item.
Acceptance Criteria |  | Describes how the requirement is met for that parameter or procedure. These are mostly standardized and match the types in SiteManager.
Minimum Frequency
| Contractor QC |  | MoDOT QA
Contractor QC |  | Under MoDOT quality management, the contractor is responsible for 100% of quality control. The contractor may delegate to subs or suppliers, but must ensure they comply with the project ITP.
MoDOT QA |  | MoDOT will follow the quality assurance scheduled here.
The frequencies listed may be in "word format" such as ONCE PER DAY. When inputted into SiteManager, the frequency may be translated to a "number format" such as 1 per 500cy that roughly represents the "word format". In case of conflict between SiteManager and the ITP frequency, the ITP should govern.
QC Documents
|  | Checklist | Test Record | Misc. | Electronic Process
Checklist |  | Checklists have been developed as an aid for more complex inspection. Be aware that the checklist may not cover all aspects of inspection.
Test Records |  | Every material test taken should generate a test record.
Misc. |  | Miscellaneous documents can cover many different types of deliverables. See the ITP or specifications for more detail.
Electronic Process |  | Indicates that there is a specific process the contractor must comply with to allow MoDOT to collect data electronically. No deviations from this requirement should be allowed without headquarters approval.
The various documents required from QC will be stored in Sharepoint with the exception of ones with an electronic process developed.

## 200
DIVISION 200: Grading and Removals | [10 empty] | Minimum Frequency |  | QC Documents
[11 empty] | Contractor QC | MoDOT QA | Checklist | Test Record | Misc. | CRE2O | GO BACK TO COVER
Spec. |  | Item Description | Parameter or Procedure | Additional Reference |  |  |  |  | Acceptance Criteria | CRE2O Link (if applicable)
Section 201: Clearing and Grubbing
201 | 0.2 | Clearing and Grubbing | Clearances, disposal, and finish | See Checklist - 200A | [5 empty] | NA | 1 per Day |  | ²
Section 202: Removal of Roadways and Buildings
202 |  | Removal of Roadways and Buildings | Construction and Conformance Requirements | See Checklist - 200A | [5 empty] | NA | 1 per Day |  | ²
Section 203: Roadway and Drainage Excavation, Embankment and Compaction
203 | .3 .5 | Borrow Material | Soil Characteristics | Proctor and Plasticity Index |  | AASHTO T99 and T90 |  |  | Testing | CRE20 - 200 | 1 per Soil Type | 1 per Borrow Area |  |  |  | ²
203 | .4.1 | Grade construction requirements |  | See Checklist - 200A | [5 empty] | NA |  |  | ²
203 |  | Placement and compaction of Embankment | Density, Moisture, Thickness, Frozen | See Checklist - 200A |  | Density Test Required |  |  | Testing | CRE20 - 200 | 1 per Lift, per 500', per activity | 1 per Day | ² | ² |  | ² | EPG 203.5
203 |  | Compaction of Cut | Density, Moisture, Thickness, Frozen | See Checklist - 200A |  | Density Test Required |  |  | Testing | CRE20 - 200 | 1 per Lift, per 500', per activity | 1 per Day | ² | ² |  | ²
203 | .5. | Comp of Emb and Treatment of Cut Areas with Moisture & Density | Standard Compaction | AASHTO T99 or TM40 |  |  |  |  | Testing | CRE20 - 200 | 1 per Soil Type | 1 per Project |  | ² |  | ²
203 | .5. | Comp of Emb and Treatment of Cut Areas with Moisture & Density | Moisture Correction Factor | TM 35 | Use with nuclear density |  |  |  | Testing | CRE20 - 200 | 1 per Soil Type | 1 per Project |  | ² |  | ²
203 | .5.2 | Compacting Rubbery Soils | Moisture Control | Class A , LL>40 within 5' of top of finished subgrade shall be compacted at no less than optimum |  |  |  | AASHTO T90 | Testing | CRE20 - 200 | 1 per Day | 1 Per Week |  | ² |  | ²
Section 204: Embankment Monitoring
204 | .10.3 | Embankment Monitoring | Settlement Gauge | Per Contract JSP |  |  |  |  | Visual | N/A | 1 per Day, or as per Contract | 1 per Week |  | ²
204 | .20.3 | Embankment Monitoring | Pore Pressure | Per Contract JSP |  |  |  |  | Visual | N/A | 1 per Day, or as per Contract | 1 per Week |  | ²
Section 205: Modified Subgrade
205 | .2. | Stabilization Material | Gradation | AASHTO T87, T88, T89, and T 90 |  |  | EPG 205.2.2 |  | Testing | N/A | 1 per 5000 Tons, 0 if < 1000 Tons | 1 per Project |  | ²
205 | .2. | Stabilization Material | Liquid Limit and Plasticity Index | AASHTO T89 and T90 |  |  | EPG 205.2.2 |  | Testing | N/A | 1 per Project/ Gradation /Source | 1 per Project |  | ²
205 | .2. | Hydrated Lime | Certification | AASHTO M 216 |  |  |  |  | Certification | N/A | 1 per Load |  |  | ²
205 | .2. | Other Material | Engineer Approval | [5 empty] | Approval of the Engineer prior to use | N/A | 1 per Project/ Source |  |  | ²
205 | .3. | Construction | Application Uniformity | Extends 18" each side of roadway. Proof rolling or testing as required |  |  | See Checklist - 200A |  | Visual | N/A | 1 per Activity | 1 per Day | ²
205 | .3.2 | Compaction - Chemically Stablilzed | Density | Compaction demonstrated by roller equipment |  |  |  |  | Visual as acceptable by Engineer | N/A | 1 per Activity |  |  | ²
205 | .3.2 | Compaction - Geogrid or Geotextile | Density | Subgrade compaction with density and moisture control of disturbed material. |  |  |  |  | Testing of disturbed material | N/A | 1 per Activity |  |  | ²
Section 206: Structure Excavation
206 | .2. | Excavation for Footings and Culvert Floors | Depth and Keyways | See Checklist - 206 |  |  |  |  | Visual | N/A | 1 per Foundation |  | ²
206 | .3.2 | Excavation | Stabilization and Testing | Test Hole and Stabilization |  |  |  |  | Measurement | N/A | 1 per Foundation | 1 per Foundation
206 | .4.6 | Excavation | Footing Drainage | See Checklist - 206 |  |  |  |  | Visual | N/A | 1 per Day |  | ²
206 | .4.7 | Excavation | Cofferdams | See Checklist - 206 |  |  |  |  | Measurement | N/A | 1 per Day |  | ²
206 | .4.8 | Excavation | Temporary Shoring | See Checklist - 206 |  |  |  |  | Measurement | N/A | 1 per Day |  | ²
206 | .4.9 | Excavation | Seal Courses | See Checklist - 206 |  |  |  |  | Measurement | N/A | 1 per Day |  | ²
206 | .4.10, | Backfill | Structure Fill; Footing Backfill | See Checklist - 206 |  |  |  |  | Visual / Testing | N/A | 1 per Lift |  | ²
206 | .4.11. | Porous Backfill | Construction | See Checklist - 206 |  |  |  |  | Visual | N/A | 1 per Lift |  | ²
206 | .4.11.1 | Porous Backfill | Material | Gradation and deleterious |  | Materials and gradation per Sec 1009 |  |  | Testing | CR2E0 - 1000 | I per 2000 Ton, 1 per Project min | 1 per Project |  | ² |  | ²
206 | .4.12 | Flowable Fill | Mix Design | Approved Mix design. |  |  |  | Sec 621 | Document | CR2E0 - 1000 |  |  |  | ² |  | ²
Section 207: Linear Grading
207 | .2.1 | Class 1 and 2 for Mainline | Construction | See Checklist - 200A |  |  |  |  | Measurement | N/A | 1 per 10 Stations, 1 per Area Worked min |  | ²
207 | .2.1 | Class 1 and 2 for Shoulder | Construction | See Checklist - 200A |  |  |  |  | Measurement | N/A | 1 per 10 Stations, per shoulder, 1 per Area Worked min |  | ²
Section 208: Interception Ditch
208 | .2. | Interception Ditch | Construction | See Checklist - 200A |  |  |  |  | Visual | N/A | 1 per Area Worked |  | ²
Section 209: Subgrade Preparation
209 |  | Construction | Grade | See Checklist - 200B |  |  |  |  | Measurement | N/A | 1 per 100' |  | ²
209 |  | Construction | Uniformity, Moisture | See Checklist - 200B |  |  |  |  | Visual / Measurement | N/A | 1 per Day |  | ²
Section 210: Subgrade Compaction
210 | .2.1 | Subgrade Compaction | Construction | See Checklist- 200B |  | Density Test Required |  |  | Testing | CRE20 - 200 | 1 per 1000 Feet of Alternating Lanes. | 1 per Day | ² | ² |  | ²
Section 211: Subgrade Scarifying
211 | .2. | Subgrade Scarifying | Construction | See Checklist - 200B |  | Performed in areas determined by Engineer |  |  | Visual | N/A | 1 per 1000 Feet of Alternating Lanes. |  | ²
Section 212: Subgrading & Shouldering
212 | .2.1. | Subgrading / Shouldering | Construction | See Checklist - 200B |  |  |  |  | Testing | N/A | 1 per Lift, per 500', per activity |  | ²
Section 214: Rock Fill
214 | .2 .3 | Rock Fill | Construction and Materials | See Checklist - 200A |  | Uniformly graded suitable rock |  |  | Visual | N/A | 1 per Lift / Activity | 1 per Day | ² | ²
Section 215: Shaping Slopes
215 | 0.2 | Shaping Slopes | Construction | See Checklist - 200B |  |  |  |  | Visual / Measurement | N/A | 1 per 10 Stations |  | ²
Section 216: Removals for Bridge Structures
216 | .10.2 | Removal | Construction | See Checklist - 216 |  |  |  |  | Visual / measurement | N/A | 1 per Structure |  | ²
Note on A10: meyerm3: needs attention

## 300
DIVISION 300: Bases and Aggregate Surfaces | [10 empty] | Minimum Frequency |  | QC Documents
[11 empty] | Contractor QC | MoDOT QA | Checklist | Test Record | Misc. | CRE2O | GO BACK TO FRONT
Spec. |  | Item Description | Parameter or Procedure | Additional Reference |  |  |  |  | Acceptance Criteria | CRE2O Link (if applicable)
Section 302: Stabilized Permeable Base
302 | .2.1 | Asphalt or Cement Stabilized Base | Material: Gradation & Deleterious | Sec 1009, T11, T27 |  |  |  |  | Testing | NA | 1 per 2000 Ton | 1 per project |  | ²
302 | .2.2 | Asphalt or Cement Stabilized Base | Construction | See Checklist - 300B |  |  |  |  | Visual | NA | 1 per Day / Activity |  | ²
Section 303: Rock Base
303 | .2.2 .2.3 | Rock Base | Material Quality and size. Section Thickness, and Compaction | See Checklist - 300B |  |  | Material report |  | Visual / Measurement | CRE2O - 1000 | 1 per lift, per 500', per active grading spread/4 per day min EPG 203.5 | 1 per 10 QC | ² | ² |  | ²
303 | .3.5 | Surface Material | top 2" Gradation | If RAP, see Sec 1007 |  |  |  |  | Testing | CRE2O - 1000 | 1 per 2000 ton | 1 per 8000 ton |  | ² |  | ²
303 | .3.5 | Surface Material | top 2" PI | [5 empty] | Testing | CRE2O - 1000 | 1 per 10,000 ton | 1 per 40,000 ton |  | ² |  | ²
303 | .3.6 | Final Grade | Construction | See Checklist - 300B |  |  |  |  | Measurement | CRE2O - 200 | 1 per 100'. | 1 per 1000' | ² |  |  | ²
Section 304: Aggregate Base Course
304 | .3.2 | Placing | Subgrade and Measuring lift thickness | See Checklist - 300A |  |  | See Sec 209 |  | Measurement | NA | 1 per 1000 Ton, 1 per Day min | 1 per 4000 ton, 1 per Project min | ²
304 | .3.4 .4.1 | Shaping and Compacting | >4" thickness Density | See Checklist - 300A |  |  | T191 or T310, TM 35, ASTM D6951 (DCP for Type 7 base) |  | Visual / Testing | CRE2O - 1000 | 1 per 1000 Ton, 1 per Day min | 1 per 4000 ton, 1 per Project min | ² | ² |  | ²
304 | .3.4 | Shaping and Compacting on shoulders | <4" thickness Density | See Checklist - 300A |  |  |  |  | Visual | NA | 1 per Day / Activity |  | ²
304 | .4.1 .4.1.3 | Aggregate Base QC/QA | Section Thickness | measurement meets plans |  |  |  |  | Measurement | NA | 1 per 1000 Ton, 1 per Day min. | 1 per 4000 ton, 1 per Project min
304 | .4.1 | Aggregate Base >1000 Tons a Week | Gradation Test & Deleterious Material | T11, T27, & TM71 |  | See Sec 1007. testing is per source. QC retains samples |  |  | Testing | CRE2O - 1000 | 1 per 2000 Ton, 1 per Day min. | 1 per 8000 Ton, 1 per Project min |  | ² |  | ²
304 | .4.1 | Aggregate Base <1000 Tons a Week | Gradation Test & Deleterious Material | T11, T27, & TM71 |  | See Sec 1007. testing is per source. QC retains samples |  |  | Testing | CRE2O - 1000 | 1 per 250 Ton, 1 per Week min. | 1 per 8000 Ton, 1 per Project min |  | ² |  | ²
304 | .4.1 | Aggregate Base | Retain Samples for Gradation Test & Deleterious Material | T11, T27, & TM71 |  | See Sec 1007. testing is per source. |  |  | Testing | NA | NA | 1 per Project min 1 per Week at least 1 per 16,000 Ton
304 | .4.1 | Aggregate Base QC/QA | Plasticity Index | T89 & T90 | See Sec 1007. testing is per source. QC retains samples |  |  |  | Testing | CRE2O - 1000 | 1 per 10000 Ton, 1 per Project min. | 1 per 40,000 Ton, 1 per Project min. |  | ² |  | ²
304 | .4.1 | Aggregate Base QC/QA | Retained Samples for Plasticity Index | T89 & T90 | See Sec 1007. testing is per source. QC retains samples |  |  |  | Testing | NA | NA | 1 per Week at least 1 per 80,000 Tons
304 | .4.2 | Aggregate Base QC/QA | Standard Compaction | T 99, Method C |  | ASTM D6951 (DCP for Type 7 base) |  |  | Testing | CRE2O - 200 | 1 per source or material change | 1 per source or material change |  | ² |  | ²
Section 310: Aggregate Surface
310 | .2. | Aggregate Surface < 500 Tons | Gradation & Deleterious | AASHTO T27, T11, TM71 |  | See Checklist - 300A |  | Spec Reference 1006 | Certification or Visual | CRE2O - 1000 | 1 per activity | 1 per activity |  | ² |  | ²
310 | .2. | Aggregate Surface > 500 Tons | Gradation & Deleterious | AASHTO T27, T11, TM71 |  | See Checklist - 300A |  | Spec Reference 1006 | Testing | CRE2O - 1000 | 1 per 2000 ton, 1 per Project min | 1 per 10000 Ton, 1 per Project min |  | ² |  | ²

## 400
DIVISION 400: Flexible Pavements | [10 empty] | Minimum Frequency |  | QC Documents
[11 empty] | Contractor QC | MoDOT QA | Checklist | Test Record | Misc. | CRE2O | GO BACK TO COVER
Spec. |  | Item Description | Parameter or Procedure | Additional Reference |  |  |  |  | Acceptance Criteria | CRE2O Link (if applicable) | [6 empty] | EPG
Section 401: Bituminous Base and Pavement
401 | .5. .9. | Aggregate Gradation & Deleterious Content Control and %AC | QA Independent Samples | T11, T27, TM 71 |  | Only applies for 200 tons or greater per day. This at the engineer's discretion. |  |  | Testing | N/A | N/A | 1 test per 4 QC tests
401 | .5. .8. .9. | Aggregate Gradation Control | QC and QA Split Samples | T11, T27, TM 71 |  | Split samples within 5% of QC |  |  | Testing | CRE2O - 400 | 1 per 1000 Ton, 1 per Day min | 1 per 5 Days, 1 per Project min |  | ² | 0 | ² | 401.2.4 460.3.15.1
401 | .5. | Deleterious Content Control | QC and QA Split Samples | T11, T27, TM 71 |  | Split samples within 5% of QC |  |  | Testing | CRE2O - 400 | 1 per 5000 tons | 1 per 5 Days, 1 per Project min |  | ² |  | ²
401 | .5. | Binder Content | QC and QA Split Samples | T164, TM54, T287, T308 |  | Asphalt Content |  |  | Testing | CRE2O - 400 | 1 per 1000 Ton, 1 per Day min | 1 per 5 Days, 1 per Project min |  | ² |  | ²
401 | .5 .8 | Recycled Asphalt Material (RAP) | Gradation and AC Content | T27, T164, T308 | Extraction or binder ignition. QC retains split samples |  |  |  | Testing | CRE2O - 400 | 1 per 10,000 tons | 1 per Project |  | ² |  | ² | 401.2.4
401 | .2.1 | Aggregate properties | Plasticity Index and Moisture Susceptibility | T89 and T90, and T283 | Additional testing if above design on fractions >10% passing #30 sieve |  |  |  | Testing | N/A | 1 per mix design | 1 per mix per project |  | ² | 0 |  | 401.4.5
401 | .5.4 | Moisture Control | Moisture Content | T329 | Testing. Same Time as AC Content. Test any time moisture content changes. See EPG 460.3.14.4. |  |  |  | Testing | CRE2O - 400 | 1 at project start up and minimum1 per Week | 1 per Week, 1 per Project min |  | ² |  | ² | 460.3.14.4
401 | .7.3 | Subgrade preparations | Roadway | See checklist - 200B |  | TM20, Sec 209, Sec 407, Sec 408 |  |  | Visual / measurement | N/A | 1 at start of day, 4 per day min | 1 per Day | ² |  | 0 |  | 401.2.6
401 | .8. | Temperature limitations | Mixture Testing | TM20 | Binder and Mix temperatures, see Sect 403.19.3 |  |  |  | Measurement | N/A | 4 per Day | 1 per Project |  |  |  |  | 460.3.8, 1015
401 | .7.8 .8.4. | Pavement Density and thickness | Coring of lifts | Core locations by random #s |  | TM41 / T166 | See Checklist - 401 |  | Testing | CRE2O - 400 | 1 per 500 Tons | 1 per Week, 1 per Project min | ² | ² |  | ² | 401.2.6
401 | .7.6 .8.4 | Pavement Joints | Density | Core locations by random #s |  | TM41 / T166 | See Checklist - 401 |  | Testing | CRE2O - 400 | 1 per Activity | N/A | ² | ² | 0 | ² | 401.2.6
401 | .10. | Surface Tolerance | Smoothness | TM 59, Sec 610 | Test prior to opening. |  | See Checklist - 610 |  | Testing | N/A | N/A | 1 per Activity | ² |  |  |  | .10.
401 | .12. | Pavement Marking | Visibility | TM80, Sec 620 | Test prior to opening. |  | See Checklist - 620 |  | Testing | N/A | N/A | 1 per Activity | ² |  |  |  | 0.1
Section 402: Bituminous Surface Leveling
402 | .2.3 | Recycled Asphalt Material (RAP) | RAP Gradation, AC content & Delt | T27, T164, T308, Sec 1004 |  | extraction, binder ignition |  |  | Testing | CRE2O - 400 | 1 per Day | N/A |  | ² |  | ² | 402.2.3 460.3.11
402 | .5. | Aggregate gradation and deleterious control | QC and QA Split Samples | T11, T27 & TM 71, Sec 1004.2 |  |  | Refer to 402 JSP 2.2 |  | Testing | CRE2O - 400 | 1 per Day | 1 per 10000 tons |  | ² | 0 | ² | 402.2.4
402 | .5. | Aggregate gradation and deleterious control | QA Independent Samples | T11, T27 & TM 71, Sec 1004.2 |  |  | Refer to 402 JSP 2.2 |  | Testing | N/A | N/A | 1 per 10000 tons
402 | .5. | Aggregate properties | Plasticity Index and TSR | T89 and T90, and T283 |  | Additional testing if above design on fractions >10% passing #30 sieve |  |  | Testing | N/A | 1 per mix | 1 per mix per project |  | ² | 0 |  | 402.2.2
402 | .5. | % Asphalt Content (Binder) | Mixture AC Content | Determine Using Oil and Plant Tickets |  |  | Refer to 402 JSP 2.3 |  | Measurement | N/A | 1 per activity | 1 per 10000 tons |  | ²
402 | .5. | % Asphalt Content (Binder) > 5000 tons | Asphalt QA Verification | T164, TM54, T287, T308 |  |  | calculation or testing |  | Testing | N/A | N/A | 1 per 10000 tons
402 | .7. | Moisture Control > 100 Tons | Moisture Content | T329 |  | Refer to 402 JSP 2.5 |  |  | Testing | CRE2O - 400 | 1 per Day | 1 per 5 days, 1 per project min |  | ² |  | ² | 402.2.6 460.3.14.4
402 |  | Plant Temperature | Mixture Testing | TM20 |  | Binder and Mix temperatures |  |  | measurement | N/A | 4 per Day | 1 per Project |  |  |  |  | 460.3.8, 1015
402 | 0.10. | Construction | Preparations, Hauling, Spreading, Compaction. | See Checklist - 402 |  |  |  |  | Visual / Measurement | N/A | 1 per Activity/Day | N/A | ²
Section 403: Asphaltic Concrete Pavement
403 | .5.1 .19.3. | Gradation and Deleterious Content Control | QC and QA Split Samples | T 27 & T 11 | QA Independent Samples 1 per 4 Sublots |  |  |  | Testing | CRE2O - 403 | 1 per 2 Sublots | 1 per 5 Days, 1 per Project min. |  | ² |  | ² | 403.1.5
403 | .5.2 .15.4 .19.3 | Mat Density | Pavement Testing | T 166 |  | By Random # |  |  | Testing | CRE2O - 403 | 1 per Sublot | 1 per 4 Sublots |  | ² | 0 | ² | 403.1.5
403 | .5.3 .19.3 | Mixture Testing | Asphalt content | AASHTO T 164, TM 54, T 287, T 308 |  |  |  |  | Testing | CRE2O - 403 | 1 per Sublot | 1 per 4 Sublots |  | ² | 0 | ² | 403.1.5
403 | .5.4 .19.3 | Mixture Testing | Voids in Min Aggr | VMA |  | T 312 and R 35 |  |  | Testing | CRE2O - 403 | 1 per Sublot | 1 per 4 Sublots |  | ² | 0 | ² | 403.1.5
403 | .5.5 .19.3 | Mixture Testing | Air Voids | Va |  | T 312 and R 35 |  |  | Testing | CRE2O - 403 | 1 per Sublot | 1 per 4 Sublots |  | ² | 0 | ² | 403.1.5
403 | .5.6. .19.3 | Mixture Testing | Tensile Strength Ratio | TSR of the mixture |  | T 283 |  |  | Testing | CRE2O - 403.19.3 | 1 per 10,000 Ton | 1 per 50,000 Tons, 1 per Project min |  | ² | 0 | ² | 403.1.5
403 | .5.7. .19.3 | Mixture Testing | Aggregate properties | FAA, CAA, clay content, and thin and elongated particles |  |  | AASHTO T304, ASTM D5821, AASHTO T176 & ASTM D 4791 |  | Testing | CRE2O - 403.19.3 | 1 per 10,000 Ton | 1 per Project |  | ² | 0 | ² | 403.1.5
403 | .5.9. | Mixture Testing | Moisture Control | Moisture Content |  | T329 Testing. Same time as AC content, See EPG 460.3.14.4 |  |  | Testing | CRE2O - 403 | start up and 1 per Week or if moisture changes | 1 per Week, 1 per Project min |  | ² |  | ² | 403.1.5 460.3.14.4
403 | .12. | Surface Prep | Tack application and Weather Limitations | See Checklist - 403 |  | Prior to Placement |  |  | Visual / Measurement | N/A | 1 per Day | N/A | ² |  |  |  | 403.1.12
403 | .15. | Pavement Density | Coring of lifts | Core locations by random #s |  | TM41 / T166 | See Checklist - 403 |  | Measurement | N/A | 1 per Sublot | 1 per 4 Sublots | ² |  |  |  | 403.1.15
403 | .19.3 | Plant Temperature | Mixture Testing | TM20 | Binder and Mix temperatures |  | See Checklist - 403 |  | Measurement | N/A | 1 per Sublot | 1 per Day | ² |  | 0
403 | .16.1. .19.3 | Pavement Testing | Unconfined Joints | T 166 |  | By Random # |  |  | Testing | CRE2O - 403 | 1 per Sublot | 1 per 4 Sublots |  | ² | 0 | ² | 403.1.16
403 | .19.3 | Mixture Testing | AC content of RAP | AASHTO T 164 |  |  |  |  | Testing | CRE2O - 403 | 1 per Lot | 1 per Project |  | ² | 0 | ²
403 | .19.3 | Mixture Testing | Voids Filled with Asphalt | VFA |  | T 312 and R 35 |  |  | Testing | CRE2O - 403 | 1 per sublot | 1 per 4 Sublots |  | ² | 0 | ²
403 | .19.3 | Mixture Testing | Rice Test - Gmm | T 209 | Absorption > than 2.0 % run a Dry-back test |  |  |  | Testing | CRE2O - 403 | 1 per sublot | 1 per 4 Sublots |  | ² | 0 | ² | 403.1.19
403 | .20. | Pavement Testing | Straightedging | 1/8" within 10' |  | See Checklist - 610 |  |  | Visual | N/A | prior to opening | verify QC | ²
403 | .22.4.1 | Lift Thickness | Average thickness of Density Cores | See Checklist - 403 |  |  | T148 |  | Measurement | N/A | 1 per Lot | 1 per Lot | ²
403 | .22.4.1 | Full Depth Pavement Thickness | Roadway | See Checklist - 403 |  |  | T148 |  | Measurement | N/A | 1 core per 1000' | verify QC 1 per 4 Sublot | ²
Section 407: Tack Coat
407 | .2. | Material |  | Emulsified Asphalt |  |  |  | Sec 1015 | Certification | N/A | Submit bill of lading for each delivery | Certification review per delivery and report |  | ² | 0 |  | 407.1.1
407 | .4.1. | Construction | Surface Prep, Application | [5 empty] | Visual | N/A | 1 per activity | N/A |  |  |  |  | 407.1.4
Section 408: Prime Coat
408 | .2. | Material |  | Type RC and MC Liquid Asphalt |  |  |  | Sec 1015 | Certification | N/A | Submit bill of lading for each delivery | Certification review per delivery and report |  | ² | 0 |  | 408.1.2
408 | .4.1. | Construction | Surface Prep, Application | [5 empty] | Visual | N/A |  | N/A |  |  |  |  | 408.1.4
Section 409: Seal Coat
409 | .2. | Material | Aggregate gradation and deleterious control | T11, T27 & TM 71 |  |  | Sec 1003 |  | Documentation | CRE2O - 1000 | 1 per activity | 1 per job |  | ² |  | ² | 409.2.2
409 | .2.2 | Material | Asphalt Binder | ASTM D5, AASHTO T301 |  |  |  |  | Certification | N/A | Submit bill of lading for each delivery | Certification review per delivery and report |  | ²
409 | .2.3, .5.3.2 | Material | Pre-coating | T164, TM54, T287, T308 |  | Sec 1015 |  |  | Testing / Certification | N/A | 1 per activity | 1 per job |  | ²
409 | .3, .4, .5 | Construction | Mix, Equipment, and Weather | See Checklist - 409 |  | Per Mix Design |  |  | Visual | N/A | 1 per Day | N/A | ² |  |  |  | 3.2
Section 413: Surface Treatment
413 | .10.2.1 | Microsurfacing Grade A | Aggregate Gradation Content Control | T 27 & T 11 | Provide Documentation prior to construction including job mix formula |  |  |  | Documentation | N/A | 1 per Day | 1 per Activity |  | ² |  |  | 413.1 413.3
413 | .10.2.1 .20.2 | Microsurfacing Grade B or C and Scrub Seals | Aggregate Gradation Content Control | T 27 & T 11 | Provide Documentation prior to construction including job mix formula |  |  |  | Documentation | N/A | 1 per Activity | 1 per Activity |  | ² |  |  | 413.1 413.3
413 | .10 .20 | Microsurfacing and Scrub Seals | Equipment and Test Review | See Checklist - 413D |  | See Checklist - 413G |  |  | Visual | N/A | 1 per mix | N/A | ² |  |  |  | 413.1
413 | .10.5, .20.4 | Microsurfacing and Scrub Seals | Surface conditions ,weather limits and roadway prep. | See Checklist - 413D |  | See Checklist - 413G |  |  | Visual | N/A | 1 per day | N/A | ² |  |  |  | 413.2
413 |  | Microsurfacing and Scrub Seals | Material - Emulsified Asphalt | Refer to Section 1015.3.1 |  |  |  |  | Certification | N/A | Submit bill of lading for each delivery | Certification review per delivery and report |  | ²
413 | .30.4.2, .30.6.1.2 | UBAWS | Aggregate Gradation and Deleterious QC and QA Split Samples | T 27, T11, and TM 71 | Sec 413.30.6, 413.30.7 |  |  |  | Testing | CRE2O - 400 | 1 per 600 Ton | 1 per week |  | ² |  | ² | 413.3.1
413 | .30.2. | UBAWS | Aggregate Gradation Content Control QA Independent Samples | T 27, T11 and TM71 | Sec 413.30.6, 413.30.7 |  |  |  | Testing | CRE2O - 400 | N/A | 1 per Day |  | ² |  | ²
413 | .30.5.1 | UBAWS | Weather limitations and Surface Condition and mix temperature | See Checklist - 413H |  |  |  |  | Visual / Measurement | N/A | 1 per Day | N/A | ²
413 | .30.5.4 | UBAWS | Membrane Application Rate | See Checklist - 413H |  |  | Polymer Modified Sec 1015 |  | Measurement | N/A | 1 per Day | 1 per Week | ² | ² |  |  | 413.3.3
413 | .30.6.1.2 | UBAWS | Asphalt content QC and QA Split Samples | AASHTO T 287, T 308 |  |  |  |  | Testing | CRE2O - 400 | 1 per 600 Ton | 1 per week |  | ² |  | ²
413 | .30.6.1.2 | UBAWS | Asphalt content QA Independent Samples | AASHTO T 287, T 308 |  |  |  |  | Testing | N/A | N/A | 1 per Day |  | ²
413 | .40.2 | Fog Sealing | Emulsified Asphalt | Sec 1015 | SS-1, SS-1H, CSS-1, CSS-1H |  |  |  | Certification | N/A | Submit bill of lading for each delivery | Certification review per delivery and report |  | ² |  |  | 413.4
413 | .40.4 | Fog Sealing | Surface Preparation and tack application, | See Checklist - 413C |  |  |  |  | Visual / Documentation | N/A | 1 per activity | N/A | ² |  |  |  | 413.4
413 | .50 .60 .70 .80 | Crack Sealing and Crack Filling | Material | M 324, Sec 1057, Sec 1015 |  |  |  |  | PAL / Certification | N/A | 1 per shipment | 1 per Project |  | ² |  |  | 413.5
413 | .50 .60 .70 .80 | Crack Sealing and Crack Filling | Surface Preparation and weather limitations | See Checklist - 413A | See Checklist - 413B | See Checklist - 413E | See Checklist - 413F |  | Visual | N/A | 1 per Day | N/A | ²

## 500
DIVISION 500: Rigid Pavements | [9 empty] | Minimum Frequency |  | QC Documents |  |  |  | QC/QA Only Contracts
[10 empty] | Contractor QC | MoDOT QA | Checklist | Test Record | Misc. | CRE2O |  | GO BACK TO COVER
Spec. |  | Item Description | Parameter or Procedure | Additional Reference |  |  |  | Acceptance Criteria | CRE2O Link (if applicable)
Section 501: Concrete
501 | .2.1 | Aggregate | QC and QA Split samples Gradations, Deleterious, and Absorptions | T27 and T11, TM 71, T85 |  | Sec 1005 |  | Testing | CRE2O - 1000 | 1 per 500 CY | 1 per 2500 CY, 1 per project min |  | ² |  | ² | ²
501 | .2.1 | Aggregate >500 cy | QA Independent samples Gradations, Deleterious, and Absorptions | T27 and T11, TM 71, T85 |  | Sec 1005 |  | Testing | NA | na | 1 per Project |  | ² |  |  | ²
501 | .2.1 | Aggregate | Thin or Elongated Pieces | ASTM D4791 |  |  |  | Testing | NA | 1 per source/project | 1 per source/year |  | ²
501 | .3.8 .4. .5. | Consistency - Structures | Compressive Strength Requirement, Slump and Air | T22, T119, T152, |  |  |  | Testing | CRE2O - 500 | 1 from first truckload and each 100 CY after - Field Cure | 1 per 500 CY - Field Cure |  | ² |  | ² | ²
501 | .3.8 | Mix Design Verification | 28 day Cured Cylinders | T22, T23 |  |  |  | Testing | NA | N/A | 1 from first truckload and each 500 CY - Standard Cure
501 | .6.3 | Concrete Plant | Calibrations | Calibrated and Certified Annually |  |  |  | Document | NA | 1 per Year | N/A | ²
501 | .6.3 | Concrete Plant | Verifications | Verify |  |  |  | Document | NA | 1 per year (six months after calibration) | N/A | ²
501 | .6.3 | Concrete Plant | Mixing and Delivery | See Checklist - 501 |  |  |  | Measurement / Check | NA | 1 per MoDOT production day | 1 per 30 days and minimum 1 per project | ²
501 | .8.2 | Concrete Plant | Uniformity Testing | See Checklist - 501 |  |  |  | Testing | NA | 1 per Year | N/A | ² |  | ²
Section 502: Concrete Base and Pavement
502 | .4. | Construction | Surface Preparation, Placing and Finishing | See Checklist - 502 |  |  |  | Visual / Measurement | NA | 1 per Day |  | ²
502 | .5. .6. .7. .9. | Construction | Joints, Curing, Formwork, Opening to Traffic | See Checklist - 502 |  |  |  | Visual | NA | 1 per activity |  | ² | ²
502 | .8. | Construction | Surface Smoothness | See Checklist - 610 |  | Sec 610 |  | Documentation | NA | 1 per Project | 1 per Project | ²
502 | .10.2 .10.3.1 | Placement | 28 day Cores for Thickness and Strength | T24, T22, T231, T148 |  |  |  | Testing | CRE2O - 500 | 1 per Sublot | 1 per Lot | ² | ² |  | ² | ²
502 | .11.2.1.1 | Material | QC and QA Split Samples- Aggregate Gradations | T27, T11 |  |  |  | Testing | CRE2O - 1000 | 1 per week | 10% of retained samples |  | ² |  | ² | ²
502 | .11.2.1.1 | Material | QA Independent Samples- Aggregate Gradations | T27, T11 |  |  |  | Testing | NA | N/A | 1 per Project |  | ² |  |  | ²
502 | .11.2.1.2 | Materials | QC and QA Split Samples-Aggregate Deleterious | TM71 |  |  |  | Testing | CRE2O - 1000 | 1 per 7,500 SQ YDS, 1 per Day min | 10% of retained samples |  | ² |  | ² | ²
502 | .11.2.1.2 | Materials | QA Independent Samples-Aggregate Deleterious | TM71 |  |  |  | Testing | NA | N/A | 1 per week |  | ² |  |  | ²
502 | .11.2.1.3 | Materials | QC and QA Split Samples-Coarse Aggregate Absorptions | Absorption of Coarse Aggregate |  |  | T85 | Testing | CRE2O - 1000 | 1 per 2000 CY | 20% of retained samples |  | ² |  | ² | ²
502 | .11.2.1.3 | Materials | QA Independent Samples - Coarse Aggregate Absorptions | Absorption of Coarse Aggregate |  |  | T85 | Testing | NA | N/A | 1 per 10,000 CY |  | ² |  |  | ²
502 | .11.2.1.4 | Materials | QC and QA Split Samples - Coarse Aggregate Thin and Elongated | ASTM D4791 |  |  | + 3/4" | Testing | CRE2O - 1000 | 1 per 10,000 CY | 20% of retained samples |  | ² |  | ² | ²
502 | .11.2.1.4 | Materials | QA Independent Samples - Coarse Aggregate Thin and Elongated | ASTM D4791 |  |  | + 3/4" | Testing | NA | N/A | 1 per Project |  | ² |  |  | ²
502 | .11.2. .11.3. | Concrete Consistency | Slump | T119 |  |  |  | Testing | CRE2O - 500 | 1 from first truckload and 1 per 500 CY thereafter, 1 per day minimum | 1 per Day | ² | ² |  | ² | ²
502 | .11.2., .11.3. | Concrete Consistency | Air Content | T152 |  | By Random # |  | Testing | CRE2O- 500 | 1 from first truckload and 1 per 500 CY thereafter, 1 per day minimum | 1 per Day | ² | ² |  | ² | ²
502 | .11.4 | Placement < 8" | Pavement Thickness | stick readings |  | random location |  | Measurement | NA | 1 per 7500 SY | 1 per 30,000 SY |  | ²
502 | .15.5 | Small Quantities | 28 day Cores/Cylinders | T22 |  |  |  | Testing | NA | 1 per 2000 SY | 1 per Project |  | ²
Section 503: Approach Slab
503 | .2. | Material | Concrete | Paving or B1 concrete |  | Sec 501 or Sec 502 |  | Testing | NA | Sec 501 | Sec 501 |  | ² |  |  | ²
503 | 0.2 | Material | Concrete | Paving or B1 concrete Sec 501 or 502 |  |  |  | Testing | NA | Sec 501 | Sec 501 |  | ² |  |  | ²
503 | .3. | Material | Aggregate Base | density and material |  |  | 1007 | Testing/ Visual | NA | Sec 304 | Sec 304 |  | ²
503 | .3. | Construction | Placement | See Checklist - 503 504 | Sec 502, Sec 703, Sec 706, Sec 1055 |  |  | Visual | NA | 1 per activity |  | ²
Section 504: Concrete Approach Pavement
504 | .2. | Material | Concrete | Paving or B1 concrete |  | Sec 501 or Sec 502 |  | Testing | NA | Sec 501 | Sec 501 |  | ² |  |  | ²
504 | .3. | Material | Aggregate Base | density and material |  | Sec 1007 |  | Testing/ Visual | NA | Sec 304 | Sec 304 |  | ²
504 | .3. | Construction | Placement | See Checklist - 503 504 | Sec 304, Sec 503, Sec 609 |  |  | Visual | NA | 1 per activity |  | ²
Section 505: Bridge Deck Concrete Wearing Surface
505 | .10, .20, .30., .40. | Material | Concrete Mixture and Components | Sec 501 |  |  |  | 1005 | NA | Sec 501 | Sec 501 |  | ² |  |  | ²
505 | .10, .20, .30., .40. | Consistency | Slump, Air Content, Unit Weight | ASSHTO T119 T152 and T121 |  |  |  | Testing | NA | 1 per 2 Hours | 1 per day | ² | ² |  |  | ²
505 | .10.4. | Mix Design Verification | 28 day cured Cylinders | T22,T23 |  | 28 Day Cure |  | Testing | NA | 1 per day / Mix | 1 per project |  | ² |  |  | ²
505 | .10.4. | Construction | Compressive Strength Requirement | T22,T23 |  | Field Cure |  | Testing | NA | per engineer | 1 per project |  | ² |  |  | ²
505 | .10, .20, .30., .40. | In Place Density | Density | MODOT TM 36 |  |  |  | Testing | NA | 1 per 100 SY, 3 per Continuous Pour Min | 1 per activity |  | ² |  |  | ²
505 | .10, .20, .30., .40. | Construction | Placement | See Checklist - 703A |  |  |  | Visual / Measurement | NA | 1 per pour |  | ²
Section 506: Concrete Overlays for Pavements
506 | .20. .30. | Materials | Concrete Mixture and Components | Sec 502 |  |  |  | Testing | NA | Sec 502 | Sec 502 |  | ² |  |  | ²
506 | .20. .30. | Construction | Placement, Joints, Curing, Formwork, Smoothness, and Opening to Traffic | See Checklist - 506 |  |  |  | Visual / Measurement | NA | Sec 502 |  | ²
506 | .20. .30. | Construction | Surface Smoothness | See Checklist - 610 |  | Sec 610 |  | Documentation | NA | 1 per Project | 1 per Project | ²
506 | .10. | Placement | Cores for Thickness and Strength | See Checklist - 506 |  |  |  | Testing | NA | Sec 502 | Sec 502 | ² | ²
506 | .11.2. .11.3. | Concrete Consistency | Air and Slump | See Checklist - 506 |  |  |  | Testing | NA | Sec 502 | Sec 502 | ² | ² |  |  | ²
506 | .20. | Placement | Interlayer | See Checklist - 506 |  |  |  | Visual | NA | 1 per activity |  | ²
506 | .20. | Construction | Profile | Establish field profile |  |  |  | Document | NA | 1 per project |  |  |  | ²
Section 507: Strength of Concrete using Maturity Method
507 | .1. | Construction | Profile | Provide necessary information if used |  |  |  | Document | NA | 1 per project |  |  |  | ²

## 600
DIVISION 600: Incidental Construction | [9 empty] | Minimum Frequency |  | QC Documents
[10 empty] | Contractor QC | MoDOT QA | Checklist | Test Record | Misc. | CRE2O | GO BACK TO COVER
Spec. |  | Item Description | Parameter or Procedure | Additional Reference |  |  |  | Acceptance Criteria | CRE2O Link (if applicable)
Section 602: Markers
602 | .3. | Construction |  | See Checklist - 602 |  | Posts driven as per Section 903 |  | Visual | NA | 1 per Day /Installation |  | ²
Section 603: Water Line Installation
603 | .3. | Construction Requirements |  | See Checklist - 603 (if MoDOT inspected) | Backfill per Sec 726, Concrete per Sec 501 |  |  | Document | NA | 1 per Activity |  | ²
Section 604: Miscellaneous Drainage
604 | .10.2 .40.2 | Materials | Concrete for CIP | Class B, Sec 501 and Sec 703. |  |  |  | Visual/ Testing | CRE2O - 500 | 1 per Day /Activity | 1 per Activity |  | ² |  | ²
604 | .10.2, .30.3 | Material | Concrete Aggregates | Sec 501 |  |  |  | Testing | CRE2O - 1000 | See 501 | See 501 |  | ² |  | ²
604 | .10.3 | Construction | Misc Drainage Items and Methods | See Checklist - 604 | Sec 206, 501, 706, 726, 1030, |  |  | Visual | NA | 1 per Day /Activity | 1 per project | ²
604 | .60.3 | Construction Slotted Drains | Orientation and Bedding | See Checklist - 604 |  |  | Sec 609.10, 726, 1051 | Visual / Testing | NA | 1 per Day /Activity |  | ²
Section 605: Underdrainage
605 | .2. | Materials | Aggregates | Sec 1009 |  | Porous Backfill T27 |  | Testing | CRE2O - 1000 | 1 per Activity | 1 per project |  | ²
605 | .10-.70.2. | Construction | Misc Underdrainage | See Checklist - 605 | See Sec 203, 501, 605.6, 1013 and Standard Drawings 605.x |  |  | Visual | NA | 1 per Activity |  | ²
605 | .60.2 | Material | Concrete Aggregates | Sec 501 |  |  |  | Testing | CRE2O - 1000 | See 501 | See 501 |  | ² |  | ²
605 | .60.2 | materials | Concrete for CIP | Sec 501 |  |  |  | Testing | CRE2O - 500 | 1 per Activity | 1 per project |  | ² |  | ²
Section 606: Guardrail, Crashworthy End Terminals, One-Strand Access Restraint Cable and Three-Strand Guard Cable
606 | .2. | Materials | Concrete | Sec 501 | Concrete place per 703 and Cold Weather Plan |  |  | Testing | CRE2O - 500 | 1 per Installation | 1 per Installation |  | ² |  | ²
606 | .3.1 | Construction | Guardrail, End Treatments, Cables | See Checklist - 606 | Sec 502, 703, 1080, 1065, and Standard Drawings 606.x |  |  | Visual | NA | 1 per Day /Installation |  | ²
606 | .3.1.2 | Construction | Slope Requirements | See Checklist - 606 |  |  |  | Measurement | NA | 1 per Day /Installation |  | ²
Section 607: Fencing
607 | .10.2 .20.2. | Materials | Concrete | Concrete class B or Commercial per 501 |  |  |  | Testing/ Certification | CRE2O - 500 | 1 per Activity | 1 per project |  | ² |  | ²
607 | .10.3 | Material | Concrete Aggregates | Sec 501 |  |  |  | Testing | CRE2O - 1000 | See 501 | See 501 |  | ² |  | ²
607 | .10.3. .20.3. | Construction | Chain Link and Woven Wire Fencing | See Checklist - 607 | See Sec 501, 903.3.1.2 and Standard Drawing 607.x |  |  | Visual | NA | 1 per Day /Installation |  | ²
Section 608: Concrete Median, Median Strip, Sidewalk, Curb Ramps, Steps and Paved Approaches
608 | .2. | Materials | Concrete | Sec 501-Concrete place per 703 and Cold Weather Plan | T22 Testing for Compressive Strength |  |  | Testing | CRE2O - 500 | 1 per 100 CY | 1 per 500 CY |  | ² |  | ²
[5 empty] | All other 501 tests |  |  | Testing | CRE2O - 500 | See 501 | See 501 |  | ² |  | ²
608 | .2. | Material | Concrete Aggregates | Sec 501 |  |  |  | Testing | CRE2O - 1000 | See 501 | See 501 |  | ² |  | ²
608 | .3.1 | Construction | Misc | See Checklist - 608 | Sec 209, 502, 703, 706, and Standard Drawings 608.x |  |  | Visual | NA | 1 per Day /Installation |  | ²
Section 609: Paved Drainage
609 | .10.2 | Materials | Concrete | Sec 501 | Class B or Pavement Concrete per 501 |  |  | Testing | CRE2O - 500 | 1 per Day | 1 per Activity |  | ² |  | ²
610 | .10.2 | Material | Concrete Aggregates | Sec 501 |  |  |  | Testing | CRE2O - 1000 | See 501 | See 501 |  | ² |  | ²
609 | .30.2, .30.3 | Materials | Asphalt Curbs | Sec 1002, 1015, 401, 403 |  |  |  | Testing | CRE2O - 400 | 1 per Day /Installation | 1 per project |  | ² |  | ²
CRE2O - 403
609 | .10.3.1, .10.3.4 | Construction | Curbs, Gutters, and Drain Basins Rock Ditch Liner | See Checklist - 609 | Sec 401, 403, 502, 604, 703, 725, Standard Drawing 609.x |  |  | Visual | NA | 1 per Day /Installation |  | ²
609 | .70.2, .70.3 | Materials | Bedding and Rock Liner | Sec 611 |  |  |  | Visual | NA | 1 per Activity | 1 per project |  | ²
Section 610: Pavement Smoothness
610 | .10.1 | Description | Pavement Smoothness | See Checklist - 610 | Sec 401, 403, 502, 506, |  |  | Testing | NA | 1 per Day /Installation |  | ²
610 | .0.2 | Materials | Pavement Smoothness | AASHTO M 328 | MODOT TM-59 |  |  | Testing | NA | 1 per Day /Installation | 10% of QC |  |  | ²
610 | .0.4 | Construction | Pavement Smoothness | See Checklist - 610 | Sec 610 |  |  | Testing | NA | 1 per Day /Installation |  | ²
Section 611: Embankment Protection
611 | .30.2 | Materials | Rock |  |  |  |  | Visual | NA | 1 per day | 1 per Activity |  | ²
611 | .30.3 | Construction | Rock Blanket, Revetment, Concrete Slope Protection | See Checklist - 611 | Sec 501, 703, Standard Drawing 611.x |  |  | Visual | NA | 1 per Day /Activity |  | ²
611 | .60.2 | Material | Concrete Aggregates | Sec 501 |  |  |  | Testing | CRE2O - 1000 | See 501 | See 501 |  | ² |  | ²
611 | .60.2. | Materials | Concrete for Slope Projection | Class B per 501 |  |  | Sec 703 | Testing / Certification | CRE2O - 500 | 1 per Activity | 1 per project |  | ² |  | ²
611 | .70.3 | Construction | Gabion Wall | See Checklist - 611 |  | per plan |  | Visual | NA | 1 per Day /Activity |  | ²
611 | .70.2 | Materials | Rock for Gabion Baskets | per plan |  |  |  | Visual | NA | 1 per Day /Activity | 1 per project |  | ²
Section 612: Impact Attenuators
612 | .2.2, .2.3 | Materials | Sand Barrels, TMAs | FS-612 Table 1 of Prequalified List, 1005, 1042, 1063 | Per MUTCD with manufacturer's certification NCHRP 350 |  |  | Certification | NA | 1 per Shipment | 1 per project |  | ²
612 | .4. | Construction | Sand Barrels | See Checklist - 612 |  | Standard Drawing 612.x |  | Visual | NA | 1 per Day |  | ²
Section 613: Pavement Repairs
613 | .0.2 | Materials | Concrete | See Checklist - 613E | Sec. 502 |  |  | Testing / Certification | CRE2O - 500 | 1 per Day /Installation | 1 per project |  | ² |  | ²
613 | .10.2 | Material | Concrete Aggregates | Sec 501 |  |  |  | Testing | CRE2O - 1000 | See 501 | See 501 |  | ² |  | ²
613 | .3 .10.2 | Construction | Full Depth Repairs | See Checklist - 613D | Sec 202, 210, 304, 502, 622, 623, Standard Drawing 613.x |  |  | Visual | NA | 1 per day |  | ²
613 | .3. .20,2 .30.2 .35.2 | Construction | Partial Depth Pavement Repair Class A, B, and C | See Checklist - 613A | Sec 202, 210, 304, 502, 622, 623, Standard Drawing 613.x |  |  | Visual | NA | 1 per day |  | ²
613 | .3. .30.2 .35.2 | Construction | Partial Depth Pavement Repair Class A, B, and C | Sec 1002, 1015, 401, 403 |  |  |  | Testing | CRE2O - 400 | 1 per Day /Installation | 1 per project |  | ² |  | ²
CRE2O - 403
613 | .3. .40.3 | Construction | Dowel Bar Retrofit | See Checklist - 613C | See plan and Standard Drawing 613.x |  |  | Visual | NA | 1 per day |  | ²
613 | .50.3 | Construction | Cross-stitching | See Checklist - 613B | See plan and Standard Drawing 613.x |  |  | Visual | NA | 1 per day |  | ²
Section 614: Drainage Fittings
614 | .30.3 | Construction | Misc. | See Checklist - 614 | See Standard Drawing 614.x |  |  | Visual | NA | 1 per Day /Installation |  | ²
Section 616: Temporary Traffic Control
616 |  | Material | misc | See Sec 1063 and MUTCD | NCHRP350 compliance |  |  | Certification | NA | 1 per Delivery | 1 per project |  | ²
616 |  | Construction | Misc. | See Checklist - 616 | Sec 107.5, 902, Plans and TCP |  |  | Visual | NA | 1 per Day /Installation |  | ²
Section 617: Concrete Traffic Barrier
617 | .10.3 | Materials | Concrete | B / air or B1 / air 4,000 psi |  |  | Sec 501 | Testing | NA | 1 per day | 1 per activity |  | ²
617 | .10.3 | Material | Concrete Aggregates | See Sec 501 |  |  |  | Testing | CRE2O - 1000 | See 501 | See 501 |  | ² |  | ²
617 | .20.2. .20.3. | Materials | Precast Temporary Barrier | Sec 1064 |  |  |  | Certification | NA | 1 per shipment | 1 per project |  | ²
617 | .10.3. | Construction | Temporary and Permanent Concrete Barrier | See Checklist - 617 | Section 501, 502, 703, Standard drawing 617.x |  |  | Visual | NA | 1 per installation |  | ²
Section 619: Pavement Edge Treatment
619 | .2. | Material | Misc. Granular | Approved material |  |  |  | Visual | NA | 1 per Installation | 1 per project |  | ²
619 | .3. | Construction | Edge Treatment | See Checklist - 619 | Standard Drawing 619.x |  |  | Visual | NA | 1 per Day /Installation |  | ²
Section 620: Pavement Marking
620 |  | Construction | Permanent Marking | See Checklist - 620 | See Standard Drawing 620.x |  |  | Visual / Measurement | NA | 1 per Installation |  | ²
620 |  | Construction | Temporary Marking | See Checklist - 620 | Sec 409, 413, Standard Drawing 620.x |  |  | Visual / Measurement | NA | 1 per Installation |  | ²
Section 621: Flowable Backfill
621 | .2. | Materials | Misc. Components | Per 1005, 1018, 1019, 1054, 1070 |  |  |  | Qualified List - Testing | NA | 1 per Day /Activity | 1 per project |  | ²
621 | .3. | Materials | Mixture | Strength and consistency |  |  |  | Testing | NA | 1 per Day /Activity | 1 per project |  | ²
621 | .4. | Construction | Flowable Fill | See Checklist - 621 |  |  |  | Visual | NA | 1 per Day /Activity |  | ²
Section 622: Pavement and Bridge Surface Removal and Texturing
622 | .10. .20. | Construction | Cold milling | See Checklist - 622 |  |  | Sec 620 | Visual / Measurement | NA | 1 per Day /Activity |  | ²
622 | .30. .40. | Construction | Diamond Grinding | See Checklist - 622 |  |  | Sec 620 | Visual / Measurement | NA | 1 per Day /Activity |  | ²
Section 623: Concrete Bonding Compound, Epoxy Mortar and Epoxy Polymer Concrete Overlay
623 | .10.3. | Construction | Bonded Concrete, polymer concrete and Epoxy Mortar | See Checklist - 623 |  |  |  | Visual / Measurement | NA | 1 per Day /Activity |  | ²
623 | .20.2 | Materials For Epoxy Mortar | Sand and aggregates | Sec 1039 |  |  |  | Certification/ QPL | NA | 1 per Installation | 1 per project |  | ²
623 | .20.3. | Construction | Epoxy Polymer Overlay | See Checklist - 623 |  |  |  | Visual / Measurement | NA | 1 per Day /Activity |  | ²
Section 624: Geotextile Construction
624 | .3. | Construction Requirements | Geotextile | See Checklist - 624 |  |  | plans | Visual | NA | 1 per Installation |  | ²
Section 625: Slab Stabilization
625 |  | Construction | Slab Undersealing and Jacking | See Checklist - 625 |  | TM64, Sec 501 |  | Visual / Measurement | NA | 1 per Installation |  | ²
Section 626: Rumble Stripes
626 | .2. | Construction | Rumble Stripes | See Checklist - 626 |  | disposal Sec 622 |  | Visual / Measurement | NA | 1 per 1000' |  | ²
Section 627: Contractor Surveying and Staking
627 | .2. | Contractor Surveying and Staking | Construction | See Checklist - 627 |  |  |  | Visual | NA | 1 per Installation |  | ²

## 700
DIVISION 700: Structures | [8 empty] | Minimum Frequency |  | QC Documents
[9 empty] | Contractor QC | MoDOT QA | Checklist | Test Record | Misc. | CRE2O | GO BACK TO COVER
Spec. |  | Item Description | Parameter or Procedure | Additional Reference |  |  | Acceptance Criteria | CRE2O Link (if applicable)
Section 701: Drilled Shafts
701 | .2. | Preconstruction Submittals |  | See Checklist - 701 |  | Submitted 30 days in advance | Documentation | NA | 1 per Structure |  | ²
701 | .3. | Material | Concrete Aggregates | Sec 501 |  |  | Testing | CRE2O - 1000 | See 501 | See 501 |  | ² |  | ²
701 | .3.1 | Concrete Mixture | Air, Slump, Cylinders | Use B2, see Sec 501 |  |  | Testing | CRE2O - 500 | 1 from first truckload and 1 per 100 CY thereafter per pour per day | 1 per 500 CY |  | ² |  | ²
701 | .3.2. .4. .4.10.3 .4.11.1. .4.11.1 .4.12 .4.13. | Casing, Construction, Excavation Inspection, Log and Cores of Excavated Material , Reinforcing Cage and Spacers Concrete Placement | Condition and Properly Sized, Sequence, Methods, Time Limitations, Television Camera Inspection, Rock Socket Foundation Inspection For shale, sand, or siltstone Fabrication and Placement General Conditions | See Checklist - 701 |  |  | Visual / Measurement | NA | 1 per Each Shaft |  | ²
701 | .3.2.6 | Casing | Welding Procedures | Sec 1080 |  |  | Documentation | NA | 1 per each | 1 per project | ²
701 | .3.3.3 | Slurry | Approval, Preparation, control tests, and sampling | See Checklist - 701 |  | Preapproval for slurry. | Visual / Documentation | NA | 1 per structure |  | ²
701 | .4.1.7 | Integrity Inspection | Crosshole Sonic Log testing | See Checklist - 701 |  |  | Documentation | NA | 1 per Each Shaft |  | ²
701 | .4.17.1 | Integrity Inspection | Coring | See Checklist - 701 |  | Only when needed | Visual | NA | 1 per each occurrence |  | ²
701 | 0.5 | Drilled Shaft Load Tests |  | If required by contract. |  |  | Visual / Measurement | NA | 1 per each occurrence |  | ²
Section 702: Load Bearing Piles
702 | .2. | Material | Concrete Aggregates | Sec 501 |  |  | Testing | CRE2O - 1000 | See 501 | See 501 |  | ² |  | ²
702 | .2.1 | Concrete Mixture | Air, Slump, Cylinders | Sec 501 |  |  | Testing | CRE2O - 500 | 1 from first truckload and 1 per 100 CY thereafter per pour per day | 1 per 500 CY |  | ² |  | ²
702 | .3. .4. | Construction | Installation/Equipment | See Checklist - 702 |  |  | Visual/ Measurement | NA | 1 per Pile |  | ²
Section 703: Concrete Masonry Construction
703 | .2. | Material | Concrete Aggregates | Sec 501 |  |  | Testing | CRE2O - 1000 | See 501 | See 501 |  | ² |  | ²
703 | .2.1 | Concrete Mixture | Air, Slump, Cylinders | Sec 501 |  |  | Testing | CRE2O - 500 | 1 from first truckload and 1 per 100 CY thereafter per pour per day | 1 per 500 CY |  | ² |  | ²
703 | .3. .3.4 .3.11 .3.12 | Construction Extending/ Widening Structures Stenciling ID Numbers | Forms, Placement, Finishing Curing or Sealing Joint Placement surface condition | See Checklist - 703A |  |  | Visual | NA | 1 per pour |  | ²
See Checklist - 703B
703 | .3.6.1 .3.6.3.2.4 | Opening to Traffic | Construction or Public |  |  |  | Documentation | NA | 1 per activity |  | ²
703 | .3.9 .3.10 | Construction | Temperature Control and Limitations |  |  |  | Measurement | NA | 1 per pour |  | ²
Section 704: Concrete Masonry Repair
704 | .2. | Material | Concrete Aggregates | Sec 501 |  | Requires Grad E coarse aggregate | Testing | CRE2O- 1000 | See 501 | See 501 |  | ² |  | ²
704 | .2. | Concrete Mixture | Air, Slump, Cylinders | Sec 501 |  |  | Testing | CRE2O - 500 | 1 per pour/day | 1 per 500 CY |  | ² |  | ²
704 | .3.6 | Construction | Superstructure Repairs Slab Edge Repair | See Checklist - 704B |  | If Concrete, Sec 501 | Testing | NA | 1 per Activity, 1 per Day min |  | ²
704 | .3.3 | Construction | Superstructure Repairs Full Depth | See Checklist - 704D |  | If Concrete, Sec 501 | Testing | NA | 1 per Activity, 1 per Day min |  | ²
704 | .3.1 .3.4 | Construction | Superstructure Repairs Half Sole and Modified | See Checklist - 704E |  | If Concrete, Sec 501 | Testing | NA | 1 per Activity, 1 per Day min |  | ²
704 | .3.7 .3.8 | Construction | Substructure Repair | See Checklist - 704C |  | If Concrete, Sec 501 | Testing | NA | 1 per Activity, 1 per Day min |  | ²
704 | .9. | Construction | Epoxy Sealing | See Checklist - 704A |  |  | Visual | NA | 1 per Activity, 1 per Day min |  | ²
Section 706: Reinforcing Steel for Concrete Structures
706 | .3. | Construction Requirements | Verification, Handling and Storage of Reinforcing Steel | See Checklist - 706 |  | Incoming PAL material should be inspected for disposition remarks | Visual | NA | 1 per shipment | 1 disposition remark per ID | ²
Section 707: Conduit System on Structures
707 | .3. | Construction | Conduit Systems | See Checklist - 707 |  |  | Visual | NA | 1 per Structure |  | ²
Section 710: Epoxy Coated Reinforcing Steel
710 | .3. | Construction Requirements | Verification, Handling and Storage of Epoxy Rebar | See Checklist - 706 |  | Incoming PAL material should be inspected for disposition remarks | Visual | NA | 1 per shipment | 1 disposition remark per ID | ²
Section 711: Protective Coatings for Exposed Concrete Surfaces
711 | .3. | Construction | Protective Coatings | See Checklist - 711B or 711C |  | Random dry film thickness | Visual / Measurement | NA | 1 per structure |  | ²
Section 712: Structural Steel Construction
712 |  | Structural Steel Construction | Erection, Bolt Tightening, Finishing | See Checklists - 712C |  |  | Visual / Testing | NA | 1 per Activity, 1 per Day min |  | ²
712 | .6. | Construction | Field Welding | Sec 1080 | Welder qualifications on file. Contractor developed Checklist based on contract documents. |  | Documentation | NA | 1 per Structure |  | ²
Section 713: Thrie Beam for Bridge Guardrail
713 | .3. | Construction Requirements | Thrie Beam; Bridge Guardrail | See Checklist - 713 |  |  | Visual | NA | 1 per Activity, 1 per Day min |  | ²
Section 715: Vertical Drain at End Bents
715 | .3. | Construction Requirements | Vertical Drain | See Checklist - 715 |  |  | Visual | NA | 1 per Activity |  | ²
Section 716: Neoprene Bearings
716 | .10.-30. | Construction | Neoprene Bearings | Sec 1038 | Check dimensions per plan |  | Documentation | NA | 1 per Shipment | 1 per project |  | ²
Section 717: Neoprene and Silicone Joint Systems
717 |  | Construction Requirements | Joint Systems | See Checklist - 717 |  | Barrier wall joint checklist rate: 1 per structure | Visual | NA | 1 per Joint |  | ²
Section 720: MSE Wall Systems
720 | .2. .2.5. | Material | Concrete Mixtures | Sec 501 |  | Class B or B1. Air entrainment for coping | Testing | CRE2O - 500 | 1 from first truckload and 1 per 100 CY thereafter per pour per day | 1 per 500 CY |  | ² |  | ²
720 | 0.2 | Material | Select Granular Backfill | Per 1010, Resistivity (if metal straps). |  |  | Testing / Certification | CRE2O - 1000 | 1 per product | 1 per project |  | ² |  | ²
720 | .2.4 | Material | Unit Fill Small Block Walls | Gradation D or E from Sec 1005, T27 |  |  | Testing | NA | 1 per product | 1 per project |  | ²
720 | .4.1. .4.2. | Construction | Wall Systems | See Checklist - 720 |  |  | Measurement | NA | 1 per day |  | ²
720 | .4.2.2 | Material | Precast Panels and Coping | Sec 1052 |  |  | Visual / Measurement | NA | 1 per shipment | 1 per project |  | ²
Section 724: Pipe Culverts
724 | .2.2 | Construction | Installation of all types | See Checklist - 724 |  |  | Visual / Testing | NA | 1 per location | 1 per project | ²
724 | .3. | Construction | Post Installation Pipe Performance Inspection | See Checklist - 724 |  | Frequency outlined in 724.3.2 | Testing | CRE2O - 724.3 | 1 per location | 1 per project | ² | ² |  | ²
Section 725: Metal Pipe and Pipe Arch Culverts
725 | .3.1 | Construction | Repairs | See Checklist - 724 |  |  | Visual | NA | 1 per location |  | ²
725 | .3.2 | Construction | Installation | Sec 724 | See Checklist - 724 |  | Visual, Level, Measurement | CRE2O - 724.3 | 1 per Installation |  | ² |  |  | ²
725 | .1.3.2. 1.3.3. | Material | Soil Conditions | Testing of soil to allow choice of metal |  |  | Testing | NA | 1 per project | 1 per project |  | ²
Section 726: Rigid Pipe Culverts
726 | .3. | Construction | Installation | Sec 724 | See Checklist - 724 |  | Visual, Level, Measurement | CRE2O - 724.3 | 1 per Installation |  | ² |  |  | ²
Section 727: Structural Plate Pipe and Plate Pipe-Arch Culverts
727 | .3. | Construction | Installation | Contractor developed Checklist based on contract documents. |  |  | Visual / Measurement | NA | 1 per Pipe |  | ²
Section 730: Thermoplastic Pipe Culverts
730 | .3. | Construction | Installation | Sec 724 | See Checklist - 724 |  | Visual, Level, Measurement | CRE2O - 724.3 | 1 per Installation |  | ² |  |  | ²
Section 731: Precast Reinforced Concrete Manholes and Drop Inlets
731 | .2.2 | Materials | Footing Concrete | Sec 501 |  | Air entrainment not required | Visual / Measurement | CRE2O - 500 | 1 per shipment | 1 per project |  | ² |  | ²
731 | .3.1 | Construction | Installation and Backfilling | See Checklist - 731 |  |  | Visual / Testing | NA | 1 per day |  | ²
Section 732: Flared End Section
732 | .2.2 | Materials | Cast in Place Concrete | Cast-in-place toe walls constructed of Class B, B-1 per section 501 |  | Air entrainment not required. Cured per Sec 703 | Testing | CRE2O - 500 | 1 per 100 CY/pour/day | 1 per project |  | ² |  | ²
732 | .3. | Construction | installation | See Checklist - 732 |  |  | Visual | NA | 1 per day |  | ²
Section 733: Precast Concrete Box Culverts
733 | .3. | Construction | Installation and Backfilling | See Checklist - 733 |  |  | Visual / Testing | NA | 1 per day |  | ²
733 | .3.1 | Material | Subgrade Bedding | Sec 206 & 1007 |  |  | Testing | CRE2O - 1000 | 1 per 250 Ton, 1 per Week min. | 1 per 8000 Ton, 1 per Project min |  | ² |  | ²
Section 734: Installation of Pipe by Horizontal Boring Methods
734 | .3. | Construction Requirements | Misc. | Contractor developed Checklist based on contract documents. |  |  | Visual | NA | 1 per structure |  | ²
Section 735: Culvert Lining
735 | .3. | Construction | Installation | See Checklist - 735 |  |  | Visual/ Measurement | NA | 1 per Pipe Liner |  | ²

## 800
DIVISION 800: Roadside Development | [8 empty] | Minimum Frequency |  | QC Documents
[9 empty] | Contractor QC | MoDOT QA | Checklist | Test Record | Misc. | CRE2O | GO BACK TO COVER
Spec. |  | Item Description | Parameter or Procedure | Additional Reference |  |  | Acceptance Criteria | CRE2O Link (if applicable)
Section 801: Lime and Fertilizer
801 | .4 | Construction Requirements | Line and Fertilizer | See Checklist - 800 |  |  | Measurement | NA | 1 per Activity |  | ²
Section 802: Mulching
802 | .3 | Construction Requirements | Mulch Application | See Checklist - 800 | Apply within 24 hours of seeding |  | Measurement | NA | 1 per Activity |  | ²
802 | .3 | Construction Requirements | Overspray Application | See Checklist - 800 |  |  | Measurement | NA | 1 per Activity |  | ²
Section 803: Sodding
803 | .3 | Sodding | Construction | See Checklist - 803 |  |  | Visual | NA | 1 per Activity |  | ²
Section 804: Topsoil
804 | .2 | Construction Requirements | Topsoil | Source Approved by Engineer | Free of Objectionable Material |  | Visual / Measurement | NA | 1 per Activity |  | ²
Section 805: Seeding
805 | .3.1 | Construction | Seed Application | Sec 801 | See Checklist - 800 |  | Visual / Measurement | NA | 1 per Activity |  | ²
805 | .4 | Construction | Growth Acceptance | See Checklist - 800 |  | Activity is an "representative area" | Visual | NA | 2 per Activity |  | ²
Section 806: Pollution, Erosion and Sediment Control
806 | .4 | Construction Maintenance | Poll, Erosion, Sediment Control | Current SWPP, EPG, and applicable permits |  | See Stormwater Database | Visual | NA | 1 per Week/ Qualifying Rainfall Event | 1 per Week/ Qualifying Rainfall Event |  |  | ²
Section 808: Trees, Shrubs, and Other Plants
808 | .3 | Construction Requirements | Planting and Maintenance | See Checklist - 808 |  |  | Visual | NA | 1 per Activity |  | ²

## 900
DIVISION 900: Traffic Control Facilities | [8 empty] | Minimum Frequency |  | QC Documents
[9 empty] | Contractor QC | MoDOT QA | Checklist | Test Record | Misc. | CRE2O | GO BACK TO COVER
Spec. |  | Item Description | Parameter or Procedure | Additional Reference |  |  | Acceptance Criteria | CRE2O Link (if applicable)
Section 901: Highway Lighting
901 | .3.2 | Materials | Concrete | Per Plan and Sec 501 |  | Test first load | Visual / Test | CRE2O - 500 | 1 per day | 1 per 500 CY |  | ² |  | ²
901 | 0.4 | Construction | Misc Lighting | See Checklist - 901 | Test Period for performance |  | Visual | NA | 1 per circuit |  | ²
Section 902: Traffic Signals
902 | .4.2 | Materials | Concrete | Per Plan and Sec 501 |  | Test first load | Visual / Test | CRE2O - 500 | 1 per day | 1 per 500 CY |  | ² |  | ²
902 | .4.5 | Construction | Misc Signal material | See Checklist - 902 | Test Period for performance |  | Visual | NA | 1 per circuit |  | ²
Section 903: Highway Signing
903 | .2.4 | Materials | Concrete | Per Plan and Sec 501 |  | Test first load | Visual / Test | CRE2O - 500 | 1 per day | 1 per 500 CY |  | ² |  | ²
903 | .2.5 | Construction | Roadside Signs | See Checklist - 903 | PSST, Pipe, and Structural Posts |  | Visual / Measurement | NA | 1 per day |  | ²
903 | .2.5 | Construction | Overhead Signs | See Checklist - 903 | Tubular supports and truss supports |  | Visual / Measurement | NA | 1 per structure |  | ²

## JSP ITS
JSP | Intelligent Traffic System
|  | I.T.S. | Dynamic Message Sign Footing | Class B, Sec 501, 703 | Sec. 706, 712 | lab report | 1 per 50yds | (1) per 500 CY |  | ² | ²
|  | I.T.S. | CCTV Foundation | Class B, Sec 501, 703 | Sec. 706, 712 | lab report | 1 per 50yds | (1) per 500 CY |  | ² | ²
|  | I.T.S. | Drilled Shafts for CCTV & DMS Structures | Sec 701 except 701.4.10.3 thru 701.4.11.4, 701.6.4, 701.6.5, 701.7.5 & 701.7.6 |  | visual | Per Foundation | Verify completion |  | ²
|  | I.T.S. | DMS Sign Structure | AWS D1.2 | ASTM's for sign posts | certificate of compliance/mill Test Reports | Per Shipment | Verify certification |  | ² | ²
|  | I.T.S. | Conduit Systems | Type of system as shown on plans | Submit shop drawing detail for support system | visual | Per Trench Line | Verify completion |  | ²
|  | I.T.S. | Conduit Systems | Orange for Communication, Black for Power, Meet Spec. 1060 | Install tracer wire, pull rope, marking tape | visual | Per Trench Line | Verify completion |  | ²
|  | I.T.S. | Conduit Systems | 10% of slurry mix shall be of a high grade Bentinite |  | visual | Per Trench Line | Verify completion |  | ²
|  | I.T.S. | Conduit Systems | Fill void between drilled hole and conduit | Backfill exposed area to grade | visual | Per Trench Line | Verify completion |  | ²
|  | I.T.S. | Fiber Optic Cable | As shown on plans | Spec 1092 | certificate of compliance | Per Completed Fiber run between Cabinets | Verify certification | ² | ² | ²
|  | I.T.S. | Fiber Optic Cable | Access cable of 20' in intermediate pb, 30' at cabinet | Label cable, fill used conduits to prevent water entry | visual | Per Completed Fiber run between Cabinets | Verfiy completion |  | ²
|  | I.T.S. | Fiber Optic Cable | Secure splices, separate tray for each buffer tube | Fusion splice w/ LID or HDCM system | visual | Per Completed Fiber run between Cabinets | Verify completion |  | ²
|  | I.T.S. | Fiber Optic Cable Acceptance Testing | Test Result Documentation |  | report | Per Completed Fiber run between Cabinets | Verify test data |  | ² | ²
|  | I.T.S. | Equipment Cabinets | As shown on plans |  | certificate of compliance | Per Completed Fiber run between Cabinets | Verify certification |  | ²
|  | I.T.S. | CAT 5E Cable | As shown on plans |  | certificate of compliance | Per Completed Fiber run between Cabinets | Verify certification |  | ²
|  | I.T.S. | Communication Equipment | As shown on plans |  | certificate of compliance/visual | Per Completed Fiber run between Cabinets | Verify certification |  | ²
|  | I.T.S. | DMS Assembly | As shown on plans |  | certificate of compliance/visual | Per DMS Structure | Verify certification |  | ²
|  | I.T.S. | CCTV Camera Assembly | As shown on plans |  | certificate of compliance/visual | Per CCTV Structure | Verify certification |  | ²