Pre-Bid Meeting

J5P3181 – Route 54, Business Route 54, Route W Intersection Safety Project

Replace existing at-grade signal with an Interchange

February 5th, 2019

- Welcome and Safety Information

- Sign in and Introductions

- General Project Information

  - Described location of project, layout of interchange, and adjoining roads that are part of the construction.

  - Commitments – VE’s will be accepted if viable and comply with commitments

    - Four lanes of traffic maintained on Route 54

    - Signalized intersection to remain open

    - Business 54, Route W, Osage Hills Road, Wilmore Lane to remain open

    - Full sized roundabouts

    - Maintain Access to Businesses

- Construction Staging - Traffic Control - Discussed our staging assumptions, contractors will be able to revise with approval of the engineer

  - WB Bridge construction

    - Build Ramps 1 and 3; move EB 54 traffic to ramps

    - Build crossover to move WB 54 traffic to existing EB 54 lanes

    - Build half of the two MSE walls; temporary shoring

    - Begin Ramp 4 and Connector Rd

  - EB Bridge construction

    - Keep EB 54 traffic on ramps

    - Move WB 54 traffic back to existing WB 54 lanes

    - Continue Ramp 4 and Connector Rd

  - Remaining Connections

    - Move EB 54 traffic back to existing EB 54 lanes

    - Complete Ramps 1 and 3, Roundabout 3, and Osage Hills

    - Wilmore Lane and Roundabout 1

    - Bus. Rte. 54, Ramp 2 and Roundabout 2

- Bridge – Bridge department discussed details of structures

  - 2 bridges; ~100’ single spans – tangent structure (roadway curved)

  - Constant 5% super-elevation on both bridges

  - Fully cast-in-place deck

  - EB – Epoxy coated reinforcing steel

  - WB – Galvanized reinforcing steel

  - MSE walls (2)

    - ~250’ long

    - Straight with possible slight kink outside of bridge

    - Potential ground improvements in one location

- Utilities – Discussed various utility relocation needs and timeline of completion; contractor may need to alter operations while relocations are completed, will be detailed in JSP’s for project if needed

  - Steel casings to be installed with the project for the city utilities along the Connector Rd and ramps

  - Ameren – multiple relocations, underground where possible, some bores under 54

  - Lightcore – fiber optic facilities on project, not clear on impacts

  - AT&T – multiple locations & types – considerable relocations along Business 54

  - City Water & Sewer – consultant designing, working towards relocation plan

  - Beach Club Condominium Association Water – discussed relocation of line

- Right of Way – Negotiations beginning with property owners

  - Potential borrow

    - Potential borrow at parcel 23

    - Potential borrow at parcel 1

  - Billboard

    - Three billboards to be removed east of Rte. 54

    - One billboard will be avoided west of Rte. 54

- Environmental Restrictions

  - Wetland @ Culvert

    - Wet area to be avoided at pipe culvert in area of Ramp 4 – no construction is shown in area

  - Bat Roosting Trees

    - Majority of trees have been or will be removed in the area of the connector road and Ramp 4

    - Some will remain to be removed in the area of the Osage Hills connection and ramp 4 during the project, within the acceptable time frame

- Question and Answer

  - What pavement types will be in the project?

    - The permanent pavement will be alternate bid (asphalt or concrete)

    - The temporary pavement will be optional bid (asphalt or concrete)

  - How much rock excavation on the project?

    - Most of the excavation is in either Class A or previously placed fill

    - There is potential for some solid rock at the bridge/wall foundations

    - Proposed design included 3:1 fill slopes

  - Other discussion

    - Schedule

      - June 2019 Letting

      - NTP in the fall

      - Completion in the winter of 2020

    - VE Opportunity

      - VE proposals will be considered

      - Construction staging opportunity

    - Lighting work

      - Interchange

      - roundabouts

    - Borrow needs

      - Roundabout 3

      - Connector Rd and/or Ramp 4

      - Roundabout 2

    - Crossover at existing signals

      - Will be removed once interchange is open and Osage Hills at Rte. 54 is closed

Contact Information

Transportation Project Manager – Ryan Libbert, 573-522-5265, ryan.libbert@modot.mo.gov

Transportation Project Designer – Nik Schaffner, 573-522-5163, nikolas.schaffner@modot.mo.gov