## Sheet3
Job No. | STIP/TIP | Proposed DBC Commitment | County | Route | Location | Proposed Improvement | Length (Miles) | Approx. Constr. Cost (thousands) | DBE Goal | Consultant Services Required | Other Comments | Anticipated Letting Date | Project Manager | Bridge Project Manager
J4P3443 | STIP-Yes TIP -Yes | FY2021-$350 FY2022-$350 FY2023-$300 FY2024-$100 | Cass | MO 7 | Over I-49, 0.2 mile east of Brookhart Drive and 0.4 mile west of Orchard Road | Bridge replacement and operational improvements over I-49. Project involves bridge A1496. Drainage work on I-49 near northbound on-ramp. MO 7 approach work. | 0.5 | 8872000 | 14% | Surveying - all field surveying including mapping, bridge survey report, geotechnical staking, legal descriptions, right of way staking, and location survey. Roadway Design - preparation of conceptual report, including MOT alternatives and operational analysis, preliminary plans, right of way plans (if necessary), geotechnical investigation/borings, traffic counts, and final design plans. Bridge Design - preparation of bridge memorandum, geotechnical investigation/borings, layout, and final bridge design for new bridge. Consultant will submit milestone Requests for Environmental Services (RES) and estimates. | New right of way or temporary easements may be needed. If a public meeting or hearing is required, consultant will provide displays and handouts. Traffic modeling work will be provided by MODOT. | 2023-11-17 | Allan Ludiker | Christopher Shanks
J4I3458 | STIP-Yes TIP -No | FY2021-$750 FY2022-$2000 FY2023-$550 FY2024-$100 | Clay | I-29 | Over Guinotte Ave, 0.4 mile south of Missouri River and 0.7 mile north of US 24. Over Bedford Ave, 1.0 mile south of MO 210 and 0.5 mile north of Missouri River | Bridge rehabilitation. Project involves bridge L0788 and bridge L0789 | 0.6 | 33220000 | 16% | Bridge Inspection and Conceptual Plan - field inspection and documentation of all components for the development of proposed work with estimate. Surveying - all field surveying including mapping, bridge survey report, right of way staking and location survey. Roadway Design - preparation of conceptual, preliminary and final design plans. Bridge Design- preparation of bridge memorandum, layout, final bridge design for new bridge. Consultant will submit milestone Requests for Environmental Services (RES). | New right of way is not anticipated. If a public information meeting is necessary, the consultant will provide support with displays and handouts. | 2024-04-01 | James Burgess | Christopher Shanks
J4S3374 | STIP-Yes TIP -No | FY2021-$250 FY2022-$900 FY2023-$200 FY2024-$50 | Jackson | Propsect | Over I-70. 0.1 mile south of 13th Street and 0.1 mile north of Truman Road. | Bridge replacement over I-70. Roadway alignment. Project involves bridge A0291. | 0.1 | 7391000 | 13% | Partial Surveying - all field surveying including mapping, bridge survey report, geotechnical layout, right of way staking and location survey (Some completed by district survey staff). Geotechnical - all work necessary for the project including bridge and potential retaining walls, Roadway Design - preparation of conceptual, right of way plans, preliminary and final design plans. Bridge Design - preparation of bridge memorandum, layout, final bridge design for new bridge. Consultant will submit milestone Requests for Environmental Services (RES). | New right of way is expected. A public meeting will be necessary during the conceptual stage and possibly during the final plans stage, the consultant will provide support with displays and handouts. The district will prepare the AJR (if necessary) as a result of the conceptual stage public meeting. | 2023-04-01 | James Burgess | Christopher Shanks
J4I3450 | STIP-Yes TIP -No | FY2021-$10 FY2022-$423 FY2023-$300 FY2024-$100 | Platte | I-29 | Over 72nd Street, 1.6 miles south of Barry Road and 1.2 miles north of 64th Street | Bridge replacement. Project involves bridge A1595. | 0.1 | 6502000 | 14% | Surveying - all field surveying including mapping, bridge survey report, geotechnical staking, legal descriptions, right of way staking, and location survey. Roadway Design - preparation of conceptual report, preliminary plans, right of way plans (if necessary), geotechnical investigation/borings, and final design plans. Bridge Design - preparation of bridge memorandum, geotechnical investigation/borings, layout, and final bridge design for new bridge. Consultant will submit milestone Requests for Environmental Services (RES) and estimates. | New right of way is not anticipated. If a public information meeting is necessary, the consultant will provide support with displays and handouts. | 2024-01-12 | Jodie Puhr/Heather Barrows | Christopher Shanks
J4I3451 | STIP-Yes TIP -No | FY2021-$100 FY2022-$400 FY2023 -$500 FY2024-$50 | Jackson | I-435 | Over 87th Street, 1.1 miles north of Rte W and 2.2 miles south of Gregory Boulevard. | Bridge replacement. Project involves bridge A1642. | 0.1 | 5204000 | 12% | Surveying - all field surveying including mapping, bridge survey report, geotechnical staking, legal descriptions, right of way staking, and location survey. Roadway Design - preparation of conceptual report, preliminary plans, right of way plans (if necessary), geotechnical investigation/borings, and final design plans. Bridge Design - preparation of bridge memorandum, geotechnical investigation/borings, layout, and final bridge design for new bridge. Consultant will submit milestone Requests for Environmental Services (RES) and estimates. | New right of way is not anticipated. If a public information meeting is necessary, the consultant will provide support with displays and handouts. | 2024-04-01 | James Burgess | Christopher Shanks