## Sheet3
Job No. | STIP/TIP | County | Route | Location | Proposed Improvement | Length (Miles) | Approx. Constr. Cost (thousands) | DBE Goal | Consultant Services Required | Other Comments | Anticipated NEPA Approval/Letting Date | Project Manager | Bridge Project Manager | Proposed DBC Commitment (thousands)
J4I3195 | STIP-Yes TIP -Yes | Jackson | I-70 | I-435 to 0.75 miles east of I-470 | Tier 2 Environmental Study for Corridor Improvements | 7 | 150275 | 14% | Consultant will conduct a second-tier environmental assessment (EA) based on the recommendations from the I-70 FTEIS 4I1486B. Including but not limited to the following: o Traffic modeling & HSM Safety Analysis o Create AJR o Noise Study o Utility investigations o Interchange layouts (70 EB to 435 SB ramp, Sterling/40 and I470 including US 40 and 39th St.) o Preliminary roadway and bridge design o Identifying right of way impacts o Geotechnical Investigation o Public outreach – including meetings/hearings, coordinating with the public and agencies o Assess the social, economic, and environmental impacts of the alternatives for the proposed action. o Compile the required NEPA documentation through the production of an administrative record. o Obtain approval of an EA by the Federal Highway Administration (FHWA) and issuance of the FONSI, if appropriate. o Consider appropriate impact mitigation: avoidance, minimization, and compensation. o Complete required documentation for and attain Section 106 clearance and Section 4(f) clearance, if required. • Surveying - Photogrammetry will be provided, scope will need to include field verification • Identify future funding opportunities and assist with grant writing • Submit milestone estimates | Includes I-470 Interchange | 2024-10-01 | Jodie Puhr | Christopher Shanks | FY2023-$1250 FY2024-$1250 FY2025 -$1000 FY2026-$1277 FY2027 - $1500
J4I2293 | STIP-Yes TIP Yes | Jackson | I-70 | 0.75 miles east of I-470 to Lafayette County Line | Re-evaluation of SIU #1 Tier 2 Environmental Study for Corridor Improvements | 13 | 95000 | 14% | Perform NEPA re-evaluation of the I-70 Tier II SIU 1 EA and FONSI (4I1341D) in Jackson County. Including but not limited to the following: o Traffic modeling o HSM Safety Analysis o Noise Study o Utility investigations o Interchange layouts o Preliminary roadway and bridge design o Identifying right of way impacts (if any) o Geotechnical Investigation o Public outreach – including meetings/hearings * Surveying - Photogrammetry will be provided, scope will need to include field verification * Identify future funding opportunities and assist with grant writing * Submit milestone estimates | Combined with KR0197 & J3I3075 | October, 2023 | Deborah Huffman | Christopher Shanks | FY2023-$1,000 FY2024-$1,000 FY2025 -$25
KR0197 | STIP-Yes TIP -No | Lafayette | I-70 | Jackson County Line to mile marker 39 | Re-evaluation of SIU #1 Tier 2 Environmental Study for Corridor Improvements | 10 | 65000 | 14% | Perform NEPA re-evaluation of the I-70 Tier II SIU 1 EA and FONSI (4I1341D) in Lafayette County. Including but not limited to the following: o Traffic modeling o HSM Safety Analysis o Noise Study o Utility investigations o Interchange layouts o Preliminary roadway and bridge design o Identifying right of way impacts (if any) o Geotechnical Investigation o Public outreach – including meetings/hearings * Surveying - Photogrammetry will be provided, scope will need to include field verification * Identify future funding opportunities and assist with grant writing * Submit milestone estimates | Combined with J4I2293 & J3I3075 | October, 2023 | Deborah Huffman | Christopher Shanks | FY2023-$800 FY2024-$100 FY2025 -$50
J3I3075/ KR0091 | STIP-Yes TIP -No | Lafayette | I-70 | Bridge and Operational Improvements at the Rte 131 in Odessa | Bridge replacement. Project involves bridge A0057 | 1 | 11700 | 12% | After NEPA re-evaluation of the I-70 Tier II SIU 1 EA for the interchange area (KR0197) the consultant will provide preliminary through final plans. * Surveying - Photogrammetry will be provided, scope will need to include professional land surveying to establish land corners (if needed), property lines, monument new right of way, and write deeds as necessary. Consultant will need to provide staking for geotechnical boring locations. * Traffic counts and projections were studied and will be given to the Consultant team. * Consultant will submit milestone Request for Environmental Services (RES) and milestone estimates * Finalize Preliminary plans and prepare Right of Way plans. * Bridge design including preparation of bridge memo geotechnical investigations/borings, layout, and final bridge design for new bridge. * Perform preliminary engineering, including final roadway and bridge plans, specifications, estimates (PS&E) and other documentation for project construction. | Combined with J4I2293 & KR0197 | Spring 2026 | Deborah Huffman | Christopher Shanks | FY2023-$150 FY2024-$460 FY2025 -$460 FY2026-$460 FY2027 - $25

## Sheet3 old
Job No. | STIP/TIP | Proposed DBC Commitment (thousands) | County | Route | Location | Proposed Improvement | Length (Miles) | Approx. Constr. Cost (thousands) | DBE Goal | Consultant Services Required | Other Comments | Anticipated NEPA Approval/Letting Date | Project Manager | Bridge Project Manager
J4I3195 | STIP-Yes TIP -Yes | FY2023-$xx FY2024-$xx FY2025 -$xx FY2026-$xx | Jackson | I-70 | I-435 to 0.75 miles east of I-470 |  | 7 | 50275 | XX% | Perform NEPA evaluation of XXXXXXX in Jackson County. Includes traffic modeling, preliminary roadway and bridge design, identifying right of way impacts, noise study, utility and SUE investigation, geotechnical investigation, HSM safety analysis, and performing public outreach - including meetings/hearings. Participate in risk assessment to determine appropriate project delivery method. Surveying - Photogrammetry will be provided, scope will need to include all other field verification. Consultant will submit milestone estimates. | Includes I-470 Interchange |  | Jodie Puhr
J4I2293 | STIP-Yes TIP Yes | FY2023-$1,265 FY2024-$1,000 FY2025 -$50 | Jackson | I-70 | 0.75 miles east of I-470 to Lafayette County Line |  | 13 | 95000 | XX% |  | Combined with J4I1436 & J3I3075 | September, 2023 | Deborah Huffman | Christopher Shanks
J4I1436 | STIP-Yes TIP -No | FY2023-$800 FY2024-$1200 FY2025 -$50 | Lafayette | I-70 | Jackson County Line to mile marker 39 |  | 10 | 65000 | XX% | Perform NEPA re-evaluation of the I-70 Tier II Section 1 EA in Lafayette County. Includes creating AJR, preliminary roadway and bridge design, identifying right of way impacts, noise study, utility and SUE investigation, geotechnical investigation, HSM safety analysis, and performing public outreach - including meetings/hearings. Participate in risk assessment to determine appropriate project delivery method. Surveying - Photogrammetry will be provided, scope will need to include all other field verification. Consultant will submit milestone estimates. | Combined with J4I2293 & J3I3075 | September, 2023 | Deborah Huffman | Christopher Shanks
J3I3075 | STIP-Yes TIP -No | FY2023-$150 FY2024-$460 FY2025 -$460 FY2026-$460 | Lafayette | I-70 | Bridge and Operational Improvements at the Rte 131 in Odessa | Bridge replacement. Project involves bridge A0057 | 1 | 11700 | XX% | Surveying - Photogrammetry will be provided, scope will need to include all other field verification, bridge survey report, geotechnical layout, right of way staking and location survey. Geotechnical - all work necessary for the project including bridge, potential retaining walls and culvert construction. Traffic counts and projections were studied and will be given to the Consultant. Roadway Design - preparation of conceptual, preliminary plans, right of way plans, and final design plans. Bridge Design - preparation of bridge memorandum, geotechnical investigation/borings, layout, and final bridge design for new bridge. Consultant will submit milestone Requests for Environmental Services (RES) and estimates. | Combined with J4I2293 & J4I1436. | January 2026 (unless receive ARPA funds) | Deborah Huffman | Christopher Shanks
· Perform NEPA re-evaluation of the I-70 Tier II Section 1 EA Jackson County. Including but not limited to the following:
o Traffic modeling
o HSM Safety Analysis
o Noise Study
o Preliminary roadway and bridge design
o Identifying right of way impacts (if any)
o Geotechnical Investigation
o Public outreach – including meetings/hearings
· Surveying - Photogrammetry will be provided, scope will need to include all other field verification.
· Submit milestone estimates
· Participate in risk assessment to determine appropriate project delivery method