## Sheet3
Job No. | STIP/TIP | County | Route | Location | Proposed Improvement | Length (Miles) | Approx. Constr. Cost (thousands) | DBE Goal | Consultant Services Required | Other Comments | Anticipated Letting Date | Project Manager
KU0010 | STIP-Yes TIP -No (draft) | Jackson | MO 7 | Shaw Parkway to Rte 40 | Scoping to upgrade pedestrian facilities, multi-use path, add turn lanes and upgrade traffic signals | 1.6 miles | 4335 | 12% | Surveying - field surveying including mapping, legal descriptions, right of way staking, and location survey. Roadway Design - preparation of conceptual report, preliminary plans, right of way plans, and final design plans. Consultant will submit milestone Requests for Environmental Services (RES) and estimates. | New right of way or temporary easements may be needed. If a public meeting or hearing is required, consultant will provide displays and handouts. | March 2024 | Jodie Puhr
KU0028 | STIP-Yes TIP -Yes | Cass | I-49 | 155th St to North Cass Parkway | Survey and Geotechnical for I-49 Widening/Lane Addition Project | 4.7 | 59689 | 12% | Surveying - all field surveying including mapping, legal descriptions, right of way staking, and location survey. Geotechnical Investigation - all work necessary for pavement and soil investigations and borings needed for potential retaining walls. |  | October 2024 | Heather Barrows