## 03-24-2023
Number of Project | District No | County | Route | Project No | Length | MPO | TIP No | Description | Federal Advanced Construction Label | Federal Funds | State Funds | Local Funds | Estimate Total | Future Cost | Anticipated Federal Funds | Let With | Previous Engineering | Current Year Engineering | Engineering 2024 Total | Engineering 2025 Total | Engineering 2026 Total | Engineering 2027 Total | Engineering 2028 Total | Previous Right of Way | Current Year Right of Way | Right of Way 2024 Total | Right of Way 2025 Total | Right of Way 2026 Total | Right of Way 2027 Total | Right of Way 2028 Total | Previous Construction | Current Year Construction | Construction 2024 Total | Construction 2025 Total | Construction 2026 Total | Construction 2027 Total | Construction 2028 Total | Previous Year FFOS | Current Year FFOS | FFOS 2024 Total | FFOS 2025 Total | FFOS 2026 Total | FFOS 2027 Total | FFOS 2028 Total | Previous Payback | Current Year Payback | Payback 2024 Total | Payback 2025 Total | Payback 2026 Total | Payback 2027 Total | Payback 2028 Total
1 | 1 | ANDREW | IS 29 S | 1I3262 | 0.046 | N |  | Bridge rehabilitation over Mill Creek 2.2 miles north of Rte. K near Amazonia. Project involves bridges A1290 in the northbound and southbound lanes. | Federal | 2275 | 253 | 0 | 2568 | 0 | NHPP |  | 40 | 96 | 161 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2271 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | 1 | ANDREW | IS 29 S | 1I3268 | 14.054 | Y | RR-2021-05 | Pavement resurfacing from Bus. 71 to 1.5 miles south of Rte. O near St. Joseph. | Federal | 8551 | 950 | 0 | 9578 | 0 | NHPP |  | 77 | 629 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8872 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | 1 | ANDREW | MO 48 E | 1S3413 | 1.836 | N |  | Bridge rehabilitation on various bridges in Andrew, Buchanan, Caldwell, Carroll, Chariton, Clinton, Daviess, Gentry, Grundy, Harrison, Linn, Livingston, Mercer, Nodaway, Putnam and Sullivan Counties. | Federal | 1999 | 500 | 0 | 2509 | 0 | NHPP |  | 10 | 90 | 100 | 187 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | 1 | ANDREW | US 59 S | 1P3323 | 69.357 | Y | RR-2021-01 | Pavement preservation treatment including Rte. 71, LP 29, Rte. E and Rte. C in Andrew County; Rte. 752, LP 29, Rte. 6, Rte. AC, Rte. A, Rte. MM, Rte. JJ in Buchanan County; and Rte. VV in Clinton County. | Adv. CN | 2017 | 504 | 0 | 2581 | 0 | AC-STBG |  | 60 | 171 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | 1 | ANDREW | BU 71 N | NW0012 | 3.703 | Y | RR-2023-01 | Pavement resurfacing from Rte. 71 to Price Street in Savannah and in the southbound lane from Price Street to Swenson Street and in the northbound lane from Price Street to I-29. | Adv. CN | 2282 | 570 | 0 | 2852 | 0 | AC-STBG | 1P3283 | 0 | 263 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2589 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | 1 | ANDREW | RT B E | NW0008 | 0.363 | N |  | Bridge rehabilitation in Atchison, Andrew, Buchanan and Holt Counties. Project involves bridges R0274, A1782, A2280, A2582, N0811 and A1906. | Adv. CN | 3314 | 829 | 0 | 4143 | 0 | AC-STBG |  | 0 | 60 | 65 | 254 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3764 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | 1 | ANDREW | RT B E | NW0047 | 0.296 | N |  | Bridge rehabilitation over One Hundred and Two River 0.8 mile west of Bolckow. Project involves bridge A1251. | Federal | 1300 | 325 | 0 | 1625 | 0 | NHPP |  | 0 | 10 | 20 | 60 | 97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1438 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | 1 | ANDREW | RT DD S | 1S3415 | 1.82 | Y |  | Bridge rehabilitation on various bridges in Andrew, Atchison, Daviess, DeKalb, Holt and Nodaway Counties. | Federal | 1545 | 386 | 0 | 1940 | 0 | NHPP |  | 9 | 42 | 138 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1751 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | 1 | ATCHISON | MO 111 S | NW0006 | 0.011 | N |  | Bridge replacement over Pike Creek Drainage Ditch 1.2 miles north of Rte. Z near Corning. Project involves bridge X0170. | Federal | 549 | 137 | 0 | 686 | 0 | NHPP | NW0005 | 0 | 60 | 69 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 552 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | 1 | ATCHISON | US 136 E | 1P3328 | 138.713 | N |  | Pavement preservation treatment on routes in Andrew, Atchison, DeKalb, Gentry, Harrison, Holt, Mercer, Nodaway, Sullivan and Worth Counties. Includes routes 71, 136, 169, 118, 146, 136, 46, EE, C and N. | Adv. CN | 4045 | 1011 | 0 | 5133 | 0 | AC-STBG |  | 77 | 381 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4675 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | 1 | ATCHISON | US 136 E | 1P3391 | 0.226 | N |  | Bridge washing over the Missouri River at Brownsville, Nebraska. Project involves bridge L0098. | Federal | 37 | 9 | 0 | 47 | 0 | NHPP |  | 1 | 3 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | 1 | ATCHISON | US 136 E | NW0021 | 23.695 | N |  | Pavement resurfacing from I-29 to the Tarkio River and from the Little Tarkio Creek Bridge to Rte. 71. | Federal | 5704 | 1426 | 0 | 7130 | 0 | NHPP |  | 0 | 10 | 140 | 457 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6523 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | 1 | ATCHISON | US 275 N | NW0055 | 0.22 | N |  | Bridge replacement over the West Fork of High Creek and over High Creek near Rte. T. Project involves bridges J0221 and J0222. | Federal | 2275 | 569 | 0 | 2844 | 0 | NHPP |  | 0 | 5 | 10 | 30 | 50 | 172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2577 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | 1 | ATCHISON | IS 29 N | NW0060 | 16.257 | N |  | Pavement resurfacing from Iowa State line to Rte. 111 near Rock Port. | Federal | 10492 | 1166 | 0 | 11658 | 0 | NHPP |  | 0 | 5 | 85 | 100 | 150 | 721 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10597 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | 1 | ATCHISON | IS 29 S | 1I3280 | 0.03 | N |  | Bridge rehabilitation over Mill Creek 0.2 mile south of Rte. Z near Corning. Project involves bridge A2714. | Federal | 1980 | 220 | 0 | 2228 | 0 | NHPP |  | 28 | 70 | 160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1970 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | 1 | ATCHISON | IS 29 S | 1I3436 | 16.266 | N |  | Pavement preservation treatment from the Iowa State line to Rte. 111 near Rock Port. | Federal | 1241 | 138 | 0 | 1394 | 0 | NHPP |  | 15 | 98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1281 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | 1 | ATCHISON | IS 29 S | NW0018 | 107.783 | Y | RR-2023-02 | Job Order Contracting for pavement repair from the Iowa State line to Platte County line. Includes I-229 in Andrew and Buchanan Counties. | Federal | 999 | 111 | 0 | 1115 | 0 | NHPP |  | 5 | 5 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | 1 | ATCHISON | MO 46 E | NW0005 | 0.027 | N |  | Bridge replacement over Little Tarkio Creek 0.4 mile west of Rte. MM near Fairfax. Project involves bridge T0103. | Federal | 1179 | 295 | 0 | 1474 | 0 | NHPP | NW0006 | 0 | 150 | 129 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1190 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | 1 | ATCHISON | MO 46 E | NW0041 | 16.219 | N |  | Pavement resurfacing from Rte. 59 near Fairfax to Rte. 113 near Burlington Junction. | Adv. CN | 1396 | 349 | 0 | 1745 | 0 | AC-STBG |  | 0 | 5 | 15 | 108 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1617 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | 1 | ATCHISON | US 59 S | 1S3326 | 36.463 | N |  | Pavement resurfacing from Rte. 46 near Fairfax to 1.1 miles west of Rte. O near Oregon. | Adv. CN | 3466 | 867 | 0 | 4344 | 0 | AC-STBG | 1S3325 | 11 | 30 | 287 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4016 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21 | 1 | BUCHANAN | MO 116 E | NW0035 | 29.6 | N |  | Pavement resurfacing from Rte. 59 near Rushville to Rte. 169. | Adv. CN | 2234 | 558 | 0 | 2792 | 0 | AC-STBG |  | 0 | 5 | 30 | 168 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2589 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22 | 1 | BUCHANAN | US 169 N | NW0036 | 24.917 | Y |  | Pavement preservation treatments in Buchanan, DeKalb and Nodaway Counties. In Buchanan County Rtes. 36, 169 and 6; in DeKalb County Rte. 36 and in Nodaway County Rte. 136. | Federal | 1394 | 348 | 0 | 1742 | 0 | NHPP |  | 0 | 5 | 20 | 107 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1610 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23 | 1 | BUCHANAN | US 169 S | NW0016 | 29.954 | Y | RR-2023-04 | Pavement resurfacing from Rte. FF to Clay County and Rte. U from west of Stockyards Expressway to end of state maintenance. | Federal | 4682 | 1170 | 0 | 5852 | 0 | NHPP |  | 0 | 100 | 375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5377 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | 1 | BUCHANAN | US 169 S | NW0045 | 0.5 | Y |  | Intersection improvements at Riverside Terrace 0.6 miles south of Rte. AC. | Federal | 2359 | 262 | 0 | 2621 | 0 | SAFETY |  | 0 | 63 | 105 | 187 | 0 | 0 | 0 | 0 | 0 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25 | 1 | BUCHANAN | IS 229 N | NW0033 | 2.774 | Y | RR-2023-05 | Pavement resurfacing from 22nd Street (Rte. 371) to I-29 in St. Joseph. | Federal | 1453 | 161 | 0 | 1614 | 0 | NHPP |  | 0 | 5 | 18 | 99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1492 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
26 | 1 | BUCHANAN | IS 229 S | 1I3386 | 0.316 | Y | BR-2022-01 | Bridge rehabilitation over 6th Street and Atchison Street 0.5 mile south of Rte. 36 in St. Joseph. Project involves bridge A3032. | Federal | 4893 | 544 | 0 | 5552 | 0 | NHPP |  | 115 | 522 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4915 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
27 | 1 | BUCHANAN | IS 29 N | NW0051 | 8.608 | Y | RR-202306 | Pavement resurfacing from Pigeon Creek to the Platte County line near Faucett. | Federal | 5212 | 579 | 0 | 5791 | 0 | NHPP |  | 0 | 5 | 20 | 60 | 365 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
28 | 1 | BUCHANAN | IS 29 N | NW0097 | 298.367 | Y |  | Striping upgrades in Andrew, Atchison, Buchanan, Caldwell, Clinton, Daviess, Dekalb, Harrison, Holt, Linn, and Livingston Counties. | Federal | 1600 | 178 | 0 | 1778 | 0 | SAFETY |  | 0 | 128 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
29 | 1 | BUCHANAN | LP 29 S | NW0090 | 0.05 | Y |  | Urgent project to replace culvert and ditch grading due to local drainage concern near South 30th Street in St. Joseph. | Adv. CN | 180 | 45 | 0 | 240 | 0 | AC-STBG |  | 10 | 16 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 209 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30 | 1 | BUCHANAN | US 36 E | NW0063 | 10.99 | Y |  | Pavement resurfacing on eastbound lane from east of Rte. AC to east of Rte. 31 north near St. Joseph. | Federal | 2533 | 633 | 0 | 3166 | 0 | NHPP |  | 0 | 10 | 15 | 30 | 25 | 187 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2899 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31 | 1 | BUCHANAN | US 59 S | NW0002 | 0.235 | Y |  | Intersection improvements at Rte. 752 and Rte. U in St. Joseph. $999,829 from DEMO ID MO249, $950,000 from FY 2009 IMD and $1,186,000 Open Container funds. | Federal | 5561 | 618 | 0 | 6179 | 0 | SAFETY |  | 0 | 150 | 396 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4633 | 0 | 0 | 0 | 0 | 0 | 0 | 1949 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
32 | 1 | BUCHANAN | MO 752 E | 1P3406 | 5.309 | Y | RR-2022-02 | Pavement resurfacing from Sherman Avenue to 22nd Street on Loop 29 from 22nd Street to Rte. 169 (Belt Highway) in St. Joseph and on Rte. 59 from Country Club Road to I-29 in Country Club Village. | Adv. CN | 2134 | 534 | 0 | 2698 | 0 | AC-STBG |  | 30 | 5 | 107 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2554 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
33 | 1 | BUCHANAN | RT AC N | NW0102 | 0.502 | Y |  | Add intersection turn lanes at Messannie Street in St. Joseph. $800,000 Governor's Cost Share Program and $800,000 private entity funds. | Federal | 0 | 960 | 800 | 1760 | 0 | STATE |  | 0 | 0 | 112 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1648 | 0 | 0 | 0 | 0 | 0 | 0 | 1600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
34 | 1 | BUCHANAN | RT AC S | 1S3030 | 0.054 | Y | BR-2022-02 | Bridge rehabilitation over Rte. 36 in St. Joseph. Project involves bridge A2822. | Federal | 1698 | 424 | 0 | 2174 | 0 | NHPP |  | 52 | 40 | 10 | 6 | 5 | 123 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1938 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35 | 1 | BUCHANAN | CST COOK RD E | 1I3330 | 0.041 | Y | BR-2021-01 | Bridge rehabilitation over I-29 in St. Joseph. Project involves bridge A0700. | Federal | 924 | 231 | 0 | 1166 | 0 | NHPP | 1I3332 | 11 | 65 | 96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 994 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
36 | 1 | BUCHANAN | RT DD E | NW0048 | 0.053 | N |  | Bridge rehabilitation over Bee Creek near Faucett. Project involves bridge A2581. | Federal | 534 | 134 | 0 | 668 | 0 | NHPP |  | 0 | 5 | 4 | 30 | 39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 590 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
37 | 1 | BUCHANAN | CST GENE FIELD RD E | 1I3332 | 0.042 | Y | BR-2021-02 | Bridge rehabilitation over I-29 in St. Joseph. Project involves bridge A0701. | Federal | 1130 | 283 | 0 | 1433 | 0 | NHPP | 1I3330 | 20 | 56 | 102 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
38 | 1 | BUCHANAN | RT KK W | 1S3331 | 0.771 | N |  | Bridge rehabilitation on various bridges in Buchanan, Carroll, Gentry and Harrison Counties. Safe and Sound bridges. | Federal | 1240 | 310 | 0 | 1612 | 0 | NHPP |  | 62 | 128 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
39 | 1 | BUCHANAN | RT Y N | 1S3360 | 0.037 | N |  | Bridge replacement over Bee Creek 0.7 mile south of Rte. 116 and 0.4 mile north of Rte. 116 near Dearborn. Project involves bridges Y0010 and W0444. | Federal | 1059 | 265 | 0 | 1486 | 0 | NHPP |  | 151 | 132 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1192 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
40 | 1 | CALDWELL | MO 13 S | 1P3446 | 0.074 | N |  | Bridge rehabilitation over Rte. 36 in Hamilton. Project involves bridge A0010. | Federal | 1659 | 415 | 0 | 2184 | 0 | NHPP |  | 110 | 274 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
41 | 1 | CALDWELL | MO 13 S | NW0004 | 6.448 | N |  | Pavement resurfacing from south city limits of Hamilton to north of Rte. HH in Kingston. | Adv. CN | 4440 | 1110 | 0 | 5550 | 0 | AC-STBG |  | 0 | 450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
42 | 1 | CALDWELL | US 36 W | NW0037 | 41.513 | N |  | Pavement preservation treatment in Caldwell, Daviess, Grundy, and Linn Counties. Includes Rte. 36 in Linn County and Rte. 6 in Daviess and Grundy Counties. | Federal | 2049 | 512 | 0 | 2561 | 0 | NHPP |  | 0 | 5 | 18 | 156 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2382 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
43 | 1 | CALDWELL | RT D S | 1S3414 | 0.394 | N |  | Bridge replacement over Shoal Creek 3.5 miles north of Rte. HH and on Rte. E over Tom Creek 1.0 mile east of Rte. 13. Project involves bridge P0428 and N0318. | Federal | 2242 | 561 | 0 | 2810 | 0 | NHPP |  | 7 | 10 | 45 | 300 | 149 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
44 | 1 | CARROLL | MO 10 E | NW0015 | 21.518 | N |  | Pavement preservation treatment from Ray County line to Rte. 65 and on Rte. 136 (Nodaway County) from 0.8 miles east of Rte. 169 to west of Rte. C in Albany. | Federal | 559 | 140 | 0 | 699 | 0 | NHPP |  | 0 | 35 | 46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 618 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
45 | 1 | CARROLL | MO 139 S | NW0030 | 2.479 | N |  | Upgrade pedestrian facilities to comply with the ADA Transition Plan in Carroll and Chariton Counties. Cities include Hale, Norborne, Bosworth, Keytesville, Sumner, Mendon and Rothville. $1,695,000 Statewide Transportation Alternatives funds. | Adv. CN | 2382 | 595 | 0 | 2977 | 0 | AC-STBG |  | 0 | 105 | 247 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2575 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
46 | 1 | CARROLL | MO 41 S | 1P3430 | 0.375 | N |  | Bridge rehabilitation over the Missouri River near Miami. Project involves bridge K0999. | Federal | 1950 | 487 | 0 | 2494 | 0 | NHPP | 4S3487 | 57 | 193 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2244 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
47 | 1 | CARROLL | US 65 S | NW0024 | 10.081 | N |  | Pavement resurfacing from Rte. 24 in Carrollton to the bridge over the Missouri River near Waverly. | Federal | 2278 | 569 | 0 | 2847 | 0 | NHPP |  | 0 | 100 | 194 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2553 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
48 | 1 | CARROLL | RT B E | NW0010 | 0.947 | N |  | Bridge rehabilitation in Carroll, Chariton and Livingston Counties. Project involves bridges R0470, N0826, N0727, N0857, A1889 and L0548. | Federal | 3006 | 752 | 0 | 3758 | 0 | NHPP |  | 0 | 90 | 100 | 231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3337 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
49 | 1 | CARROLL | RT B E | NW0095 | 84.425 | N |  | Pavement resurfacing including Rte. MM in Carroll County and Rtes. 129, HH, O, WW, KK, VV and DD in Chariton County. | Federal | 0 | 9929 | 0 | 9939 | 0 | STATE | CD0130 NE0164 | 10 | 647 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9282 | 0 | 0 | 0 | 0 | 0 | 0 | 9282 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
50 | 1 | CARROLL | RT M E | 1S3387 | 0.306 | N |  | Bridge rehabilitation over the Grand River near Bosworth. Project involves bridge A2867. | Federal | 2493 | 623 | 0 | 3177 | 0 | NHPP |  | 61 | 438 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2678 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
51 | 1 | CARROLL | RT YY S | NW0093 | 106.744 | N |  | Pavement resurfacing including Rtes. Z and C in Carroll County, Rtes. BB, Y, JJ, KK, K and U in Livingston County, Rtes. K and U in Grundy County and Rte. 139 in Linn and Sullivan Counties. | Federal | 0 | 11690 | 0 | 11700 | 0 | STATE |  | 10 | 760 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10930 | 0 | 0 | 0 | 0 | 0 | 0 | 10930 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
52 | 1 | CHARITON | MO 5 S | 1P3223 | 21.123 | N |  | Pavement resurfacing from Rte. 24 to Saline County line and in Linn County from Rte. 36 to Bear Creek. Project also includes Rte. 41 in Carroll County from Rte. 24 to the Saline County line. | Adv. CN | 1908 | 477 | 0 | 2466 | 0 | AC-STBG |  | 81 | 21 | 157 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2207 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
53 | 1 | CLINTON | MO 33 N | NW0011 | 19.975 | N |  | Pavement resurfacing from Rte. 36 to Rte. 116 near Plattsburg and from Rte. 116 in Lathrop to the Clay County line. | Adv. CN | 1487 | 372 | 0 | 1859 | 0 | AC-STBG |  | 0 | 199 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1660 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
54 | 1 | CLINTON | LP 35 N | 1P3267 | 15.684 | N |  | Pavement resurfacing on Bus. 36 (Dekalb County), Rte. C (DeKalb County), Rte. 69 (Clinton County), Rte. 121 and LP 35 (Clinton County). | Adv. CN | 1770 | 442 | 0 | 2228 | 0 | AC-STBG |  | 16 | 2 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2070 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
55 | 1 | CLINTON | US 69 S | NW0042 | 7.015 | N |  | Pavement resurfacing from Rte. 116 near Lathrop to the Clay County line. | Adv. CN | 688 | 172 | 0 | 860 | 0 | AC-STBG |  | 0 | 5 | 25 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
56 | 1 | CLINTON | RT H E | 1S3363 | 0.04 | N |  | Bridge replacement over I-35 6.5 miles south of Cameron. Project involves bridge R0228. | Adv. CN | 1663 | 416 | 0 | 2202 | 0 | AC-STBG |  | 123 | 160 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 1913 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
57 | 1 | CLINTON | RT H E | NW0029 | 82.671 | Y |  | Pavement resurfacing on Rte. CC, Rte. V and Rte. Z (Andrew County), Rte. CC, Rte. NN and Rte. Z (Buchanan County), Rte. J (Clay County), Rte. H, Rte. J, Rte. NN and Rte. O (Clinton County), Rte. D, Rte. F and Rte. V (DeKalb County) and Rte. D (Gentry County). | Adv. CN | 5923 | 1481 | 0 | 7404 | 0 | AC-STBG |  | 0 | 20 | 30 | 458 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6896 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
58 | 1 | CLINTON | RT NN E | 1S3211 | 0.026 | N |  | Bridge replacement over Castile Creek 0.9 mile east of Rte. K near Stewartsville. Project involves bridge T0045. | Federal | 1007 | 252 | 0 | 1430 | 0 | NHPP |  | 161 | 121 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1138 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
59 | 1 | DAVIESS | MO 13 S | NW0089 | 14.777 | N |  | Pavement resurfacing from Rte. 6 in Gallatin to Hamilton south city limits. | Adv. CN | 2375 | 594 | 0 | 2969 | 0 | AC-STBG |  | 0 | 2 | 2 | 2 | 177 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2786 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
60 | 1 | DAVIESS | MO 190 E | NW0031 | 0.028 | N |  | Bridge replacement over Clear Creek 0.3 miles from Rte. V near Lock Springs. Project involves bridge S0442. | Federal | 1072 | 268 | 0 | 1340 | 0 | NHPP |  | 0 | 27 | 77 | 121 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
61 | 1 | DAVIESS | IS 35 N | NW0032 | 9.413 | N |  | Pavement resurfacing from Rte. C near Pattonsburg to Rte. 69. | Federal | 8716 | 968 | 0 | 9684 | 0 | NHPP |  | 0 | 20 | 80 | 606 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8978 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
62 | 1 | DAVIESS | MO 6 E | NW0062 | 8.465 | N |  | Pavement resurfacing west of Rte. V to the Grundy County line near Jamesport. | Federal | 1978 | 495 | 0 | 2473 | 0 | NHPP |  | 0 | 2 | 5 | 30 | 20 | 148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2268 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
63 | 1 | DEKALB | US 169 S | 1S3324 | 50.799 | Y | RR-2022-05 | Pavement resurfacing on Rte. 169 (DeKalb, Andrew and Buchanan County), Rte. 48 (Andrew and Gentry County), Rte. 59 (Buchanan County), Rte. 45 (Buchanan County), Rte. E (Andrew County) and Rte. CC (Gentry County). | Adv. CN | 9093 | 2273 | 0 | 11482 | 0 | AC-STBG |  | 116 | 50 | 711 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10605 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
64 | 1 | DEKALB | US 36 E | 1P3388 | 107.168 | N |  | Pavement preservation treatment including routes in Chariton, Caldwell, Carroll and Daviess Counties. Includes routes 36 (eastbound lanes), 24, 6, 69, 31, 190, A, J, and W. | Federal | 2122 | 530 | 0 | 2708 | 0 | NHPP |  | 56 | 193 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2459 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
65 | 1 | DEKALB | US 36 E | NW0098 | 0.018 | N |  | Bridge rehabilitation over I-35 in Cameron. Project involves eastbound bridge A1059. | Federal | 0 | 847 | 0 | 847 | 0 | STATE |  | 0 | 148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 699 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
66 | 1 | DEKALB | US 36 W | NW0003 | 5.52 | N |  | Pavement preservation treatment in westbound lanes from 0.8 mile east of Rte. 31 to Reservoir Road and eastbound lanes from 2.0 miles west of Rte. C to the Caldwell County line near Cameron. | Federal | 747 | 187 | 0 | 934 | 0 | NHPP |  | 0 | 10 | 2 | 2 | 56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 864 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
67 | 1 | DEKALB | MO 6 E | NW0038 | 22.77 | N |  | Pavement resurfacing from Rte. 31 to Rte. 69 near Altamont. | Adv. CN | 2284 | 571 | 0 | 2855 | 0 | AC-STBG |  | 0 | 5 | 50 | 192 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2608 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
68 | 1 | DEKALB | US 69 S | 1P3373 | 0.1 | N |  | Add intersection turn lanes at intersection with Rte. EE north of Cameron. | Federal | 783 | 87 | 0 | 994 | 0 | SAFETY |  | 124 | 114 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 751 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
69 | 1 | GENTRY | US 136 E | 1P3235 | 24.742 | N |  | Pavement resurfacing from Stanberry to 0.7 mile east of Rte. 169 and from 0.6 mile east of Rte. C in Albany to Rte. 13 near Bethany. Two disconnected sections. | Federal | 4132 | 1033 | 0 | 5241 | 0 | NHPP |  | 76 | 40 | 361 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4764 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
70 | 1 | GENTRY | RT B N | NW0009 | 0.745 | N |  | Bridge rehabilitation in Daviess, Gentry, Harrison and Worth Counties. Project involves bridges A1589, A1874, A07448, A2291 and A1048. | Adv. CN | 4472 | 1118 | 0 | 5590 | 0 | AC-STBG |  | 0 | 145 | 150 | 336 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4959 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
71 | 1 | GENTRY | RT E E | 1S3216 | 0.023 | N |  | Bridge replacement over Walnut Fork 1.1 miles east of Rte. 169 near Stanberry. Project involves bridge T0195. | Federal | 740 | 185 | 0 | 1033 | 0 | NHPP | 1S3361 | 106 | 88 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 837 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
72 | 1 | GENTRY | RT FF E | NW0001 | 33.54 | N |  | Pavement resurfacing in Gentry, Harrison and Worth Counties. Includes Rtes. FF, U and J in Gentry and Worth County, Rte. NN in Harrison County, and Rte. Y in Worth County. $2,460,000 District Operation funds. | Adv. CN | 2107 | 527 | 0 | 2649 | 0 | AC-STBG |  | 15 | 174 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2460 | 0 | 0 | 0 | 0 | 0 | 0 | 2460 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
73 | 1 | GENTRY | RT YY S | NW0007 | 0.116 | N |  | Bridge replacement over Bear Creek 1.8 miles north of Rte. 169 near Gentry. Project involves bridge H0551. | Federal | 1361 | 340 | 0 | 1701 | 0 | NHPP |  | 0 | 175 | 147 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1374 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
74 | 1 | GRUNDY | MO 190 E | NW0053 | 11.459 | N |  | Pavement resurfacing from Rte. 46 to Rte. 6 near Jamesport. | Adv. CN | 968 | 242 | 0 | 1210 | 0 | AC-STBG |  | 0 | 5 | 15 | 30 | 78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1082 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
75 | 1 | GRUNDY | MO 6 E | 1P3316 | 0.36 | N |  | Add intersection turn lanes at Rte. 146 and at 30th Avenue, 1.4 miles and 0.3 mile west of the Thompson River near Trenton. $493,000 Open Container funds. | Federal | 2311 | 257 | 0 | 2686 | 0 | SAFETY |  | 112 | 125 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2443 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
76 | 1 | GRUNDY | RT E E | NW0013 | 0.676 | N |  | Bridge rehabilitation in Grundy and Linn Counties. Project involves bridges X0153, P0891 and A1802. | Federal | 1276 | 319 | 0 | 1595 | 0 | NHPP |  | 0 | 30 | 30 | 103 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
77 | 1 | GRUNDY | RT W N | 1S3361 | 0.041 | N |  | Bridge replacement over Hickory Creek 0.7 mile north of Rte. F and Wolf Creek 1.3 miles north of Rte. WW near Trenton. Project involves bridges P0202 and S0657. | Federal | 1715 | 429 | 0 | 2390 | 0 | NHPP | 1S3216 | 231 | 186 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1958 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
78 | 1 | HARRISON | IS 35 N | NW0052 | 7.875 | N |  | Pavement resurfacing from Iowa State line to Rte. N near Eagleville. | Federal | 8032 | 892 | 0 | 8924 | 0 | NHPP |  | 0 | 10 | 80 | 150 | 584 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
79 | 1 | HARRISON | IS 35 S | 1I3437 | 14.037 | N |  | Pavement preservation treatment from Rte. N to Rte. 136 in Bethany. | Federal | 637 | 71 | 0 | 710 | 0 | NHPP |  | 2 | 15 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
80 | 1 | HARRISON | IS 35 S | NW0017 | 81.29 | N |  | Job Order Contracting for pavement repair from the Iowa State line to the Clay County line. | Federal | 999 | 111 | 0 | 1124 | 0 | NHPP |  | 14 | 5 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
81 | 1 | HARRISON | US 69 N | NW0057 | 0.165 | N |  | Bridge replacement over Zadie Branch 1.0 mile west of I-35. Project involves bridge L0267. | Federal | 351 | 88 | 0 | 439 | 0 | NHPP |  | 0 | 5 | 5 | 20 | 30 | 41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 338 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
82 | 1 | HARRISON | RT N E | NW0058 | 0.469 | N |  | Bridge rehabilitation over East Fork Big Creek 1.6 miles east of I-35. Project involves bridge A2402. | Federal | 1226 | 306 | 0 | 1532 | 0 | NHPP |  | 0 | 5 | 10 | 20 | 30 | 103 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
83 | 1 | HOLT | MO 111 N | NW0056 | 0.359 | N |  | Bridge replacement over the Tarkio River near Craig. Project involves bridge T0104. | Adv. CN | 1266 | 316 | 0 | 1582 | 0 | AC-STBG |  | 0 | 5 | 15 | 50 | 100 | 95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1317 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
84 | 1 | HOLT | US 159 N | 1P3383 | 0.462 | N |  | Payment to Nebraska DOT for bridge rehabilitation over the Missouri River, near Rulo Nebraska. Project involves bridge A7698. | Federal | 282 | 70 | 0 | 353 | 0 | NHPP |  | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
85 | 1 | HOLT | US 159 S | 1S3329 | 6.399 | N |  | Pavement resurfacing from Little Tarkio Creek to I-29 near Mound City. | Adv. CN | 1642 | 410 | 0 | 2064 | 0 | AC-STBG |  | 12 | 47 | 145 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1860 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
86 | 1 | HOLT | IS 29 N | NW0050 | 15.09 | N |  | Pavement resurfacing from Rte. 118 to Rte. W near Mound City. | Federal | 9239 | 1027 | 0 | 10266 | 0 | NHPP |  | 0 | 10 | 25 | 100 | 602 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
87 | 1 | HOLT | IS 29 N | NW0061 | 9.32 | N |  | Pavement resurfacing from Rte. 59 to Rte. 118. | Federal | 17844 | 1983 | 0 | 19827 | 0 | NHPP |  | 0 | 15 | 50 | 150 | 250 | 1160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18202 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
88 | 1 | HOLT | IS 29 S | 1I3317 | 14.027 | Y | RR-2022-04 | Pavement resurfacing from Rte. 59 north of Nodaway River to Bus. 71 north of St. Joseph. | Federal | 7372 | 819 | 0 | 8242 | 0 | NHPP |  | 51 | 108 | 564 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7519 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
89 | 1 | HOLT | US 59 S | 1S3325 | 22.125 | N |  | Pavement resurfacing and add rumble stripes from east of Rte. B to I-29 in Holt County; pavement resurfacing from Iowa State line to Rte. 136 in Tarkio; from Rte. 136 east of Tarkio to Rte. 46 in Atchison County. $759,000 Open Container funds. | Adv. CN | 2328 | 582 | 0 | 2927 | 0 | AC-STBG | 1S3326 | 17 | 36 | 198 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2676 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90 | 1 | HOLT | US 59 S | NW0019 | 0.1 | N |  | Repair slide 1.1 miles south of Rte. 111 near Oregon. | Adv. CN | 1616 | 404 | 0 | 2035 | 0 | AC-STBG |  | 15 | 45 | 136 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1819 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
91 | 1 | HOLT | RT B S | 1S3276 | 0.017 | N |  | Bridge replacement over Hickory Creek 4.2 miles south of Rte. 113 near Mound City. Project involves bridge K0841. | Federal | 1292 | 323 | 0 | 1711 | 0 | NHPP |  | 96 | 3 | 103 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1499 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
92 | 1 | HOLT | RT H E | NW0091 | 76.393 | N |  | Pavement resurfacing including Rtes. T, DD, BB and HH in Holt County, Rtes. EE, CC, Z, and KK in Atchison County, Rte. PP in Nodaway County and Rte. M in Gentry and Nodaway Counties. | Federal | 0 | 7995 | 0 | 8005 | 0 | STATE |  | 10 | 523 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7472 | 0 | 0 | 0 | 0 | 0 | 0 | 7472 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
93 | 1 | LINN | MO 11 S | NW0096 | 0.102 | N |  | Payment to private entity to add turn lane at Park Circle Drive in Brookfield. $111,125 Cost Share funds. | Adv. CN | 90 | 23 | 0 | 113 | 0 | AC-STBG |  | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
94 | 1 | LINN | US 36 E | 1P3333 | 0.292 | N |  | Curve safety improvements in the eastbound and westbound lanes 0.5 mile east of Rte. 5 near Marceline and in the westbound lane 0.1 mile east of Rte. B near Wheeling in Livingston County. | Federal | 120 | 13 | 0 | 143 | 0 | SAFETY |  | 10 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
95 | 1 | LINN | MO 5 N | NW0054 | 32.476 | N |  | Pavement resurfacing from Rte. 36 to Rte. 6 north near Milan. | Adv. CN | 7510 | 1878 | 0 | 9388 | 0 | AC-STBG |  | 0 | 10 | 15 | 100 | 557 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8706 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
96 | 1 | LINN | MO 5 S | 1P3288 | 1.122 | N |  | Upgrade pedestrian facilities to comply with the ADA Transition Plan along Rte. O in Purdin and along Rte. MM in Browning. $423,000 Statewide Transportation Alternatives funds. | Adv. CN | 662 | 165 | 0 | 1052 | 0 | AC-STBG |  | 225 | 278 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
97 | 1 | LINN | RT Y N | NW0027 | 77.632 | N |  | Pavement resurfacing on Rte. Y, Rte. FF, Rte. DD, Rte. 130 and Rte. Y (Linn County), Rte. YY, Rte. Y, Rte. FF and Rte. MM (Chariton County), Rte. V ( Livingston County) and Rte. V (Grundy County). | Adv. CN | 7297 | 1824 | 0 | 9121 | 0 | AC-STBG |  | 0 | 65 | 575 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8481 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
98 | 1 | LIVINGSTON | US 36 E | 1P3318 | 9.98 | N |  | Pavement resurfacing on US 36 at Canadian Pacific railroad and Rte. 65 in Chillicothe and in the westbound lanes from Coon Creek to the Caldwell County line. | Federal | 4974 | 1243 | 0 | 6251 | 0 | NHPP |  | 34 | 6 | 394 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5817 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
99 | 1 | LIVINGSTON | US 65 S | 1P3367 | 30.656 | N |  | Pavement resurfacing from Rte. 36 in Chillicothe to Rte. 24 in Carrollton. Impacts Canadian Pacific railroad at Rte. 65. | Federal | 11971 | 2993 | 0 | 15003 | 0 | NHPP |  | 39 | 30 | 64 | 934 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13936 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
100 | 1 | LIVINGSTON | US 65 S | NW0022 | 4.447 | N |  | Pavement resurfacing from 1.3 miles north of Rte. 190 to Rte. 36 in Chillicothe. | Federal | 3098 | 775 | 0 | 3873 | 0 | NHPP |  | 0 | 20 | 247 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3606 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
101 | 1 | LIVINGSTON | RT B E | 1S3393 | 0.894 | N |  | Upgrade pedestrian facilities to comply with the ADA Transition Plan on Rte. B in Wheeling Rte K in Chula and Rtes. D and DD in Ludlow. | Adv. CN | 1465 | 366 | 0 | 1990 | 0 | AC-STBG |  | 159 | 400 | 171 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
102 | 1 | LIVINGSTON | RT C S | 1S3362 | 0.035 | N |  | Bridge replacement over Shoal Creek drainage ditch 4.2 miles south of Utica. Project involves bridge S0639. | Federal | 1789 | 447 | 0 | 2318 | 0 | NHPP |  | 80 | 88 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
103 | 1 | MERCER | US 136 E | 1P3225 | 7.4 | N |  | Pavement resurfacing and add rumblestripes from Rte. 65 in Princeton to Rte. C. $505,000 Open Container funds. | Adv. CN | 2108 | 527 | 0 | 2683 | 0 | AC-STBG |  | 48 | 25 | 172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2438 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
104 | 1 | MERCER | US 136 E | 1P3226 | 11.979 | N |  | Pavement resurfacing from Harrison County line to Rte. 65 in Princeton. | Federal | 2162 | 541 | 0 | 2725 | 0 | NHPP |  | 22 | 14 | 173 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2516 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
105 | 1 | MERCER | US 136 E | 1S3396 | 0.11 | N |  | Section 14 streambank protection at bridge over Weldon Fork. Corps of Engineers to design and administer project. Cost shown represents MoDOT's share. Payment to Corps for design work. Project involves bridge A3767. | Adv. CN | 195 | 49 | 0 | 254 | 0 | AC-STBG |  | 10 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
106 | 1 | MERCER | US 136 E | 1S3442 | 24.175 | N |  | Pavement resurfacing from Rte. C to Rte. 5 west of Unionville. | Adv. CN | 2402 | 601 | 0 | 3053 | 0 | AC-STBG |  | 50 | 10 | 55 | 197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2741 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
107 | 1 | MERCER | US 65 S | 1S3438 | 2.052 | N |  | Upgrade pedestrian facilities to comply with ADA Transition Plan in Mercer and Putnam Counties. Towns involved are Mercer, Princeton, South Lineville and Powersville. $776,000 Statewide Transportation Alternatives funds. | Adv. CN | 2369 | 592 | 0 | 3014 | 0 | AC-STBG |  | 53 | 100 | 291 | 254 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2295 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
108 | 1 | MERCER | RT D E | NW0026 | 1.08 | N |  | Bridge replacements in Carroll, Chariton, Grundy, Linn, Livingston, Mercer, Putnam and Sullivan Counties. Design-Build project. | Adv. CN | 22057 | 5514 | 0 | 27571 | 0 | AC-STBG |  | 0 | 500 | 2247 | 0 | 0 | 0 | 0 | 0 | 0 | 52 | 0 | 0 | 0 | 0 | 0 | 0 | 24772 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
109 | 1 | MERCER | RT E E | NW0014 | 0.901 | N |  | Bridge rehabilitation in Mercer, Putnam and Sullivan Counties. Project involves bridges A2636, N0254, P0833 and N0973. | Adv. CN | 1832 | 458 | 0 | 2290 | 0 | AC-STBG |  | 0 | 50 | 70 | 138 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2032 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
110 | 1 | MERCER | RT E E | NW0059 | 0.402 | N |  | Bridge rehabilitation over Little Medicine Creek 2 miles west of Rte. 139 near Harris. Project involves bridge A2636. | Federal | 2480 | 620 | 0 | 3100 | 0 | NHPP |  | 0 | 5 | 30 | 50 | 80 | 188 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2747 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
111 | 1 | NODAWAY | US 136 E | NW0034 | 7.354 | N |  | Pavement resurfacing from Rte. 46 south of Ravenwood to Rte. J. | Federal | 1557 | 389 | 0 | 1946 | 0 | NHPP |  | 0 | 3 | 20 | 119 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1804 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
112 | 1 | NODAWAY | MO 46 E | 1S3429 | 11.653 | N |  | Pavement resurfacing from Icon Road to east of 102 River in Maryville and from Rte. J to Rte. 169 in Stanberry. | Federal | 3006 | 751 | 0 | 3870 | 0 | NHPP |  | 113 | 286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3471 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
113 | 1 | NODAWAY | US 71 N | 1P3283 | 5.16 | Y |  | Pavement resurfacing in Andrew County in southbound lanes from south of Rte. B to north of Rte. 48 and on various sections of northbound lane in Andrew and Nodaway Counties from south of Rte. T to south of Rte. V in Maryville. | Federal | 11226 | 2807 | 0 | 14059 | 0 | NHPP | NW0012 | 26 | 1079 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12954 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
114 | 1 | NODAWAY | US 71 S | NW0044 | 21.545 | N |  | Pavement resurfacing from the Iowa State line to Rte. 148 north of Maryville. | Federal | 4917 | 1229 | 0 | 6146 | 0 | NHPP |  | 0 | 85 | 100 | 409 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5552 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
115 | 1 | NODAWAY | RT NN E | NW0028 | 78.237 | N |  | Pavement resurfacing in Andrew, Holt and Nodaway Counties. Routes include Rte. Y (Andrew County); Rte. C (Holt County); Rte.'s NN, AH, WW, AB, JJ, N and Y (Nodaway County). | Adv. CN | 5498 | 1375 | 0 | 6873 | 0 | AC-STBG |  | 0 | 50 | 437 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6386 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
116 | 1 | NODAWAY | RT VV E | NW0046 | 0.207 | N |  | Bridge replacement over Platte River 0.4 mile west of Rte. AH near conception Junction. Project involves bridge R0014. | Federal | 2294 | 573 | 0 | 2867 | 0 | NHPP |  | 0 | 15 | 100 | 250 | 153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2349 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
117 | 1 | PUTNAM | US 136 E | NW0043 | 17.838 | N |  | Pavement resurfacing from Rte. 5 west of Unionville to Rte. N at Livonia. | Adv. CN | 2359 | 590 | 0 | 2949 | 0 | AC-STBG |  | 0 | 10 | 75 | 212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2652 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
118 | 1 | PUTNAM | MO 5 S | 1P3246 | 8.435 | N |  | Pavement resurfacing from Iowa State line to Rte. 136 in Unionville. | Adv. CN | 2060 | 515 | 0 | 2590 | 0 | AC-STBG |  | 15 | 47 | 177 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
119 | 1 | PUTNAM | MO 5 S | NW0040 | 20.667 | N |  | Pavement resurfacing and add rumblestripes from Rte. 136 east of Unionville to Rte. 6 north of Milan. $770,000 Open Container funds. | Adv. CN | 8039 | 2010 | 0 | 10049 | 0 | AC-STBG |  | 0 | 50 | 150 | 645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
120 | 1 | PUTNAM | RT F W | NW0094 | 111.903 | N |  | Pavement resurfacing including Rtes. FF, N, KK, EE and BB in Putnam County, Rtes. BB, M, V, O and U in Sullivan County and Rtes. V and CC in Linn County. | Federal | 0 | 13102 | 0 | 13112 | 0 | STATE |  | 10 | 851 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12251 | 0 | 0 | 0 | 0 | 0 | 0 | 12251 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
121 | 1 | SULLIVAN | MO 129 S | 1P3168 | 1.19 | N |  | Upgrade pedestrian facilities to comply with the ADA Transition Plan in Green City. $135,000 Statewide Transportation Alternatives funds. | Adv. CN | 645 | 161 | 0 | 986 | 0 | AC-STBG |  | 180 | 5 | 5 | 25 | 66 | 0 | 0 | 0 | 0 | 0 | 46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 659 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
122 | 1 | SULLIVAN | MO 6 E | NW0023 | 3.58 | N |  | Pavement resurfacing from Rte. 129 in Green City to west city limits of Green Castle. | Adv. CN | 592 | 148 | 0 | 740 | 0 | AC-STBG |  | 0 | 15 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 670 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
123 | 1 | SULLIVAN | Various | 1S3392 | 0 | N |  | Roadway and bridge improvements around the proposed East Locust Creek Reservoir on Rtes. 5, N, VV and RA near Milan. $13,459,009 BUILD and $9,227,601 Cost Share funds. | Adv. CN | 17294 | 4324 | 0 | 22887 | 0 | AC-STBG |  | 1217 | 1124 | 0 | 0 | 0 | 0 | 0 | 52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20494 | 0 | 0 | 0 | 0 | 0 | 212 | 13247 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
124 | 1 | VARIOUS | Various | 1P3244 | 0 | Y | HE-2019-01 | Job Order Contracting for guardrail and guard cable repair on various major route locations in the Northwest District. | Adv. CN | 1716 | 429 | 0 | 2152 | 0 | AC-NHPP |  | 7 | 145 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
125 | 1 | VARIOUS | Various | 1P3394 | 0 | Y |  | On-call work zone enforcement at various locations in the Northwest District. | Federal | 10 | 1 | 0 | 12 | 0 | SAFETY |  | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
126 | 1 | VARIOUS | Various | 1P3439 | 0 | Y |  | On-call work zone enforcement at various locations in the Northwest District. | Federal | 11 | 1 | 0 | 13 | 0 | SAFETY |  | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
127 | 1 | VARIOUS | Various | 5B0800O | 0 | Y | BR-33 | Payback beginning in SFY 2008 for Safe and Sound bridges in the Northwest District. | Federal | 0 | 44865 | 0 | 143557 | 50,001 - 75,000 | STATE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 169 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 169 | 0 | 0 | 0 | 0 | 0 | 0 | 98523 | 8973 | 8973 | 8973 | 8973 | 8973 | 0
128 | 1 | VARIOUS | Various | NW0025 | 0 | Y | RR-2022-06 | Job Order Contracting for concrete pavement repair on various routes in the Northwest district. | Adv. CN | 1716 | 429 | 0 | 2150 | 0 | AC-STBG |  | 5 | 145 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
129 | 1 | VARIOUS | Various | NW0039 | 0 | Y |  | On-call work zone enforcement at various locations in the Northwest District. | Federal | 9 | 2 | 0 | 11 | 0 | NHPP |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
130 | 1 | VARIOUS | Various | NW0065 | 0 | Y | HE-2023-05 | Job Order Contracting for guardrail and guard cable repair on various major routes in the Northwest District. | Adv. CN | 1705 | 426 | 0 | 2131 | 0 | AC-NHPP |  | 0 | 2 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
131 | 1 | WORTH | US 169 N | NW0049 | 0.886 | N |  | Bridge rehabilitation over Middle Fork Grand River 2.3 miles south of Grant City. Project involves bridge A0448. | Federal | 1140 | 285 | 0 | 1425 | 0 | NHPP |  | 0 | 15 | 35 | 20 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
132 | 1 | WORTH | US 169 S | 1P3304 | 5.863 | N |  | Pavement resurfacing from the Iowa State line to Rte. 46 at Grant City. | Adv. CN | 2282 | 570 | 0 | 2883 | 0 | AC-STBG |  | 31 | 18 | 113 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2721 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
133 | 1 | WORTH | MO 46 E | NW0020 | 0.074 | N |  | Bridge replacement over Marlowe Branch and over the West Fork Grand River. Project involves bridges J0024 and X0142. | Federal | 2419 | 605 | 0 | 3024 | 0 | NHPP |  | 0 | 30 | 55 | 187 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2742 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
134 | 1 | WORTH | RT M E | NW0092 | 119.349 | N |  | Pavement resurfacing including Rtes. F, MM, T and M in Harrison County, Rtes. U, JJ, D, C and NN in Mercer County and Rtes. NN, B and C in Grundy County. | Federal | 0 | 13972 | 0 | 13982 | 0 | STATE |  | 10 | 907 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13065 | 0 | 0 | 0 | 0 | 0 | 0 | 13065 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
135 | 2 | ADAIR | MO 11 S | 2S3256 | 0.075 | N |  | Bridge improvement over Mussel Fork 2.6 miles north of Rte. 129 near Winigan. Project involves bridge K0304. | Federal | 1183 | 296 | 0 | 1502 | 0 | NHPP |  | 23 | 110 | 174 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1193 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
136 | 2 | ADAIR | MO 3 S | 2S3410 | 52.175 | N |  | Pavement improvement from Rte. 11 to Rte. 24 in Clifton Hill in Randolph County (three disconnected sections). | Adv. CN | 3833 | 958 | 0 | 4793 | 0 | AC-STBG |  | 2 | 2 | 332 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4456 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
137 | 2 | ADAIR | MO 6 E | 2P2193 | 0.172 | N |  | Bridge replacement over Chariton River 1 mile east of Rte. 149 near Novinger. Project involves bridge L0534. | Federal | 3986 | 997 | 0 | 5403 | 0 | NHPP | 2P0791 | 418 | 463 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4520 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
138 | 2 | ADAIR | MO 6 E | NE0045 | 6.062 | N |  | Pavement improvement from 1 mile east of Rte. 149 at the Chariton River to Bus. 63 in Kirksville. | Federal | 184 | 46 | 0 | 230 | 0 | NHPP |  | 0 | 1 | 2 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
139 | 2 | ADAIR | MO 6 E | NE0046 | 20.866 | N |  | Pavement improvement from 0.2 mile east of Rte. 63 to Rte. 15 south junction in Knox County near Edina. | Federal | 630 | 158 | 0 | 788 | 0 | NHPP |  | 0 | 2 | 6 | 49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 731 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
140 | 2 | ADAIR | MO 6 E | NE0142 | 0.201 | N |  | Bridge improvement over abandoned railroad 0.3 mile east of Rte. B in Kirksville. Project involves bridge A2901. | Federal | 464 | 116 | 0 | 580 | 0 | NHPP |  | 0 | 80 | 5 | 35 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 458 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
141 | 2 | ADAIR | MO 6 W | NE0044 | 15 | N |  | Pavement improvement from the Chariton River near Novinger to Rte. 129 in Sullivan County. | Federal | 298 | 75 | 0 | 373 | 0 | NHPP |  | 0 | 1 | 5 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
142 | 2 | ADAIR | BU 63 S | NE0100 | 3.179 | N |  | Pavement improvement from 0.4 mile south of Rte. 63 to Rte. 11 in Kirksville. | Adv. CN | 1906 | 477 | 0 | 2383 | 0 | AC-STBG |  | 0 | 2 | 2 | 15 | 25 | 143 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2185 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
143 | 2 | ADAIR | RT A N | NE0135 | 0.984 | N |  | Bridge deck sealing in Adair, Macon, Schuyler, Scotland, Clark, Knox, Lewis, Shelby Cos. Bridges B0113, B0114, B0118, B0177, B0178, B0179, B0181, B0182, B0183, B0184, B0185, B0186, B0187, B0580, B0188, B0141, B0143, B0144, B0160, B0161, B0162, B0217, B0218, B0219, B0221. | Federal | 1202 | 301 | 0 | 1503 | 0 | NHPP |  | 0 | 279 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1224 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
144 | 2 | ADAIR | RT A S | NE0140 | 0.033 | N |  | Bridge improvement over North Fork South Fabius River 1.2 miles east of Rte. J near Willmathsville. Project involves bridge T0885. | Federal | 1206 | 302 | 0 | 1508 | 0 | NHPP |  | 0 | 200 | 15 | 83 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1208 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
145 | 2 | ADAIR | RT B S | 2S3449 | 0.034 | N |  | Bridge replacement over Hazel Creek 3.8 miles south of Rte. K near Fegley. Project involves bridge P0092. | Federal | 897 | 224 | 0 | 1338 | 0 | NHPP | 2S3320 2S3322 | 215 | 86 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
146 | 2 | ADAIR | RT E E | NE0141 | 0.021 | N |  | Bridge improvement over Bear Creek 1.6 miles west of Rte. V near Gibbs. Project involves bridge X0160. | Federal | 902 | 225 | 0 | 1127 | 0 | NHPP |  | 0 | 199 | 10 | 60 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 856 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
147 | 2 | ADAIR | RT P E | NE0025 | 1.562 | N |  | Pavement improvement from Bus. 63 to Rte. 63 in Kirksville. | Adv. CN | 130 | 33 | 0 | 163 | 0 | AC-STBG |  | 0 | 1 | 2 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 149 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
148 | 2 | ADAIR | RT V S | NE0049 | 0.017 | N |  | Bridge improvement over North Timber Creek 0.9 mile south of Rte. 6 near Brashear. Project involves bridge S0393. | Federal | 935 | 234 | 0 | 1169 | 0 | NHPP |  | 0 | 199 | 75 | 68 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 825 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
149 | 2 | AUDRAIN | MO 22 E | 2P3396 | 0.442 | N |  | Upgrade pedestrian facilities to comply with the ADA Transition Plan at various locations in Mexico and Farber. $541,000 Statewide Transportation Alternatives funds. | Federal | 641 | 160 | 0 | 1007 | 0 | STBG |  | 206 | 15 | 72 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 709 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
150 | 2 | AUDRAIN | MO 22 E | NE0151 | 0.081 | N |  | Bridge improvement over Kansas City Southern Railroad 0.2 mile west of Rte. 151 west junction, near Sturgeon. Project involves bridge K0672. | Federal | 2444 | 611 | 0 | 3055 | 0 | NHPP |  | 0 | 200 | 100 | 125 | 176 | 0 | 0 | 0 | 0 | 52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2402 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
151 | 2 | AUDRAIN | MO 22 W | 2P3095 | 17.661 | N |  | Pavement improvement and add rumblestripes from 0.1 mile west of Rte. E near Mexico to Rte. F in Boone County. | Adv. CN | 2505 | 626 | 0 | 3158 | 0 | AC-STBG |  | 27 | 5 | 10 | 192 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2923 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
152 | 2 | AUDRAIN | US 54 E | 2P3406 | 0.099 | N |  | Bridge painting over West Fork Cuivre River and on Rte. 61 over Norfolk Southern Railroad and over Bear Creek in Ralls County. Project involves bridges G0870, A1060 and A1061. | Federal | 421 | 105 | 0 | 536 | 0 | NHPP |  | 10 | 43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 483 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
153 | 2 | AUDRAIN | RT C S | NE0125 | 0.018 | N |  | Bridge improvement over Goodwater Creek 1.8 miles north of Rte. T near Centrailia. Project involves bridge R0428. | Federal | 798 | 199 | 0 | 997 | 0 | NHPP |  | 0 | 145 | 74 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 776 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
154 | 2 | AUDRAIN | RT D W | 2S3415 | 16.25 | N |  | Pavement improvement from Rte. Z to 0.1 mile south of Rte. 15 in Mexico. | Adv. CN | 1218 | 305 | 0 | 1525 | 0 | AC-STBG |  | 2 | 2 | 104 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
155 | 2 | AUDRAIN | RT FF W | 2S3417 | 13.568 | N |  | Pavement improvement from Rte. Z to 1 mile east of Rte. 15 in Mexico. | Adv. CN | 982 | 245 | 0 | 1228 | 0 | AC-STBG |  | 1 | 2 | 83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1142 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
156 | 2 | AUDRAIN | RT K E | 2S3314 | 0.06 | N |  | Bridge improvement over Hickory Creek 1.7 miles west of Rte. W near Farber. Project involves bridge X0614. | Federal | 857 | 214 | 0 | 1084 | 0 | NHPP |  | 13 | 105 | 112 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
157 | 2 | AUDRAIN | RT M S | 2S3418 | 2.222 | N |  | Pavement improvement from Rte. FF to Rte. D near Mexico. | Adv. CN | 186 | 46 | 0 | 233 | 0 | AC-STBG |  | 1 | 1 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
158 | 2 | CLARK | US 136 E | 2P3335 | 19.014 | N |  | Pavement resurfacing from 2.5 miles east of Rte. BB to Rte. 61 near Alexandria (two disconnected sections). | Adv. CN | 4807 | 1202 | 0 | 6013 | 0 | AC-STBG | 2MAMD02 2MAMD09 2S3338 | 4 | 414 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5595 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
159 | 2 | CLARK | US 136 E | NE0155 | 0.016 | N |  | Bridge improvement over drainage ditch 3 miles west of Rte. 61 near Alexandria. Project involves bridge F0955. | Federal | 1067 | 267 | 0 | 1334 | 0 | NHPP |  | 0 | 60 | 50 | 20 | 118 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
160 | 2 | CLARK | US 61 S | 2P3062 | 1.65 | N |  | Roadway improvement from the Iowa State line to east of Rte. 136 near Alexandria. | Federal | 4038 | 1010 | 0 | 5220 | 0 | NHPP |  | 172 | 10 | 318 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4620 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
161 | 2 | CLARK | US 61 S | 2P3353 | 13.161 | N |  | Pavement improvements from the Iowa State line to 0.5 mile north of Rte. B in Lewis County near LaGrange (nine disconnected sections). Project includes southbound and northbound lanes on Rte. 27 from the Iowa State line to the Rte. 61 interchange. | Federal | 3950 | 987 | 0 | 4956 | 0 | NHPP |  | 19 | 55 | 375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4507 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
162 | 2 | CLARK | MO 81 S | 2S3338 | 14.284 | N |  | Pavement resurfacing from Iowa State line to Rte. 136 at Kahoka. | Adv. CN | 1306 | 326 | 0 | 1638 | 0 | AC-STBG | 2MAMD02 2MAMD09 2P3335 | 4 | 115 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1517 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
163 | 2 | CLARK | RT D E | NE0165 | 41.655 | N |  | Pavement resurfacing from Rte. A to Rte. 81 and on Rte. AA in Knox County, Rte. W in Scotland County and Rte. M in Scotland and Knox Counties. | Federal | 0 | 6498 | 0 | 6578 | 0 | STATE |  | 80 | 421 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6077 | 0 | 0 | 0 | 0 | 0 | 0 | 6077 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
164 | 2 | KNOX | MO 11 S | NE0024 | 42.609 | N |  | Pavement improvement from Rte. 15 near Baring to Rte. 129 in Linn County (three disconnected sections). | Adv. CN | 3526 | 882 | 0 | 4408 | 0 | AC-STBG |  | 0 | 2 | 50 | 279 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4077 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
165 | 2 | KNOX | MO 15 S | NE0101 | 32.044 | N |  | Pavement improvement from Rte. 6 north junction at Edina to Rte. 168 in Shelbyville in Shelby County. | Adv. CN | 1017 | 254 | 0 | 1271 | 0 | AC-STBG |  | 0 | 1 | 1 | 2 | 2 | 74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1191 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
166 | 2 | KNOX | MO 151 S | NE0030 | 22.702 | N |  | Pavement improvement from Rte. 15 to 0.3 mile north of Rte. 36 near Clarence in Shelby County. | Adv. CN | 1868 | 467 | 0 | 2335 | 0 | AC-STBG |  | 0 | 2 | 15 | 144 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2173 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
167 | 2 | KNOX | RT BB S | NE0148 | 0.025 | N |  | Bridge improvement over North River 1.1 miles south of Rte. 15. Project involves bridge P0989. | Federal | 1077 | 269 | 0 | 1346 | 0 | NHPP |  | 0 | 2 | 125 | 100 | 90 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
168 | 2 | KNOX | RT F E | NE0149 | 0.016 | N |  | Bridge improvement over Little Fabius Creek 3.3 miles west of Rte. 15 near Hurdland. Project involves bridge P0400. | Federal | 750 | 187 | 0 | 937 | 0 | NHPP |  | 0 | 2 | 100 | 25 | 57 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 751 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
169 | 2 | LEWIS | MO 16 E | 2S3328 | 0.093 | N |  | Bridge rehabilitation over Rte. 61 0.7 mile north of Rte. P at Canton. Project involves bridge A3381. | Federal | 527 | 132 | 0 | 680 | 0 | NHPP | 2S3327 | 21 | 83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
170 | 2 | LEWIS | RT C E | NE0027 | 14.38 | N |  | Pavement improvement from Rte. 6 in Ewing to Rte. B in LaGrange. | Adv. CN | 1188 | 297 | 0 | 1485 | 0 | AC-STBG |  | 0 | 2 | 10 | 94 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
171 | 2 | LEWIS | RT H S | NE0150 | 0.06 | N |  | Bridge improvement over Middle Fabius River 2.3 miles south of Rte. Y. Project involves bridge R0153. | Federal | 1955 | 489 | 0 | 2444 | 0 | NHPP |  | 0 | 2 | 202 | 125 | 148 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
172 | 2 | LEWIS | RT P S | 2S3327 | 0.083 | N |  | Bridge rehabilitation over Rte. 61 0.7 mile south of Rte. 16 at Canton. Project involves bridge A3382. | Federal | 410 | 102 | 0 | 530 | 0 | NHPP | 2S3328 | 18 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 442 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
173 | 2 | LEWIS | RT V E | NE0146 | 0.484 | N |  | Upgrade pedestrian facilities to comply with the ADA Transition Plan from Olive Avenue to 292nd Avenue in Maywood. $108,000 Statewide Transportation Alternatives funds. | Federal | 151 | 38 | 0 | 189 | 0 | STBG |  | 0 | 15 | 10 | 19 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
174 | 2 | LINCOLN | MO 147 S | 2S3375 | 2.333 | N |  | Pavement resurfacing from beginning of state maintenance to Rte. 47 near Troy. | Federal | 0 | 266 | 0 | 267 | 0 | STATE |  | 1 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 236 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
175 | 2 | LINCOLN | MO 147 S | NE0124 | 0.015 | N |  | Bridge improvement over Little Sugar Creek 1.8 miles north of Rte. 47 near Troy. Project involves bridge L0844. | Adv. CN | 686 | 171 | 0 | 857 | 0 | AC-STBG |  | 0 | 125 | 60 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 671 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
176 | 2 | LINCOLN | MO 47 S | 2P3043 | 0.524 | N |  | Modify interchange configuration at Rte. 61 in Troy. Project involves bridge A2604. | Adv. CN | 15828 | 3957 | 0 | 20422 | 0 | AC-STBG |  | 637 | 810 | 1200 | 0 | 0 | 0 | 0 | 0 | 1985 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15790 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
177 | 2 | LINCOLN | MO 47 S | 2P3304 | 10.523 | N |  | Pavement resurfacing from Rte. A in Hawk Point to 0.2 mile north of I-70 in Warrenton. | Adv. CN | 2090 | 522 | 0 | 2635 | 0 | AC-STBG | 2P3216 | 23 | 180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
178 | 2 | LINCOLN | MO 47 S | 2P3393 | 12.747 | N |  | Pavement resurfacing from Rte. 79 to 0.7 mile east of Rte. 61 near Troy. | Adv. CN | 2413 | 603 | 0 | 3018 | 0 | AC-STBG |  | 2 | 222 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2794 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
179 | 2 | LINCOLN | MO 47 S | NE0003 | 6.691 | N |  | Pavement, safety and shoulder improvements from 0.3 mile west of Rtes. H and J in Troy to Rtes. A and D in Hawk Point. | Adv. CN | 16303 | 4076 | 0 | 20594 | 0 | AC-STBG |  | 215 | 400 | 300 | 1334 | 0 | 0 | 0 | 0 | 0 | 2060 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16285 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
180 | 2 | LINCOLN | MO 47 S | NE0023 | 0.213 | N |  | Bridge preventive maintenance over Cuivre River 1.3 miles east of Rte. 61 near Troy. Project involves bridge A5595. | Federal | 150 | 37 | 0 | 187 | 0 | NHPP |  | 0 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 156 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
181 | 2 | LINCOLN | US 61 S | NE0004 | 2.895 | N |  | Corridor and safety improvement from 0.2 mile north of Rtes. V and K to 0.2 mile south of Creech Lane. | Federal | 17820 | 4455 | 0 | 22575 | 0 | NHPP |  | 300 | 400 | 500 | 800 | 700 | 1488 | 0 | 0 | 0 | 0 | 265 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
182 | 2 | LINCOLN | US 61 S | NE0144 | 0.7 | N |  | Safety and intersection improvements at Rte. B and Rte. E near Troy. | Federal | 14750 | 3687 | 0 | 18437 | 0 | NHPP |  | 0 | 600 | 300 | 750 | 750 | 1060 | 0 | 0 | 0 | 0 | 53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14924 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
183 | 2 | LINCOLN | US 61 S | NE0161 | 0.191 | N |  | Bridge rehabilitation over Cuivre River near Troy. Project involves bridges A7990 and A7991 | Federal | 639 | 160 | 0 | 799 | 0 | NHPP |  | 0 | 126 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 673 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
184 | 2 | LINCOLN | MO 79 S | 2P3395 | 1.755 | N |  | Upgrade pedestrian facilities to comply with the ADA Transition Plan at various locations in Louisville, Olney, Elsberry, Eolia and Paynesville. $138,000 Statewide Transportation Alternatives funds. | Federal | 162 | 41 | 0 | 257 | 0 | STBG |  | 54 | 5 | 17 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
185 | 2 | LINCOLN | MO 79 S | NE0086 | 17.063 | N |  | Pavement improvement from Pike County line to Rte. 47 in Winfield. | Adv. CN | 2300 | 575 | 0 | 2875 | 0 | AC-STBG |  | 0 | 1 | 35 | 5 | 169 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2665 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
186 | 2 | LINCOLN | RT E E | 2S3407 | 5.253 | N |  | Pavement improvement from Rte. UU in Silex to Rte. 61. | Adv. CN | 178 | 44 | 0 | 223 | 0 | AC-STBG |  | 1 | 1 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 205 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
187 | 2 | LINCOLN | RT F E | NE0007 | 7.207 | N |  | Pavement resurfacing from Rte. 61 to Rte. W near Whiteside. | Federal | 0 | 593 | 0 | 593 | 0 | STATE | 2S3387 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 548 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
188 | 2 | LINCOLN | RT J S | NE0051 | 0.084 | N |  | Bridge improvement over Big Creek 0.2 mile south of Rte. U South junction. Project involves bridge P0746. | Federal | 1761 | 440 | 0 | 2201 | 0 | NHPP |  | 0 | 250 | 50 | 139 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1760 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
189 | 2 | LINCOLN | RT JJ E | 2S3387 | 8.035 | N |  | Pavement resurfacing from Rte. W to Rte. 79 near Elsberry. | Adv. CN | 616 | 154 | 0 | 771 | 0 | AC-STBG | NE0007 | 1 | 54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 716 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
190 | 2 | LINCOLN | RT W S | 2S3377 | 4.02 | N |  | Pavement preservation treatment from Rte. KK to Rte. 47 near Troy. | Adv. CN | 229 | 57 | 0 | 287 | 0 | AC-STBG |  | 1 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
191 | 2 | LINCOLN | West Outer Road 61 | 2S3368 | 0 | N |  | Payment to Lincoln County to construct new two-lane roadway from Old Moscow Mills Rd. to Rte. C at Moscow Mills. $2,035,240 Cost Share funds. | Federal | 0 | 2045 | 0 | 2050 | 0 | STATE |  | 5 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
192 | 2 | MACON | MO 129 S | NE0018 | 6.231 | N |  | Pavement improvement from Rte. 36 to the Chariton County line. | Adv. CN | 394 | 99 | 0 | 493 | 0 | AC-STBG |  | 0 | 3 | 32 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 457 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
193 | 2 | MACON | MO 149 S | NE0138 | 0.005 | N |  | Urgent culvert and roadway repairs due to flooding over Walnut Creek 1.2 miles south of Rte. 156 near Gifford. Project involves culvert X0935. | Federal | 1437 | 359 | 0 | 1796 | 0 | NHPP |  | 0 | 200 | 123 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1471 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
194 | 2 | MACON | MO 156 E | 2S3266 | 53.051 | N |  | Pavement resurfacing from Rte. 149 to Rte. 6 in Lewis County at Ewing (two disconnected sections). | Adv. CN | 4068 | 1017 | 0 | 5095 | 0 | AC-STBG |  | 8 | 355 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4730 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
195 | 2 | MACON | MO 156 E | NE0147 | 2.118 | N |  | Upgrade pedestrian facilities to comply with the ADA Transition Plan at various locations in LaPlata, Gifford, Elmer, Ethel, Callao and College Mound. $318,000 Statewide Transportation Alternatives funds. | Federal | 447 | 112 | 0 | 559 | 0 | STBG |  | 0 | 35 | 25 | 40 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 457 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
196 | 2 | MACON | US 63 S | 2P3245 | 10.099 | N |  | Pavement improvement on southbound and northbound lanes from 0.6 mile south of Rte. YY to 1.8 miles north of Rte. 24 in Randolph County near Moberly (five disconnected sections). | Federal | 6941 | 1735 | 0 | 8684 | 0 | NHPP |  | 8 | 40 | 633 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8003 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
197 | 2 | MACON | US 63 S | NE0137 | 0.258 | N |  | Interchange improvement at Rte. 36 in Macon. Project involves bridge A2043. | Federal | 1602 | 400 | 0 | 2002 | 0 | NHPP |  | 0 | 125 | 100 | 136 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1639 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
198 | 2 | MACON | RT C S | 2S3414 | 24.111 | N |  | Pavement improvement from Rte. 36 to Rte. JJ in Huntsville in Randolph County. | Adv. CN | 2382 | 596 | 0 | 2980 | 0 | AC-STBG |  | 2 | 2 | 200 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2775 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
199 | 2 | MACON | RT J E | 2S2160 | 0.071 | N |  | Bridge improvement over Mussel Fork 0.8 mile east of Rte. 129 near New Boston. Project involves bridge N0251. | Federal | 1063 | 266 | 0 | 1365 | 0 | NHPP |  | 36 | 127 | 112 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1088 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
200 | 2 | MACON | RT VV S | NE0139 | 0.039 | N |  | Bridge improvement over BNSF Railway 0.4 mile south of Arctic Road near Hart. Project involves bridge W0404. | Adv. CN | 1323 | 331 | 0 | 1654 | 0 | AC-STBG |  | 0 | 200 | 15 | 97 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1340 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
201 | 2 | MACON | RT YY E | NE0058 | 6.286 | N |  | Pavement improvement from Rte. 63 near Macon to end of state maintenance. | Federal | 0 | 678 | 0 | 678 | 0 | STATE |  | 0 | 1 | 1 | 10 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 622 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
202 | 2 | MARION | MO 168 E | NE0065 | 6.68 | N |  | Pavement improvement from 0.2 mile east of Rte. JJ to Rte. 61 at Hannibal. | Adv. CN | 1946 | 487 | 0 | 2433 | 0 | AC-STBG |  | 0 | 1 | 30 | 15 | 146 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2239 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
203 | 2 | MARION | US 24 E | NE0108 | 0.43 | N |  | Payment to IDOT for bridge replacement study on the Quincy Memorial Bridge over the Mississippi River. Project involves bridge L0099. | Federal | 2448 | 612 | 0 | 3060 | 0 | NHPP |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3060 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
204 | 2 | MARION | US 24 W | 2P3284 | 0 | N |  | Payment to IDOT for cable inspection on the Quincy Bayview bridge over the Mississippi River. Project involves bridge A4274. | Federal | 600 | 150 | 0 | 750 | 0 | NHPP |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
205 | 2 | MARION | US 24 W | 2P3365 | 0 | N |  | Payment to IDOT for deck sealing on the Quincy Bayview bridge over the Mississippi River. Project involves bridge A4274. | Federal | 226 | 57 | 0 | 283 | 0 | NHPP |  | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
206 | 2 | MARION | US 36 E | 2P3354 | 2.743 | N |  | Pavement improvement on eastbound lanes from 0.9 mile east of Rte. H to 1.8 miles east of Rte. 24 east junction and on westbound lanes from 0.7 mile west of Rte. 61 to 0.5 mile west of Rte. Z near Monroe City. | Federal | 1517 | 379 | 0 | 1912 | 0 | NHPP |  | 16 | 20 | 136 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1740 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
207 | 2 | MARION | IS 72 E | 2I3367 | 0.394 | N |  | Bridge washing on Mark Twain Memorial Bridge over Mississippi River at Hannibal. Project involves bridge A5054. $24,000 IDOT funds. | Federal | 33 | 0 | 24 | 57 | 0 | NHPP |  | 0 | 0 | 1 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
208 | 2 | MARION | MO 79 S | 2P3357 | 0.29 | N |  | Bridge replacement over Lyon Street, Warren Barrett Drive, BNSF Railway and Bear Creek 0.4 mile north of Rte. T in Hannibal. Project involves bridge A1044. | Federal | 6846 | 1711 | 0 | 9457 | 0 | NHPP |  | 820 | 1162 | 0 | 0 | 0 | 0 | 0 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7395 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
209 | 2 | MARION | MO 79 S | 2P3412 | 0.943 | N |  | Pavement improvement from 0.3 mile south of I-72 interchange to 0.5 mile north of Rte. T in Hannibal. | Adv. CN | 269 | 67 | 0 | 338 | 0 | AC-STBG |  | 2 | 2 | 25 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 308 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
210 | 2 | MARION | RT T S | NE0012 | 7.683 | N |  | Pavement improvement from 0.8 mile south of Rte. 79 in Hannibal to Rte. V. | Adv. CN | 654 | 164 | 0 | 818 | 0 | AC-STBG |  | 0 | 4 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 759 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
211 | 2 | MONROE | MO 154 E | NE0037 | 22.246 | N |  | Pavement improvement from Rte. 24 at Paris to 0.4 mile west of Rte. 19 (two disconnected sections). | Adv. CN | 670 | 168 | 0 | 838 | 0 | AC-STBG |  | 0 | 1 | 5 | 52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 780 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
212 | 2 | MONROE | US 24 E | NE0047 | 36.539 | N |  | Culvert improvement from the Randolph County line to Rte. W at Monroe City. | Federal | 602 | 151 | 0 | 753 | 0 | NHPP |  | 0 | 100 | 10 | 48 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 590 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
213 | 2 | MONROE | RT AA E | 2S3317 | 0.069 | N |  | Bridge improvement over Bee Creek 2.9 miles west of Rte. 15 near Paris. Project involves bridge P0826. | Adv. CN | 986 | 247 | 0 | 1254 | 0 | AC-STBG |  | 21 | 50 | 139 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1042 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
214 | 2 | MONROE | RT AA E | NE0153 | 0.086 | N |  | Bridge improvement over Elk Fork Salt River 3.3 miles south of Rte. 24 near Madison. Project involves bridge R0548. | Adv. CN | 998 | 250 | 0 | 1248 | 0 | AC-STBG |  | 0 | 50 | 50 | 50 | 93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1005 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
215 | 2 | MONROE | RT D E | 2S3244 | 0.093 | N |  | Bridge rehabilitation over South Fork Salt River 0.9 mile west of Rte. E near Santa Fe. Project involves bridge R0494. | Federal | 694 | 174 | 0 | 934 | 0 | NHPP | 2S3257 3S2164 | 66 | 72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 796 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
216 | 2 | MONROE | RT J E | 2S3257 | 0.073 | N |  | Bridge rehabilitation over Middle Fork Salt River 0.5 mile east of Rte. OO near Duncans Bridge. Project involves bridge X0624. | Federal | 527 | 132 | 0 | 680 | 0 | NHPP | 2S3244 3S2164 | 21 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 579 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
217 | 2 | MONROE | RT M E | 2S3147 | 0.065 | N |  | Bridge replacement over Milligan Creek 0.9 mile west of Rte. Y near Middle Grove. Project involves bridge T0382. | Federal | 900 | 225 | 0 | 1176 | 0 | NHPP |  | 49 | 259 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 866 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
218 | 2 | MONROE | RT Z S | 3S2164 | 0.024 | N |  | Bridge rehabilitation over Brush Creek 1.9 miles north of Rte. D near Strother. Project involves bridge R0056. | Federal | 406 | 101 | 0 | 530 | 0 | NHPP | 2S3244 2S3257 | 23 | 56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 451 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
219 | 2 | MONTGOMERY | MO 161 N | 2S3356 | 0.536 | N |  | Upgrade pedestrian facilities to comply with the ADA Transition Plan in Montgomery City and in Middletown and Rte. CC and Rte. ZZ in Wellsville. $220,000 Statewide Transportation Alternatives funds. | Federal | 367 | 92 | 0 | 598 | 0 | STBG | 2P3355 | 129 | 72 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 387 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
220 | 2 | MONTGOMERY | MO 161 S | NE0126 | 0.062 | N |  | Bridge improvement over Elkhorn Creek 1.6 miles south of Rte. CC near Buell. Project involves bridge S0368. | Federal | 909 | 227 | 0 | 1136 | 0 | NHPP |  | 0 | 165 | 89 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 880 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
221 | 2 | MONTGOMERY | MO 19 S | 2P3090 | 0.62 | N |  | Bridge replacement over I-70 and construct roundabouts near New Florence. Project involves bridge A0986. $808,000 Open Container and $443,195 private developer funds. | Federal | 11052 | 2320 | 443 | 15122 | 0 | NHPP | 2S3452 | 1007 | 884 | 0 | 0 | 0 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12931 | 0 | 0 | 0 | 0 | 0 | 0 | 443 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
222 | 2 | MONTGOMERY | MO 19 S | 2S3452 | 4.672 | N |  | Pavement resurfacing from 0.4 mile to 0.2 mile north of I-70 and on I-70 North Outer Road from Rte. 161 to 0.1 mile east of Rte. 19 in New Florence. | Adv. CN | 801 | 200 | 0 | 1006 | 0 | AC-STBG | 2P3090 | 5 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 936 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
223 | 2 | MONTGOMERY | MO 19 S | NE0006 | 8.734 | N |  | Pavement improvement from 0.2 mile north of Montgomery City to 1.7 miles south of I-70. | Adv. CN | 871 | 218 | 0 | 1089 | 0 | AC-STBG |  | 0 | 12 | 77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
224 | 2 | MONTGOMERY | MO 19 S | NE0016 | 13.406 | N |  | Pavement improvement and rumblestripes from 1.7 miles south of I-70 to 1.2 miles south of Rte. 94 near McKittrick. | Adv. CN | 3295 | 824 | 0 | 4119 | 0 | AC-STBG |  | 0 | 120 | 324 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3665 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
225 | 2 | MONTGOMERY | MO 19 S | NE0022 | 0.831 | N |  | Bridge deck sealing over the Missouri River and the Loutre River near Hermann. Project involves bridges A6288 and A5624. | Federal | 541 | 135 | 0 | 676 | 0 | NHPP |  | 0 | 128 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 548 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
226 | 2 | MONTGOMERY | IS 70 E | 2I3226Z | 4.098 | N |  | Payback for MTFC loan to add eastbound and westbound climbing lanes, replace westbound bridge over Loutre River Overflow from 1.1 miles east of Rte. N to 0.3 mile west of Rte. 161 near Mineola. Total cost of $3,878,000 with payments from 2024 to 2030. | Adv. CN | 1994 | 222 | 0 | 2216 | 1,001 - 2,000 | AC-NHFP |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 554 | 554 | 554 | 554 | 0
227 | 2 | MONTGOMERY | IS 70 E | 2I3309 | 21.59 | N |  | Pavement improvement from 1.4 miles east of Rte. F to the St. Charles County line near Foristell. | Federal | 19797 | 2200 | 0 | 22021 | 0 | NHPP |  | 24 | 35 | 36 | 1370 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20556 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
228 | 2 | MONTGOMERY | IS 70 E | 2I3372 | 38.595 | N |  | Job Order Contracting for pavement repair from the Callaway County line to the St. Charles County line. | Adv. CN | 484 | 54 | 0 | 539 | 0 | AC-NHPP |  | 1 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
229 | 2 | MONTGOMERY | IS 70 E | NE0128 | 38.6 | N |  | Job Order Contracting for pavement repair from the Callaway County line to the St. Charles County line. | Adv. CN | 513 | 57 | 0 | 570 | 0 | AC-NHPP |  | 0 | 1 | 1 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 530 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
230 | 2 | MONTGOMERY | IS 70 E | NE0130 | 42.196 | N |  | Job Order Contracting for guard cable repair on I-70 in Montgomery and Warren Counties, Rte. 61 in Lincoln County, Rte. T in Ralls County and Rte. 36 in Macon County. | Adv. CN | 1542 | 386 | 0 | 1928 | 0 | AC-STBG |  | 0 | 128 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
231 | 2 | MONTGOMERY | IS 70 E | NE0131 | 42.196 | N |  | Job Order Contracting for guard cable repair on I-70 in Montgomery and Warren Counties, Rte. 61 in Lincoln County, Rte. T in Ralls County and Rte. 36 in Macon County. | Adv. CN | 1898 | 475 | 0 | 2373 | 0 | AC-STBG |  | 0 | 1 | 1 | 1 | 1 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2229 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
232 | 2 | MONTGOMERY | IS 70 E | NE0143 | 48.648 | N |  | Job Order Contracting for concrete pavement repair in Montgomery and Warren Counties and on Rte. 61 in Lincoln County. | Adv. CN | 1160 | 129 | 0 | 1289 | 0 | AC-NHPP |  | 0 | 89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
233 | 2 | MONTGOMERY | IS 70 E | NE0169 | 252.888 | N |  | Striping upgrades in Clark, Lewis, Lincoln, Macon, Marion, Montgomery, Pike, Ralls, Randolph, Shelby, and Warren Counties. | Federal | 1588 | 176 | 0 | 1764 | 0 | SAFETY |  | 0 | 114 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
234 | 2 | MONTGOMERY | RT E E | 2S3408 | 35.398 | N |  | Pavement improvement from I-70 to Rte. UU in Silex. | Adv. CN | 2692 | 673 | 0 | 3367 | 0 | AC-STBG |  | 2 | 2 | 229 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3133 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
235 | 2 | MONTGOMERY | RT E E | 2S3439 | 0.027 | N |  | Bridge improvement over I-70 in Jonesburg. Project involves bridge A0866. | Federal | 3301 | 825 | 0 | 4128 | 0 | NHPP |  | 2 | 300 | 200 | 314 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3302 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
236 | 2 | MONTGOMERY | RT F S | 2S3440 | 0.036 | N |  | Bridge improvement over I-70 in High Hill. Project involves bridge A0865. | Federal | 3142 | 785 | 0 | 3929 | 0 | NHPP |  | 2 | 300 | 50 | 264 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3303 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
237 | 2 | MONTGOMERY | RT K E | NE0053 | 0.063 | N |  | Bridge improvement over Dry Fork Creek 1.8 miles west of Rte. 19 near Big Spring. Project involves bridge L0564. | Federal | 1626 | 407 | 0 | 2033 | 0 | NHPP |  | 0 | 220 | 45 | 150 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1616 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
238 | 2 | MONTGOMERY | RT K E | NE0154 | 0.055 | N |  | Bridge improvement over Loutre River 0.4 mile west of Rte. 19 near Big Spring. Project involves bridge A0737. | Federal | 1836 | 459 | 0 | 2295 | 0 | NHPP |  | 0 | 120 | 35 | 25 | 148 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
239 | 2 | MONTGOMERY | RT T E | NE0163 | 21.683 | N |  | Pavement resurfacing from Rte. 161 to Rte. O in Lincoln County, Rte. MM in Montgomery County and Rtes. N and CC in Warren County. | Federal | 0 | 3380 | 0 | 3440 | 0 | STATE |  | 60 | 221 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3159 | 0 | 0 | 0 | 0 | 0 | 0 | 3159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
240 | 2 | MONTGOMERY | RT Y E | 2S3392 | 14.928 | N |  | Pavement preservation treatment from Rte. 19 to Rte. E in Jonesburg. | Adv. CN | 366 | 91 | 0 | 458 | 0 | AC-STBG | 2S3382 2S3383 2S3384 | 1 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 425 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
241 | 2 | MONTGOMERY | RT ZZ S | 2S3195 | 0.058 | N |  | Bridge improvement over Little Loutre Creek 0.5 mile south of Rte. RA near Wellsville. Project involves bridge R0638. | Adv. CN | 827 | 207 | 0 | 1055 | 0 | AC-STBG |  | 21 | 115 | 104 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 813 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
242 | 2 | PIKE | MO 161 S | 2S3215 | 17.363 | N |  | Pavement resurfacing from Bus. 61 to Rte. M near Middletown. | Adv. CN | 1892 | 473 | 0 | 2370 | 0 | AC-STBG | 2S3378 2S3388 2S3389 2S3390 | 5 | 168 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
243 | 2 | PIKE | MO 161 S | 2S3388 | 23.25 | N |  | Pavement resurfacing from Rte. M to Rte. I-70 near Danville in Montgomery County. | Adv. CN | 2398 | 599 | 0 | 2998 | 0 | AC-STBG | 2S3215 2S3378 2S3389 2S3390 | 1 | 217 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2780 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
244 | 2 | PIKE | US 54 E | NE0001 | 0.5 | N |  | Add intersection and turn lanes at Industrial Park 0.8 mile east of Bus. 54 in Bowling Green. $880,650 Cost Share funds. | Federal | 754 | 188 | 0 | 1043 | 0 | NHPP |  | 86 | 76 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 866 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
245 | 2 | PIKE | US 54 E | NE0001B | 0.5 | N |  | Payment to Bowling Green for study of intersection and turn lanes at Industrial Park 0.8 mile east of Bus. 54. $49,250 Cost Share funds. | Federal | 39 | 10 | 0 | 49 | 0 | NHPP |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
246 | 2 | PIKE | BU 61 S | 2S3390 | 3.574 | N |  | Pavement resurfacing from 0.3 mile south of Rte. UU to roundabout in Bowling Green. | Adv. CN | 749 | 187 | 0 | 946 | 0 | AC-STBG | 2S3215 2S3378 2S3388 2S3389 | 10 | 74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 862 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
247 | 2 | PIKE | US 61 N | 2P3243 | 5.747 | N |  | Pavement resurfacing from 0.5 mile south of Rte. 19 in Ralls County to 0.5 mile south of Rte. UU near Bowling Green (3 disconnected sections). | Federal | 3774 | 944 | 0 | 4761 | 0 | NHPP |  | 43 | 324 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4394 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
248 | 2 | PIKE | MO 79 S | NE0014 | 21.11 | N |  | Pavement improvement from 0.9 mile south of Rte. 54 east junction in Louisiana to Lincoln County line. | Adv. CN | 614 | 153 | 0 | 767 | 0 | AC-STBG |  | 0 | 2 | 51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
249 | 2 | PIKE | RT B E | NE0015 | 6.342 | N |  | Pavement improvement from Rte. 61 near Frankford to Rte. 79. | Adv. CN | 169 | 42 | 0 | 211 | 0 | AC-STBG |  | 0 | 2 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 194 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
250 | 2 | PIKE | RT B E | NE0052 | 0.037 | N |  | Bridge improvement over Peno Creek 0.4 mile west of Rte. 61 near Frankford. Project involves bridge L0242. | Federal | 1420 | 355 | 0 | 1775 | 0 | NHPP |  | 0 | 210 | 40 | 111 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1412 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
251 | 2 | PIKE | RT D S | NE0075 | 15.092 | N |  | Pavement improvement from Rte. 79 to Rte. 61 in Eolia. | Adv. CN | 1276 | 319 | 0 | 1595 | 0 | AC-STBG |  | 0 | 1 | 1 | 7 | 97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1489 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
252 | 2 | PIKE | RT NN S | 2S3378 | 11.157 | N |  | Pavement resurfacing from Rte. 54 to Rte. 61 near Bowling Green. | Adv. CN | 910 | 228 | 0 | 1143 | 0 | AC-STBG | 2S3215 2S3388 2S3389 2S3390 | 5 | 88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
253 | 2 | PIKE | RT UU E | 2S3389 | 8.481 | N |  | Pavement preservation treatment from Rte. 61 to Rte. 54 near Louisiana. | Adv. CN | 216 | 54 | 0 | 271 | 0 | AC-STBG | 2S3215 2S3378 2S3388 2S3390 | 1 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 251 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
254 | 2 | PIKE | RT W S | NE0136 | 0.368 | N |  | Bridge preventative maintenance at various locations in the Northeast District. Project includes bridges B0172, B0173, B0174, B0176, B0193, B0198, B0201, B0203, B0204, B0205, B0206, B0208, B0212 and B0213. | Federal | 1001 | 250 | 0 | 1251 | 0 | NHPP |  | 0 | 150 | 92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1009 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
255 | 2 | PIKE | RT W S | NE0152 | 0.02 | N |  | Bridge improvement over Little Ramsey Creek 0.5 mile north of Rte. H in Paynesville. Project involves bridge P0366. | Federal | 918 | 230 | 0 | 1148 | 0 | NHPP |  | 0 | 60 | 75 | 60 | 75 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 876 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
256 | 2 | RALLS | MO 154 E | NE0107 | 12.351 | N |  | Pavement improvement from Rte. 19 south junction to Rte. 54 near Vandalia in Pike County. | Adv. CN | 1073 | 268 | 0 | 1341 | 0 | AC-STBG |  | 0 | 1 | 1 | 4 | 4 | 77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1254 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
257 | 2 | RALLS | MO 19 S | 2P3278 | 27.01 | N |  | Pavement resurfacing from 0.2 mile east of Rte. 61 to Rte. J in Audrain County. Project involves bridges J0429 and B0216. | Federal | 7009 | 1752 | 0 | 8798 | 0 | NHPP | 2P3446 | 37 | 644 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8117 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
258 | 2 | RALLS | MO 19 S | 2P3446 | 0.44 | N |  | Add intersection turn lanes between Bus Barn Road and Mark Twain Road near Center. | Federal | 587 | 147 | 0 | 819 | 0 | NHPP | 2P3278 | 75 | 100 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 634 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
259 | 2 | RALLS | RT A E | NE0011 | 16.021 | N |  | Pavement improvement from Rte. J to Bus. Rte. 61 near New London. | Adv. CN | 386 | 96 | 0 | 482 | 0 | AC-STBG |  | 0 | 2 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 448 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
260 | 2 | RALLS | RT B S | 2S3413 | 19.272 | N |  | Pavement improvements from Rte. 154 to Rte. 54 in Audrain County 5.2 miles east of Mexico. | Adv. CN | 1425 | 356 | 0 | 1783 | 0 | AC-STBG |  | 2 | 2 | 121 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1657 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
261 | 2 | RALLS | RT F S | 2S3416 | 16.806 | N |  | Pavement improvement from Rte. 19 to just north of Daniels Avenue near Vandalia. | Adv. CN | 1301 | 325 | 0 | 1628 | 0 | AC-STBG |  | 2 | 8 | 105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1513 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
262 | 2 | RALLS | RT J S | NE0072 | 19.163 | N |  | Pavement improvement from Rte. 36 to Rte. 154 in Perry (two disconnected sections). | Adv. CN | 1642 | 411 | 0 | 2053 | 0 | AC-STBG |  | 0 | 1 | 10 | 30 | 124 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
263 | 2 | RALLS | RT V E | 2S3420 | 4.494 | N |  | Pavement improvement from Bus. 61 in New London to Rte. T. | Adv. CN | 368 | 92 | 0 | 462 | 0 | AC-STBG |  | 2 | 8 | 30 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 421 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
264 | 2 | RANDOLPH | US 24 E | NE0121 | 7.636 | N |  | Pavement improvement from the Chariton County line to 1.5 miles west of Rte. C near Huntsville. | Federal | 1362 | 341 | 0 | 1703 | 0 | NHPP |  | 0 | 20 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1573 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
265 | 2 | RANDOLPH | MO 3 N | 2S3448 | 0.66 | N |  | Slide repair and rebuild road from 0.2 mile south of County Road 2130 to Sweet Springs Creek. | Adv. CN | 2482 | 621 | 0 | 3228 | 0 | AC-STBG |  | 125 | 545 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 2553 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
266 | 2 | RANDOLPH | MO 3 S | 2P3411 | 9.075 | N |  | Pavement improvement from Rte. 24 east junction to Rte. 129 in Roanoke. | Adv. CN | 249 | 62 | 0 | 312 | 0 | AC-STBG |  | 1 | 1 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 287 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
267 | 2 | RANDOLPH | BU 63 S | NE0002 | 0.301 | N |  | Payment to Moberly for ADA Transition Plan improvements and add center turn lane from Burkhart Street to Carpenter Street. $1,056,161 Cost Share funds. | Adv. CN | 738 | 184 | 0 | 1066 | 0 | AC-STBG |  | 3 | 2 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 141 | 7 | 908 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
268 | 2 | RANDOLPH | US 63 S | 2P3351 | 14.54 | N |  | Pavement improvement from 0.3 mile south of Rte. 24 at Moberly to the Boone County line (two disconnected sections). | Federal | 2366 | 591 | 0 | 2963 | 0 | NHPP |  | 6 | 12 | 212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2733 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
269 | 2 | RANDOLPH | RT B W | NE0077 | 18.294 | N |  | Pavement improvement from Rte. 63 near Clark to Rte. 3 near Roanoke in Howard County (two disconnected sections). | Adv. CN | 1583 | 396 | 0 | 1979 | 0 | AC-STBG |  | 0 | 1 | 1 | 15 | 119 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1843 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
270 | 2 | RANDOLPH | RT BB E | NE0079 | 10.284 | N |  | Pavement improvement from Rte. 3 to Rte. A near Moberly. | Adv. CN | 872 | 218 | 0 | 1090 | 0 | AC-STBG |  | 0 | 1 | 1 | 5 | 67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1016 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
271 | 2 | RANDOLPH | RT DD S | NE0040 | 10.337 | N |  | Pavement improvement from County Road 1650 to Rte. 24 in Moberly. | Adv. CN | 855 | 214 | 0 | 1069 | 0 | AC-STBG |  | 0 | 1 | 10 | 67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 991 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
272 | 2 | RANDOLPH | RT P S | NE0164 | 13.022 | N |  | Pavement resurfacing from Rte. NN to Rte. 63 and on Rte. NN from Rte. 63 to Rte. Y in Monroe County. | Federal | 0 | 2077 | 0 | 2157 | 0 | STATE | CD0130 NW0095 | 80 | 143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1934 | 0 | 0 | 0 | 0 | 0 | 0 | 1934 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
273 | 2 | SCHUYLER | US 136 E | 2P0791 | 0.072 | N |  | Bridge replacement over abandoned railroad 1.2 miles west of Rte. 63 near Lancaster. Project involves bridge A0116. | Federal | 406 | 101 | 0 | 695 | 0 | NHPP | 2P2193 | 184 | 37 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 470 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
274 | 2 | SCHUYLER | US 136 E | 2P3197 | 0.057 | N |  | Bridge replacement over North Fork Middle Fabius River 1.1 miles east of Rte. C near Lancaster. Project involves bridge J0690. | Federal | 1035 | 259 | 0 | 1421 | 0 | NHPP | 2P3249 | 126 | 127 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
275 | 2 | SCHUYLER | US 136 W | NE0019 | 8.175 | N |  | Pavement improvement from Rte. 63 to 0.3 mile west of Rte. N near Livonia in Putnam County. | Adv. CN | 674 | 169 | 0 | 843 | 0 | AC-STBG |  | 0 | 2 | 2 | 54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 785 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
276 | 2 | SCHUYLER | MO 202 E | 2S3333 | 8.546 | N |  | Pavement improvement from Iowa State line to Rte. 63 near Lancaster. | Adv. CN | 1226 | 306 | 0 | 1536 | 0 | AC-STBG |  | 4 | 10 | 104 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
277 | 2 | SCHUYLER | MO 202 E | NE0145 | 1.467 | N |  | Upgrade pedestrian facilities to comply with the ADA Transition Plan at various locations in Greentop, Glenwood, Queen City, Coatesville, Brashear and Gibbs. $204,000 Statewide Transportation Alternatives funds. | Federal | 277 | 69 | 0 | 346 | 0 | STBG |  | 0 | 35 | 15 | 23 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 271 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
278 | 2 | SCHUYLER | US 63 S | 2P2212 | 24.677 | N |  | Pavement improvement from the Iowa State line to 0.6 mile north of Bus. 63 near Kirksville in Adair County. | Federal | 7133 | 1783 | 0 | 8946 | 0 | NHPP |  | 30 | 75 | 576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8265 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
279 | 2 | SCHUYLER | RT N S | NE0097 | 7.981 | N |  | Pavement improvement from Iowa State line to Rte. 136 in Downing. | Adv. CN | 696 | 174 | 0 | 870 | 0 | AC-STBG |  | 0 | 1 | 1 | 1 | 3 | 51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 813 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
280 | 2 | SCHUYLER | RT T E | NE0166 | 108.422 | N |  | Pavement resurfacing from Rte. A to Rte. 15 in Scotland County, Rte. N and E in Scotland County, Rte. A in Schuyler and Adair Counties, Rte. J and K in Adair County, Rte. JJ, HH, and EE in Macon County, Rte. J in Macon and Linn Counties. | Federal | 0 | 16926 | 0 | 17016 | 0 | STATE |  | 90 | 1096 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15830 | 0 | 0 | 0 | 0 | 0 | 0 | 15830 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
281 | 2 | SCOTLAND | MO 15 S | 2P3249 | 0.05 | N |  | Bridge replacement over North Fork Wyaconda River 0.4 mile south of Rte. EE near Memphis. Project involves bridge H0898. | Federal | 886 | 221 | 0 | 1134 | 0 | NHPP | 2P3197 | 22 | 127 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 980 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
282 | 2 | SCOTLAND | MO 15 S | NE0056 | 10.821 | N |  | Pavement improvement from the Iowa State line to Rte. 136 east junction in Memphis. | Adv. CN | 1334 | 334 | 0 | 1668 | 0 | AC-STBG |  | 0 | 1 | 1 | 15 | 102 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1549 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
283 | 2 | SCOTLAND | MO 15 S | NE0057 | 22.465 | N |  | Pavement improvement from Rte. 136 west junction at Memphis to Rte. 6 north junction at Edina in Knox County. | Adv. CN | 2173 | 543 | 0 | 2716 | 0 | AC-STBG |  | 0 | 1 | 1 | 40 | 163 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2511 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
284 | 2 | SCOTLAND | RT A S | 2S3324 | 0.069 | N |  | Bridge improvement over BNSF Railway 0.3 mile east of Rte. M near Rutledge. Project involves bridge A2740. | Federal | 472 | 118 | 0 | 596 | 0 | NHPP |  | 6 | 80 | 51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 459 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
285 | 2 | SCOTLAND | RT H E | 2S3320 | 0.059 | N |  | Bridge replacement over North Branch Wyaconda River 3.2 miles east of Rte. 15 near Brock. Project involves bridge X0173. | Federal | 869 | 217 | 0 | 1189 | 0 | NHPP | 2S3322 2S3449 | 101 | 304 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 782 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
286 | 2 | SCOTLAND | RT MM S | NE0098 | 5.238 | N |  | Pavement improvement from Rte. 136 in Memphis to Rte. M. | Adv. CN | 457 | 114 | 0 | 571 | 0 | AC-STBG |  | 0 | 1 | 1 | 1 | 1 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 533 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
287 | 2 | SCOTLAND | RT T E | 2S3322 | 0.065 | N |  | Bridge replacement over South Fork Middle Fabius River 4 miles east of Rte. A near Bible Grove. Project involves bridge P0401. | Federal | 915 | 229 | 0 | 1316 | 0 | NHPP | 2S3320 2S3449 | 170 | 261 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
288 | 2 | SCOTLAND | RT T E | 2S3326 | 0.081 | N |  | Bridge improvement over North Fork Middle Fabius River 1.9 miles west of Rte. 15 near Bible Grove. Project involves bridge A2885. | Federal | 606 | 151 | 0 | 763 | 0 | NHPP |  | 6 | 98 | 69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 590 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
289 | 2 | SHELBY | MO 15 S | 2P3386 | 7.188 | N |  | Pavement improvements from Rte. 168 at Shelbyville to just north of Rte. 36 at Shelbina. | Adv. CN | 250 | 63 | 0 | 316 | 0 | AC-STBG |  | 3 | 2 | 21 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 289 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
290 | 2 | SHELBY | MO 15 S | NE0017 | 18.096 | N |  | Pavement improvement from 0.2 mile south of Rte. 36 to Rte. 154 north junction in Monroe County at Paris. | Adv. CN | 464 | 116 | 0 | 580 | 0 | AC-STBG |  | 0 | 2 | 38 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 539 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
291 | 2 | SHELBY | MO 168 E | NE0063 | 31.272 | N |  | Pavement improvement from Rte. 15 to Bus. 61 in Palmyra in Marion County. | Adv. CN | 9216 | 2304 | 0 | 11520 | 0 | AC-STBG |  | 0 | 50 | 200 | 100 | 706 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10443 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
292 | 2 | SHELBY | RT C E | NE0067 | 19.006 | N |  | Pavement improvement from Rte. Z to Rte. 168 near Palmyra in Marion County. | Adv. CN | 1616 | 404 | 0 | 2020 | 0 | AC-STBG |  | 0 | 1 | 1 | 26 | 119 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1873 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
293 | 2 | SHELBY | RT J E | NE0050 | 0.025 | N |  | Bridge improvement over Tiger Fork 0.6 mile west of Rte. W. Project involves bridge N0015. | Federal | 1079 | 270 | 0 | 1349 | 0 | NHPP |  | 0 | 200 | 15 | 83 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
294 | 2 | SHELBY | RT K E | NE0029 | 10.657 | N |  | Pavement improvement from Rte. 15 to Rte. 151 in Shelbyville. | Adv. CN | 876 | 219 | 0 | 1095 | 0 | AC-STBG |  | 0 | 1 | 5 | 68 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1020 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
295 | 2 | SHELBY | RT K E | NE0127 | 0.061 | N |  | Bridge improvement over Black Creek 1.1 miles west of Rte. 15 near Shelbyville. Project involves bridge P0238. | Federal | 879 | 220 | 0 | 1099 | 0 | NHPP |  | 0 | 155 | 90 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
296 | 2 | VARIOUS | Various | 2P3399 | 0 | N |  | On-call work zone enforcement at various locations in the Northeast District. | Federal | 10 | 1 | 0 | 11 | 0 | SAFETY |  | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
297 | 2 | VARIOUS | Various | 2P3404 | 0 | N |  | Job Order Contracting for guardrail repair at various locations in the Northeast District. | Adv. CN | 1286 | 322 | 0 | 1608 | 0 | AC-STBG |  | 0 | 108 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
298 | 2 | VARIOUS | Various | 2P3405 | 0 | N |  | On-call work zone enforcement at various locations in the Northeast District. | Federal | 10 | 1 | 0 | 11 | 0 | SAFETY |  | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
299 | 2 | VARIOUS | Various | 5B0800Q | 0 | N |  | Payback beginning in SFY 2008 for Safe and Sound bridges in the Northeast District. | Federal | 0 | 26400 | 0 | 83810 | 25,001 - 50,000 | STATE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 0 | 0 | 0 | 0 | 0 | 57314 | 5280 | 5280 | 5280 | 5280 | 5280 | 0
300 | 2 | VARIOUS | Various | NE0009 | 0 | N |  | On-call work zone enforcement at various locations in the Northeast District. | Federal | 12 | 1 | 0 | 13 | 0 | SAFETY |  | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
301 | 2 | VARIOUS | Various | NE0132 |  | N |  | Job Order Contracting for guardrail repair at various locations in the Northeast District. | Adv. CN | 1090 | 272 | 0 | 1362 | 0 | AC-STBG |  | 0 | 1 | 1 | 87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1273 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
302 | 2 | VARIOUS | Various | NE0134 | 0 | N |  | Job Order Contracting for guardrail repair at various locations in the Northeast District. | Adv. CN | 1266 | 317 | 0 | 1583 | 0 | AC-STBG |  | 0 | 1 | 1 | 1 | 1 | 93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1486 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
303 | 2 | WARREN | MO 47 S | 2P3216 | 21.698 | N |  | Pavement resurfacing from 0.1 mile south of Rtes. M and MM in Warrenton to Missouri River Bridge in Washington. | Adv. CN | 4530 | 1132 | 0 | 5708 | 0 | AC-STBG | 2P3304 | 46 | 393 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5269 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
304 | 2 | WARREN | MO 47 S | 2P3355 | 0.831 | N |  | Upgrade pedestrian facilities to comply with the ADA Transition Plan in Warrenton and on Rte. J, Rte. F and I-70 North Outer Road in Wright City. $571,000 Statewide Transportation Alternatives funds. | Federal | 760 | 190 | 0 | 1049 | 0 | STBG | 2S3356 | 89 | 235 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 715 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
305 | 2 | WARREN | MO 47 S | NE0117 | 21.698 | N |  | Pavement improvement from 0.1 mile south of Rtes. M and MM in Warrenton to Missouri River Bridge near Washington. | Adv. CN | 2065 | 516 | 0 | 2581 | 0 | AC-STBG |  | 0 | 1 | 1 | 5 | 30 | 160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2384 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
306 | 2 | WARREN | S OR 70 E | NE0167 | 0.303 | N |  | Payment to Warren County to add turn lanes at Archer Road. $1,594,577 Cost Share funds. | Federal | 0 | 1599 | 0 | 1599 | 0 | STATE |  | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1594 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
307 | 2 | WARREN | S OR 70 E | NE0167B | 3.624 | Y |  | Payment to Warren County for resurfacing from Rte. F to west of Rte. T in St. Charles County. $1,275,840 Cost Share funds. | Federal | 0 | 1281 | 0 | 1281 | 0 | STATE |  | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1276 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
308 | 2 | WARREN | RT A S | 2S3438 | 0.037 | N |  | Bridge improvement over I-70 near Pendleton. Project involves bridge R0069. | Federal | 3037 | 759 | 0 | 3798 | 0 | NHPP |  | 2 | 302 | 50 | 256 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
309 | 2 | WARREN | RT AA E | 2S3384 | 3.646 | N |  | Pavement preservation treatment from I-70 north outer road in Warrenton to end of state maintenance. | Adv. CN | 116 | 29 | 0 | 146 | 0 | AC-STBG | 2S3382 2S3383 2S3392 | 1 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 134 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
310 | 2 | WARREN | RT B S | 2S3379 | 11.925 | N |  | Pavement resurfacing from I-70 near Pendleton to Rte. 94. | Adv. CN | 868 | 217 | 0 | 1086 | 0 | AC-STBG | 2S3380 2S3381 | 1 | 79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1006 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
311 | 2 | WARREN | RT H S | 2S3383 | 3.625 | N |  | Pavement preservation treatment from Rte. F to Rte. M near Innsbrook. | Adv. CN | 128 | 32 | 0 | 161 | 0 | AC-STBG | 2S3382 2S3384 2S3392 | 1 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
312 | 2 | WARREN | RT O S | 2S3380 | 10.163 | N |  | Pavement resurfacing from Rte. M to Rte. 47 near Marthasville. | Adv. CN | 705 | 176 | 0 | 882 | 0 | AC-STBG | 2S3379 2S3381 | 1 | 63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
313 | 2 | WARREN | RT OO E | 2S3381 | 1.511 | N |  | Pavement resurfacing from Rte. M to Rte. T near Innsbrook. | Adv. CN | 133 | 33 | 0 | 167 | 0 | AC-STBG | 2S3379 2S3380 | 1 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
314 | 2 | WARREN | RT U S | 2S3382 | 11.589 | N |  | Pavement preservation treatment from West Booneslick Road in Warrenton to Rte. 94. | Adv. CN | 269 | 67 | 0 | 337 | 0 | AC-STBG | 2S3383 2S3384 2S3392 | 1 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 311 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
315 | 3 | JOHNSON | MO 13 N | KR0084 | 10.282 | N |  | Pavement resurfacing from Rte. 13 to Henry County line. | Federal | 2310 | 577 | 0 | 2887 | 0 | NHPP |  | 0 | 10 | 20 | 191 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2666 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
316 | 3 | JOHNSON | MO 13 S | 3P3109 | 0.23 | N |  | Add turn lanes, grading and drainage at the intersection of Rte. E. | Federal | 436 | 48 | 0 | 529 | 0 | SAFETY |  | 45 | 10 | 31 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 438 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
317 | 3 | JOHNSON | MO 13 S | KR0126 | 0.16 | N |  | Intersection improvements at Rte. 2. | Federal | 1728 | 192 | 0 | 1920 | 0 | SAFETY |  | 0 | 5 | 5 | 5 | 5 | 109 | 0 | 0 | 0 | 0 | 0 | 66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1725 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
318 | 3 | JOHNSON | MO 2 W | 3S3156 | 0.118 | N |  | Bridge replacement, guardrail and grading over Mineral Creek 2.3 miles east of Rte. 13 and 0.5 mile west of Lee Street in Leeton. Project involves bridge G0095. | Adv. CN | 695 | 174 | 0 | 925 | 0 | AC-STBG |  | 56 | 40 | 65 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 759 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
319 | 3 | JOHNSON | MO 23 N | 3P3085E | 0.176 | N |  | Add lighting and replace signage at Rte. D. | Federal | 90 | 10 | 0 | 188 | 0 | SAFETY | 3S3076 | 88 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
320 | 3 | JOHNSON | MO 23 N | 3S3076 | 0.175 | N |  | Add turn lane at Whiteman Air Force Base entrance at Spirit Boulevard. | Adv. CN | 356 | 89 | 0 | 541 | 0 | AC-STBG | 3P3085E | 91 | 36 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 409 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
321 | 3 | JOHNSON | MO 23 S | KR0090 | 1.9 | N |  | Pavement resurfacing, upgrade signal and add turn lanes from Rte. 50 to Rte. DD. | Federal | 832 | 208 | 0 | 1040 | 0 | NHPP |  | 0 | 30 | 30 | 97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
322 | 3 | JOHNSON | US 50 E | KR0101 | 0.739 | N |  | Bridge rehabilitation over Blackwater Creek and bridge replacement over Butchers Branch, 0.4 mile east of County Road 671 and 1.4 mile west of County Road NW 601. Project involves bridges A1175 and A1176. | Federal | 4424 | 1106 | 0 | 5530 | 0 | NHPP |  | 0 | 300 | 300 | 504 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4426 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
323 | 3 | JOHNSON | US 50 E | KR0104 | 0.071 | N |  | Bridge rehabilitation over South Fork Blackwater River 1 mile west of County Road NW 1601 and 0.1 mile east of Rte. Z. Project involves bridge A1223. | Federal | 2266 | 567 | 0 | 2833 | 0 | NHPP |  | 0 | 400 | 50 | 50 | 30 | 161 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2142 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
324 | 3 | JOHNSON | US 50 E | KR0107 | 0.738 | N |  | Bridge rehabilitation over Devils Branch and Post Oak Creek, 0.6 mile west of County Road 105 and 0.7 mile east of County Road NW 191. Project involves bridges A1042 and A1043. | Federal | 2544 | 636 | 0 | 3180 | 0 | NHPP |  | 0 | 200 | 100 | 100 | 20 | 176 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2584 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
325 | 3 | JOHNSON | US 50 E | KR0134 | 1.05 | N |  | Intersection improvements at 1601st Street. $527,000 Open Container funds. | Federal | 2431 | 270 | 0 | 2701 | 0 | SAFETY |  | 0 | 150 | 200 | 284 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2067 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
326 | 3 | JOHNSON | US 50 E | KR0136 | 3.239 | N |  | Add J-turns from 0.7 mile east of Rte. 58 and 0.2 mile east of NW 121st Road. | Federal | 8191 | 910 | 0 | 9101 | 0 | SAFETY |  | 0 | 200 | 400 | 906 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7595 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
327 | 3 | JOHNSON | US 50 E | KR0137 | 0.64 | N |  | Intersection improvements at Bus. 50. | Federal | 1517 | 168 | 0 | 1685 | 0 | SAFETY |  | 0 | 100 | 240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1345 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
328 | 3 | JOHNSON | US 50 W | 3P3095 | 0.16 | N |  | Bridge rehabilitation over Union Pacific Railroad 1.2 miles east of Rte. 23 and 0.5 mile west of Rte. D. Project involves bridge L0801. | Federal | 2368 | 592 | 0 | 3160 | 0 | NHPP |  | 195 | 303 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2657 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
329 | 3 | JOHNSON | US 50 W | KR0102 | 0.201 | N |  | Bridge rehabilitation over Clear Creek, 1.3 miles west of Rte. 23 and 0.9 mile east of 175th Street. Project involves bridge L0901. | Federal | 774 | 193 | 0 | 967 | 0 | NHPP |  | 0 | 20 | 30 | 81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 836 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
330 | 3 | JOHNSON | RT WW S | 3S3173 | 0.058 | N |  | Bridge replacement over Muddy Creek 0.7 mile east of Rte. 23 and 0.5 mile west of 1101 Road. Project involves bridge N0944. | Federal | 1011 | 253 | 0 | 1340 | 0 | NHPP |  | 76 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 1144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
331 | 3 | LAFAYETTE | MO 13 N | 3P3085H | 0.078 | N |  | Add signals to interchange ramps at I-70. $780,000 Open Container funds. | Federal | 862 | 96 | 0 | 968 | 0 | SAFETY |  | 10 | 20 | 115 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 823 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
332 | 3 | LAFAYETTE | MO 13 N | 3P3118E | 0.64 | N |  | Signal improvements from Fairground Avenue to Rte. FF. $210,000 Open Container funds. | Adv. CN | 190 | 48 | 0 | 243 | 0 | AC-STBG |  | 5 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 214 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
333 | 3 | LAFAYETTE | MO 13 N | KR0141 | 5.27 | N |  | Pavement resurfacing, guardrail upgrades and replace existing rumblestripes from Burns School Road to Rte. 20. | Adv. CN | 1940 | 485 | 0 | 2435 | 0 | AC-STBG |  | 10 | 5 | 156 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2264 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
334 | 3 | LAFAYETTE | MO 13 S | 4P2333 | 12.034 | N |  | Pavement resurfacing and add turn lanes from north of NW 435 Road to 0.5 mile south of I-70. | Federal | 17571 | 4393 | 0 | 22749 | 0 | NHPP |  | 785 | 1950 | 1923 | 0 | 0 | 0 | 0 | 0 | 630 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17461 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
335 | 3 | LAFAYETTE | MO 13 S | KR0124 | 12.713 | N |  | Upgrade signal interconnect in Lafayette and Ray Counties including Rte. 224. | Adv. CN | 350 | 88 | 0 | 443 | 0 | AC-STBG |  | 5 | 5 | 5 | 49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 379 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
336 | 3 | LAFAYETTE | MO 131 S | 3I3075 | 0.558 | N |  | Bridge replacement and interchange operational improvements from I-70 to 0.5 mile west of Rte. 131 on the south outer road of I-70 in Odessa. Project involves bridge A0057. $1,111,000 Open Container funds. | Adv. CN | 19463 | 4866 | 0 | 25149 | 0 | AC-STBG |  | 820 | 400 | 400 | 200 | 919 | 0 | 0 | 0 | 0 | 0 | 2125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20285 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
337 | 3 | LAFAYETTE | MO 20 E | KR0079 | 12.07 | N |  | Pavement resurfacing from Rte. W to Rte. EE in Saline County. | Adv. CN | 1754 | 439 | 0 | 2193 | 0 | AC-STBG |  | 0 | 10 | 10 | 10 | 10 | 136 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2017 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
338 | 3 | LAFAYETTE | MO 20 E | KR0153 | 9.958 | N |  | Pavement resurfacing from Rte. 213 to Rte. W. | Adv. CN | 1119 | 280 | 0 | 1399 | 0 | AC-STBG |  | 0 | 15 | 20 | 97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1267 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
339 | 3 | LAFAYETTE | US 24 E | KR0105 | 0.684 | N |  | Bridge rehabilitation over Tabo Creek, 1.1 miles east of Northrup Road and 0.4 mile west of Garr Road. Project involves bridge A2850. | Federal | 1705 | 426 | 0 | 2131 | 0 | NHPP |  | 0 | 10 | 20 | 20 | 20 | 127 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1934 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
340 | 3 | LAFAYETTE | IS 70 E | KR0092 | 13.24 | N |  | Pavement resurfacing, upgrade guardrail, repair slides and permanent aggregate edge treatment from Rte. 13 to Rte. Y. | Federal | 4424 | 491 | 0 | 4915 | 0 | NHPP |  | 0 | 30 | 40 | 15 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4530 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
341 | 3 | LAFAYETTE | IS 70 E | KR0234 | 57.548 | N |  | Striping upgrades on I-70. | Federal | 368 | 41 | 0 | 409 | 0 | SAFETY |  | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 390 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
342 | 3 | LAFAYETTE | IS 70 W | 4I3365B | 13.239 | N |  | Pavement resurfacing, upgrade guardrail and shoulders westbound from Rte. Y to Rte. 13. | Federal | 4753 | 528 | 0 | 5286 | 0 | NHPP |  | 5 | 20 | 20 | 26 | 20 | 311 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4884 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
343 | 3 | LAFAYETTE | IS 70 W | KR0100 | 0.218 | N |  | Bridge rehabilitation over Horseshoe Creek, 1.3 miles east of Rte. H and 1.9 mile west of Rte. D. Project involves bridges A0163 and A0164. | Federal | 2003 | 223 | 0 | 2226 | 0 | NHPP |  | 0 | 10 | 15 | 148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2053 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
344 | 3 | LAFAYETTE | RT AA E | 3S3121 | 0.08 | N |  | Bridge replacement over Branch to City Lake between Airport Road and Country Club Road. Project involves bridge Z0997. | Federal | 782 | 195 | 0 | 1048 | 0 | NHPP |  | 71 | 263 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 704 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
345 | 3 | LAFAYETTE | RT T N | 3S3174 | 0.06 | N |  | Bridge replacement over I-70, 3.5 miles east of Higginsville. Project involves bridge A0099. | Adv. CN | 2339 | 585 | 0 | 3469 | 0 | AC-STBG |  | 545 | 281 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2643 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
346 | 3 | LAFAYETTE | RT Y S | 3S3162 | 0.12 | N |  | Bridge replacement over I-70 0.5 mile east of Alexander Road and 1 mile west of Amber Road. Project involves bridge A0120. | Federal | 3060 | 765 | 0 | 4040 | 0 | NHPP |  | 215 | 22 | 644 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3109 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
347 | 3 | PETTIS | MO 127 S | 3S3154 | 0.4 | N |  | Bridge replacement over Basin Fork Creek 0.6 mile south of Dove Road and 0.7 mile north of Chaney Road. Project involves bridge X0439. | Federal | 766 | 192 | 0 | 1034 | 0 | NHPP | 3P3164 | 75 | 97 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 861 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
348 | 3 | PETTIS | US 50 E | 3P3205 | 0.66 | N |  | Bridge rehabilitation, pavement resurfacing and upgrade guardrails over Muddy Creek 0.5 mile east of Rte. MM and 1.7 miles west of Main Street. Project involves bridge A2663. | Federal | 3630 | 907 | 0 | 4552 | 0 | NHPP |  | 15 | 5 | 10 | 155 | 357 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4010 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
349 | 3 | PETTIS | US 50 W | 3P3112B | 0.23 | N |  | Upgrading pedestrian facilities to comply with the ADA Transition Plan from Emmet Avenue to Murray Avenue in Sedalia. $130,000 Statewide Transportation Alternatives funds. | Federal | 210 | 52 | 0 | 275 | 0 | NHPP |  | 12 | 99 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 163 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
350 | 3 | PETTIS | MO 52 W | 3P3164 | 1.117 | N |  | Bridge replacement over South Flat Creek 0.1 mile east of Bennet Road and 1 mile west of Rte. E. Project involves bridge H0881. | Adv. CN | 931 | 233 | 0 | 1299 | 0 | AC-STBG | 3S3154 | 130 | 190 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 974 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
351 | 3 | PETTIS | US 65 N | 3P3203 | 2.284 | N |  | Bridge rehabilitation, joint repair, guardrail, and pavement resurfacing over Muddy Creek, 0.2 mile north of John Road and 0.3 mile north of Smelser Road. Project involves bridges A3039 and A3040. | Federal | 2151 | 538 | 0 | 2709 | 0 | NHPP |  | 20 | 60 | 252 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2377 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
352 | 3 | PETTIS | US 65 N | 3P3210 | 0.652 | N |  | Payment to Pettis County to add interchange north of Sedalia near Cedar Drive. $8,290,950 Governor's Cost Share Program funds. | Federal | 6643 | 1661 | 0 | 8304 | 0 | NHPP |  | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8291 | 0 | 0 | 0 | 0 | 0 | 0 | 8291 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
353 | 3 | PETTIS | US 65 S | 3P3206 | 0.205 | N |  | Bridge rehabilitation over Turkey Creek, 0.1 mile south of John Road and 1.2 miles north of Smelser Road. Project involves bridges A0808 and A3039. | Federal | 1538 | 385 | 0 | 1948 | 0 | NHPP |  | 25 | 10 | 53 | 149 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1711 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
354 | 3 | PETTIS | RT M S | 3S3204 | 0.2 | N |  | Bridge replacement over Lake Creek, 0.1 mile south of Rte. V and 0.6 mile north of Echo Road. Project involves bridge X0340. | Federal | 1032 | 258 | 0 | 1350 | 0 | NHPP |  | 60 | 60 | 96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1134 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
355 | 3 | RAY | MO 10 E | 3P3198 | 0.039 | N |  | Bridge replacement over Crooked River, 0.8 mile east of Quarry Road and 0.2 mile west of West 118th Street. Project involves bridge G0949. | Federal | 1414 | 353 | 0 | 1837 | 0 | NHPP |  | 70 | 264 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1503 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
356 | 3 | RAY | MO 10 E | KR0077 | 8.425 | N |  | Pavement resurfacing and replace guardrail from Rte. C to Merrifield Lane. | Adv. CN | 2906 | 727 | 0 | 3633 | 0 | AC-STBG |  | 0 | 5 | 5 | 5 | 10 | 217 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3391 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
357 | 3 | RAY | MO 10 E | KR0078 | 8.3 | N |  | Pavement resurfacing and replace guardrail from Merrifield Lane to Carroll County line. | Adv. CN | 2226 | 557 | 0 | 2783 | 0 | AC-STBG |  | 0 | 5 | 5 | 5 | 5 | 165 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2598 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
358 | 3 | RAY | MO 13 S | 3P3108 | 17.504 | N |  | Pavement resurfacing, guardrail and pavement repair from Caldwell County line to Black Diamond Street. | Federal | 6552 | 1638 | 0 | 8403 | 0 | NHPP |  | 213 | 80 | 374 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7736 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
359 | 3 | RAY | MO 13 S | 3P3108B | 1.307 | N |  | Pavement resurfacing, pavement repair, sidewalks and ADA ramps from Black Diamond Street to Walmart Avenue. | Federal | 576 | 144 | 0 | 730 | 0 | NHPP |  | 10 | 7 | 38 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 670 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
360 | 3 | RAY | MO 210 W | 3S3166 | 2.885 | N |  | Pavement resurfacing from Clay County line to 0.3 mile west of Pendleton Road. | Adv. CN | 994 | 249 | 0 | 1308 | 0 | AC-STBG | 4S3337 | 65 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1168 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
361 | 3 | RAY | RT EE S | KR0228 | 34.839 | N |  | Pavement resurfacing on Rte. EE, Rte. HH, Rte. H, Rte. FF, Rte. V, Rte. BB, Rte. CC, Rte. Z and Rte. OO; Potential pavement resurfacing on Rte. W. | Federal | 0 | 5353 | 0 | 5353 | 0 | STATE |  | 0 | 353 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
362 | 3 | RAY | RT T E | 3S3178 | 0.085 | N |  | Bridge replacement over Panther Creek, 30 feet west of Triple Springs Road. Project involves bridge S0700. | Adv. CN | 904 | 226 | 0 | 1195 | 0 | AC-STBG |  | 65 | 200 | 150 | 141 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 634 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
363 | 3 | RAY | RT Z S | KR0103 | 0.101 | N |  | Bridge replacement over Kinny Creek 0.6 mile south of Agnes Street and 0.3 mile north of Centennial Road. Project involves bridge A1773. | Federal | 895 | 224 | 0 | 1119 | 0 | NHPP |  | 0 | 30 | 50 | 116 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 923 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
364 | 3 | SALINE | MO 127 S | 3S3163 | 0.098 | N |  | Bridge replacement over Robertson Creek 0.3 mile south of 257th and 1 mile north of 245th Road. Project involves bridge T0068. | Adv. CN | 985 | 246 | 0 | 1296 | 0 | AC-STBG | 3S3155 | 60 | 254 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 977 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
365 | 3 | SALINE | US 65 N | 3P3112 | 17.193 | N |  | Pavement resurfacing, upgrade pedestrian facilities to comply with the ADA Transition Plan, upgrade guardrails and pavement repair from east of Rte. 24 to Rte. 240 in Marshall. $169,000 Statewide Transportation Alternatives funds. | Federal | 5161 | 1290 | 0 | 6646 | 0 | NHPP |  | 195 | 419 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6032 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
366 | 3 | SALINE | US 65 N | 3P3168 | 0.331 | N |  | Add intersection turn lane at Morrow Street in Marshall. $549,000 Open Container funds. | Federal | 608 | 68 | 0 | 715 | 0 | SAFETY | 3P3182 | 38 | 82 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 594 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
367 | 3 | SALINE | US 65 S | 3P3182 | 3.663 | N |  | Pavement resurfacing, upgrade pedestrian facilities to comply with the ADA Transition Plan, upgrade guardrails, upgrade signals and pavement repair from Rte. 240 to 0.3 mile north of Bus. 65 in Marshall. | Federal | 1810 | 453 | 0 | 2322 | 0 | NHPP | 3P3168 | 59 | 179 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
368 | 3 | SALINE | US 65 S | KR0122 | 1.783 | N |  | Upgrade signals from Rte. 20 (Arrow Street) to Fairground Road in Marshall. | Federal | 326 | 81 | 0 | 412 | 0 | NHPP |  | 5 | 5 | 5 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 352 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
369 | 3 | SALINE | IS 70 E | 4I3366B | 9.546 | N |  | Pavement resurfacing on the eastbound lanes from the bridge over Blackwater River to Cooper County line. | Federal | 5231 | 581 | 0 | 5822 | 0 | NHPP |  | 10 | 53 | 407 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5352 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
370 | 3 | SALINE | IS 70 W | 4I3366 | 9.562 | N |  | Pavement resurfacing on the westbound from the bridge over Blackwater River to Cooper County line. | Federal | 5256 | 584 | 0 | 6045 | 0 | NHPP |  | 205 | 10 | 10 | 363 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5457 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
371 | 3 | SALINE | RT E N | KR0106 | 0.072 | N |  | Bridge rehabilitation over Salt Fork Creek, 1.2 miles north of 170th Trail and 0.3 mile south of Mallard Trail. Project involves bridge R0545. | Federal | 1057 | 264 | 0 | 1321 | 0 | NHPP |  | 0 | 10 | 10 | 10 | 10 | 109 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
372 | 3 | SALINE | RT EE S | 3S3155 | 0.092 | N |  | Bridge replacement over Salt Branch Creek, 1.4 miles south of 230th Road and 0.7 mile north of Rte. 20. Project involves bridge N0100. | Adv. CN | 830 | 208 | 0 | 1065 | 0 | AC-STBG | 3S3163 | 20 | 174 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 864 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
373 | 3 | SALINE | RT K S | 3S3123 | 0.196 | N |  | Bridge replacement and ramp redesign over I-70, 0.1 mile south of 126th Road off of Rte EE. Project involves bridge A0128. | Federal | 2713 | 678 | 0 | 3597 | 0 | NHPP |  | 206 | 608 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2783 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
374 | 3 | VARIOUS | Various | 3I3103 | 0 | N |  | Job Order Contracting for guard cable and guardrail repair at various locations in the rural Kansas City District. | Adv. CN | 1622 | 406 | 0 | 2039 | 0 | AC-STBG |  | 11 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
375 | 3 | VARIOUS | Various | 3P3202 | 0 | N |  | Upgrade pedestrian facilities to comply with the ADA Transition Plan at various locations in the rural Kansas City District. $523,000 Statewide Transportation Alternatives funds. | Adv. CN | 720 | 180 | 0 | 903 | 0 | AC-STBG |  | 3 | 245 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 655 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
376 | 3 | VARIOUS | Various | 3P3221 | 0 | N |  | On-call work zone enforcement at various locations in the rural Kansas City District. | Federal | 14 | 1 | 0 | 15 | 0 | SAFETY |  | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
377 | 3 | VARIOUS | Various | 3P3226 | 0 | N |  | On-call work zone enforcement at various locations in the rural Kansas City District. | Federal | 14 | 1 | 0 | 15 | 0 | SAFETY |  | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
378 | 3 | VARIOUS | Various | 5B0800R | 0 | N |  | Payback beginning in SFY 2008 for Safe and Sound bridges in rural Kansas City District. | Federal | 0 | 28825 | 0 | 95517 | 25,001 - 50,000 | STATE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 66542 | 5765 | 5765 | 5765 | 5765 | 5765 | 0
379 | 3 | VARIOUS | Various | KR0119 | 0 | N |  | Job Order Contracting for asphalt pavement repair in the rural Kansas City District. | Adv. CN | 880 | 220 | 0 | 1100 | 0 | AC-STBG |  | 0 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1020 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
380 | 3 | VARIOUS | Various | KR0138 | 0 | N |  | Upgrade pedestrian facilities to comply with the ADA Transition Plan at various locations in the rural Kansas City District. | Adv. CN | 934 | 233 | 0 | 1167 | 0 | AC-STBG |  | 0 | 5 | 5 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1082 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
381 | 3 | VARIOUS | Various | KR0139 | 0 | N |  | Bridge painting at various locations in rural Kansas City District. | Adv. CN | 1434 | 359 | 0 | 1793 | 0 | AC-STBG |  | 0 | 5 | 5 | 160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1623 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
382 | 3 | VARIOUS | Various | KR0160 | 0 | N |  | On-call work zone enforcement at various locations in the rural Kansas City District. | Federal | 14 | 1 | 0 | 15 | 0 | SAFETY |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
383 | 3 | VARIOUS | Various | KR0163 | 0 | N |  | Job Order Contracting for guard cable and guardrail repair at various locations in the rural Kansas City District. | Adv. CN | 1726 | 431 | 0 | 2157 | 0 | AC-STBG |  | 0 | 5 | 5 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
384 | 3 | VARIOUS | Various | KR0227 | 0 | N |  | Job Order Contracting for concrete pavement repair at various major route and interstate locations in the rural Kansas City District. | Adv. CN | 1745 | 436 | 0 | 2181 | 0 | AC-STBG |  | 0 | 141 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
385 | 3 | CASS | MO 2 E | KU0049 | 14.3 | Y |  | Pavement resurfacing from Independence Street to Rte. ZZ. | Adv. CN | 2568 | 642 | 0 | 3210 | 0 | AC-STBG |  | 0 | 5 | 5 | 10 | 195 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2995 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
386 | 3 | CASS | MO 291 S | 4P3488 | 0.148 | Y | 790127 | Add roundabout at Rte. 58 south junction. $2,106,000 Open Container funds. | Federal | 2801 | 311 | 0 | 3130 | 0 | SAFETY |  | 18 | 200 | 441 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
387 | 3 | CASS | E OR 49 N | 4S3449 | 0.101 | Y | 790135 | Bridge rehabilitation over East Fork Creek, 0.6 mile east of Overpass Road and 0.6 mile east of Indian Springs Road. Project involves bridge A2293. | Federal | 570 | 143 | 0 | 730 | 0 | NHPP |  | 16 | 60 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 653 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
388 | 3 | CASS | E OR 49 S | 4S3399 | 0.222 | Y | 790120 | Payment to Belton for outer road improvements on the east outer road from 155th Street to Hill Street and 162nd Street to 163rd Street. $976,813 Cost Share funds. | Adv. CN | 848 | 212 | 0 | 1060 | 0 | AC-STBG |  | 0 | 83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 977 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
389 | 3 | CASS | IS 49 S | KU0028 | 4.646 | Y |  | Add lanes from 155th Street to North Cass Parkway in Belton. | Federal | 64028 | 7114 | 0 | 71142 | 0 | NHPP |  | 0 | 1000 | 1000 | 4415 | 0 | 0 | 0 | 0 | 0 | 1403 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63324 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
390 | 3 | CASS | W OR 49 S | 4S3444 | 0.026 | Y | 790134 | Bridge replacement over Grand River, 1.2 miles north of Miller Road and 0.1 mile south of 237th Street. Project involves bridge G0484. | Federal | 1078 | 269 | 0 | 1438 | 0 | NHPP |  | 91 | 169 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 1173 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
391 | 3 | CASS | MO 58 E | 4P3268D | 4.188 | Y | 790139 | Upgrade pedestrian facilities to comply with the ADA Transition Plan at various locations in Cass County. $731,000 Statewide Transportation Alternatives funds. | Adv. CN | 2510 | 628 | 0 | 3143 | 0 | AC-STBG |  | 5 | 309 | 610 | 0 | 0 | 0 | 0 | 0 | 53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2166 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
392 | 3 | CASS | MO 58 E | 4S3272 | 0.696 | Y | 790098 | Add roundabout at Prairie Road. $1,763,000 Open Container funds. | Federal | 2086 | 232 | 0 | 2858 | 0 | SAFETY |  | 525 | 143 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
393 | 3 | CASS | MO 58 E | 4S3483 | 0.137 | Y | 790140 | Payment to Belton to modify intersection configuration and add pedestrian trail from I-49 to west of Powell Parkway. $1,023,690 Cost Share funds. | Adv. CN | 831 | 208 | 0 | 1039 | 0 | AC-STBG |  | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
394 | 3 | CASS | MO 7 N | 4P3268C | 3.138 | Y | 790141 | Upgrade pedestrian facilities to comply with the ADA Transition Plan from 163rd Street to Richland Parkway and Rte. VV from Rte. 7 to Lexington Road. $886,000 Statewide Transportation Alternatives funds. | Adv. CN | 2071 | 518 | 0 | 2700 | 0 | AC-STBG |  | 111 | 379 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 2175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
395 | 3 | CASS | MO 7 S | 4P3443 | 0.518 | Y | 790136 | Bridge replacement and auxiliary lane extension at I-49 1.4 miles south of Rte. 2 and 0.9 mile north of 283rd Street. Project involves bridge A1496. $38,220 Harrisonville funds. | Federal | 9426 | 2319 | 38 | 13118 | 0 | NHPP |  | 1335 | 1649 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 10034 | 0 | 0 | 0 | 0 | 0 | 0 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
396 | 3 | CASS | MO 7 S | KU0007 | 18.053 | Y |  | Pavement resurfacing from 0.2 mile west of I-49 to 0.3 mile east of Rte. B in Creighton. | Federal | 12058 | 3015 | 0 | 15078 | 0 | NHPP |  | 5 | 1529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13544 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
397 | 3 | CASS | MO 7 S | KU0098 | 0.143 | Y |  | Bridge replacement over Big Creek 0.3 mile north of Raffurty Road and 0.9 mile south of First Street near Pleasant Hill. Project involves bridge L0023. | Federal | 5998 | 1499 | 0 | 7497 | 0 | NHPP |  | 0 | 100 | 100 | 100 | 519 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6678 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
398 | 3 | CASS | RT C S | 4S3433 | 0.435 | Y | 790132 | Upgrade intersection and add turn lanes from Legend Lane to the south intersection of Peculiar Drive in Peculiar. $300,000 STBG-Urban and $597,000 Peculiar funds. | Adv. CN | 1938 | 0 | 597 | 2555 | 0 | AC-STBG |  | 20 | 269 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2266 | 0 | 0 | 0 | 0 | 0 | 0 | 897 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
399 | 3 | CASS | RT D S | 4S3453 | 0.111 | Y | 790142 | Bridge replacement over Coldwater Road, 0.1 mile south of East 319th Street and 0.3 mile north of 323rd Street. Project involves bridge A2568. | Federal | 987 | 247 | 0 | 1274 | 0 | NHPP |  | 40 | 37 | 145 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1052 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
400 | 3 | CASS | RT D S | KU0045 | 9.604 | Y |  | Pavement resurfacing from Rte. 58 to Rte. Y. | Adv. CN | 938 | 235 | 0 | 1173 | 0 | AC-STBG |  | 0 | 1 | 1 | 89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1082 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
401 | 3 | CASS | RT D S | KU0109 | 0.048 | Y |  | Bridge rehabilitation over Massey Creek, 0.9 mile south of 231st Street and 1.1 mile north of Rte. Y. Project involves bridge A2251. | Federal | 1076 | 269 | 0 | 1345 | 0 | NHPP |  | 0 | 40 | 40 | 40 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1115 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
402 | 3 | CASS | RT VV E | KU0044 | 4.884 | Y |  | Pavement resurfacing from Rte. 7 to Rte. E. | Adv. CN | 377 | 94 | 0 | 471 | 0 | AC-STBG |  | 0 | 2 | 2 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 433 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
403 | 3 | CASS | RT YY E | KU0067 | 4.205 | Y |  | Pavement resurfacing from Rte. Y to Rte. C in Peculiar. | Adv. CN | 827 | 207 | 0 | 1034 | 0 | AC-STBG |  | 0 | 5 | 5 | 72 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 947 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
404 | 3 | CLAY | MO 1 N | 4S3412 | 3.77 | Y | 590289 | Pavement reconstruction, upgrade pedestrian facilities and upgrade signals from north of 72nd Street to north of NE 42nd Street. | Federal | 16819 | 4205 | 0 | 21084 | 0 | NHPP |  | 60 | 208 | 200 | 1616 | 0 | 0 | 0 | 0 | 0 | 103 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18897 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
405 | 3 | CLAY | MO 1 S | KU0046 | 2.733 | Y |  | Pavement resurfacing from Rte. 152 to 72nd Street. | Federal | 1610 | 402 | 0 | 2012 | 0 | NHPP |  | 0 | 20 | 20 | 161 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1811 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
406 | 3 | CLAY | MO 1 S | KU0096 | 0.13 | Y |  | Upgrade pedestrian facilities to comply with the ADA Transition Plan under I-35 from NE 43rd Street to NE 44th Street. | Adv. CN | 826 | 206 | 0 | 1032 | 0 | AC-STBG |  | 0 | 30 | 40 | 47 | 81 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 829 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
407 | 3 | CLAY | MO 152 E | KU0052 | 2.294 | Y |  | Pavement resurfacing from Rte. 169 to Rte. 1. | Federal | 1424 | 356 | 0 | 1780 | 0 | NHPP | KU0050 KU0054 | 0 | 10 | 20 | 113 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1634 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
408 | 3 | CLAY | MO 152 E | KU0054 | 4.456 | Y |  | Pavement resurfacing from Rte. 1 to I-35. | Federal | 2670 | 667 | 0 | 3337 | 0 | NHPP | KU0050 KU0052 | 0 | 10 | 15 | 210 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3099 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
409 | 3 | CLAY | MO 152 E | KU0142 | 0.344 | Y |  | Payback to Kansas City for added bicycle/pedestrian overpass at Rte. 169. $1,059,392 Cost Share funds. | Federal | 859 | 215 | 0 | 1074 | 0 | NHPP |  | 0 | 5 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1059 | 0 | 0 | 0 | 0
410 | 3 | CLAY | US 169 N | KU0039 | 5.9 | Y |  | Bridge rehabilitation over I-435 and NW Cookingham Drive, 1.3 miles north of NW Shoal Creek Parkway and 0.6 mile south of NW 124th Street. Project involves bridges A3333 and A3345. | Federal | 2321 | 580 | 0 | 2901 | 0 | NHPP |  | 0 | 10 | 10 | 374 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2507 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
411 | 3 | CLAY | US 169 N | KU0099 | 0.375 | Y |  | Bridge replacement over BNSF Railway 2.7 miles north of Harlem Road and 0.6 mile south of Rte. 9. Project involves bridge A4642. | Federal | 12191 | 3048 | 0 | 15239 | 0 | NHPP |  | 0 | 500 | 502 | 600 | 1582 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
412 | 3 | CLAY | US 169 S | 4P3295 | 0.154 | Y | 990311 | Improve sight distance and drainage and add turn lanes at 188th Street. | Federal | 1450 | 161 | 0 | 2370 | 0 | SAFETY |  | 715 | 84 | 0 | 0 | 0 | 0 | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1527 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
413 | 3 | CLAY | US 169 S | KU0064 | 4.514 | Y |  | Pavement resurfacing from I-29 to the Buck O'Neil Bridge. | Federal | 3122 | 781 | 0 | 3903 | 0 | NHPP |  | 0 | 10 | 20 | 20 | 233 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3620 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
414 | 3 | CLAY | MO 210 E | 4S3414 | 5.893 | Y | 590270 | Pavement resurfacing from I-435 to 0.3 mile west of Rte. 291. | Federal | 3378 | 844 | 0 | 4262 | 0 | NHPP | 4S3350 | 40 | 285 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3937 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
415 | 3 | CLAY | MO 210 E | KU0111 | 0.329 | Y |  | Bridge rehabilitation over Rte. 269, 0.8 mile east of Walker Road and 0.8 mile west of N Brighton Avenue. Project involves bridges A2175 and A2176. | Federal | 7242 | 1811 | 0 | 9053 | 0 | NHPP |  | 0 | 400 | 400 | 156 | 200 | 449 | 0 | 0 | 0 | 0 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7426 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
416 | 3 | CLAY | MO 210 W | 4S3337 | 12.037 | Y | 590298 | Pavement resurfacing and add guardrail from west of Rte. 291 to Ray County line. | Federal | 4298 | 1074 | 0 | 5482 | 0 | NHPP | 3S3166 | 110 | 359 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
417 | 3 | CLAY | MO 210 W | 4S3350 | 3.691 | Y | 690593 | Pavement resurfacing from I-29 to west of I-435. | Federal | 3142 | 785 | 0 | 3967 | 0 | NHPP | 4S3414 | 40 | 286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3641 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
418 | 3 | CLAY | MO 269 S | 4S3487 | 0.841 | Y | 590300 | Bridge rehabilitation over the Missouri River from Riverboat Drive to West Access Road. Project involves bridge A5817. | Federal | 2038 | 509 | 0 | 2747 | 0 | NHPP | 1P3430 | 200 | 201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2346 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
419 | 3 | CLAY | IS 29 S | 4I3458 | 0.591 | Y | 590295 | Bridge replacement over Guinotte Avenue 0.4 mile south of Missouri River and 0.7 mile north of Rte. 24 and over Bedford Avenue 1 mile south of Rte. 210 and 0.5 mile north of Missouri River. Project involves bridges L0788 and L0789. | Federal | 34851 | 3872 | 0 | 39233 | 0 | NHFP |  | 510 | 1001 | 250 | 100 | 2477 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34894 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
420 | 3 | CLAY | IS 29 S | 4I3458B | 0.6 | Y |  | Bridge rehabilitation over Guinotte Avenue, 0.4 mile south of Missouri River and 0.7 mile north of Rte. 24, and over Bedford Avenue, 1.0 mile south of Rte. 210 and 0.5 mile north of Missouri River. Project involves bridges L0788 and L0789. | Federal | 2102 | 234 | 0 | 2336 | 0 | NHPP |  | 0 | 618 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1718 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
421 | 3 | CLAY | IS 29 S | KU0059 | 1.33 | Y |  | Pavement resurfacing from 0.2 mile north of Parvin Road to Rte. 210. | Federal | 2166 | 241 | 0 | 2407 | 0 | NHPP |  | 0 | 20 | 20 | 153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2214 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
422 | 3 | CLAY | IS 29 S | KU0061 | 0.324 | Y |  | Bridge rehabilitation over Parvin Road 0.7 mile north of Rte. 1 and 1.5 miles south of Rte. 210. Project involves bridges L0659 and L0660. | Federal | 8672 | 964 | 0 | 9636 | 0 | NHPP |  | 0 | 200 | 400 | 300 | 100 | 583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8053 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
423 | 3 | CLAY | MO 291 N | KU0125 | 0.07 | Y |  | Bridge rehabilitation over Union Pacific Railroad 1.2 miles north of Ruth Ewing Road and 0.2 mile south of Leonard Street. Project involves bridge A2503. | Federal | 1582 | 395 | 0 | 1977 | 0 | NHPP |  | 0 | 100 | 285 | 285 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1307 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
424 | 3 | CLAY | MO 291 S | KU0117 | 0.028 | Y |  | Upgrade signals at Flintlock Road. | Adv. CN | 189 | 47 | 0 | 236 | 0 | AC-STBG | KU0121 KU0132 | 0 | 1 | 1 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 219 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
425 | 3 | CLAY | MO 291 S | KU0121 | 0.021 | Y |  | Add signal and westbound turn lane at North Sherman Road. | Federal | 340 | 85 | 0 | 425 | 0 | NHPP | KU0117 KU0132 | 0 | 10 | 8 | 31 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 371 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
426 | 3 | CLAY | MO 33 N | KU0035 | 13.11 | Y |  | Pavement resurfacing from Rte. PP to Rte. 69. | Adv. CN | 2169 | 542 | 0 | 2711 | 0 | AC-STBG |  | 0 | 5 | 30 | 30 | 158 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2488 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
427 | 3 | CLAY | IS 35 N | KU0013 | 0.435 | Y |  | Bridge deck sealing at various locations in the urban Kansas City District. | Federal | 444 | 111 | 0 | 555 | 0 | STBG |  | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 510 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
428 | 3 | CLAY | IS 35 N | KU0073 | 5.799 | Y |  | Pavement and shoulder resurfacing from bridge over Pleasant Valley Road to the I-29/I-35 split. Includes ramps at Antioch Road, Chouteau Trafficway, Winn Road and Rte. 69. | Federal | 5153 | 572 | 0 | 5725 | 0 | NHPP |  | 0 | 30 | 30 | 366 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
429 | 3 | CLAY | IS 35 S | KU0008 | 8.208 | Y |  | Concrete pavement repair from Clinton County line to Fishing Creek. | Federal | 5785 | 643 | 0 | 6428 | 0 | NHPP |  | 0 | 506 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5922 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
430 | 3 | CLAY | IS 35 S | KU0060 | 9.558 | Y |  | Pavement resurfacing from 1.6 miles north of 128th Street to Pleasant Valley Road. | Federal | 6506 | 723 | 0 | 7229 | 0 | NHPP |  | 0 | 50 | 50 | 462 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
431 | 3 | CLAY | IS 435 S | 4I3334 | 6.158 | Y | 590290 | Pavement resurfacing from northeast 108th Street to Rte. 69. | Federal | 6449 | 717 | 0 | 7387 | 0 | NHPP | 4I3335 | 221 | 480 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6686 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
432 | 3 | CLAY | IS 435 S | 4I3335 | 6.581 | Y | 490215 | Pavement resurfacing from Cookingham Drive to 108th Street. | Federal | 7238 | 804 | 0 | 8197 | 0 | NHPP | 4I3334 | 155 | 554 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7488 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
433 | 3 | CLAY | IS 435 S | KU0005 | 4.44 | Y |  | Repair Slides on southbound at 53rd Street, southbound I-29 north of Rte. U, southbound I-29 north of truck parking area and northbound I-29 north of Rte. 273. | Adv. CN | 1898 | 475 | 0 | 2373 | 0 | AC-STBG |  | 0 | 212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2161 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
434 | 3 | CLAY | IS 435 S | KU0030 | 2.942 | Y |  | Pavement resurfacing from Rte. 69 to the Missouri River. | Federal | 5943 | 660 | 0 | 6603 | 0 | NHPP | KU0036 | 0 | 1 | 1 | 554 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
435 | 3 | CLAY | US 69 N | 4S3482 | 0.896 | Y | 590277 | Payment to Kansas City to add shared use path, upgrade pedestrian facilities and drainage improvements from Highland Avenue to Chouteau Trafficway. $2,745,217 Cost Share funds. | Federal | 2205 | 551 | 0 | 2756 | 0 | NHPP |  | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2745 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
436 | 3 | CLAY | US 69 N | KU0055 | 0.078 | Y |  | Add roundabout at Rte. D in Lawson. | Federal | 2020 | 224 | 0 | 2244 | 0 | SAFETY |  | 0 | 10 | 10 | 145 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2079 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
437 | 3 | CLAY | US 69 N | KU0097 | 0.508 | Y |  | Upgrade sidewalks from Agnes Avenue to North Cleveland Avenue. | Adv. CN | 718 | 180 | 0 | 898 | 0 | AC-STBG |  | 0 | 56 | 50 | 94 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 677 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
438 | 3 | CLAY | US 69 S | 4P3465 | 0.799 | Y | 590293 | Remove the pedestrian bridge and upgrade pedestrian facilities to comply with the ADA Transition Plan from Park Avenue to Randolph Road. | Adv. CN | 650 | 163 | 0 | 873 | 0 | AC-STBG |  | 60 | 48 | 74 | 0 | 0 | 0 | 0 | 0 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 665 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
439 | 3 | CLAY | US 69 S | 4S3413 | 3.183 | Y | 590276 | Pavement resurfacing from Rte. 92 to McCleary Road. | Federal | 1588 | 397 | 0 | 2010 | 0 | NHPP |  | 25 | 10 | 130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1845 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
440 | 3 | CLAY | MO 9 N | 4S3401 | 0 | Y | 590261 | Payment to North Kansas City for pavement resurfacing and ADA upgrades from 10th Avenue to 32nd Avenue. | Adv. CN | 249 | 62 | 0 | 311 | 0 | AC-STBG |  | 0 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 288 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
441 | 3 | CLAY | MO 9 S | KU0031 | 1.948 | Y |  | Pavement resurfacing on the southbound lane from North Oak Trafficway to Brookfield Sub. | Federal | 546 | 137 | 0 | 683 | 0 | NHPP |  | 0 | 2 | 4 | 4 | 42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 631 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
442 | 3 | CLAY | MO 92 E | 4P3323C | 0.041 | Y | 590292 | Replace box culvert 0.1 mile west of Cordell Road between Excelsior Springs and Kearney. | Federal | 246 | 62 | 0 | 327 | 0 | NHPP |  | 19 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 257 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
443 | 3 | CLAY | MO 92 E | 4P3420 | 1.495 | Y | 590301 | Pavement resurfacing including ramps at I-35, asphalt entrances and loop detector replacement from Nation Road to east side of Rte. 33. Upgrade pedestrian facilities to comply with the ADA Transition Plan on ramps at Rte. 33. | Federal | 2006 | 502 | 0 | 2523 | 0 | NHPP |  | 15 | 313 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2195 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
444 | 3 | CLAY | RT A S | KU0070 | 5.559 | Y |  | Pavement resurfacing from Rte. 92 to Liberty city limits. | Adv. CN | 770 | 193 | 0 | 963 | 0 | AC-STBG |  | 0 | 10 | 20 | 75 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 856 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
445 | 3 | CLAY | CST BRYANT ST N | KU0123 | 0.031 | Y |  | Bridge rehabilitation over I-35, 0.3 mile east of Poe Street and 0.5 mile west of I-435. Project involves bridge L0756. | Federal | 2034 | 509 | 0 | 2543 | 0 | NHPP |  | 0 | 10 | 200 | 100 | 100 | 160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1973 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
446 | 3 | CLAY | CST CHOUTEAU TRFY N | 4S3400 | 0.247 | Y | 590262 | Payment to Kansas City for lane addition, bike/ped lanes and ADA traffic signal upgrades at I-35. $951,925 Cost Share funds. | Adv. CN | 818 | 204 | 0 | 1022 | 0 | AC-STBG |  | 0 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 952 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
447 | 3 | CLAY | RT DD E | KU0071 | 1.733 | Y |  | Pavement resurfacing from Litton Way to Rte. 92. | Adv. CN | 343 | 86 | 0 | 429 | 0 | AC-STBG |  | 0 | 2 | 4 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 395 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
448 | 3 | CLAY | RP IS29S TO IS35N N | KU0025 | 0 | Y |  | Bridge rehabilitation over I-35, 0.2 mile south of Davidson Road and 0.5 mile west of Rte. 1. Project involves bridge A1763. | Federal | 8996 | 2249 | 0 | 11245 | 0 | NHPP |  | 0 | 200 | 200 | 300 | 300 | 871 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9374 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
449 | 3 | CLAY | RT N S | 4S3367 | 5.599 | Y | 590287 | Pavement resurfacing from Seybold Road to Rte. 210. | Adv. CN | 724 | 181 | 0 | 925 | 0 | AC-STBG |  | 20 | 5 | 61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 839 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
450 | 3 | CLAY | CST NW BARRY RD E | KU0225 | 0.037 | Y |  | Urgent bridge rehabilitation on the westbound bridge over Rte.169. Project includes bridge L0873. | Federal | 398 | 100 | 0 | 498 | 0 | NHPP |  | 0 | 126 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 372 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
451 | 3 | JACKSON | MO 12 E | 4P3268G | 2.4 | Y |  | Upgrade pedestrian facilities to comply with the ADA Transition Plan from Arlington to Spring Street. $299,000 Statewide Transportation Alternatives funds. | Adv. CN | 1754 | 438 | 0 | 2197 | 0 | AC-STBG |  | 5 | 100 | 125 | 319 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1608 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
452 | 3 | JACKSON | MO 150 E | 4S3395 | 0.988 | Y | 690544 | Payment to Grandview for construction of roundabout and turn lanes and installation of traffic signals from Byars Road to Kelly Road in Grandview. $915,628 Cost Share funds. | Federal | 738 | 184 | 0 | 922 | 0 | NHPP |  | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 916 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
453 | 3 | JACKSON | MO 150 E | KU0043 | 11.805 | Y |  | Pavement resurfacing from Rte. 291 to Rte. E. | Federal | 2074 | 518 | 0 | 2592 | 0 | NHPP |  | 0 | 5 | 15 | 20 | 156 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2396 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
454 | 3 | JACKSON | MO 150 E | KU0140 | 0.085 | Y |  | Bridge rehabilitation over Blue River 0.1 mile south of Wyandotte Street in Martin City. Project involves bridges A5495 and A5496. | Federal | 5844 | 1461 | 0 | 7305 | 0 | NHPP |  | 0 | 200 | 300 | 300 | 200 | 557 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5748 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
455 | 3 | JACKSON | MO 210 E | KU0132 | 0.15 | Y |  | Upgrade signals at Rte. 291. | Federal | 479 | 120 | 0 | 599 | 0 | NHPP | KU0117 KU0121 | 0 | 10 | 20 | 49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 520 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
456 | 3 | JACKSON | US 24 E | 4P3409 | 11.916 | Y | 690599 | Pavement resurfacing, guardrail upgrades and adding rumblestripes from Rte. 7 to Lafayette County line near Napoleon. | Federal | 3954 | 989 | 0 | 5023 | 0 | NHPP |  | 80 | 383 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4560 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
457 | 3 | JACKSON | US 24 E | 4S3405 | 0.958 | Y | 690533 | Add turn lanes, improve signage, upgrade pedestrian facilities to comply with the ADA Transition Plan, upgrade drainage, replace signals and access management from Sterling Avenue to River Boulevard. $2,793,000 Open Container funds. | Federal | 5990 | 665 | 0 | 6829 | 0 | SAFETY | 4S3405B | 94 | 495 | 0 | 0 | 0 | 0 | 0 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
458 | 3 | JACKSON | US 24 E | 4S3405B | 2.925 | Y |  | Add intersection turn lane and bicycle/pedestrian facilities from River Boulevard to Rte. 291. $4,491,000 Cost Share, $3,435,332 STBG-Urban and $1,680,833 Independence funds. | Adv. CN | 8216 | 374 | 1680 | 10370 | 0 | AC-STBG | 4S3405 | 100 | 664 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9606 | 0 | 0 | 0 | 0 | 0 | 0 | 5115 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
459 | 3 | JACKSON | US 24 E | KU0040 | 3.7 | Y |  | Bridge rehabilitation over Fire Prairie Creek and Drainage Ditch from 0.3 mile west of Schuster Road to 0.4 mile east of Burnley Road. Project involves bridges A2721, A2722, A2723 and A2724. | Federal | 1034 | 258 | 0 | 1292 | 0 | NHPP |  | 0 | 3 | 10 | 162 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1117 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
460 | 3 | JACKSON | US 24 E | KU0226 | 0.67 | Y |  | Upgrade bicycle and pedestrian facilities, drainage, signal upgrades and add intersection lighting from Sterling Avenue to Wilson Road. $3,443,438 Cost Share and $3,308,000 Independence funds. | Adv. CN | 4468 | 0 | 3308 | 7776 | 0 | AC-STBG |  | 0 | 10 | 160 | 451 | 0 | 0 | 0 | 0 | 0 | 258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6897 | 0 | 0 | 0 | 0 | 0 | 250 | 3058 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
461 | 3 | JACKSON | US 24 W | KU0038 | 0.096 | Y |  | Bridge rehabilitation over Union Pacific Railroad 0.2 mile north of Lake City Buckner Road and 0.3 mile south of Old Lexington Road. Project involves bridge A2725. | Federal | 1101 | 275 | 0 | 1376 | 0 | NHPP |  | 0 | 5 | 5 | 128 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1238 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
462 | 3 | JACKSON | MO 269 S | 4S3452 | 0.796 | Y | 690600 | Pavement resurfacing from the Missouri River to Front Street. | Adv. CN | 434 | 109 | 0 | 558 | 0 | AC-STBG |  | 15 | 5 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
463 | 3 | JACKSON | MO 291 N | 4P3196 | 0.158 | Y |  | Bridge replacement, rebuild pavement, add sidewalks and realign north ramp of interchange from SE 7th Terrace to SE Oldham Parkway. Project involves bridge A1748. $10,705,407 Cost Share and $4,595,665 Lee's Summit funds. | Federal | 13175 | 0 | 4595 | 19420 | 0 | NHPP |  | 1650 | 1 | 1282 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16487 | 0 | 0 | 0 | 0 | 0 | 0 | 4595 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
464 | 3 | JACKSON | MO 291 N | 4P3485 | 1.417 | Y |  | Bridge washing at various locations over the Missouri River in the urban Kansas City District. Project involves bridges L0568, A4757 and A7650. | Federal | 130 | 33 | 0 | 168 | 0 | NHPP |  | 5 | 5 | 5 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 139 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
465 | 3 | JACKSON | MO 291 S | 4P3404 | 2.25 | Y | 690601 | Pavement resurfacing from Rte. 78 to 39th Street. | Federal | 2743 | 686 | 0 | 3494 | 0 | NHPP | 4S3348 4S3429 | 65 | 235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3194 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
466 | 3 | JACKSON | MO 291 S | KU0065 | 2.747 | Y |  | Pavement resurfacing from 0.7 mile south of Rte. 150 to Rte. 58. | Federal | 1769 | 442 | 0 | 2211 | 0 | NHPP |  | 0 | 20 | 30 | 20 | 180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
467 | 3 | JACKSON | MO 291 S | KU0130 | 0.082 | Y |  | Upgrade signal and turn lane extension from Rte. 78 to Hidden Valley Road. | Federal | 411 | 103 | 0 | 514 | 0 | NHPP |  | 0 | 2 | 2 | 2 | 2 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
468 | 3 | JACKSON | IS 35 S | KU0018 | 2.821 | Y |  | Pavement resurfacing from I-70 to Kansas State line. | Federal | 3205 | 356 | 0 | 3561 | 0 | NHPP |  | 0 | 5 | 5 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3331 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
469 | 3 | JACKSON | MO 350 E | 4S3339 | 2.585 | Y | 690535 | Add turn lanes, pedestrian crosswalks and signals from Laurel Avenue to Westridge Road. | Federal | 935 | 104 | 0 | 1290 | 0 | SAFETY | 4S3410 | 250 | 104 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 935 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
470 | 3 | JACKSON | MO 350 E | 4S3410 | 5.669 | Y | 690585 | Pavement resurfacing from 63rd Street to 0.7 mile west of Colbern Road. | Federal | 6988 | 1747 | 0 | 8800 | 0 | NHPP | 4S3339 | 65 | 553 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 8172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
471 | 3 | JACKSON | US 40 E | 4S3347 | 0.12 | Y | 690587 | Pavement and shoulder replacement at the north side of Moore Street. | Federal | 235 | 26 | 0 | 281 | 0 | SAFETY |  | 20 | 2 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 253 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
472 | 3 | JACKSON | US 40 E | KU0066 | 0.666 | Y |  | Corridor improvements and signal upgrades from Cliff Avenue to Little Blue Parkway. | Federal | 3825 | 956 | 0 | 4781 | 0 | NHPP |  | 0 | 100 | 100 | 100 | 50 | 298 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4133 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
473 | 3 | JACKSON | US 40 E | KU0074 | 14.035 | Y |  | Pavement resurfacing from Sterling Avenue to I-70 in Grain Valley. | Federal | 8806 | 2202 | 0 | 11008 | 0 | NHPP |  | 0 | 50 | 100 | 734 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10124 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
474 | 3 | JACKSON | IS 435 N | 4I3451 | 0.199 | Y | 690597 | Bridge replacement over 87th Street, 1.1 miles north of Rte. W and 2.2 miles south of Gregory Boulevard. Project involves bridge A1642. | Federal | 5880 | 653 | 0 | 6899 | 0 | NHPP |  | 361 | 617 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5916 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
475 | 3 | JACKSON | IS 435 N | 4P3468 | 0.251 | Y | 990349 | Bridge rehabilitation at various locations within the urban Kansas City District. Project involves bridges A1667, A1674, A1268 and L0232. | Federal | 2372 | 264 | 0 | 2691 | 0 | NHPP |  | 55 | 207 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
476 | 3 | JACKSON | IS 435 N | KU0036 | 3.383 | Y |  | Pavement resurfacing from Missouri River to Rte. 24. | Federal | 3603 | 400 | 0 | 4003 | 0 | NHPP | KU0030 | 0 | 25 | 25 | 289 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3664 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
477 | 3 | JACKSON | IS 435 S | KU0062 | 1.74 | Y |  | Pavement resurfacing from Rte. 24 to Rte. 78. | Federal | 3107 | 345 | 0 | 3452 | 0 | NHPP |  | 0 | 20 | 30 | 174 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3228 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
478 | 3 | JACKSON | IS 470 E | KU0020 | 4.076 | Y |  | Pavement resurfacing from Hickman Mills Drive to Raytown Road. | Federal | 2989 | 332 | 0 | 3322 | 0 | NHPP |  | 1 | 1 | 1 | 203 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3116 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
479 | 3 | JACKSON | IS 470 E | KU0115 | 0.174 | Y |  | Drainage and pavement repair at Rte. 291. | Federal | 406 | 45 | 0 | 451 | 0 | NHPP |  | 0 | 5 | 5 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 410 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
480 | 3 | JACKSON | IS 470 W | KU0232 | 10.442 | Y |  | Striping upgrades on various routes in various counties in the urban Kansas City District. | Federal | 1213 | 135 | 0 | 1348 | 0 | SAFETY |  | 0 | 24 | 63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1261 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
481 | 3 | JACKSON | IS 49 S | 4I3494 | 0.136 | Y | 690552 | Bridge rehabilitation over Little Blue River 0.6 mile north of 155th Street and 0.6 mile south of Rte. 150. Project involves bridges L0530 and A0478. | Federal | 4011 | 446 | 0 | 4582 | 0 | NHPP |  | 125 | 50 | 50 | 52 | 273 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4021 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
482 | 3 | JACKSON | IS 49 S | 4P3268H | 28.671 | Y |  | Upgrade pedestrian facilities to comply with the ADA Transition Plan at various locations in Kansas City and Grandview. | Adv. CN | 1536 | 384 | 0 | 1925 | 0 | AC-STBG |  | 5 | 5 | 20 | 175 | 273 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
483 | 3 | JACKSON | IS 49 S | KU0158 | 0.001 | Y |  | Replace sign truss 0.3 mile south of Longview Road and 0.3 mile north of Blue Ridge Boulevard. | Federal | 279 | 31 | 0 | 310 | 0 | NHPP |  | 0 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 281 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
484 | 3 | JACKSON | IS 670 E | 4P2316 | 0.079 | Y | 690407 | Payback to Kansas City for replacement of Wyandotte and Central bridges from Central Street to Wyandotte Street. | Federal | 0 | 3621 | 0 | 3621 | 0 | STATE |  | 0 | 240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3381 | 0 | 0 | 0 | 0 | 0
485 | 3 | JACKSON | IS 670 W | KU0029 | 1.366 | Y |  | Pavement resurfacing from the Belleview Overpass to Troost Avenue. | Federal | 1928 | 214 | 0 | 2142 | 0 | NHPP | KU0018 | 0 | 14 | 25 | 151 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1952 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
486 | 3 | JACKSON | MO 7 N | 4S3298B | 0.486 | Y |  | Upgrade pedestrian facilities to comply with the ADA Transition Plan from Roanoke Drive to Pink Hill Road. | Adv. CN | 193 | 48 | 0 | 242 | 0 | AC-STBG |  | 1 | 1 | 1 | 1 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 223 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
487 | 3 | JACKSON | MO 7 S | 4P3268I | 4.541 | Y |  | Upgrade pedestrian facilities to comply with the ADA Transition Plan at various locations in Jackson County. $1,373,000 Statewide Transportation Alternatives funds. | Adv. CN | 2766 | 692 | 0 | 3463 | 0 | AC-STBG |  | 5 | 5 | 50 | 250 | 518 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2617 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
488 | 3 | JACKSON | MO 7 S | 4S3348 | 6.188 | Y | 690589 | Pavement resurfacing from Rte. 24 to Pink Hill Road. | Federal | 2026 | 506 | 0 | 2572 | 0 | NHPP | 4P3404 4S3429 | 40 | 190 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2342 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
489 | 3 | JACKSON | MO 7 S | 4S3408 | 21.511 | Y | 690561 | Pavement resurfacing from 0.2 mile south of Colbern Road to Bird Street in Harrisonville. | Federal | 10066 | 2516 | 0 | 12622 | 0 | NHPP |  | 40 | 30 | 831 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11721 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
490 | 3 | JACKSON | MO 7 S | 4S3429 | 3.318 | Y | 690602 | Pavement resurfacing from Pink Hill Road to Victor Road. | Federal | 2672 | 668 | 0 | 3421 | 0 | NHPP | 4P3404 4S3348 | 81 | 229 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
491 | 3 | JACKSON | IS 70 E | 4I1486D | 4.489 | Y | 690563 | Bridge replacement, removal and rebuild pavement from Paseo to I-435. Design-Build project includes various bridges in Jackson County. $576,000 Open Container funds. | Federal | 227014 | 25224 | 0 | 255138 | 0 | NHPP |  | 2900 | 3500 | 18366 | 0 | 0 | 0 | 0 | 0 | 3193 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 227179 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
492 | 3 | JACKSON | IS 70 E | 4I3288 | 0.3 | Y | 690513 | Bridge replacement at Rte. AA and Rte. BB, 4 miles east of Rte. 7 and 3.8 miles west of Rte. F. Project involves twin bridges L0984. | Federal | 6102 | 678 | 0 | 7556 | 0 | NHFP |  | 775 | 528 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6252 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
493 | 3 | JACKSON | IS 70 E | 4P3323B | 3.701 | Y | 690591 | Replace median barrier from Manchester Trafficway to Chrysler Street. | Federal | 3444 | 383 | 0 | 3857 | 0 | SAFETY |  | 30 | 35 | 35 | 35 | 34 | 244 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3444 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
494 | 3 | JACKSON | IS 70 E | KU0016 | 0.088 | Y |  | Bridge rehabilitation at 11th Street, 0.1 mile south of 10th Street and 0.1 mile north of 12th Street. Project involves bridge A0243. | Federal | 7367 | 818 | 0 | 8185 | 0 | NHPP |  | 0 | 300 | 220 | 220 | 611 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6834 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
495 | 3 | JACKSON | IS 70 E | KU0114 | 0.509 | Y |  | Bridge rehabilitation over Rte. 40, 0.1 mile west of Blue Ridge Boulevard and bridge rehabilitation over Sterling Avenue, 0.7 mile east of Pittman Road. Project involves twin bridges L0973 and L0972. Potential Design-Build. | Federal | 18455 | 2051 | 0 | 20506 | 0 | NHPP |  | 0 | 400 | 500 | 500 | 500 | 1480 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17126 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
496 | 3 | JACKSON | N OR 70 E | 4S3411 | 4.971 | Y | 690571 | Pavement resurfacing from I-470 to Lafayette County line. | Adv. CN | 974 | 244 | 0 | 1235 | 0 | AC-STBG |  | 17 | 5 | 54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
497 | 3 | JACKSON | US 71 N | 4S3490 | 0.708 | Y | 690573 | Bridge rehabilitation over Rte. W (Bannister Road) 0.6 mile north of I-435 and 0.7 mile south of Blue River Road. Project involves bridges H0033, A2395 and twin bridges L0842. | Federal | 9948 | 2487 | 0 | 12680 | 0 | NHPP |  | 245 | 1400 | 100 | 100 | 695 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10119 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
498 | 3 | JACKSON | MO 78 E | 4P3268F | 4.561 | Y |  | Upgrade pedestrian facilities to comply with the ADA Transition Plan from Maywood Street to Redwood Avenue. $927,000 Statewide Transportation Alternatives funds. | Adv. CN | 1337 | 334 | 0 | 1676 | 0 | AC-STBG |  | 5 | 10 | 119 | 289 | 0 | 0 | 0 | 0 | 0 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1222 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
499 | 3 | JACKSON | MO 78 E | KU0042 | 6.019 | Y |  | Pavement resurfacing from I-435 to Rte. 291. | Federal | 4188 | 1047 | 0 | 5235 | 0 | NHPP |  | 0 | 0 | 20 | 30 | 346 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4839 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
500 | 3 | JACKSON | CST BLUE RIDGE BLVD N | 4I3024 | 0.15 | Y | 690421 | Bridge replacement over I-70 in Independence. Project involves bridge L0997. | Federal | 1886 | 471 | 0 | 2710 | 0 | NHPP |  | 351 | 78 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2279 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
501 | 3 | JACKSON | CST BLUE RIDGE BLVD N | 4I3024B | 0.078 | Y | 590266 | Modify interchange configuration over I-70 in Independence. | Federal | 9176 | 2294 | 0 | 12584 | 0 | NHPP |  | 490 | 1499 | 0 | 0 | 0 | 0 | 0 | 624 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9971 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
502 | 3 | JACKSON | RT E S | KU0069 | 2.05 | Y |  | Pavement resurfacing from Rte. 50 to Rte. KK. | Adv. CN | 242 | 61 | 0 | 303 | 0 | AC-STBG |  | 0 | 2 | 2 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 279 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
503 | 3 | JACKSON | RT F S | KU0110 | 0.06 | Y |  | Bridge replacement over Phillips Creek, 0.5 mile north of Zumait Road and 0.5 mile south of Cline Road. Project involves culvert Y0024. | Adv. CN | 1157 | 289 | 0 | 1446 | 0 | AC-STBG |  | 0 | 50 | 66 | 128 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
504 | 3 | JACKSON | RT FF E | 4S3361 | 9.299 | Y | 690592 | Pavement resurfacing from Rte. 7 to Webb Road, excluding Rte. BB. | Adv. CN | 1178 | 294 | 0 | 1492 | 0 | AC-STBG |  | 20 | 2 | 94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1376 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
505 | 3 | JACKSON | CST HOLMES ST N | KU0024 | 0.61 | Y |  | Bridge replacement over I-670, 0.1 mile north of Truman Road and 0.1 mile south of 13th Street. Project involves bridge A0825. | Federal | 6079 | 1520 | 0 | 7599 | 0 | NHPP |  | 0 | 200 | 200 | 617 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6582 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
506 | 3 | JACKSON | RP IS670E TO IS70W W | 4S3383B | 0.039 | Y | 990337 | Bridge rehabilitation at various locations in the urban Kansas City District. Project involves bridges A0805, A1111, A1112, A1124, A4151, A5164 and A7646. | Federal | 2230 | 558 | 0 | 2868 | 0 | NHPP |  | 80 | 156 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2632 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
507 | 3 | JACKSON | CRD LEFHOLZ RD N | KU0127 | 0.105 | Y |  | Bridge rehabilitation over I-70 south of McQuerry Road and north of Old US Highway 40. Project involves bridge R0135. | Federal | 2203 | 551 | 0 | 2754 | 0 | NHPP |  | 0 | 50 | 50 | 50 | 50 | 193 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2356 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
508 | 3 | JACKSON | CST LITTLE BLUE PKWY S | KU0033 | 0.175 | Y |  | Bridge rehabilitation, widen interchange ramps and upgrade signals at I-70 in Independence. Project involves bridge A5726. | Federal | 1203 | 301 | 0 | 1504 | 0 | NHPP |  | 0 | 20 | 20 | 20 | 20 | 108 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1316 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
509 | 3 | JACKSON | CST PITTMAN RD S | KU0133 | 0.135 | Y |  | Drainage upgrade from 41st Street to 42nd Street. | Adv. CN | 273 | 68 | 0 | 341 | 0 | AC-STBG |  | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 301 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
510 | 3 | JACKSON | CST PROSPECT AVE N | 4S3374 | 0.083 | Y | 690595 | Bridge replacement over I-70, 0.1 mile south of 13th Street and 0.1 mile north of Truman Road. Project involves bridge A0291. | Federal | 7170 | 1792 | 0 | 11137 | 0 | NHPP |  | 1125 | 818 | 0 | 0 | 0 | 0 | 0 | 1050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
511 | 3 | JACKSON | RP STADIUM DR TO IS435S S | 4I3501 | 0.132 | Y | 690579 | Bridge rehabilitation over Raytown Road 1 mile north of Sni A Bar Road and 0.4 mile south of Stadium Boulevard. Project involves bridges A2852 and A2853. | Federal | 1372 | 343 | 0 | 1735 | 0 | NHPP |  | 20 | 15 | 15 | 15 | 108 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1562 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
512 | 3 | JACKSON | RT V S | 4S3351 | 5.159 | Y | 690590 | Pavement resurfacing from Rte. 40 to Rte. 350. | Federal | 1819 | 455 | 0 | 2294 | 0 | NHPP |  | 20 | 160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2114 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
513 | 3 | JACKSON | CST VIEW HIGH DR N | 4I3470 | 0.186 | Y | 690594 | Payment to I-470 Western Gateway Transportation Development District to modify interchange configuration at I-470. $3,992,500 Cost Share funds. | Adv. CN | 3422 | 855 | 0 | 4277 | 0 | AC-STBG |  | 0 | 284 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3993 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
514 | 3 | JACKSON | Various | 4P3268 | 0 | Y | 590257 | Upgrade pedestrian facilities to comply with the ADA Transition Plan at various locations in the urban Kansas City district. $20,000 Statewide Transportation Alternatives funds. | Adv. CN | 1827 | 457 | 0 | 2325 | 0 | AC-STBG |  | 41 | 1 | 1 | 6 | 642 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1613 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
515 | 3 | JACKSON | Various | KU0116 | 0 | Y |  | Lighting improvements at various locations in Jackson County. | Adv. CN | 926 | 232 | 0 | 1158 | 0 | AC-STBG |  | 0 | 2 | 2 | 72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1082 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
516 | 3 | JACKSON | CST W 14TH ST E | KU0129 | 0.082 | Y |  | Bridge replacement over I-35, 0.1 mile west of Pennsylvania Avenue and 0.1 mile east of W 13th Street. Project involves bridge A1122. | Federal | 3560 | 890 | 0 | 4450 | 0 | NHPP |  | 0 | 100 | 200 | 100 | 100 | 244 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3706 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
517 | 3 | JACKSON | RP WYOMING ST TO IS670E E | 4I3486 | 0.312 | Y | 990356 | Bridge rehabilitation on ramp from Wyoming Street to I-670 eastbound. Project involves bridge A3139. | Federal | 1232 | 308 | 0 | 1656 | 0 | NHPP |  | 106 | 122 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1418 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
518 | 3 | LAFAYETTE | N OR 70 E | 4S3394 | 30.04 | Y |  | Pavement resurfacing on disconnected sections of westbound and eastbound I-70 outer roads from 0.7 mile east of Salem Street to Rte. Y. | Adv. CN | 4338 | 1085 | 0 | 5467 | 0 | AC-STBG |  | 44 | 389 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
519 | 3 | PLATTE | MO 152 E | KU0050 | 4.15 | Y |  | Pavement resurfacing from I-29 to Rte. 169. | Federal | 3635 | 909 | 0 | 4544 | 0 | NHPP | KU0052 KU0054 | 0 | 20 | 50 | 295 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4176 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
520 | 3 | PLATTE | MO 273 S | KU0009 | 0.109 | Y |  | Signalize intersection and add intersection turn lanes at Rte. 371. | Federal | 622 | 69 | 0 | 691 | 0 | SAFETY |  | 0 | 5 | 5 | 41 | 0 | 0 | 0 | 0 | 0 | 46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 594 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
521 | 3 | PLATTE | MO 273 S | KU0041 | 4.484 | Y |  | Pavement resurfacing and guardrail replacement Rte. 45 to Rte. 371. | Adv. CN | 1186 | 297 | 0 | 1483 | 0 | AC-STBG |  | 0 | 5 | 5 | 10 | 92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1371 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
522 | 3 | PLATTE | IS 29 N | 4I3450 | 0.722 | Y | 490216 | Bridge replacement over NW 72nd Street. Project involves bridge A1595. | Federal | 8780 | 975 | 0 | 10465 | 0 | NHFP |  | 710 | 1468 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8287 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
523 | 3 | PLATTE | IS 29 S | KU0017 | 12.232 | Y |  | Pavement resurfacing from 0.8 mile south of Mexico Avenue to Rte. 69. | Federal | 14027 | 1559 | 0 | 15586 | 0 | NHPP | KU0072 | 0 | 100 | 200 | 1023 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14263 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
524 | 3 | PLATTE | IS 29 S | KU0072 | 6.783 | Y |  | Pavement resurfacing from Rte. 273 to 0.8 mile south of Mexico Avenue. | Federal | 7239 | 804 | 0 | 8043 | 0 | NHPP | KU0017 | 0 | 50 | 50 | 422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7521 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
525 | 3 | PLATTE | MO 371 S | 4S3349 | 10.816 | Y | 490214 | Pavement resurfacing from Rte. 273 to the Buchanan County line. | Adv. CN | 2318 | 579 | 0 | 2962 | 0 | AC-STBG |  | 65 | 5 | 176 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2716 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
526 | 3 | PLATTE | IS 435 N | 4I3474 | 0.533 | Y | 490219 | Payment to KDOT for column repair on I-435 from 0.16 mile south of Northwest River Road and 1.17 miles north of Wolcott Drive. Project involves twin bridges A3289. | Federal | 91 | 10 | 0 | 101 | 0 | NHPP |  | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
527 | 3 | PLATTE | MO 45 N | KU0120 | 0.335 | Y |  | Add southbound left turn lane at Jones-Meyer Road. | Adv. CN | 591 | 148 | 0 | 739 | 0 | AC-STBG |  | 0 | 10 | 16 | 62 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 649 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
528 | 3 | PLATTE | MO 45 S | 4P3460 | 13.668 | Y | 490205 | Pavement resurfacing from Buchanan County line to Rte. 273. | Adv. CN | 4452 | 1113 | 0 | 5580 | 0 | AC-STBG | 4P3460B | 15 | 437 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5128 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
529 | 3 | PLATTE | MO 45 S | 4P3460B | 12.181 | Y | 490220 | Pavement resurfacing and replacement from Rte. 273 to Moore's Ferry Road. | Adv. CN | 11234 | 2809 | 0 | 14218 | 0 | AC-STBG | 4P3460 | 175 | 1089 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12954 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
530 | 3 | PLATTE | IS 635 N | 4P3268E | 17.346 | Y | 490221 | Upgrade pedestrian facilities to comply with the ADA Transition Plan at various locations in Clay and Platte County. $1,353,000 Statewide Transportation Alternatives funds. | Adv. CN | 1874 | 469 | 0 | 2348 | 0 | AC-STBG |  | 5 | 220 | 382 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1709 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
531 | 3 | PLATTE | IS 635 S | KU0095 | 0.19301 | Y |  | Scour mitigation and bridge repair over the Missouri River. Project involves bridge A1800. | Federal | 2402 | 267 | 0 | 2669 | 0 | NHPP |  | 0 | 50 | 50 | 100 | 240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2229 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
532 | 3 | PLATTE | MO 9 N | 4S3391 | 0.675 | Y | 490187 | Payment to Parkville for added sidewalks, bicycle/pedestrian trails, and for lighting and traffic signal improvements from Rte. 45 to Lakeview Drive. $1,734,500 Cost Share funds. | Federal | 1395 | 349 | 0 | 1749 | 0 | NHPP |  | 5 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1734 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
533 | 3 | PLATTE | MO 9 S | 4S3496 | 0.515 | Y | 590279 | Bridge rehabilitation over NW Briarcliff Parkway 0.3 mile north of Rte. 169 and 0.6 mile south of Riverway Boulevard. Project involves twin bridges A2020. | Federal | 1948 | 487 | 0 | 2490 | 0 | NHPP | 4S3497 4S3498 | 55 | 35 | 30 | 221 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2149 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
534 | 3 | PLATTE | MO 9 S | 4S3497 | 0.073 | Y | 490207 | Bridge rehabilitation over Riverway Boulevard 0.8 mile north of NW Briarcliff Parkway and 0.7 mile south of I-635. Project involves twin bridges A2019. | Federal | 1701 | 425 | 0 | 2181 | 0 | NHPP | 4S3496 4S3498 | 55 | 20 | 23 | 189 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1894 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
535 | 3 | PLATTE | MO 9 S | 4S3498 | 0.245 | Y | 490213 | Bridge rehabilitation over Line Creek 0.2 mile north of Riverway Boulevard and 0.4 mile south of I-635. Project involves twin bridges A2029. | Federal | 3522 | 881 | 0 | 4428 | 0 | NHPP | 4S3496 4S3497 | 25 | 47 | 50 | 407 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3899 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
536 | 3 | PLATTE | MO 92 E | 4P3329 | 0.2 | Y | 490183 | Payment to KDOT for bridge rehabilitation at Leavenworth (Missouri River bridge on Rte. 92). Project involves twin bridges K0941. | Federal | 3201 | 800 | 0 | 4005 | 0 | NHPP |  | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
537 | 3 | PLATTE | MO 92 E | 4P3393 | 0.2 | Y | 490195 | Payment to KDOT for deck and lighting repair at Centennial Bridge over the Missouri River at Leavenworth. Project involves bridge K0941. | Federal | 217 | 54 | 0 | 271 | 0 | NHPP |  | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
538 | 3 | PLATTE | MO 92 E | 4P3473 | 0.634 | Y | 490222 | Payment to KDOT for navigation light repair at Centennial Bridge over the Missouri River at Leavenworth from 0.2 mile east of North 4th Street and 0.5 mile west of Rte. 45. Project involves bridge K0941. | Federal | 205 | 51 | 0 | 256 | 0 | NHPP |  | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 238 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
539 | 3 | PLATTE | MO 92 E | KU0056 | 14.503 | Y |  | Pavement resurfacing from Rte. 273 to Rte. DD. | Federal | 4689 | 1172 | 0 | 5861 | 0 | NHPP |  | 0 | 20 | 20 | 30 | 370 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5421 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
540 | 3 | PLATTE | MO 92 E | KU0057 | 1.003 | Y |  | Rebuild pavement from Marshall Street to Kentucky Avenue. | Adv. CN | 6136 | 1534 | 0 | 7670 | 0 | AC-STBG |  | 0 | 100 | 100 | 100 | 100 | 512 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6753 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
541 | 3 | PLATTE | MO 92 E | KU0303 | 1.238 | Y |  | Payment to Platte City for roadway realignment and add bicycle and pedestrian facilities. $6,667,950 Governor's Cost Share Program funds. | Federal | 0 | 6669 | 0 | 6669 | 0 | STATE |  | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6668 | 0 | 0 | 0 | 0 | 0 | 0 | 6668 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
542 | 3 | PLATTE | RT B S | 4S3492 | 0.034 | Y | 490208 | Bridge replacement over Grove Creek 0.1 mile north of Perrin Street and 0.1 mile south of Main Street. Project involves bridge R0247. | Federal | 1090 | 273 | 0 | 1418 | 0 | NHPP |  | 55 | 50 | 20 | 88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1205 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
543 | 3 | PLATTE | RT FF E | KU0068 | 2.245 | Y |  | Pavement resurfacing from River Road to Rte. 9. | Adv. CN | 453 | 113 | 0 | 566 | 0 | AC-STBG |  | 0 | 2 | 5 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 522 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
544 | 3 | PLATTE | RT H S | KU0135 | 0.008 | Y |  | Replace culverts north of Taulbee Road, 0.3 mile south of Taulbee Road and Rte. E 0.3 mile east of Skinner Lake Road. | Adv. CN | 855 | 214 | 0 | 1069 | 0 | AC-STBG |  | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 949 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
545 | 3 | PLATTE | RT HH E | KU0128 | 0.125 | Y |  | Modify interchange configuration at I-29. Project involves bridge A7784. | Adv. CN | 9263 | 2316 | 0 | 11579 | 0 | AC-STBG |  | 0 | 200 | 200 | 500 | 200 | 911 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9563 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
546 | 3 | PLATTE | CST MEXICO CITY AVE S | KU0302 | 0.774 | Y |  | Payment to private entity to add turn lanes and signalize intersection at Mexico City Avenue. $2,574,149 Governor's Cost Share Program funds. | Federal | 0 | 2575 | 0 | 2575 | 0 | STATE |  | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2574 | 0 | 0 | 0 | 0 | 0 | 0 | 2574 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
547 | 3 | PLATTE | CST NW COOKINGHAM DR E | 4S3489 | 0.198 | Y | 490211 | Bridge rehabilitation over I-435 1 mile west of Rte. 169 and 1 mile east of NW Robinhood Lane. Project involves bridge A3287. | Federal | 9690 | 2422 | 0 | 12197 | 0 | NHPP |  | 85 | 488 | 480 | 1253 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9891 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
548 | 3 | PLATTE | CRD OLD PIKE RD E | KU0053 | 0.209 | Y |  | Bridge replacement over I-29, 1.8 miles south of New Market Road and 1.4 miles north of Rte. U. Project involves bridge A0105. | Adv. CN | 2118 | 530 | 0 | 2648 | 0 | AC-STBG |  | 0 | 50 | 50 | 55 | 100 | 222 | 0 | 0 | 0 | 0 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2149 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
549 | 3 | PLATTE | RT Z E | 4S3454 | 0.271 | Y | 490223 | Bridge replacement, guardrail and striping over Platte River, 1.4 mile east of Rte. F and 0.7 mile west of Sherwood Forest. Project involves bridge S0025. | Federal | 5286 | 1322 | 0 | 6818 | 0 | NHPP |  | 210 | 401 | 709 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5493 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
550 | 3 | PLATTE | RT Z W | KU0047 | 11.151 | Y |  | Pavement resurfacing from I-29 to Clinton County line. | Adv. CN | 1484 | 371 | 0 | 1855 | 0 | AC-STBG |  | 0 | 10 | 10 | 121 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
551 | 3 | VARIOUS | Various | 4I3174 | 0 | Y | 990357 | Job Order Contracting for lighting repair at various locations in the urban Kansas City District. | Federal | 0 | 2572 | 0 | 2581 | 0 | STATE |  | 9 | 50 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2472 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
552 | 3 | VARIOUS | Various | 4I3176 | 0 | Y | 990270 | Job Order Contracting for bridge repairs at various locations in the urban Kansas City District. | Adv. CN | 1332 | 333 | 0 | 1665 | 0 | AC-STBG |  | 0 | 0 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
553 | 3 | VARIOUS | Various | 4I3516 | 0 | Y | 990347 | On-call work zone enforcement at various locations in the urban Kansas City District. | Federal | 154 | 17 | 0 | 173 | 0 | SAFETY |  | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 170 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
554 | 3 | VARIOUS | Various | 4I3522 | 0 | Y | 990348 | On-call work zone enforcement at various locations in the urban Kansas City District. | Federal | 154 | 17 | 0 | 171 | 0 | SAFETY |  | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 170 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
555 | 3 | VARIOUS | Various | 4P3117 | 0 | Y | 990283 | Job Order Contracting for fence repair at various locations in the urban Kansas City District. | Federal | 0 | 816 | 0 | 825 | 0 | STATE |  | 9 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
556 | 3 | VARIOUS | Various | 4P3188 | 0 | Y | 990275 | Job Order Contracting for concrete pavement repair at various major route locations in the urban Kansas City District. | Adv. CN | 1626 | 406 | 0 | 2036 | 0 | AC-STBG |  | 4 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
557 | 3 | VARIOUS | Various | 4P3402 | 0 | Y | 990333 | Replace signage at various locations in the urban Kansas City District. | Adv. CN | 876 | 219 | 0 | 1205 | 0 | AC-STBG |  | 110 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1020 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
558 | 3 | VARIOUS | Various | 4P3523 | 0 | Y | 990350 | Job Order Contracting for asphalt pavement repair at various locations on major and interstate routes in the urban Kansas City District. | Adv. CN | 3304 | 826 | 0 | 4135 | 0 | AC-STBG |  | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
559 | 3 | VARIOUS | Various | 4Q3479 | 0 | Y | 990351 | ITS operations, staffing, and equipment for the KC Scout Intelligent Transportation System at the Transportation Management Center (TMC) building. Payment transfer of $2,940,000 to the District Operation budget and $2,470,000 KDOT. | Adv. CN | 2941 | 0 | 2470 | 5411 | 0 | AC-STBG |  | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5410 | 0 | 0 | 0 | 0 | 0 | 0 | 2470 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
560 | 3 | VARIOUS | Various | 4Q3480 | 0 | Y | 990352 | Emergency response operations and staffing in the urban Kansas City District. STIP funds will be transferred to the District Operation budget. | Adv. CN | 1333 | 333 | 0 | 1666 | 0 | AC-STBG |  | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1665 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
561 | 3 | VARIOUS | Various | 4Q3481 | 0 | Y | 990353 | ITS asset management and device replacements at various locations in the urban Kansas City District. | Adv. CN | 1812 | 453 | 0 | 2420 | 0 | AC-STBG |  | 155 | 174 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2091 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
562 | 3 | VARIOUS | Various | 4Q3524 | 0 | Y | 990354 | Emergency response operations and staffing in the urban Kansas City District. These funds will be transferred to the District Operation budget. | Adv. CN | 1333 | 333 | 0 | 1666 | 0 | AC-STBG |  | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1665 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
563 | 3 | VARIOUS | Various | 4Q3525 | 0 | Y |  | ITS operations, staffing, and equipment for the KC Scout Intelligent Transportation System at the Transportation Management Center (TMC) building. Payment transfer of $2.885 million to the MoDOT's operations budget and $2.496 million from KDOT. | Adv. CN | 2886 | 0 | 2496 | 5382 | 0 | AC-STBG |  | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5381 | 0 | 0 | 0 | 0 | 0 | 0 | 2496 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
564 | 3 | VARIOUS | Various | 5B0800S | 0 | Y | 990107 | Payback beginning in SFY 2008 for Safe and Sound bridges in urban Kansas City District. | Federal | 0 | 19335 | 0 | 65124 | 15,001 - 25,000 | STATE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61 | 0 | 0 | 0 | 0 | 0 | 0 | 45728 | 3867 | 3867 | 3867 | 3867 | 3867 | 0
565 | 3 | VARIOUS | Various | KU0001 | 0 | Y |  | ITS operations, staffing, and equipment for the KC Scout Intelligent Transportation System at the Transportation Management Center (TMC) building. Payment transfer of $2,885,000 to the District Operation budget and $2,496,000 KDOT. | Adv. CN | 2886 | 0 | 2496 | 5382 | 0 | AC-STBG |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5381 | 0 | 0 | 0 | 0 | 0 | 0 | 2496 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
566 | 3 | VARIOUS | Various | KU0002 | 0 | Y |  | Emergency response operations and staffing in the urban Kansas City District. These funds will be transferred to the District Operation budget. | Adv. CN | 1369 | 342 | 0 | 1711 | 0 | AC-STBG |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1710 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
567 | 3 | VARIOUS | Various | KU0004 | 0 | Y |  | ITS asset management and device replacements at various locations in the urban Kansas City District. | Adv. CN | 2026 | 506 | 0 | 2532 | 0 | AC-STBG |  | 0 | 247 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2285 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
568 | 3 | VARIOUS | Various | KU0012 | 0 | Y |  | Bridge painting at various locations in urban Kansas City District. | Federal | 1907 | 477 | 0 | 2384 | 0 | STBG |  | 0 | 20 | 30 | 170 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2164 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
569 | 3 | VARIOUS | Various | KU0014 | 0 | Y |  | Signing improvements at various locations in the urban Kansas City District. | Federal | 1502 | 376 | 0 | 1878 | 0 | NHPP |  | 0 | 50 | 50 | 155 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1623 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
570 | 3 | VARIOUS | Various | KU0026 | 0 | Y |  | Scout Intelligent Transportation System (ITS) asset management and device replacements at various locations in Cass and Jackson Counties in the urban Kansas City District. | Adv. CN | 756 | 189 | 0 | 945 | 0 | AC-STBG |  | 0 | 30 | 20 | 73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 822 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
571 | 3 | VARIOUS | Various | KU0034 | 0 | Y |  | Signing improvements at various locations in the urban Kansas City District. | Federal | 1554 | 388 | 0 | 1942 | 0 | NHPP |  | 0 | 50 | 50 | 50 | 153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1639 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
572 | 3 | VARIOUS | Various | KU0037 | 0 | Y |  | Signing improvements at various locations in the urban Kansas City District. | Federal | 1613 | 403 | 0 | 2016 | 0 | NHPP |  | 0 | 50 | 50 | 50 | 50 | 128 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1688 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
573 | 3 | VARIOUS | Various | KU0048 | 0 | Y |  | Upgrade lighting, high-mast luminaires, street lighting and underpass luminaires with LED lighting. | Federal | 4400 | 1100 | 0 | 5500 | 0 | NHPP |  | 0 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
574 | 3 | VARIOUS | Various | KU0063 | 0 | Y |  | Upgrade to flashing yellow arrow signal improvements at various locations in the urban Kansas City District. | Adv. CN | 946 | 236 | 0 | 1182 | 0 | AC-STBG |  | 0 | 10 | 10 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1082 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
575 | 3 | VARIOUS | Various | KU0108 | 0 | Y |  | Scout Intelligent Transportation System (ITS) asset management and device replacements at various locations in Cass and Jackson Counties in the urban Kansas City District. | Adv. CN | 518 | 129 | 0 | 647 | 0 | AC-STBG |  | 0 | 10 | 10 | 10 | 10 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 563 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
576 | 3 | VARIOUS | Various | KU0113 | 0 | Y |  | Upgrade attenuators at various locations in the urban Kansas City District. | Adv. CN | 934 | 233 | 0 | 1167 | 0 | AC-STBG |  | 0 | 5 | 5 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1082 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
577 | 3 | VARIOUS | Various | KU0159 | 0 | Y | 990348 | On-call work zone enforcement at various locations in the urban Kansas City District. | Federal | 154 | 17 | 0 | 171 | 0 | SAFETY |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 170 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
578 | 3 | VARIOUS | Various | KU0161 | 0 | Y | 990264 | Job Order Contracting for guard cable and guardrail repair at various locations in the urban Kansas City District. | Adv. CN | 5202 | 1301 | 0 | 6503 | 0 | AC-STBG |  | 0 | 5 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6483 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
579 | 3 | VARIOUS | Various | KU0051 | 0 | Y |  | Striping replacement at various locations in Jackson and Clay Counties. | Adv. CN | 260 | 65 | 0 | 325 | 0 | AC-STBG |  | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 297 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
580 | 4 | BENTON | MO 7 S | 5P3325 | 15.829 | N |  | Pavement improvement from Rte. 5 to Rte. AA. | Federal | 1466 | 367 | 0 | 1844 | 0 | NHPP | 7P3490 CD0138 | 11 | 25 | 124 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1684 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
581 | 4 | BOONE | MO 163 S | 5S3412 | 0.161 | Y |  | Bridge replacement over Bonne Femme Creek. Project involves bridge W0559. | Federal | 864 | 216 | 0 | 1156 | 0 | NHPP |  | 76 | 225 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 845 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
582 | 4 | BOONE | MO 163 S | 5S3496 | 5.525 | Y |  | Pavement resurfacing from I-70 to Rte. K and add turn lanes at Southampton Drive and Corporate Lake Drive. | Federal | 3238 | 810 | 0 | 4135 | 0 | NHPP | 5P3511 5S3519 CD0107 | 87 | 390 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3658 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
583 | 4 | BOONE | MO 22 E | CD0030 | 0.119 | N |  | Intersection improvement at Rte. 22, Rte. 124 and Rte. 151. | Adv. CN | 1102 | 275 | 0 | 1377 | 0 | AC-STBG |  | 0 | 40 | 186 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1101 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
584 | 4 | BOONE | US 63 S | 5P3511 | 3.598 | Y |  | Pavement resurfacing from Rte. 763 to Rte. B. | Federal | 4317 | 1079 | 0 | 5401 | 0 | NHPP | 5S3496 5S3519 CD0107 | 5 | 618 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4778 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
585 | 4 | BOONE | US 63 S | CD0021 | 0.102 | Y |  | Bridge preventive maintenance over Rte. B and Wagon Trail Road over Rte. 63. Project involves bridges A4033, A4086 and A4087. | Federal | 1410 | 353 | 0 | 1763 | 0 | NHPP |  | 0 | 1 | 1 | 10 | 350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1401 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
586 | 4 | BOONE | US 63 S | CD0109 | 126.35 | Y |  | Signing improvements from Randolph County line to Rte. 54 and from Rte. 50 at Cole County line to Texas County line. | Federal | 698 | 175 | 0 | 873 | 0 | NHPP |  | 0 | 5 | 5 | 141 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 722 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
587 | 4 | BOONE | US 63C S | 5S3411 | 6.626 | Y |  | Intersection, bridge and pavement improvements at I-70. Includes pavement improvements on I-70, North Outer Road 70 East, and Rte. PP. Design-Build. Project potentially involves various bridges. | Adv. CN | 155250 | 38812 | 0 | 195382 | 0 | AC-STBG |  | 1320 | 7680 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 185382 | 0 | 0 | 0 | 0 | 0 | 0 | 4300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
588 | 4 | BOONE | IS 70 E | 5I3534 | 15.892 | Y |  | Pavement improvement east of Rte. BB to Stadium Boulevard and east of Rte. 63 Connector to Callaway County line. | Federal | 9735 | 1082 | 0 | 10818 | 0 | NHPP |  | 1 | 1 | 1 | 49 | 1101 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9665 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
589 | 4 | BOONE | LP 70 E | CD0124 | 1.362 | Y |  | Update pedestrian facilities to comply with the ADA Transition Plan in Columbia. $656,000 Statewide Transportation Alternatives funds. | Adv. CN | 763 | 191 | 0 | 954 | 0 | AC-STBG |  | 0 | 5 | 50 | 85 | 0 | 0 | 0 | 0 | 0 | 373 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 441 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
590 | 4 | BOONE | S OR 70 E | CD0054 | 2.24 | Y |  | Pavement improvement from 0.2 mile west of Rte. ZZ to Rte. 740. | Adv. CN | 78 | 19 | 0 | 97 | 0 | AC-STBG |  | 0 | 1 | 1 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
591 | 4 | BOONE | S OR 70 E | CD0107 | 1.168 | Y |  | Pavement resurfacing from Rte. 740 to Loop 70. | Adv. CN | 277 | 69 | 0 | 346 | 0 | AC-STBG | 5P3511 5S3496 5S3519 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 306 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
592 | 4 | BOONE | MO 740 E | 5S3369C | 6.897 | Y |  | Upgrade pedestrian facilities to address nonstandard ADA facilities in Columbia and Ashland. | Adv. CN | 1645 | 411 | 0 | 2155 | 0 | AC-STBG |  | 99 | 467 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1589 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
593 | 4 | BOONE | MO 763 S | 5S3519 | 3.787 | Y |  | Pavement resurfacing from Big Bear Boulevard to Bus. 70, from Rte. 63 to Rte. VV and includes Bus. 70 from Sexton Road to Eastland Circle. | Federal | 1675 | 419 | 0 | 2174 | 0 | NHPP | 5P3511 5S3496 CD0107 | 80 | 255 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1839 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
594 | 4 | BOONE | MO 763 S | CD0125 | 6.289 | Y |  | Upgrade pedestrian facilities to comply with the ADA Transition Plan including Rte. 163 and Rte. PP in Columbia. $1,011,000 Statewide Transportation Alternatives funds. | Adv. CN | 1146 | 286 | 0 | 1432 | 0 | AC-STBG |  | 0 | 5 | 100 | 251 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1073 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
595 | 4 | BOONE | RT AB E | 5S3471 | 8.106 | N |  | Pavement resurfacing from Rte. 63 to end of state maintenance, Rte. H from Log Providence Road to end of state maintenance and Log Providence Road from end of state maintenance to Rte. H. | Adv. CN | 470 | 117 | 0 | 612 | 0 | AC-STBG | CD0093 | 25 | 53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 534 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
596 | 4 | BOONE | RT AC E | 5P3433 | 0.072 | Y |  | Interchange improvement at Rte. 63 in Columbia. | Federal | 10936 | 2734 | 0 | 14045 | 0 | NHPP |  | 375 | 203 | 847 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7620 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
597 | 4 | BOONE | RT AC E | CD0123 | 2.239 | Y |  | Upgrade pedestrian facilities to comply with the ADA Transition Plan in Columbia. $1,430,000 Statewide Transportation Alternatives funds. | Adv. CN | 1621 | 405 | 0 | 2026 | 0 | AC-STBG |  | 0 | 5 | 200 | 304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1517 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
598 | 4 | BOONE | RT B S | 5S3531 | 0.044 | Y |  | Bridge improvement over I-70. Project involves bridge L0286. | Federal | 1522 | 380 | 0 | 1903 | 0 | NHPP |  | 1 | 1 | 1 | 23 | 360 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1506 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
599 | 4 | BOONE | RT E S | CD0055 | 13.3 | Y |  | Pavement improvement from Rte. 124 to I-70. | Adv. CN | 1083 | 271 | 0 | 1354 | 0 | AC-STBG |  | 0 | 1 | 1 | 92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
600 | 4 | BOONE | RT F S | 5S3447 | 0.094 | N |  | Bridge replacement over Coon Creek and rehabilitation over Perche Creek and Blaze Creek. Includes bridge rehabilitation on Rte. 124 over Grindstone Creek. Project involves bridges P0384, P0383, P0385 and A8673. | Federal | 1523 | 381 | 0 | 2127 | 0 | NHPP |  | 221 | 334 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1570 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
601 | 4 | BOONE | RT K E | CD0093 | 7.22 | Y |  | Pavement resurfacing from Rte. 163 to end of state maintenance. | Adv. CN | 690 | 172 | 0 | 862 | 0 | AC-STBG | 5S3471 | 0 | 64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 798 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
602 | 4 | BOONE | RT K E | CD0132 | 0.037 | Y |  | Payment to Columbia to add roundabout at West Old Plank Road. $887,850 Cost Share funds. | Adv. CN | 722 | 181 | 0 | 903 | 0 | AC-STBG |  | 0 | 3 | 5 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 108 | 780 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
603 | 4 | BOONE | CST PERRY AVE S | 5S3590 | 0.035 | N |  | Payment to Ashland to construct roadway extension from Ashley Lane to Industrial Drive and close Rte. 63 access at Liberty Lane. $392,710 Cost Share funds. | Federal | 0 | 403 | 0 | 403 | 0 | STATE |  | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 393 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
604 | 4 | BOONE | RT V S | CD0064 | 10.365 | N |  | Pavement improvement from Rte. 22 to Rte. U. Includes Rte. U from Rte. V to Rte. 124. | Adv. CN | 727 | 182 | 0 | 909 | 0 | AC-STBG |  | 0 | 1 | 1 | 63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 844 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
605 | 4 | BOONE | RT VV S | CD0066 | 10.958 | Y |  | Pavement improvement from Rte. 763 to end of state maintenance. Includes Rte. PP from Kircher Road to 0.1 mile west of Black Hills Drive and Outer Road 63 from Rte. VV to 0.5 mile north of East Circle Drive. | Adv. CN | 935 | 234 | 0 | 1169 | 0 | AC-STBG |  | 0 | 2 | 2 | 79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
606 | 4 | BOONE | RT WW E | CD0050 | 15.612 | Y |  | Pavement improvement from Rte. 63 to Rte. J and Rte. N from Rte. 163 to end of state maintenance. | Adv. CN | 1347 | 337 | 0 | 1684 | 0 | AC-STBG |  | 0 | 1 | 1 | 116 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1566 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
607 | 4 | BOONE | RT Y E | CD0068 | 9.129 | N |  | Pavement improvements from Rte. 63 to Rte. J. | Adv. CN | 299 | 75 | 0 | 374 | 0 | AC-STBG |  | 0 | 1 | 1 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 349 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
608 | 4 | BOONE | RT Z S | CD0049 | 29.348 | Y |  | Pavement improvement from Gano Chance Road to I-70, Rte. HH from Rte. B to Rte. Z and Rte. OO from Rte. B to Rte. Z. | Adv. CN | 2057 | 514 | 0 | 2571 | 0 | AC-STBG |  | 0 | 3 | 3 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2390 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
609 | 4 | CALLAWAY | BU 54 E | 5S3591 | 0.201 | N |  | Payment to Fulton to construct turn lanes and pedestrian facilities from Collier Lane to Westminster Avenue. $300,233 Cost Share funds. | Adv. CN | 246 | 62 | 0 | 310 | 0 | AC-STBG |  | 2 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
610 | 4 | CALLAWAY | US 54 E | 5P3417 | 0.78 | N |  | Interchange improvements at I-70 in Kingdom City. | Federal | 9098 | 2274 | 0 | 11682 | 0 | NHPP |  | 310 | 10 | 10 | 10 | 1966 | 0 | 0 | 0 | 0 | 0 | 1326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
611 | 4 | CALLAWAY | US 54 E | 5P3576 | 0.838 | Y |  | Modify interchange configuration with addition of roundabout, turn lanes and pavement resurfacing at Simon Boulevard and Rte. OO. $11,000 Holts Summit funds. | Federal | 2714 | 290 | 11 | 3410 | 0 | SAFETY |  | 305 | 264 | 0 | 0 | 0 | 0 | 0 | 90 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2751 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
612 | 4 | CALLAWAY | US 54 E | CD0058 | 0.152 | N |  | Bridge improvement over Kansas City Southern Railroad and Richland Creek. Includes I-70 westbound over Auxvasse Creek and Rte. F over Rte. 54. Project involves bridges A2111, H0284, A0096 and A2296. | Federal | 1095 | 274 | 0 | 1369 | 0 | NHPP |  | 0 | 1 | 20 | 119 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1229 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
613 | 4 | CALLAWAY | US 54 E | CD0059 | 0.096 | N |  | Bridge improvement over I-70. Project involves twin bridges L0964. | Federal | 111 | 28 | 0 | 139 | 0 | NHPP |  | 0 | 1 | 1 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
614 | 4 | CALLAWAY | US 54 E | CD0100 | 31.496 | Y |  | Pavement improvement from County Road 147 north of Kingdom City to Missouri River bridge. | Federal | 18179 | 4545 | 0 | 22724 | 0 | NHPP | CD0114 | 0 | 200 | 2352 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
615 | 4 | CALLAWAY | US 54 E | CD0114 | 0.331 | N |  | Add auxiliary lanes at Old Jefferson City Road near Fulton. | Federal | 1085 | 271 | 0 | 1356 | 0 | NHPP |  | 0 | 100 | 290 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 956 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
616 | 4 | CALLAWAY | US 63 N | 5S3458 | 0.153 | Y |  | Bridge rehabilitation over Rte. 54 includes Rte. 94, Rte. H and Rte. W. Project involves bridges A3508, A4635 and twin bridges A3539. | Federal | 2470 | 618 | 0 | 3203 | 0 | NHPP |  | 115 | 554 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2534 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
617 | 4 | CALLAWAY | IS 70 E | 5I3455 | 10.182 | N |  | Pavement resurfacing and repair from 0.7 mile west of Rte. Z to Montgomery County line. | Federal | 2493 | 277 | 0 | 2783 | 0 | NHPP |  | 13 | 426 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
618 | 4 | CALLAWAY | IS 70 E | 5I3529 | 6.595 | N |  | Pavement improvement from Rte. 54 to 0.7 mile west of Rte. Z and westbound I-70 from Montgomery County line to Rte. 54. | Federal | 5059 | 562 | 0 | 5623 | 0 | NHPP |  | 2 | 30 | 84 | 501 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5006 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
619 | 4 | CALLAWAY | RT B E | CD0026 | 14.771 | N |  | Pavement improvement from Rte. 54 to Rte. 19. | Adv. CN | 541 | 135 | 0 | 676 | 0 | AC-STBG | CD0025 | 0 | 2 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 630 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
620 | 4 | CALLAWAY | RT BB S | 5S3463 | 0.1 | N |  | Bridge improvement over Hillers Creek. Project involves bridge A2361. | Federal | 567 | 142 | 0 | 710 | 0 | NHPP |  | 1 | 24 | 127 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 553 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
621 | 4 | CALLAWAY | RT BB S | CD0041 | 21.598 | N |  | Pavement improvement from Rte. 54 to Rte. AA. Includes Rte. MM from County Road 397 to Rte. J and Rte. FF from County Road 225 to Rte. 54. | Adv. CN | 563 | 141 | 0 | 704 | 0 | AC-STBG |  | 0 | 1 | 7 | 41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 655 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
622 | 4 | CALLAWAY | RT C S | 5S3520 | 35.507 | N |  | Pavement resurfacing from Bus. 54 to Rte. 94, Rte. AE from Rte. J to Rte. TT, Rte. TT from Rte. AE to end of state maintenance, Rte. OO from Rte. AA to end of state maintenance and Rte. AA from Rte. OO to Rte. 94. | Adv. CN | 2314 | 578 | 0 | 3042 | 0 | AC-STBG | 5S3441 | 150 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
623 | 4 | CALLAWAY | RT CC S | 5S3441 | 9.624 | N |  | Pavement resurfacing from Rte. O to Rte. 94 and Rte. AD from Rte. C to the end of state maintenance. | Adv. CN | 516 | 129 | 0 | 648 | 0 | AC-STBG | 5S3520 | 3 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
624 | 4 | CALLAWAY | RT E E | CD0025 | 11.647 | N |  | Pavement improvement from Rte. DD to Rte. 54. | Adv. CN | 343 | 86 | 0 | 429 | 0 | AC-STBG | CD0026 | 0 | 1 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
625 | 4 | CALLAWAY | RT H E | CD0073 | 0.025 | N |  | Bridge improvement over Middle River. Project involves bridge R0417. | Adv. CN | 476 | 119 | 0 | 595 | 0 | AC-STBG |  | 0 | 1 | 1 | 18 | 101 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 469 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
626 | 4 | CALLAWAY | RT J S | 5S3443 | 0.076 | N |  | Bridge rehabilitation over Millers Creek. Project involves bridge N0743. | Federal | 579 | 145 | 0 | 800 | 0 | NHPP |  | 71 | 175 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 549 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
627 | 4 | CALLAWAY | RT J S | CD0029 | 48.666 | N |  | Pavement improvement from I-70 to Rte. 54. Includes Rte. RA from Rte. J to end of state maintenance, Rte. F from Rte. J to Jefferson Street in Fulton, Rte. H from Rte. J to Rte. 54 and Rte. M from I-70 to 0.5 mile north of Rte. D. | Adv. CN | 3423 | 856 | 0 | 4279 | 0 | AC-STBG |  | 0 | 10 | 34 | 255 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3980 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
628 | 4 | CALLAWAY | CRD S SUMMIT DR S | CD0072 | 0.051 | Y |  | Bridge improvement over Rte. 54. Project involves bridge A3521. | Federal | 608 | 152 | 0 | 760 | 0 | NHPP |  | 0 | 1 | 1 | 18 | 136 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 604 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
629 | 4 | CAMDEN | US 54 E | 5P3270 | 0.371 | N |  | Bridge rehabilitation over the Lake of the Ozarks. Project involves bridge J0832. | Federal | 655 | 164 | 0 | 896 | 0 | NHPP | 5P3460 CD0082 | 77 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 699 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
630 | 4 | CAMDEN | US 54 E | 5P3270B | 0.371 | N |  | Bridge preventative maintenance over Lake of the Ozarks. Project involves bridge J0832. | Federal | 405 | 101 | 0 | 506 | 0 | NHPP | 5P3460B | 0 | 1 | 108 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 397 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
631 | 4 | CAMDEN | US 54 E | 5P3460 | 0.571 | N |  | Bridge rehabilitation over Grand Glaize arm and over Niangua River. Project involves bridges A5310 and A5753. | Federal | 1229 | 307 | 0 | 1551 | 0 | NHPP | 5P3270 CD0082 | 15 | 326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1210 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
632 | 4 | CAMDEN | US 54 E | 5P3460B | 0.571 | N |  | Bridge preventative maintenance over the Grand Glaize Arm and over Niangua River. Project involves bridges A5310 and A5753. | Federal | 182 | 46 | 0 | 228 | 0 | NHPP | 5P3270B | 0 | 1 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 179 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
633 | 4 | CAMDEN | US 54 E | 5P3554 | 21.597 | N |  | Pavement improvement from west of the Niangua River to city limits of Camdenton, Rte. 54 East from Court Circle in Camdenton to the Osage River, Rte. 54 West from Osage River to Bus. 5 in Camdenton and Rte. KK from West Osage Beach Parkway to end of state maintenance. | Federal | 10254 | 2564 | 0 | 12820 | 0 | NHPP |  | 2 | 2 | 20 | 226 | 809 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11761 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
634 | 4 | CAMDEN | US 54 E | 5P3573 | 1.375 | N |  | Roadway improvement from Bus. 5 South to city limits of Camdenton. | Federal | 5667 | 1417 | 0 | 7104 | 0 | NHPP |  | 20 | 129 | 230 | 662 | 0 | 0 | 0 | 0 | 108 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5955 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
635 | 4 | CAMDEN | MO 7 S | 5P3538 | 0.248 | N |  | Bridge improvement over Wet Glaize Creek south of Rte. T. Project involves bridges A1236 and A1237. | Federal | 1049 | 262 | 0 | 1313 | 0 | NHPP |  | 2 | 2 | 10 | 23 | 155 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1121 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
636 | 4 | CAMDEN | RT A E | 5S3578 | 34.726 | N |  | Pavement resurfacing from Rte. 54 to Rte. 7. Includes Rte. Z from Cable Ridge Road to Rte. 7 and Rte. NN from Rte. 7 to Green Ridge Road. | Adv. CN | 2159 | 540 | 0 | 2700 | 0 | AC-STBG |  | 1 | 179 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2520 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
637 | 4 | CAMDEN | RT BB S | 5S3493 | 23.095 | N |  | Pavement resurfacing from Rte. 7 to Rte. F and Rte. MM from Pennington Drive to Rte. N. | Adv. CN | 1246 | 311 | 0 | 1597 | 0 | AC-STBG |  | 40 | 115 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1442 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
638 | 4 | CAMDEN | RT D S | 5S3336 | 28.271 | N |  | Pavement improvement and add rumblestripes from Rte. 54 to Rte. E. Includes pavement improvement on Rte. E from Rte. D to end of state maintenance. | Adv. CN | 3078 | 769 | 0 | 3942 | 0 | AC-STBG | CD0099 | 95 | 20 | 143 | 369 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3315 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
639 | 4 | CAMDEN | RT F S | 5S3475 | 15.655 | N |  | Pavement preservation treatment from Rte. TT to end of state maintenance, Rte. FF from Rte. DD to end of state maintenance, Rte. P from Rte. 5 to end of state maintenance and Rte. TT from Rte. MM to end of state maintenance. | Adv. CN | 373 | 93 | 0 | 471 | 0 | AC-STBG |  | 5 | 62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
640 | 4 | CAMDEN | RT J S | 5S3321 | 0.125 | N |  | Payment to private entity for bridge relinquishment over the Niangua Arm of Lake of the Ozarks. Project involves bridge S0391. | Adv. CN | 258 | 64 | 0 | 333 | 0 | AC-STBG |  | 11 | 113 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 209 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
641 | 4 | CAMDEN | RT KK E | CD0082 | 0.343 | N |  | Bridge deck sealing over Rte. 54. Includes Nichols Road, Case Road, Jeffries Road, Passover Road, East Osage Beach Parkway, Rte. 242, Rte. 42 East and Rte. 42 West. Project involves bridges A7697, A7696, A5742, A5743, A7321, A7360, A7409, A7359 and A7622. | Adv. CN | 635 | 159 | 0 | 794 | 0 | AC-STBG | 5P3270 5P3460 | 0 | 86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 708 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
642 | 4 | CAMDEN | RT N S | CD0099 | 11.449 | N |  | Pavement improvement from Rte. 54 to end of state maintenance. Includes Rte. W from Rte. 54 to end of state maintenance. | Adv. CN | 850 | 212 | 0 | 1062 | 0 | AC-STBG |  | 0 | 3 | 20 | 67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 972 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
643 | 4 | CAMDEN | RT T S | 5S3535 | 45.57 | N |  | Pavement and safety improvement from Rte 7 to I-44, Rte J from I-44 to Rte 5, Rte A from Rte 32 to I-44, Rte F from Rte BB to I-44, Rte YY from Hemlock Road to Rte 5, Rte BB from Rte F to Rte 5 and outer road 44 from I-44 to Rte 66. $493,000 Open Container funds. | Adv. CN | 4022 | 1006 | 0 | 5038 | 0 | AC-STBG |  | 10 | 125 | 369 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4533 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
644 | 4 | CAMDEN | CST WEST OSAGE BEACH PKWY N | 5S3508 | 0.012 | N |  | Payment to Osage Beach to construct roadway extension to Executive Drive and close Rte. 54 access at Executive Drive. $189,395 Cost Share funds. | Adv. CN | 166 | 41 | 0 | 207 | 0 | AC-STBG |  | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 189 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
645 | 4 | COLE | MO 179 S | 5S3454 | 14.911 | Y |  | Pavement resurfacing from north of Truman Boulevard to Rte. B, Rte. B from Rte. 179 to east of Tanner Bridge, Bus. 50 from Rte. 50 to Rte. 179, Rte. 50 from south of Truman Boulevard to west of Dix Road and east of Vetter Lane to 0.5 mile east of Moreau River. | Federal | 5665 | 1416 | 0 | 7112 | 0 | NHPP | 5P3453 CD0090 | 31 | 605 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6476 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
646 | 4 | COLE | MO 179 S | CD0074 | 0.019 | N |  | Bridge improvement over Rock Creek. Project involves bridge X0035. | Federal | 375 | 94 | 0 | 469 | 0 | NHPP |  | 0 | 1 | 1 | 18 | 75 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 369 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
647 | 4 | COLE | BU 50 E | 5P3490 | 5.91 | Y |  | Upgrade pedestrian facilities at various locations in Jefferson City, Columbia, Fulton, Holts Summit, Steelville, Eldon, Latham, Jamestown, Stover, Rich Fountain, Rolla and St. James. | Adv. CN | 1474 | 369 | 0 | 2008 | 0 | AC-STBG |  | 165 | 364 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 1460 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
648 | 4 | COLE | BU 50 E | CD0126 | 3.303 | Y |  | Upgrade pedestrian facilities to comply with the ADA Transition Plan in Jefferson City, Taos, Wardsville and Frankenstein. $1,135,000 Statewide Transportation Alternatives funds. | Adv. CN | 1323 | 331 | 0 | 1654 | 0 | AC-STBG |  | 0 | 12 | 100 | 289 | 0 | 0 | 0 | 0 | 0 | 49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
649 | 4 | COLE | S OR 50 E | 5S3418 | 0.269 | Y |  | Intersection improvements at South Ten Mile Drive in Jefferson City. | Adv. CN | 1314 | 329 | 0 | 1658 | 0 | AC-STBG |  | 15 | 1 | 90 | 328 | 0 | 0 | 0 | 0 | 0 | 108 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1116 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
650 | 4 | COLE | US 50 E | 5P3453 | 3.769 | Y |  | Pavement resurfacing and high friction surface treatment from 0.2 mile east of Vetter Lane to 0.3 mile west of Dix Road. | Federal | 4580 | 1145 | 0 | 5754 | 0 | NHPP | 5S3454 CD0090 | 29 | 486 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5239 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
651 | 4 | COLE | US 50 E | 5P3523 | 0.076 | Y |  | Bridge improvement over Vetter Lane. Includes Bolivar Street over Rte. 50. Project involves bridge A1420 and twin bridges A0722. | Federal | 1286 | 321 | 0 | 1608 | 0 | NHPP | CD0075 | 1 | 20 | 53 | 264 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1270 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
652 | 4 | COLE | US 50 E | CD0106 | 4.99 | Y |  | Pavement improvement from west of Shamrock Road to east of Stoney Gap Road. Includes westbound Rte. 50 from west of Maries River to east of Mari Osa Delta Lane and from west of Osage River to Moreau River. | Federal | 2662 | 666 | 0 | 3328 | 0 | NHPP |  | 0 | 1 | 1 | 1 | 33 | 232 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3060 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
653 | 4 | COLE | US 50 W | CD0039 | 0.111 | Y |  | Bridge rehabilitation over Moreau River. Project involves bridge A4351. | Federal | 659 | 165 | 0 | 824 | 0 | NHPP |  | 0 | 181 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 643 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
654 | 4 | COLE | US 54 E | 5P3451 | 0.349 | Y |  | Bridge improvement over Missouri River. Project involves bridges A4497 and L0550. | Federal | 66 | 17 | 0 | 84 | 0 | NHPP |  | 1 | 1 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
655 | 4 | COLE | US 54 E | 5P3497 | 1.54 | Y |  | Roadway improvement from West McCarty Street to Rte. 63 north of Missouri River bridge in Jefferson City. | Federal | 3283 | 821 | 0 | 4354 | 0 | NHPP | 5S3458 CD0100 CD0114 | 250 | 25 | 302 | 0 | 0 | 0 | 0 | 0 | 577 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
656 | 4 | COLE | US 54 E | 5P3507B | 2.321 | N |  | Add intersection turn lanes and J-turns at Clark Fork Road and Penny Hollow Lane. | Federal | 3408 | 379 | 0 | 3827 | 0 | SAFETY |  | 40 | 616 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3171 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
657 | 4 | COLE | US 54 E | 5P3525 | 0.187 | Y |  | Bridge improvement over Bus. 50, Linden Drive, Moreau Overflow and Stadium Boulevard. Includes Madison Street Ramp over Rte. 54. Project involves bridges A1415, A1309 and twin bridges A1305, A1307 and A1672. | Federal | 1898 | 474 | 0 | 2373 | 0 | NHPP |  | 1 | 21 | 112 | 364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
658 | 4 | COLE | US 54 E | 5P3560 | 0.356 | Y |  | Bridge improvement over Neighorn Branch. Project involves bridges K0760 and G0302. | Federal | 2854 | 714 | 0 | 3569 | 0 | NHPP |  | 1 | 50 | 150 | 650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2718 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
659 | 4 | COLE | US 54 E | CD0090 | 1.825 | Y |  | Pavement resurfacing from west of Stadium Drive to Missouri River bridge. | Federal | 990 | 248 | 0 | 1238 | 0 | NHPP | 5P3453 5S3454 | 0 | 111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1127 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
660 | 4 | COLE | US 54 W | 5P3467 | 0.294 | Y |  | Bridge improvement over McCarty Street and Rte. 50. Project involves bridges A1416 and A1417. | Federal | 2301 | 575 | 0 | 2922 | 0 | NHPP |  | 46 | 119 | 463 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2294 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
661 | 4 | COLE | RT AA S | 5S3551 | 0.12 | N |  | Bridge improvement over Moreau River. Project involves bridge R0445. | Federal | 431 | 108 | 0 | 540 | 0 | NHPP |  | 1 | 1 | 1 | 18 | 90 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
662 | 4 | COLE | RT B S | 5S3464 | 0.25 | Y |  | Bridge improvement over Moreau River. Project involves bridge A3618. | Federal | 673 | 168 | 0 | 842 | 0 | NHPP |  | 1 | 26 | 154 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 661 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
663 | 4 | COLE | RT D S | 5S3526 | 0.09 | Y |  | Bridge improvement over North Moreau Creek. Project involves bridge A1470. | Federal | 1091 | 273 | 0 | 1387 | 0 | NHPP |  | 23 | 40 | 234 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1085 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
664 | 4 | COLE | RT E E | CD0040 | 5.769 | Y |  | Pavement improvement from Rte. 54 to Rte. B. | Adv. CN | 152 | 38 | 0 | 190 | 0 | AC-STBG | CD0042 | 0 | 1 | 1 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 176 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
665 | 4 | COLE | RT H S | CD0043 | 13.122 | Y |  | Pavement improvement from Rte. E to end of state maintenance. Includes Rte. BB from Rte. 17 to Rte. H and Rte. CC from Rte. C to Rte. 54. | Adv. CN | 843 | 211 | 0 | 1054 | 0 | AC-STBG |  | 0 | 1 | 10 | 62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 981 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
666 | 4 | COLE | PVT OVERPASS S | CD0075 | 0.04001 | Y |  | Bridge removal on tri-level over Rte. 50. Project involves bridge A1418. | Adv. CN | 168 | 42 | 0 | 210 | 0 | AC-STBG | 5P3523 | 0 | 1 | 1 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 181 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
667 | 4 | COLE | RP US50E TO US54E E | 5P3459 | 0.058 | Y |  | Bridge rehabilitation over Rte. 50. Project involves bridge A1419. | Federal | 278 | 69 | 0 | 373 | 0 | NHPP |  | 26 | 56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 291 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
668 | 4 | COLE | CST W TRUMAN BLVD E | 5S3457 | 0.181 | Y |  | Bridge rehabilitation over Rte. 50 and Rte. D over Rte. 50. Project involves bridges A3978 and A4154. | Federal | 960 | 240 | 0 | 1257 | 0 | NHPP |  | 57 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 980 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
669 | 4 | COOPER | MO 179 S | CD0051 | 8.045 | N |  | Pavement improvement from Rte. 98 to Moniteau County line. | Adv. CN | 226 | 57 | 0 | 283 | 0 | AC-STBG |  | 0 | 1 | 1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 263 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
670 | 4 | COOPER | MO 41 S | 5P3530 | 11.725 | N |  | Pavement improvement from Cooper County line to I-70. | Adv. CN | 942 | 235 | 0 | 1178 | 0 | AC-STBG |  | 1 | 4 | 79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1094 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
671 | 4 | COOPER | MO 41 S | CD0062 | 0.087 | N |  | Bridge improvement over Lamine River. Project involves bridge A8112. | Federal | 286 | 71 | 0 | 357 | 0 | NHPP |  | 0 | 1 | 1 | 70 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
672 | 4 | COOPER | MO 5 S | 5P3513 | 0.101 | N |  | Bridge improvement over Petite Saline Creek. Project involves bridge A4366. | Federal | 330 | 82 | 0 | 415 | 0 | NHPP |  | 3 | 12 | 71 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 324 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
673 | 4 | COOPER | MO 5 S | CD0017 | 19.566 | N |  | Pavement preservation treatment from I-70 to Rte. 50. | Federal | 615 | 154 | 0 | 769 | 0 | STBG |  | 0 | 1 | 51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 717 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
674 | 4 | COOPER | IS 70 E | 5I3358Z | 4.8 | N |  | Payback for MTFC loan to construct new Missouri River bridge at Rocheport. Total cost of $60,739,000 with payments from SFY 2024 to SFY 2030. | Adv. CN | 31237 | 3471 | 0 | 34708 | 25,001 - 50,000 | AC-NHFP |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8677 | 8677 | 8677 | 8677 | 0
675 | 4 | COOPER | IS 70 E | 5I3581 | 78.025 | Y |  | Job Order Contracting for asphalt pavement repair in Cooper, Boone and Callaway Counties. | Adv. CN | 513 | 57 | 0 | 570 | 0 | AC-NHPP |  | 0 | 1 | 1 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 530 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
676 | 4 | COOPER | IS 70 E | 5I3585 | 78.025 | Y |  | Job Order Contracting for asphalt pavement repair in Cooper, Boone and Callaway Counties. | Adv. CN | 500 | 56 | 0 | 557 | 0 | AC-NHPP |  | 1 | 1 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 515 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
677 | 4 | COOPER | IS 70 E | 5I3587 | 78.025 | Y |  | Job Order Contracting for concrete pavement repair in Cooper, Boone and Callaway Counties. | Adv. CN | 487 | 54 | 0 | 542 | 0 | AC-NHPP |  | 1 | 41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
678 | 4 | COOPER | IS 70 E | CD0008 | 78.025 | Y |  | Job Order Contracting for asphalt pavement repair in Cooper, Boone and Callaway Counties. | Adv. CN | 527 | 58 | 0 | 585 | 0 | AC-NHPP |  | 0 | 1 | 1 | 1 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 546 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
679 | 4 | COOPER | IS 70 E | CD0011 | 78.025 | Y |  | Job Order Contracting for concrete pavement repair in Cooper, Boone and Callaway Counties. | Adv. CN | 527 | 58 | 0 | 585 | 0 | AC-NHPP |  | 0 | 1 | 1 | 1 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 546 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
680 | 4 | COOPER | IS 70 E | CD0038 | 190.246 | Y |  | Signing replacements from Saline County line to Montgomery County line and I-44 from Webster County line to Franklin County line. | Federal | 374 | 42 | 0 | 416 | 0 | NHPP |  | 0 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
681 | 4 | COOPER | IS 70 E | CD0080 | 78.018 | Y |  | Upgrade dynamic message signs in Cooper, Boone and Callaway Counties. | Federal | 1140 | 127 | 0 | 1267 | 0 | NHPP |  | 0 | 211 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1056 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
682 | 4 | COOPER | IS 70 E | CD0083 | 78.03 | Y |  | Striping upgrades including Boone and Callaway Counties. | Federal | 526 | 58 | 0 | 584 | 0 | SAFETY | CD0079 | 0 | 84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
683 | 4 | COOPER | IS 70 E | CD0091 | 190.246 | Y |  | Signing improvements from Saline County line to Montgomery County line and I-44 from Webster County line to Franklin County line. | Federal | 698 | 78 | 0 | 776 | 0 | NHPP |  | 0 | 1 | 74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
684 | 4 | COOPER | IS 70 E | CD0096 | 78.03 | Y |  | Striping upgrades in Cooper, Boone and Callaway Counties. | Federal | 719 | 80 | 0 | 799 | 0 | SAFETY |  | 0 | 1 | 111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 687 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
685 | 4 | COOPER | IS 70 E | CD0097 | 78.03 | Y |  | Striping upgrades in Cooper, Boone and Callaway Counties. | Federal | 760 | 84 | 0 | 844 | 0 | SAFETY |  | 0 | 1 | 1 | 113 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 729 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
686 | 4 | COOPER | IS 70 E | CD0134 | 369.372 | Y |  | Job Order Contracting for sign repair in Cooper, Boone and Callaway Counties, I-44 in Laclede, Pulaski and Phelps Counties, Rte. 63 in Boone, Callaway and Cole Counties and Rte. 54 in Camden, Miller, Cole and Callaway Counties. | Adv. CN | 173 | 43 | 0 | 216 | 0 | AC-STBG |  | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
687 | 4 | COOPER | MO 87 S | CD0023 | 0.056 | N |  | Bridge improvement over Petite Saline Creek. Project involves bridge A4607. | Federal | 292 | 73 | 0 | 365 | 0 | NHPP | CD0024 | 0 | 1 | 1 | 10 | 60 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 288 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
688 | 4 | COOPER | MO 87 S | CD0024 | 0.037 | N |  | Bridge improvement over Clarks Fork Creek. Project involves bridge A4608. | Federal | 267 | 67 | 0 | 334 | 0 | NHPP | CD0023 | 0 | 1 | 1 | 6 | 57 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 264 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
689 | 4 | COOPER | CRD DUNKLES DR S | CD0022 | 0.038 | N |  | Bridge improvement over I-70. Project involves bridge L0945. | Federal | 1087 | 272 | 0 | 1359 | 0 | NHPP |  | 0 | 1 | 1 | 28 | 243 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
690 | 4 | COOPER | RT HH E | 5S3462 | 0.254 | N |  | Bridge replacement over Brushy Creek. Project involves bridge N0401. | Federal | 1158 | 290 | 0 | 1549 | 0 | NHPP |  | 101 | 297 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 1131 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
691 | 4 | COOPER | RT K S | CD0012 | 0.383 | N |  | Bridge preventative maintenance over Blackwater River, Dunkles Drive over I-70, I-70 over Lamine River, Rte. B over Petite Saline Creek and Rte. U over Clarks Creek. Project involves bridges A1382, L0945, A0201, A1691, N0696 and N0697. | Federal | 2902 | 725 | 0 | 3627 | 0 | NHPP |  | 0 | 57 | 723 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2847 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
692 | 4 | COOPER | RT K S | CD0016 | 5.787 | N |  | Pavement resurfacing from Rte. 41 to I-70. | Federal | 482 | 120 | 0 | 602 | 0 | STBG |  | 0 | 3 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 559 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
693 | 4 | COOPER | RT N E | 5S3445 | 0.029 | N |  | Bridge rehabilitation over Clear Creek. Project involves bridge R0560. | Federal | 593 | 148 | 0 | 842 | 0 | NHPP |  | 101 | 162 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 579 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
694 | 4 | COOPER | RT O S | 5S3450 | 0.046 | N |  | Bridge improvement over Moniteau Creek. Project involves bridge A1861. | Federal | 982 | 246 | 0 | 1236 | 0 | NHPP |  | 8 | 50 | 205 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 968 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
695 | 4 | COOPER | RT O S | CD0095 | 13.158 | N |  | Pavement preservation treatment from Rte. J to Rte. 87. | Adv. CN | 324 | 81 | 0 | 405 | 0 | AC-STBG |  | 0 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 376 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
696 | 4 | COOPER | RT U S | 5S3465 | 0.091 | N |  | Bridge rehabilitation over Petite Saline Creek. Project involves bridge N0983. | Federal | 601 | 150 | 0 | 781 | 0 | NHPP |  | 30 | 177 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 574 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
697 | 4 | COOPER | CRD WOODLAND SCHOOL DR E | 5S3512 | 0.032 | N |  | Bridge rehabilitation over I-70 on Woodland School Road. Project involves bridge A0007. | Federal | 658 | 165 | 0 | 974 | 0 | NHPP |  | 151 | 180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 643 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
698 | 4 | CRAWFORD | MO 19 S | 5P3515 | 0.272 | N |  | Bridge improvement over I-44. Includes Rte. F and Rte. H. over I-44. Project involves bridges A1191, A1383 and A1192. | Adv. CN | 2064 | 516 | 0 | 2607 | 0 | AC-STBG |  | 27 | 151 | 383 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2046 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
699 | 4 | CRAWFORD | IS 44 E | 5I3477 | 19.33 | N |  | Pavement improvement from Phelps County line to Franklin County line. | Federal | 6811 | 757 | 0 | 7570 | 0 | NHPP |  | 2 | 60 | 788 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6720 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
700 | 4 | CRAWFORD | S OR 44 E | 5S3533 | 0.028 | N |  | Bridge improvement over Little Bourbeuse River. Project involves bridge A1385. | Federal | 475 | 119 | 0 | 600 | 0 | NHPP |  | 6 | 30 | 93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 471 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
701 | 4 | CRAWFORD | MO 49 S | CD0084 | 20.078 | N |  | Pavement improvement from Rte. 19 to Rte. 32 in Iron County. | Adv. CN | 621 | 155 | 0 | 776 | 0 | AC-STBG |  | 0 | 1 | 3 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 722 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
702 | 4 | CRAWFORD | MO 8 E | CD0102 | 28.213 | N |  | Pavement improvement from west of the Washington County line to Big River in St. Francois County. | Federal | 4573 | 1143 | 0 | 5716 | 0 | NHPP |  | 0 | 1 | 1 | 1 | 25 | 350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5338 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
703 | 4 | CRAWFORD | CRD BEAMER LN N | 5S3545 | 0.129 | N |  | Bridge improvement over I-44. Project involves bridge A2055. | Federal | 144 | 36 | 0 | 181 | 0 | NHPP |  | 1 | 1 | 10 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
704 | 4 | CRAWFORD | RT C E | 5S3550 | 0.04 | N |  | Bridge improvement over I-44. Project involves bridge A1753. | Federal | 603 | 151 | 0 | 755 | 0 | NHPP | 5S3545 5S3579 | 1 | 1 | 41 | 116 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
705 | 4 | CRAWFORD | RT FF S | 5S3579 | 0.049 | N |  | Bridge improvement over I-44. Project involves bridge A1853. | Federal | 493 | 123 | 0 | 617 | 0 | NHPP |  | 1 | 1 | 24 | 104 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 487 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
706 | 4 | CRAWFORD | RT HH S | 5S3479 | 0.02 | N |  | Bridge improvement over Dry Creek. Project involves bridge N0898. | Federal | 523 | 131 | 0 | 658 | 0 | NHPP |  | 4 | 16 | 122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 516 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
707 | 4 | CRAWFORD | RT J S | 5S3552 | 0.02 | N |  | Bridge improvement over Boone Creek. Project involves bridge P0020. | Federal | 790 | 198 | 0 | 989 | 0 | NHPP |  | 1 | 1 | 47 | 190 | 0 | 0 | 0 | 0 | 0 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 719 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
708 | 4 | CRAWFORD | RT N W | CD0037 | 0.068 | N |  | Bridge improvement over Meramec River. Project involves bridge A3354. | Federal | 230 | 58 | 0 | 288 | 0 | NHPP |  | 0 | 1 | 1 | 1 | 7 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 230 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
709 | 4 | DENT | MO 119 S | 5S3466 | 0.05 | N |  | Bridge rehabilitation over Pigeon Creek. Project involves bridge A5335. | Federal | 157 | 39 | 0 | 202 | 0 | NHPP |  | 6 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 158 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
710 | 4 | DENT | MO 19 S | 5P3420 | 0.054 | N |  | Bridge replacement over Gladden Creek. Project involves bridge G0537. | Federal | 1376 | 344 | 0 | 1826 | 0 | NHPP |  | 106 | 301 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 1413 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
711 | 4 | DENT | MO 19 S | CD0035 | 0.012 | N |  | Bridge improvement over Spring Creek. Project involves bridge A4433. | Federal | 114 | 29 | 0 | 143 | 0 | NHPP |  | 0 | 1 | 1 | 1 | 6 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 114 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
712 | 4 | DENT | MO 32 E | CD0129 | 3.108 | N |  | Upgrade pedestrian facilities to comply with the ADA Transition Plan including Rte. 19 in Salem. $1,279,000 Statewide Transportation Alternatives funds. | Adv. CN | 1421 | 355 | 0 | 1776 | 0 | AC-STBG |  | 0 | 23 | 100 | 299 | 0 | 0 | 0 | 0 | 0 | 92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1262 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
713 | 4 | DENT | RT B E | 5S3559 | 0.02 | N |  | Bridge improvement over Dry Creek. Project involves bridge T0582. | Federal | 597 | 149 | 0 | 747 | 0 | NHPP |  | 1 | 1 | 1 | 36 | 145 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 563 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
714 | 4 | DENT | RT K S | 5S3564 | 19.136 | N |  | Pavement improvement from Rte. 19 to Rte. KK. Includes Rte. J from Rte. 72 to Rte. 32. | Adv. CN | 1282 | 320 | 0 | 1603 | 0 | AC-STBG |  | 1 | 1 | 8 | 102 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1491 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
715 | 4 | GASCONADE | MO 19 S | 5P3542 | 0.06 | N |  | Bridge improvement over Frene Creek. Project involves bridge J0009. | Federal | 565 | 141 | 0 | 707 | 0 | NHPP |  | 1 | 36 | 128 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 541 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
716 | 4 | GASCONADE | MO 19 S | CD0045 | 19.555 | N |  | Pavement improvement from Rte. 50 to Rte. CC in Crawford County. | Adv. CN | 2599 | 650 | 0 | 3249 | 0 | AC-STBG |  | 0 | 10 | 43 | 223 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2973 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
717 | 4 | GASCONADE | RT B S | 5S3446 | 0.049 | N |  | Bridge rehabilitation over Dry Fork Creek. Project involves bridge R0500. | Federal | 750 | 187 | 0 | 1007 | 0 | NHPP |  | 60 | 212 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 725 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
718 | 4 | GASCONADE | RT EE S | CD0027 | 13.293 | N |  | Pavement improvement from Jackson Avenue to Rte. F. | Adv. CN | 875 | 219 | 0 | 1094 | 0 | AC-STBG | CD0028 | 0 | 10 | 68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1016 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
719 | 4 | HOWARD | US 40 E | 5P3518 | 26.984 | Y |  | Pavement improvement from Rte. 87 to I-70 and Rte. 3 from the Randolph County line to Rte. 5. | Adv. CN | 903 | 226 | 0 | 1130 | 0 | AC-STBG |  | 1 | 3 | 76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
720 | 4 | HOWARD | MO 5 S | 5P3498 | 0.09 | N |  | Bridge improvement over Bear Creek. Project involves bridge J0007. | Federal | 2534 | 633 | 0 | 3178 | 0 | NHPP |  | 11 | 184 | 598 | 0 | 0 | 0 | 0 | 0 | 39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2346 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
721 | 4 | HOWARD | MO 5 S | 5P3517 | 37.777 | N |  | Pavement improvement and safety improvement from Rte. 87 to Rte. 40 and Rte. 240 from Rte. 5 to Rte. 40. $1,771,000 Open Container funds. | Adv. CN | 7615 | 1904 | 0 | 9529 | 0 | AC-STBG |  | 10 | 240 | 1299 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7960 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
722 | 4 | HOWARD | MO 5 S | 5P3532 | 0.027 | N |  | Bridge improvement over Sulphur Creek. Project involves bridge H0266. | Federal | 401 | 100 | 0 | 502 | 0 | NHPP |  | 1 | 1 | 1 | 6 | 91 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 397 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
723 | 4 | HOWARD | MO 5 S | 5S3546 | 77.852 | Y |  | Upgrade pedestrian facilities at various locations in Glasgow, Fayette, New Franklin, Stoutland, Sleeper, Conway and Columbia. | Adv. CN | 466 | 117 | 0 | 584 | 0 | AC-STBG |  | 1 | 41 | 129 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 403 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
724 | 4 | HOWARD | MO 5 S | CD0110 | 0.147 | N |  | Intersection improvements at Rte. 5 and Rte. 40 south of New Franklin. | Adv. CN | 898 | 224 | 0 | 1122 | 0 | AC-STBG |  | 0 | 1 | 1 | 187 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 928 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
725 | 4 | HOWARD | MO 87 S | CD0018 | 20.043 | N |  | Pavement preservation treatment from Rte. 5 to Rte. 40 and Rte. 240 from Missouri River bridge to Rte. 5. | Adv. CN | 648 | 162 | 0 | 810 | 0 | AC-STBG |  | 0 | 1 | 54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 755 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
726 | 4 | HOWARD | RT H N | CD0130 | 50.69 | N |  | Pavement resurfacing from Rte. 124 to Rte. B, Rte. O from Rte. H to Rte. A, Rte. U from Rte. 3 to Rte. H, and all of Rte. K, Rte. HH, Rte. FF, Rte. BB, Rte. JJ and Rte. CC. | Federal | 0 | 5399 | 0 | 5399 | 0 | STATE | NE0164 NW0095 | 0 | 399 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
727 | 4 | HOWARD | RT J E | 5S3469 | 16.712 | N |  | Pavement resurfacing from Rte. Z to Rte. 5 and Rte. DD from Rte. 5 to Rte. P. | Adv. CN | 998 | 249 | 0 | 1297 | 0 | AC-STBG |  | 50 | 92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1155 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
728 | 4 | HOWARD | RT P E | 5S3461 | 0.059 | N |  | Bridge rehabilitation over Bonne Femme Creek. Project involves bridge A0724. | Federal | 595 | 149 | 0 | 779 | 0 | NHPP |  | 35 | 134 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 605 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
729 | 4 | LACLEDE | MO 32 E | 5P3527 | 52.174 | N |  | Pavement improvement from Rte. 5 to Rte. 17 in Texas County. | Adv. CN | 1121 | 280 | 0 | 1402 | 0 | AC-STBG |  | 1 | 16 | 83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1302 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
730 | 4 | LACLEDE | IS 44 E | 5I3584 | 112.213 | N |  | Job Order Contracting for asphalt pavement repair in Laclede, Pulaski, Phelps and Crawford Counties. | Adv. CN | 621 | 155 | 0 | 777 | 0 | AC-STBG |  | 1 | 1 | 54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 721 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
731 | 4 | LACLEDE | IS 44 E | 5I3586 | 112.213 | N |  | Job Order Contracting for concrete pavement repair in Laclede, Pulaski, Phelps and Crawford Counties. | Adv. CN | 445 | 111 | 0 | 557 | 0 | AC-STBG |  | 1 | 1 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 515 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
732 | 4 | LACLEDE | IS 44 E | CD0009 | 112.213 | N |  | Job Order Contracting for asphalt pavement repair in Laclede, Pulaski, Phelps and Crawford Counties. | Adv. CN | 654 | 164 | 0 | 818 | 0 | AC-STBG |  | 0 | 1 | 1 | 1 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 765 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
733 | 4 | LACLEDE | IS 44 E | CD0010 | 112.213 | N |  | Job Order Contracting for concrete pavement repair in Laclede, Pulaski, Phelps and Crawford Counties. | Adv. CN | 468 | 117 | 0 | 585 | 0 | AC-STBG |  | 0 | 1 | 1 | 1 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 546 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
734 | 4 | LACLEDE | IS 44 E | CD0079 | 112.162 | N |  | Striping upgrades including Pulaski, Phelps and Crawford Counties. | Federal | 812 | 90 | 0 | 902 | 0 | SAFETY | CD0083 | 0 | 130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 772 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
735 | 4 | LACLEDE | IS 44 E | CD0081 | 112.195 | N |  | Upgrade dynamic message signs in Laclede, Pulaski, Phelps and Crawford Counties. | Federal | 1140 | 127 | 0 | 1267 | 0 | NHPP |  | 0 | 211 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1056 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
736 | 4 | LACLEDE | IS 44 E | CD0103 | 112.162 | N |  | Striping upgrades in Laclede, Pulaski, Phelps and Crawford Counties. | Adv. CN | 832 | 208 | 0 | 1040 | 0 | AC-STBG |  | 0 | 1 | 97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 942 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
737 | 4 | LACLEDE | IS 44 E | CD0104 | 112.162 | N |  | Striping upgrades in Laclede, Pulaski, Phelps and Crawford Counties. | Adv. CN | 883 | 221 | 0 | 1104 | 0 | AC-STBG |  | 0 | 1 | 1 | 103 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
738 | 4 | LACLEDE | S OR 44 E | CD0101 | 0.119 | N |  | Bridge improvement over Bear Creek. Project involves bridge G0248. | Adv. CN | 96 | 24 | 0 | 120 | 0 | AC-STBG |  | 0 | 1 | 7 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
739 | 4 | LACLEDE | MO 5 S | 5P3494 | 28.331 | N |  | Pavement resurfacing from Lawson Avenue to Rte. J. Includes Camden County Rte. V from Lake Street to Rte. 7, Rte. E from Rte. 7 to Rte. A, Rte. Y from Rte. 54 to end of state maintenance and east and west Rte. 54 outer roads at Rte. Y intersection. | Adv. CN | 686 | 171 | 0 | 872 | 0 | AC-STBG |  | 15 | 109 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 748 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
740 | 4 | LACLEDE | MO 5 S | CD0046 | 0.228 | N |  | Rebuild pavement at BNSF Railway crossing. | Adv. CN | 747 | 187 | 0 | 1159 | 0 | AC-NHPP |  | 225 | 160 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 773 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
741 | 4 | LACLEDE | MO 64 E | 5P3244 | 0.415 | N |  | Bridge improvement over Goodwin Creek. Project involves bridge J0560. | Federal | 1942 | 486 | 0 | 2548 | 0 | NHPP |  | 120 | 120 | 346 | 0 | 0 | 0 | 0 | 0 | 191 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1771 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
742 | 4 | LACLEDE | RT B S | 5S3484 | 0.155 | N |  | Bridge improvement over Osage Fork of Gasconade River. Project involves bridge R0482. | Federal | 1199 | 300 | 0 | 1504 | 0 | NHPP |  | 5 | 85 | 234 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
743 | 4 | LACLEDE | RT C E | CD0048 | 21.117 | N |  | Pavement improvement from I-44 to Rte. 5. Includes Rte. HH from Rte. 5 to end of state maintenance and Rte. PP from Rte. C to Rte. J. | Adv. CN | 1475 | 369 | 0 | 1844 | 0 | AC-STBG |  | 0 | 1 | 1 | 154 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1688 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
744 | 4 | LACLEDE | CRD DOVE RD E | 5S3562 | 0.096 | N |  | Bridge improvement over I-44. Project involves bridge A2892. | Federal | 346 | 87 | 0 | 434 | 0 | NHPP |  | 1 | 1 | 1 | 1 | 6 | 53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 371 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
745 | 4 | LACLEDE | RT J E | CD0056 | 0.093 | N |  | Bridge improvement over I-44. Project includes bridge A1196. | Federal | 843 | 211 | 0 | 1054 | 0 | NHPP |  | 0 | 2 | 2 | 36 | 60 | 111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 843 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
746 | 4 | LACLEDE | PVT RT 66 E | 5S3322 | 0.138 | N |  | Payment to private entity for bridge relinquishment over Gasconade River. Project involves bridge G0245. | Adv. CN | 234 | 59 | 0 | 317 | 0 | AC-STBG |  | 24 | 113 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
747 | 4 | MARIES | MO 28 E | 5P3476 | 0.163 | N |  | Bridge replacement over Dry Fork Creek. Includes bridge rehabilitation on Rte. C over Peavine Creek and Rte. P over Lanes Fork Creek. Project involves bridges H0980, R0561 and A1882. | Federal | 1738 | 434 | 0 | 2249 | 0 | NHPP |  | 67 | 423 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1749 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
748 | 4 | MARIES | MO 28 E | CD0061 | 31.83 | N |  | Pavement improvement from Rte. 63 to Rte. 50. | Adv. CN | 2271 | 568 | 0 | 2839 | 0 | AC-STBG | CD0027 | 0 | 5 | 199 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2635 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
749 | 4 | MARIES | MO 42 E | 5P3565 | 0.071 | N |  | Bridge improvement over Fly Creek and Maries River. Project involves bridges L0187 and A1177. | Federal | 1327 | 332 | 0 | 1660 | 0 | NHPP |  | 1 | 1 | 100 | 247 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1311 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
750 | 4 | MARIES | MO 42 E | 5S3473 | 19.603 | N |  | Pavement resurfacing from Rte. 63 to Rte. 28. Includes Rte. EE from Rte. 28 to end of state maintenance. | Adv. CN | 1163 | 291 | 0 | 1516 | 0 | AC-STBG | 5S3354 | 62 | 98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1356 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
751 | 4 | MARIES | RT AA S | 5S3543 | 0.079 | N |  | Bridge improvement over Maries River and over Little Maries River. Project involves bridges A1857 and A1858. | Adv. CN | 1274 | 318 | 0 | 1593 | 0 | AC-STBG |  | 1 | 1 | 94 | 239 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
752 | 4 | MILLER | MO 134 W | 5S3571 | 5.071 | N |  | Pavement resurfacing from Rte. 42 to end of state maintenance. | Adv. CN | 152 | 38 | 0 | 191 | 0 | AC-STBG | 5S3474 | 1 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 164 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
753 | 4 | MILLER | MO 17 S | CD0047 | 22.131 | N |  | Pavement preservation treatment from Rte. 42 to Rte. 66. | Adv. CN | 539 | 135 | 0 | 674 | 0 | AC-STBG |  | 0 | 8 | 41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
754 | 4 | MILLER | MO 42 E | 5P3569 | 58.5 | N |  | Pavement improvement from east of Osage Beach Parkway in Osage Beach to Rte. 28. | Adv. CN | 1495 | 374 | 0 | 1870 | 0 | AC-STBG |  | 1 | 1 | 1 | 1 | 14 | 106 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1746 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
755 | 4 | MILLER | MO 52 E | CD0121 | 2.468 | N |  | Upgrade pedestrian facilities to comply with the ADA Transition Plan and address nonstandard ADA facilities in St. Elizabeth, Tuscumbia, Osage Beach, Lebanon, Richland and Dixon. $603,000 Statewide Transportation Alternatives funds. | Adv. CN | 1281 | 320 | 0 | 1601 | 0 | AC-STBG |  | 0 | 205 | 202 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1183 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
756 | 4 | MILLER | US 54 E | 5P3500 | 22.084 | N |  | Pavement improvement and add guard cable from 0.4 mile east of Rte. AA to 0.4 mile east of Rte. 242. $703,000 Open Container funds. | Federal | 11351 | 2838 | 0 | 14194 | 0 | NHPP |  | 5 | 15 | 145 | 825 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
757 | 4 | MILLER | US 54 E | CD0133 | 69.179 | Y |  | Striping upgrades in Miller, Cole and Callaway Counties. | Federal | 662 | 74 | 0 | 736 | 0 | SAFETY |  | 0 | 101 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 635 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
758 | 4 | MILLER | RT C S | 5S3444 | 0.207 | N |  | Bridge rehabilitation over Mill Creek and over Brumley Creek. Project involves bridges A1951 and A1952. | Federal | 735 | 184 | 0 | 950 | 0 | NHPP |  | 31 | 118 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 801 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
759 | 4 | MILLER | RT C S | CD0098 | 17.15 | N |  | Pavement improvement from Rte. 17 to Rte. A. | Adv. CN | 1130 | 283 | 0 | 1413 | 0 | AC-STBG |  | 0 | 1 | 1 | 118 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1293 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
760 | 4 | MILLER | RT Y S | 5S3474 | 32.53 | N |  | Pavement resurfacing from Rte. 52 to end of state maintenance, Rte. AA from Rte. C to Rte. 54, Rte. D from East Osage Beach Parkway to end of state maintenance and Rte. H from Rte. 17 to end of state maintenance. | Adv. CN | 734 | 183 | 0 | 929 | 0 | AC-STBG | 5S3571 | 12 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 797 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
761 | 4 | MONITEAU | MO 179 S | CD0115 | 0.12 | N |  | Bridge improvement over Moniteau Creek. Project involves bridge A1984. | Federal | 855 | 214 | 0 | 1070 | 0 | NHPP |  | 1 | 8 | 20 | 193 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 843 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
762 | 4 | MONITEAU | MO 5 S | 5P3044 | 46.598 | N |  | Pavement resurfacing from Rte. 50 to 1.3 miles south of Rte. 7 and add turn lane at Rte. O. | Federal | 9944 | 2486 | 0 | 12609 | 0 | NHPP |  | 179 | 1613 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10817 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
763 | 4 | MONITEAU | US 50 E | CD0136 | 35.954 | Y |  | Striping upgrades in Moniteau, Cole and Osage Counties. | Adv. CN | 358 | 40 | 0 | 398 | 0 | AC-SAFETY |  | 0 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 343 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
764 | 4 | MONITEAU | MO 87 S | 5S3369B | 4.995 | N |  | Upgrade pedestrian facilities to comply with the ADA Transition Plan and address nonstandard ADA facilities in California, Tipton, Syracuse, Stover, Lone Elm, Armstrong, Roanoke, Fayette, Hallsville and Harrisburg. $349,000 Statewide Transportation Alternatives funds. | Adv. CN | 1786 | 447 | 0 | 2283 | 0 | AC-STBG |  | 50 | 535 | 0 | 0 | 0 | 0 | 0 | 0 | 57 | 0 | 0 | 0 | 0 | 0 | 0 | 1641 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
765 | 4 | MONITEAU | MO 87 S | CD0113 | 0.256 | N |  | Intersection improvement at Rte. C. | Adv. CN | 1177 | 294 | 0 | 1471 | 0 | AC-STBG |  | 0 | 100 | 300 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1061 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
766 | 4 | MONITEAU | RT CC S | 5S3555 | 0.16 | N |  | Bridge improvement over South Moreau Creek. Project involves bridge A1835. | Federal | 679 | 170 | 0 | 850 | 0 | NHPP |  | 1 | 1 | 1 | 24 | 147 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 671 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
767 | 4 | MONITEAU | RT U E | CD0057 | 0.058 | N |  | Bridge improvement over Howard Creek. Project involves bridge A2358. | Federal | 242 | 61 | 0 | 303 | 0 | NHPP | CD0115 | 0 | 1 | 16 | 46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
768 | 4 | MORGAN | MO 5 S | CD0070 | 0.499 | N |  | Bridge improvement over Gravois Creek. Project involves bridge A0146. | Adv. CN | 5066 | 1267 | 0 | 6333 | 0 | AC-STBG |  | 0 | 1 | 1 | 1 | 1 | 1501 | 0 | 0 | 0 | 0 | 0 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4801 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
769 | 4 | MORGAN | MO 52 E | 5P3575 | 0.477 | N |  | Roadway improvement from Fairgrounds Road to Rte. 5 and Rte. 5 from Rte. 52 to Business Park entrance. | Adv. CN | 2297 | 574 | 0 | 2881 | 0 | AC-STBG |  | 10 | 153 | 299 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2405 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
770 | 4 | MORGAN | MO 52 E | CD0131 | 11.281 | N |  | Pavement resurfacing from Haw Creek to 0.6 mile west of Rte. 5 in Versailles. | Adv. CN | 3532 | 883 | 0 | 4415 | 0 | AC-STBG |  | 0 | 328 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4087 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
771 | 4 | MORGAN | RT DD E | 5S3440 | 0.23 | N |  | Bridge rehabilitation over Haw Creek. Project involves bridge R0592. | Adv. CN | 971 | 243 | 0 | 1332 | 0 | AC-STBG |  | 117 | 221 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 993 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
772 | 4 | MORGAN | RT DD E | 5S3440B | 0.23 | N |  | Bridge preventative maintenance over Haw Creek. Project involves bridge R0592. | Adv. CN | 205 | 51 | 0 | 256 | 0 | AC-STBG |  | 0 | 22 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
773 | 4 | MORGAN | RT T S | 5S3398 | 14.705 | N |  | Pavement improvement and safety improvement from Rte. 52 to the end of state maintenance. | Adv. CN | 2264 | 566 | 0 | 2880 | 0 | AC-STBG |  | 50 | 63 | 248 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2509 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
774 | 4 | MORGAN | RT TT S | 5S3456 | 31.8 | N |  | Pavement resurfacing from Rte. 5 north junction to Rte. 5 south junction, Rte. K from Rte. E to end of state maintenance, Rte. FF from Rte. 52 to end of state maintenance, and Rte. E from Rte. 50 to Rte. C. | Adv. CN | 1817 | 454 | 0 | 2291 | 0 | AC-STBG |  | 20 | 149 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
775 | 4 | MORGAN | RT W S | 5S3536 | 0.129 | N |  | Bridge improvement over Indian Creek south of Rte. AA. Project involves bridge R0605. | Federal | 658 | 165 | 0 | 824 | 0 | NHPP |  | 1 | 1 | 5 | 16 | 118 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 683 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
776 | 4 | OSAGE | MO 100 E | CD0078 | 27.598 | N |  | Pavement improvement from Rte. 50 to Rte. N. | Adv. CN | 1706 | 426 | 0 | 2132 | 0 | AC-STBG |  | 0 | 1 | 13 | 135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1983 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
777 | 4 | OSAGE | MO 133 S | CD0076 | 183.807 | Y |  | Upgrade pedestrian facilities at various locations in Meta, Linn, Newburg, Columbia, Sturgeon, Fulton, New Bloomfield, Woolridge, Blackwater and Phillipsburg. | Adv. CN | 1710 | 427 | 0 | 2137 | 0 | AC-STBG |  | 0 | 22 | 160 | 446 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1494 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
778 | 4 | OSAGE | MO 133 S | CD0077 | 51.018 | N |  | Pavement improvement from Rte. 63 to Rte. 17. Includes Rte. EE from County Road 505 to Rte. 133. | Adv. CN | 3221 | 805 | 0 | 4026 | 0 | AC-STBG |  | 0 | 1 | 25 | 255 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3745 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
779 | 4 | OSAGE | US 50 E | 5P3574 | 0.682 | N |  | Intersection improvement at Rte. CC in Linn. | Federal | 3006 | 752 | 0 | 3881 | 0 | NHPP |  | 123 | 200 | 509 | 0 | 0 | 0 | 0 | 0 | 824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
780 | 4 | OSAGE | US 50 E | CD0044 | 35.758 | N |  | Pavement improvement from 0.3 mile east of Loose Creek Highway to Franklin County line. | Federal | 7891 | 1973 | 0 | 9864 | 0 | NHPP |  | 0 | 40 | 101 | 696 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
781 | 4 | OSAGE | US 63 S | CD0108 | 5.78 | N |  | Corridor improvements from Rte. 50 to County Road 611 south of Westphalia. | Federal | 50328 | 12582 | 0 | 62910 | 0 | NHPP |  | 0 | 500 | 500 | 500 | 1789 | 4992 | 0 | 0 | 0 | 0 | 0 | 7825 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46804 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
782 | 4 | OSAGE | MO 89 S | CD0105 | 0.007 | N |  | Bridge improvement over Indian Creek. Project involves bridge K0214. | Federal | 637 | 159 | 0 | 796 | 0 | NHPP |  | 0 | 1 | 1 | 1 | 43 | 145 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
783 | 4 | OSAGE | RT A S | CD0028 | 8.061 | N |  | Pavement improvement from Main Street to Rte. 50. | Adv. CN | 802 | 201 | 0 | 1003 | 0 | AC-STBG | CD0027 | 0 | 9 | 63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 931 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
784 | 4 | OSAGE | RT E E | CD0060 | 0.006 | N |  | Bridge improvement over Town Creek. Project involves bridge Y0198. | Federal | 54 | 14 | 0 | 68 | 0 | NHPP |  | 0 | 1 | 1 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
785 | 4 | OSAGE | RT T S | CD0042 | 18.39 | N |  | Pavement improvement from Rte. 63 to Rte. 42. | Adv. CN | 479 | 120 | 0 | 599 | 0 | AC-STBG | CD0040 | 0 | 1 | 6 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 557 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
786 | 4 | OSAGE | RT T S | CD0071 | 0.021 | N |  | Bridge improvement over Osage Creek. Project involves bridge A1839. | Adv. CN | 420 | 105 | 0 | 525 | 0 | AC-STBG |  | 0 | 1 | 1 | 18 | 87 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 413 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
787 | 4 | OSAGE | RT U S | 5S3354 | 14.704 | N |  | Pavement resurfacing, add rumblestripes from Rte. 50 to Rte. E. Includes Rte. E from Rte. 63 to Rte. 89. $1,390,000 Open Container funds. | Adv. CN | 2702 | 676 | 0 | 3507 | 0 | AC-STBG | 5S3473 | 114 | 470 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2908 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
788 | 4 | PHELPS | IS 44 E | 5I3561 | 0.348 | N |  | Bridge improvement over Little Piney Creek and BNSF Railway. Project involves bridge G0418. | Federal | 813 | 90 | 0 | 904 | 0 | NHFP |  | 1 | 1 | 39 | 149 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
789 | 4 | PHELPS | IS 44 W | 5I3481 | 0 | N |  | Bridge improvement over Little Piney Creek and BNSF Railway. Project involves bridge A6671. | Federal | 516 | 57 | 0 | 577 | 0 | NHPP |  | 4 | 30 | 90 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 453 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
790 | 4 | PHELPS | LP 44 E | 5S3563 | 0.056 | N |  | Bridge improvement over I-44. Project involves bridge A1259. | Federal | 641 | 160 | 0 | 802 | 0 | NHPP |  | 1 | 1 | 47 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 633 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
791 | 4 | PHELPS | N OR 44 E | CD0085 | 18.033 | N |  | Pavement improvement from Parker Street to end of state maintenance, south Outer Road 44 from Marion Drive to end of state maintenance, east Outer Road 44 from begin of state maintenance to end of state maintenance and Rte. C from MacArthur Street to east Outer Road 44. | Adv. CN | 1782 | 445 | 0 | 2227 | 0 | AC-STBG |  | 0 | 1 | 10 | 144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2072 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
792 | 4 | PHELPS | US 63 S | 5P3537 | 0.065 | N |  | Bridge improvement over Little Piney Creek. Project involves bridge J0115. | Federal | 2256 | 564 | 0 | 2821 | 0 | NHPP |  | 1 | 46 | 100 | 445 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2229 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
793 | 4 | PHELPS | US 63 S | CD0088 | 30.181 | N |  | Pavement improvement from north of Rolla to Rte. CC. | Federal | 7137 | 1784 | 0 | 8921 | 0 | NHPP |  | 0 | 1 | 1 | 120 | 828 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7971 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
794 | 4 | PHELPS | MO 72 E | CD0122 | 4.073 | N |  | Upgrade pedestrian facilities to address nonstandard ADA facilities including Rte. KK in St. James. | Adv. CN | 1486 | 371 | 0 | 1857 | 0 | AC-STBG |  | 0 | 200 | 277 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1380 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
795 | 4 | PHELPS | MO 8 E | 5P3568 | 35.357 | N |  | Pavement resurfacing from I-44 to east of Courtois Creek and Rte. 68 from south of Matlock Drive to I-44. | Federal | 3957 | 989 | 0 | 5328 | 0 | NHPP |  | 382 | 335 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4611 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
796 | 4 | PHELPS | MO 8 E | CD0033 | 0.081 | N |  | Bridge improvement over I-44. Project involves bridges A0602 and A1869. | Federal | 733 | 183 | 0 | 916 | 0 | NHPP |  | 0 | 1 | 1 | 48 | 138 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 728 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
797 | 4 | PHELPS | CRD 8490 S | 5S3547 | 0.043 | N |  | Bridge improvement over I-44. Project involves bridge A1627. | Federal | 350 | 87 | 0 | 438 | 0 | NHPP | 5S3539 5S3541 5S3548 5S3549 CD0101 | 1 | 1 | 27 | 63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 346 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
798 | 4 | PHELPS | RT BB E | CD0089 | 0.078 | N |  | Bridge improvement over Oak Street, Olive Street and BNSF Railway. Project involves bridge A3080. | Federal | 1688 | 422 | 0 | 2110 | 0 | NHPP |  | 0 | 1 | 1 | 52 | 379 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1677 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
799 | 4 | PHELPS | RT CC E | CD0086 | 7.62 | N |  | Pavement improvement from Rte. 63 to end of state maintenance. Includes Rte. T from I-44 to Rte. P. | Adv. CN | 578 | 144 | 0 | 722 | 0 | AC-STBG | CD0067 | 0 | 1 | 5 | 46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 670 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
800 | 4 | PHELPS | RT D E | 5S3549 | 0.04 | N |  | Bridge improvement over I-44. Project involves bridge A1634. | Federal | 563 | 141 | 0 | 705 | 0 | NHPP | 5S3539 5S3541 5S3547 5S3548 CD0101 | 1 | 1 | 30 | 116 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 557 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
801 | 4 | PHELPS | RT E N | 5S3310 | 0 | N |  | Payment to Rolla for pedestrian bridge construction over I-44 at Rolla. | Adv. CN | 401 | 100 | 0 | 502 | 0 | AC-STBG |  | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
802 | 4 | PHELPS | RT E S | 5S3541 | 0.04 | N |  | Bridge improvement over I-44. Project involves bridge A1261. | Federal | 163 | 41 | 0 | 205 | 0 | NHPP | 5S3539 5S3547 5S3548 5S3549 CD0101 | 1 | 1 | 16 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 162 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
803 | 4 | PHELPS | RT F E | 5P3528 | 48.658 | N |  | Pavement preservation treatment from Rte. 72 to Rte. 68. Includes Rte. E from University Drive to end of state maintenance, Rte. BB from 0.1 mile east of Independence Drive to Rte. 68. Also includes all of Rte. H and Rte. E in Crawford County. | Adv. CN | 1574 | 393 | 0 | 1977 | 0 | AC-STBG |  | 10 | 11 | 121 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1835 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
804 | 4 | PHELPS | RT HH S | CD0036 | 0.03 | N |  | Bridge improvement over Spring Creek. Project involves bridge N0668. | Federal | 1317 | 329 | 0 | 1646 | 0 | NHPP |  | 0 | 1 | 1 | 1 | 87 | 299 | 0 | 0 | 0 | 0 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
805 | 4 | PHELPS | RT J S | 5S3548 | 0.044 | N |  | Bridge improvement over I-44. Project involves bridge A1633. | Federal | 516 | 129 | 0 | 646 | 0 | NHPP | 5S3539 5S3541 5S3547 5S3549 CD0101 | 1 | 1 | 38 | 96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 510 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
806 | 4 | PHELPS | RT O S | 5S3468 | 18.88 | N |  | Pavement resurfacing and add rumblestripes from Rte. 72 to end of state maintenance. $380,000 Open Container funds. | Adv. CN | 2914 | 728 | 0 | 3657 | 0 | AC-STBG |  | 15 | 329 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3313 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
807 | 4 | PHELPS | RT V E | 5S3472 | 15.343 | N |  | Pavement preservation treatment from Hypoint Boulevard to Rte. 68, Rte. DD from Rte. 68 to end of state maintenance and Rte. U from I-44 outer road to end of state maintenance. | Adv. CN | 372 | 93 | 0 | 474 | 0 | AC-STBG |  | 9 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
808 | 4 | PHELPS | RT V E | 5S3539 | 0.055 | N |  | Bridge improvement over I-44. Project involves bridge A1296. | Federal | 338 | 84 | 0 | 424 | 0 | NHPP | 5S3541 5S3547 5S3548 5S3549 CD0101 | 2 | 3 | 27 | 57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 335 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
809 | 4 | PULASKI | IS 44 E | 5I3483 | 0.279 | N |  | Bridge rehabilitation over Big Piney River, Roubidoux River and Gasconade River. Project involves bridges L0093, L0697 and twin bridges A3061. | Federal | 5400 | 600 | 0 | 6089 | 0 | NHFP |  | 89 | 1223 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4777 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
810 | 4 | PULASKI | IS 44 W | CD0111 | 0.761 | N |  | Add auxiliary lanes from 1 mile east of Rte. H to 0.1 mile west of Superior Road and eastbound I-44 from Superior Road to 0.7 mile west of Rte. 66 Trail. | Federal | 4493 | 499 | 0 | 4992 | 0 | NHPP | CD0112 | 0 | 3 | 144 | 710 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
811 | 4 | PULASKI | IS 44 W | CD0112 | 0 | N |  | Ramp improvements at westbound on-ramp at Loop 44 in St. Robert. | Federal | 653 | 73 | 0 | 726 | 0 | NHPP | CD0111 | 0 | 5 | 5 | 112 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 594 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
812 | 4 | PULASKI | LP 44 E | 5S3480 | 0.2 | N |  | Bridge improvement over I-44. Project involves bridges A0803 and twin bridges A0801. | Federal | 1705 | 426 | 0 | 2133 | 0 | NHPP |  | 2 | 108 | 349 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1674 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
813 | 4 | PULASKI | LP 44 E | CD0128 | 3.788 | N |  | Upgrade pedestrian facilities to comply with the ADA Transition Plan in St. Robert and Waynesville. $1,855,000 Statewide Transportation Alternatives funds. | Adv. CN | 2140 | 535 | 0 | 2675 | 0 | AC-STBG |  | 0 | 10 | 200 | 453 | 0 | 0 | 0 | 0 | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1968 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
814 | 4 | PULASKI | SP 44 E | CD0127 | 2.221 | N |  | Upgrade pedestrian facilities to comply with the ADA Transition Plan in St. Robert. $1,064,000 Statewide Transportation Alternatives funds. | Adv. CN | 1204 | 301 | 0 | 1505 | 0 | AC-STBG |  | 0 | 9 | 100 | 267 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
815 | 4 | PULASKI | MO 7 S | 5P3544 | 0.12 | N |  | Bridge improvement over Gasconade River. Project involves bridge A0843. | Federal | 172 | 43 | 0 | 216 | 0 | NHPP |  | 1 | 1 | 1 | 1 | 1 | 39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
816 | 4 | PULASKI | MO 7 S | CD0031 | 0.042 | N |  | Bridge improvement over I-44. Project involves bridge A3051. | Federal | 725 | 181 | 0 | 906 | 0 | NHPP |  | 0 | 1 | 1 | 47 | 137 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 720 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
817 | 4 | PULASKI | RT AB E | CD0087 | 7.064 | N |  | Pavement improvement from I-44 to Rte. 17. Includes Rte. Z from Rte. Y to Rte. J. | Adv. CN | 199 | 50 | 0 | 249 | 0 | AC-STBG |  | 0 | 1 | 2 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
818 | 4 | PULASKI | RT Y S | 5S3312 | 0.08 | N |  | Payment to St. Robert to add sidewalks and upgrade signalized intersection at St. Robert Boulevard in St. Robert. | Adv. CN | 544 | 136 | 0 | 684 | 0 | AC-STBG |  | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 679 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
819 | 4 | PULASKI | RT Y S | 5S3352 | 17.145 | N |  | Pavement improvement and add rumblestripes from I-44 outer road to end of state maintenance. Pavement improvement on Rte. W from Rte. 7 to end of state maintenance and Rte. O from Rte. 28 to end of state maintenance. $179,000 Open Container funds. | Adv. CN | 1813 | 453 | 0 | 2274 | 0 | AC-STBG |  | 8 | 20 | 167 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2078 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
820 | 4 | PULASKI | RT Y S | 5S3510 | 0.056 | N |  | Bridge rehabilitation over I-44. Project involves twin bridges A0802. | Federal | 861 | 215 | 0 | 1086 | 0 | NHPP |  | 10 | 226 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
821 | 4 | VARIOUS | Various | 5B0800T | 0 | Y |  | Payback beginning in SFY 2008 for Safe and Sound bridges in the Central District. | Federal | 0 | 21995 | 0 | 75692 | 25,001 - 50,000 | STATE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 107 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 107 | 0 | 0 | 0 | 0 | 0 | 0 | 53590 | 4399 | 4399 | 4399 | 4399 | 4399 | 0
822 | 4 | VARIOUS | Various | 5P3485 | 0 | Y |  | Job Order Contracting for guard cable and guardrail repair on various routes in the northern portion of the Central District. | Adv. CN | 1884 | 471 | 0 | 2356 | 0 | AC-STBG |  | 1 | 155 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
823 | 4 | VARIOUS | Various | 5P3486 | 0 | N |  | Job Order Contracting for guard cable and guardrail repair on various routes in the southern portion of the Central District. | Adv. CN | 2055 | 514 | 0 | 2570 | 0 | AC-STBG |  | 1 | 169 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
824 | 4 | VARIOUS | Various | 5P3487 | 0 | Y |  | Job Order Contracting for guard cable and guardrail repair on various routes in the northern portion of the Central District. | Adv. CN | 2174 | 543 | 0 | 2718 | 0 | AC-STBG |  | 1 | 1 | 1 | 169 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2546 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
825 | 4 | VARIOUS | Various | 5P3488 | 0 | N |  | Job Order Contracting for guard cable and guardrail repair on various routes in the southern portion of the Central District. | Adv. CN | 2354 | 589 | 0 | 2944 | 0 | AC-STBG |  | 1 | 1 | 1 | 183 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2758 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
826 | 4 | VARIOUS | Various | 5P3495 | 0 | Y |  | On-call work zone enforcement at various locations in the Central District. | Federal | 58 | 6 | 0 | 64 | 0 | SAFETY |  | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
827 | 4 | VARIOUS | Various | 5P3521 | 0 | Y |  | On-call work zone enforcement at various locations in the Central District. | Federal | 58 | 6 | 0 | 64 | 0 | SAFETY |  | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
828 | 4 | VARIOUS | Various | CD0004 | 0 | Y |  | Job Order Contracting for guard cable and guardrail repair on various routes in the northern portion of the Central District. | Adv. CN | 2490 | 623 | 0 | 3113 | 0 | AC-STBG |  | 0 | 1 | 1 | 1 | 1 | 183 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2926 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
829 | 4 | VARIOUS | Various | CD0005 | 0 | N |  | Job Order Contracting for guard cable and guardrail repair on various routes in the southern portion of the Central District. | Adv. CN | 2682 | 670 | 0 | 3352 | 0 | AC-STBG |  | 0 | 1 | 1 | 1 | 1 | 197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3151 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
830 | 4 | VARIOUS | Various | CD0006 | 0 | Y |  | On-call work zone enforcement at various locations in the Central District. | Federal | 58 | 6 | 0 | 64 | 0 | SAFETY |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
831 | 4 | WASHINGTON | MO 185 S | 5S3557 | 0.03 | N |  | Bridge improvement over Miller Swan Brook. Project involves bridge A0761. | Federal | 472 | 118 | 0 | 591 | 0 | NHPP |  | 1 | 1 | 1 | 28 | 90 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 470 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
832 | 4 | WASHINGTON | MO 185 S | CD0034 | 0.04 | N |  | Bridge improvement over Bates Creek. Project involves bridge A0760. | Federal | 681 | 170 | 0 | 851 | 0 | NHPP |  | 0 | 1 | 1 | 1 | 57 | 145 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 646 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
833 | 4 | WASHINGTON | MO 21 S | CD0092 | 32.227 | N |  | Pavement improvement from Jefferson County line to Rte. 32 in Iron County. | Adv. CN | 6047 | 1512 | 0 | 7559 | 0 | AC-STBG |  | 0 | 1 | 1 | 1 | 1 | 603 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6952 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
834 | 4 | WASHINGTON | MO 47 S | 5P3516 | 0.08 | N |  | Bridge improvement over Mineral Fork Creek. Project involves bridge A3775. | Federal | 1278 | 320 | 0 | 1615 | 0 | NHPP | 5P3524 | 17 | 87 | 244 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1267 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
835 | 4 | WASHINGTON | MO 47 S | 5S3540 | 0.03 | N |  | Bridge improvement over Mill Creek. Project involves bridge R0514. | Federal | 533 | 133 | 0 | 668 | 0 | NHPP |  | 2 | 4 | 56 | 78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 528 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
836 | 4 | WASHINGTON | MO 8 E | 5P3522 | 0.08 | N |  | Bridge improvement over Union Pacific Railroad. Project involves bridge A1997. | Federal | 1004 | 251 | 0 | 1262 | 0 | NHPP |  | 7 | 47 | 217 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 991 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
837 | 4 | WASHINGTON | MO 8 E | 5P3524 | 0.03 | N |  | Bridge improvement over Bates Creek. Project involves bridge A4741. | Federal | 175 | 44 | 0 | 221 | 0 | NHPP | 5P3516 | 2 | 9 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 173 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
838 | 4 | WASHINGTON | MO 8 E | 5P3558 | 0.074 | N |  | Bridge improvement over Allen Creek, over Mid Fork Fourche a Renault and over North Fork Fourche a Renault. Project involves bridges A1437, A1438 and A1439. | Federal | 2006 | 501 | 0 | 2508 | 0 | NHPP |  | 1 | 1 | 1 | 98 | 413 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1994 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
839 | 4 | WASHINGTON | RT A E | 5S3478 | 0.121 | N |  | Bridge replacement over Cyclone Hollow and over Richwoods Creek. Project involves bridges R0313 and Y0412. | Federal | 1055 | 264 | 0 | 1445 | 0 | NHPP |  | 126 | 302 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 997 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
840 | 4 | WASHINGTON | RT C E | 5S3506 | 0.056 | N |  | Bridge improvement over Big River near Belgrade. Project involves bridge T0114. | Federal | 1887 | 472 | 0 | 2361 | 0 | NHPP |  | 2 | 1 | 111 | 469 | 0 | 0 | 0 | 0 | 0 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1747 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
841 | 4 | WASHINGTON | RT E S | 5S3369 | 2.417 | N |  | Upgrade pedestrian facilities to comply with the ADA Transition Plan and address nonstandard ADA facilities in Hermann, Rosebud, Bland, Potosi, Bourbon and Vienna. $197,000 Statewide Transportation Alternatives funds. | Adv. CN | 923 | 231 | 0 | 2214 | 0 | AC-STBG |  | 1060 | 163 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 977 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
842 | 4 | WASHINGTON | RT T S | 5S3556 | 0.05 | N |  | Bridge improvement over Big Indian Creek. Project involves bridge W0217. | Federal | 227 | 57 | 0 | 285 | 0 | NHPP |  | 1 | 1 | 1 | 13 | 42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 227 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
843 | 4 | WASHINGTON | RT W S | CD0032 | 0.023 | N |  | Bridge improvement over Ashley Branch. Project involves bridge R0442. | Federal | 416 | 104 | 0 | 520 | 0 | NHPP |  | 0 | 1 | 1 | 21 | 84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 413 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
844 | 5 | FRANKLIN | MO 100 E | 6P3561 | 1.966 | Y | 7216Y-22 | Pavement resurfacing, upgrade guardrail and upgrade pedestrian facilities to comply with the ADA Transition Plan from Washington Crossing to east of Fifth Street. | Federal | 1586 | 397 | 0 | 2029 | 0 | NHPP |  | 36 | 141 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1842 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
845 | 5 | FRANKLIN | MO 100 E | 6P3635 | 8.676 | Y | 7217M-22 | Pavement resurfacing from Rte. OO to 0.8 mile east of Rte. 109. | Federal | 10806 | 2701 | 0 | 13607 | 0 | NHPP |  | 100 | 200 | 347 | 563 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12397 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
846 | 5 | FRANKLIN | MO 100 E | 6S3583B | 0.126 | Y |  | Replace signals at Rte. At and on South Woods Mill Road at South Outer Forty Drive in St. Louis County. | Adv. CN | 560 | 140 | 0 | 700 | 0 | AC-STBG |  | 0 | 0 | 40 | 49 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 610 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
847 | 5 | FRANKLIN | MO 100 E | SL0035 | 7.189 | Y | 7228K-23 | Pavement resurfacing, pavement repairs and upgrade guardrails on eastbound lanes from Dubois Creek to Rte. AT. | Adv. CN | 2206 | 551 | 0 | 2757 | 0 | AC-STBG | SL0036 SL0060 | 0 | 100 | 200 | 243 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2214 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
848 | 5 | FRANKLIN | MO 100 E | SL0036 | 8.615 | Y | 7228L-23 | Pavement resurfacing, pavement repairs and upgrade guardrail from Rte. AT to 0.7 mile east of Rte. OO. | Adv. CN | 2026 | 506 | 0 | 2532 | 0 | AC-STBG | SL0035 SL0060 | 0 | 150 | 300 | 173 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
849 | 5 | FRANKLIN | MO 100 E | SL0060 | 0.652 | Y | 7229I-23 | Bridge rehabilitation from Rte. M to Old Highway 100. Project involves bridges H0353 and A7453. | Federal | 986 | 246 | 0 | 1232 | 0 | NHPP | SL0035 SL0036 | 0 | 20 | 50 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1082 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
850 | 5 | FRANKLIN | MO 100 E | SL0085 | 28.63 | Y | 7230B-23 | Pavement preservation treatment from Yeates Road to Rte. KK and on Rte. YY from Rte. 185 to Rte. A. Potential pavement preservation treatment on Rte. 185 from Rte. 100 to Rte. 50. | Adv. CN | 618 | 154 | 0 | 772 | 0 | AC-STBG |  | 0 | 78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 694 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
851 | 5 | FRANKLIN | MO 30 E | 6S3435 | 31.419 | Y | 6990Y-20 | Pavement resurfacing, bridge replacement, upgrade guardrail and upgrade pedestrian facilities to comply with the ADA Transition Plan from I-44 North Outer Road to Rte. PP. Project involves bridges H0995 and H0994. | Adv. CN | 22526 | 5632 | 0 | 29309 | 0 | AC-STBG |  | 1151 | 750 | 1805 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
852 | 5 | FRANKLIN | IS 44 E | SL0038 | 14.864 | Y | 7228N-23 | Pavement resurfacing from the Crawford County line to Rte. 30. | Federal | 5428 | 603 | 0 | 6031 | 0 | NHPP |  | 0 | 50 | 250 | 200 | 374 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5157 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
853 | 5 | FRANKLIN | IS 44 E | SL0048 | 4.754 | Y | 7228X-23 | Pavement resurfacing and upgrade guardrail from Rte. 100 to Viaduct Street. | Federal | 4522 | 502 | 0 | 5024 | 0 | NHPP |  | 0 | 25 | 50 | 300 | 200 | 279 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4170 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
854 | 5 | FRANKLIN | IS 44 E | SL0114 | 69.235 | Y | 7265A-23 | Striping upgrades in Franklin and St. Louis Counties and St. Louis City. | Federal | 1566 | 174 | 0 | 1740 | 0 | SAFETY |  | 0 | 159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1581 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
855 | 5 | FRANKLIN | IS 44 W | SL0063 | 0.126 | Y | 7227V-23 | Bridge rehabilitation at Rte. 50, Rte. AH and Outer Road 44. Project involves bridges L0930, A2018 and A2089. | Federal | 641 | 71 | 0 | 712 | 0 | NHPP |  | 0 | 5 | 10 | 40 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 613 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
856 | 5 | FRANKLIN | N OR 44 E | 6S3609 | 17.931 | Y | 7219V-22 | Pavement resurfacing, pavement repairs and upgrade guardrail from Crawford County line to Rte. 47 and South Outer Road from Rte. WW to Rte. AF. | Adv. CN | 4172 | 1043 | 0 | 5265 | 0 | AC-STBG |  | 50 | 200 | 423 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4592 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
857 | 5 | FRANKLIN | MO 47 S | SL0033 | 1.325 | Y | 7228I-23 | Pavement resurfacing and upgrade guardrail from 0.1 mile north of Missouri Avenue to Rte. 100. | Adv. CN | 998 | 249 | 0 | 1247 | 0 | AC-STBG |  | 0 | 100 | 100 | 158 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 889 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
858 | 5 | FRANKLIN | MO 47 S | SL0082 | 12.366 | Y | 7218A-23 | Safety and capacity improvements from Washington to St. Clair (Phase I). Potential Design-Build. | Federal | 68594 | 17148 | 0 | 85742 | 0 | NHPP |  | 0 | 10 | 200 | 2000 | 2000 | 4670 | 0 | 0 | 0 | 0 | 0 | 1093 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
859 | 5 | FRANKLIN | US 50 E | 6P2350 | 0.575 | Y | 5307A-11 | Intersection improvements from 0.4 mile west of Rte. AT to I-44. Project involves bridge A6361. | Federal | 5842 | 1461 | 0 | 7806 | 0 | NHPP |  | 503 | 300 | 400 | 494 | 0 | 0 | 0 | 0 | 0 | 1545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4564 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
860 | 5 | FRANKLIN | US 50 E | 6P3436 | 2.419 | Y | 6990Z-20 | Pavement resurfacing, upgrade guardrail, drainage pipe replacement and upgrade pedestrian facilities to comply with the ADA Transition Plan from 0.5 mile west of Independence Drive to Rte. 47. | Federal | 4949 | 1237 | 0 | 7065 | 0 | NHPP |  | 691 | 444 | 0 | 0 | 0 | 0 | 0 | 188 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5742 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
861 | 5 | FRANKLIN | US 50 E | SL0047 | 9.107 | Y | 7228W-23 | Pavement resurfacing, pavement repairs and upgrade guardrail from the Gasconade County line to Rte. C and from Rte. BB to Independence Drive. | Federal | 8018 | 2005 | 0 | 10023 | 0 | NHPP |  | 0 | 250 | 350 | 666 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8757 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
862 | 5 | FRANKLIN | US 50 E | SL0067 | 0.272 | Y | 7229O-23 | Bridge rehabilitation over the Bourbeuse River. Project involves bridges A3961 and A4047. | Federal | 3398 | 850 | 0 | 4248 | 0 | NHPP |  | 0 | 10 | 10 | 50 | 250 | 254 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3674 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
863 | 5 | FRANKLIN | RT A S | SL0049 | 8.083 | Y | 7228Y-23 | Pavement resurfacing and pavement repair from Rte. 100 to Rte. 47. | Adv. CN | 1442 | 361 | 0 | 1803 | 0 | AC-STBG |  | 0 | 4 | 45 | 100 | 150 | 134 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1370 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
864 | 5 | FRANKLIN | RT AB S | SL0050 | 2.037 | Y | 7228Z-23 | Pavement resurfacing and pavement repairs from end of state maintenance to I-44 North Outer Road. | Adv. CN | 242 | 61 | 0 | 303 | 0 | AC-STBG |  | 0 | 5 | 20 | 25 | 50 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 168 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
865 | 5 | FRANKLIN | RT AP E | SL0031 | 0.748 | Y | 7228G-23 | Pavement resurfacing from Rte. NN to end of state maintenance. | Adv. CN | 134 | 34 | 0 | 168 | 0 | AC-STBG |  | 0 | 25 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
866 | 5 | FRANKLIN | RT CC S | 6S3563 | 0.006 | Y | 7219K-22 | Replace box culvert over branch of Big Creek. Project involves culvert R0840. | Adv. CN | 265 | 66 | 0 | 358 | 0 | AC-STBG |  | 27 | 67 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 254 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
867 | 5 | FRANKLIN | RT F S | SL0034 | 2.081 | Y | 7228J-23 | Pavement resurfacing and upgrade guardrail from Pacific Street to Rte. O. | Adv. CN | 1046 | 261 | 0 | 1307 | 0 | AC-STBG | SL0037 SL0043 | 0 | 50 | 200 | 205 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
868 | 5 | FRANKLIN | RT K S | SL0059 | 14.337 | Y | 7229H-23 | Bridge rehabilitation over the Meramec River and bridge replacements over the Brush Creek in two locations. Project involves bridges A3871, A8533 and A8534. | Adv. CN | 2559 | 640 | 0 | 3199 | 0 | AC-STBG |  | 0 | 50 | 150 | 229 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
869 | 5 | FRANKLIN | RT KK E | 6S3619 | 10.033 | Y | 7219Y-22 | Pavement resurfacing from Rte. C to Rte. 185 and Rte. 185 to Rte. 100. | Adv. CN | 2608 | 652 | 0 | 3410 | 0 | AC-STBG |  | 150 | 150 | 265 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2845 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
870 | 5 | FRANKLIN | RT MM S | 6S3368 | 4.138 | Y | 6852O-18 | Pavement resurfacing, upgrade guardrail, curve realignment, add shoulders and extend box culverts from Rte. T to Rte. 100. Project involves culverts X0926 and X0913. | Adv. CN | 5399 | 1350 | 0 | 8302 | 0 | AC-STBG |  | 553 | 240 | 412 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6097 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
871 | 5 | FRANKLIN | RT N S | 6S3630 | 10.396 | Y | 7220E-22 | Pavement resurfacing, pavement repairs and upgrade guardrail from Rte. O to Rte. 30 and Rte. O to end of state maintenance. | Adv. CN | 2350 | 588 | 0 | 3088 | 0 | AC-STBG |  | 150 | 200 | 218 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2520 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
872 | 5 | FRANKLIN | RT NN S | SL0043 | 10.263 | Y | 7228S-23 | Pavement resurfacing and upgrade guardrail from Rte. O to Rte. 30. | Adv. CN | 1812 | 453 | 0 | 2265 | 0 | AC-STBG | SL0034 SL0037 | 0 | 100 | 100 | 219 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1846 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
873 | 5 | FRANKLIN | RT O E | SL0037 | 12.128 | Y | 7228M-23 | Pavement resurfacing, pavement repairs and upgrade guardrail from Rte. AT to Rte. F. | Adv. CN | 3426 | 857 | 0 | 4283 | 0 | AC-STBG | SL0034 SL0043 | 0 | 100 | 250 | 380 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3553 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
874 | 5 | FRANKLIN | RT PP S | SL0032 | 6.717 | Y | 7228H-23 | Pavement resurfacing and upgrade guardrail from Rte. 30 to end of state maintenance. | Federal | 0 | 1490 | 0 | 1490 | 0 | STATE |  | 0 | 50 | 136 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1289 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
875 | 5 | FRANKLIN | RT T E | 6S3611 | 14.976 | Y | 7219W-22 | Pavement resurfacing, pavement repairs and upgrade guardrail from Rte. 100 to Rte. 100. | Adv. CN | 3817 | 954 | 0 | 4871 | 0 | AC-STBG |  | 100 | 250 | 329 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4192 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
876 | 5 | FRANKLIN | RT VV S | SL0068 | 0.715 | Y | 7230O-23 | Culvert rehabilitations on Rte. VV over Rohlfing Creek, Rte. UU over Buesher Creek, I-44 over Branch of Bourbeuse River, Rte. OO over Little Fox Creek and Rte. PP over Branch of Meramec River. Project involves culverts N0820, A4693, L0355, R0261 and N0351. | Adv. CN | 505 | 126 | 0 | 631 | 0 | AC-STBG |  | 0 | 5 | 35 | 45 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 541 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
877 | 5 | FRANKLIN | RT Y N | 6S2319 | 0.22 | Y | 5305D-11 | Bridge replacement over Cedar Fork Creek. Project involves bridge X0489. | Federal | 1405 | 351 | 0 | 1796 | 0 | NHPP |  | 40 | 200 | 116 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
878 | 5 | FRANKLIN | RT YY E | 6S3369 | 15.528 | Y | 6852P-18 | Pavement repair and upgrade guardrail from Rte. Y to Rte. 185 and Rte. E from Gasconade County line to Rte. 100. | Adv. CN | 3728 | 932 | 0 | 4912 | 0 | AC-STBG |  | 252 | 100 | 378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
879 | 5 | JEFFERSON | MO 110 E | SL0069 | 0.453 | Y | 7229P-23 | Bridge rehabilitation on Rte. 110 over Union Pacific Railroad and Joachim Creek and on Rte. 61 over Rock Creek. Project involves bridges A3616 and A4588. | Adv. CN | 1510 | 378 | 0 | 1888 | 0 | AC-STBG |  | 0 | 30 | 100 | 135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1623 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
880 | 5 | JEFFERSON | MO 21 S | 6P3288 | 0.854 | Y | 6806N-18 | Bridge rehabilitation at various locations on and over Rte. 21. Project involves bridges A2941, A2942, A2943, A2944, A2945, A2956, A2957, A2958, A2959, A2977, A3097, A3098, A3099, A3100, A3101, A5529 and A5530. | Federal | 10583 | 2646 | 0 | 13885 | 0 | NHPP |  | 656 | 896 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
881 | 5 | JEFFERSON | MO 21 S | 6S3283B | 11.218 | Y | 6798RR-23 | Pavement resurfacing and upgrade guardrail from Meramec River to Schenk Road and on Old Rte. 21 from Rte. 21 to Konert Road. $8,470,000 District Operation funds. | Federal | 13475 | 3369 | 0 | 16844 | 0 | NHPP |  | 0 | 2046 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14798 | 0 | 0 | 0 | 0 | 0 | 0 | 8470 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
882 | 5 | JEFFERSON | MO 21 S | SL0044 | 13.981 | Y | 7228T-23 | Pavement resurfacing and upgrade guardrail from Rte. B to the Washington County line. | Adv. CN | 4050 | 1012 | 0 | 5062 | 0 | AC-STBG |  | 0 | 50 | 175 | 175 | 323 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4339 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
883 | 5 | JEFFERSON | MO 231 S | SL0042 | 2.189 | Y | 7228R-23 | Pavement resurfacing and upgrade guardrail from the Meramec River to Rte. 61. | Federal | 873 | 218 | 0 | 1091 | 0 | NHPP | 6S3631 6S3632 | 0 | 50 | 150 | 101 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 790 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
884 | 5 | JEFFERSON | MO 30 E | SL0046 | 5.593 | Y | 7228V-23 | Pavement resurfacing and pavement repairs from Rte. PP to the St. Louis County line. | Federal | 2934 | 734 | 0 | 3668 | 0 | NHPP |  | 0 | 10 | 20 | 70 | 150 | 244 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3174 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
885 | 5 | JEFFERSON | IS 55 N | 6I3290 | 0.284 | Y | 6806L-18 | Bridge rehabilitation over the Meramec River. Project involves bridge A0609. | Federal | 12851 | 1428 | 0 | 14640 | 0 | NHFP |  | 361 | 300 | 300 | 850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12829 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
886 | 5 | JEFFERSON | IS 55 N | 6I3484 | 43.199 | Y | 6991D-20 | Replace structural signs from St. Genevieve County line to I-44. | Federal | 3790 | 421 | 0 | 4921 | 0 | NHPP |  | 710 | 5 | 194 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4012 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
887 | 5 | JEFFERSON | IS 55 S | 6I3526B | 18.09 | Y | 6992HH-24 | Improve capacity, pavement, bridges, safety and operations from Rte M to 1 mile south of Rte 67; safety and operations on Rte 67 from Rte 61 to Buck Creek Rd and pavement and signals on Rte A from Collins Rd to Rte 61. Design-Build. Potentially involves various bridges. | Adv. CN | 194193 | 48548 | 0 | 245641 | 0 | AC-STBG |  | 2900 | 28249 | 0 | 0 | 0 | 0 | 0 | 0 | 1005 | 0 | 0 | 0 | 0 | 0 | 0 | 213487 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
888 | 5 | JEFFERSON | IS 55 S | SL0005 | 65.872 | Y | 7227L-23 | Bridge deck sealing on various bridges in Franklin and Jefferson Counties. Project involves bridges on I-44, Rte. 185 and Rte. AT in Franklin County and bridges on I-55, Rte. 61, Rte. 21 and Rte. V in Jefferson County. | Federal | 1540 | 171 | 0 | 1711 | 0 | NHPP |  | 0 | 15 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
889 | 5 | JEFFERSON | US 61 N | 6S3289 | 0.919 | Y | 6892C-18 | Bridge replacement over Joachim Creek between Scenic Drive and Herky-Horine Road. Slide repair north of Herky-Horine Road to Joachim Avenue. Project involves bridge K0294. | Adv. CN | 11742 | 2936 | 0 | 16634 | 0 | AC-STBG | 6S3391 6S3399 | 1031 | 50 | 917 | 0 | 0 | 0 | 0 | 925 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13711 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
890 | 5 | JEFFERSON | US 61 N | 6S3391 | 1.078 | Y | 6887D-19 | Add center turn lane and pavement resurfacing from Brandon Wallace Way to 6th Street in Crystal City. | Federal | 2817 | 313 | 0 | 3416 | 0 | SAFETY | 6S3289 6S3399 | 201 | 100 | 224 | 0 | 0 | 0 | 0 | 85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2806 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
891 | 5 | JEFFERSON | US 61 N | 6S3399 | 10.972 | Y | 6892R-19 | Pavement resurfacing, upgrade guardrail and upgrade pedestrian facilities to comply with the ADA Transition Plan from Rte. 67 to Rte. M. Project involves culverts G0511, G0512 and G0641. | Federal | 10095 | 2524 | 0 | 13389 | 0 | NHPP | 6S3289 6S3391 | 770 | 40 | 694 | 0 | 0 | 0 | 0 | 0 | 1470 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10415 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
892 | 5 | JEFFERSON | US 61 S | 6S3640 | 0.339 | Y | 7220J-22 | Signalize intersection and add intersection turn lanes at Miller Road and St. John's Church Road. | Federal | 1730 | 192 | 0 | 2026 | 0 | SAFETY |  | 104 | 100 | 119 | 0 | 0 | 0 | 0 | 0 | 139 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1564 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
893 | 5 | JEFFERSON | RT C S | SL0040 | 4.658 | Y | 7228P-23 | Pavement resurfacing, pavement repairs and upgrade guardrail from Rte. B to Rte. Y. | Adv. CN | 1518 | 380 | 0 | 1898 | 0 | AC-STBG |  | 0 | 200 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
894 | 5 | JEFFERSON | RT CC S | SL0041 | 5.737 | Y | 7228Q-23 | Pavement resurfacing and upgrade guardrail from Rte. 67 to Rte. 110. | Adv. CN | 1123 | 281 | 0 | 1404 | 0 | AC-STBG |  | 0 | 200 | 169 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
895 | 5 | JEFFERSON | RT M E | 6S3432 | 1.224 | Y | 6991A-19 | Add J-turns at St. Luke's Church Road and Moss Hollow Road. | Federal | 1429 | 159 | 0 | 1764 | 0 | SAFETY |  | 176 | 103 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1485 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
896 | 5 | JEFFERSON | RT M E | 6S3652 | 6.731 | Y |  | Pavement resurfacing from Rte. 21 to Metropolitan Boulevard. | Federal | 1417 | 354 | 0 | 1786 | 0 | NHPP |  | 15 | 70 | 125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
897 | 5 | JEFFERSON | RT MM E | 6S3575 | 4.343 | Y | 7219N-22 | Pavement resurfacing and upgrade guardrail from Rte. 30 to Buckeye Valley Road. | Federal | 1785 | 446 | 0 | 2356 | 0 | NHPP |  | 125 | 11 | 147 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2068 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
898 | 5 | JEFFERSON | RT P S | SL0039 | 8.625 | Y | 7228O-23 | Pavement resurfacing, pavement repairs and upgrade guardrail from Rte. A to Rte. 110. | Adv. CN | 1157 | 289 | 0 | 1446 | 0 | AC-STBG |  | 0 | 150 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1121 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
899 | 5 | JEFFERSON | RT PP E | SL0045 | 2.158 | Y | 7228U-23 | Pavement resurfacing, pavement repairs and upgrade guardrail from end of Byrnes Mill Road to Rte. 30. | Adv. CN | 575 | 144 | 0 | 719 | 0 | AC-STBG |  | 0 | 25 | 25 | 50 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 559 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
900 | 5 | JEFFERSON | RT T E | SL0066 | 0.098 | Y | 7229N-23 | Bridge rehabilitation at Plattin Creek. Project involves bridge A4789. | Adv. CN | 250 | 63 | 0 | 313 | 0 | AC-STBG |  | 0 | 20 | 26 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 237 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
901 | 5 | ST. CHARLES | MO 364 E | 6P3350 | 0.723 | Y | 6830AA-18 | Payment to St. Charles County for adding an interchange at Gutermuth Road. Project involves bridges A6105 and A6106. | Federal | 2410 | 602 | 0 | 3012 | 0 | NHPP |  | 0 | 112 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
902 | 5 | ST. CHARLES | MO 364 E | SL0056 | 0.504 | Y | 7229E-23 | Pavement repair at Rte. K. $500,000 District Operation funds. | Federal | 714 | 179 | 0 | 893 | 0 | NHPP |  | 0 | 128 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 765 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
903 | 5 | ST. CHARLES | MO 370 E | 6P3551 | 0.295 | Y | 7216V-22 | Bridge rehabilitations between I-70 and Rte. 94. Project involves bridges A5308, A5309, A5322, A5323, A5326, A5327, A5116, A5123, A4999 and A5109. | Federal | 5235 | 1309 | 0 | 6554 | 0 | NHPP |  | 10 | 90 | 200 | 574 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5680 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
904 | 5 | ST. CHARLES | MO 370 E | 6P3554 | 0.64 | Y | 7216W-22 | Bridge rehabilitation over the Missouri River. Project involves bridge A4557. | Federal | 36304 | 9076 | 0 | 45390 | 0 | NHPP |  | 10 | 500 | 1776 | 3558 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39546 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
905 | 5 | ST. CHARLES | MO 370 E | 6P3584 | 34.341 | Y | 7217A-22 | Striping and signage upgrade for wrong way countermeasures at various locations between I-70 and I-270 and Rte. 364 from Hawk Ridge Trail to I-270. | Federal | 503 | 56 | 0 | 579 | 0 | SAFETY |  | 20 | 59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
906 | 5 | ST. CHARLES | MO 370 E | 6P3603 | 0.564 | Y | 6964C | Add interchange flyover ramp onto westbound Salt River Road. $6,274,309 Cost Share and $7,499,310 St. Peters funds. | Federal | 7862 | 0 | 6974 | 15376 | 0 | NHPP |  | 540 | 410 | 1250 | 0 | 0 | 0 | 0 | 0 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12956 | 0 | 0 | 0 | 0 | 525 | 625 | 6349 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
907 | 5 | ST. CHARLES | MO 370 E | 6P3612 | 0.123 | Y | 7217J-22 | Bridge rehabilitation over Premier Parkway and Salt River Road over Rte. 370. Project involves bridges A5321, A5493 and A5494. $370,000 St. Peters funds. | Federal | 1547 | 17 | 370 | 1939 | 0 | NHPP |  | 5 | 67 | 187 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1680 | 0 | 0 | 0 | 0 | 0 | 0 | 370 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
908 | 5 | ST. CHARLES | MO 370 E | 6P3649 | 7.051 | Y | 7217U-22 | Pavement resurfacing from east of Elm Point Road to I-270. | Federal | 15567 | 3892 | 0 | 19509 | 0 | NHPP |  | 50 | 150 | 300 | 500 | 1611 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16898 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
909 | 5 | ST. CHARLES | E OR 61 S | SL0014 | 0.548 | Y | 7227P-23 | Pavement resurfacing from Pitman Avenue to end of state maintenance. | Federal | 0 | 126 | 0 | 126 | 0 | STATE |  | 0 | 1 | 1 | 6 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
910 | 5 | ST. CHARLES | US 61 S | 6P3331 | 0.245 | Y | 6811N-18 | Bridge rehabilitation at Pitman Avenue, I-70, I-64 and Rte. A in Wentzville. Project involves bridges A2755, A2756, L0428, A2543, L0624, A4236 and A4237. | Federal | 5434 | 1359 | 0 | 6946 | 0 | NHPP |  | 153 | 250 | 200 | 432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5911 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
911 | 5 | ST. CHARLES | US 61 S | SL0019 | 3.66 | Y | 7227U-23 | Intersection safety upgrades at Rte. W, North Point Prairie Road, McHugh Road and Timber Trace Drive. | Federal | 1642 | 182 | 0 | 1824 | 0 | SAFETY |  | 0 | 5 | 100 | 128 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1591 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
912 | 5 | ST. CHARLES | US 61 S | SL0083 | 6.044 | Y | 7229Z-23 | Safety and operational improvements from Lincoln County to I-64 (Phase I). Potential Design-Build. | Federal | 36905 | 9226 | 0 | 46131 | 0 | NHPP |  | 0 | 200 | 200 | 1000 | 2000 | 2550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40181 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
913 | 5 | ST. CHARLES | IS 64 E | 6I3033 | 9.992 | Y | 7220M-22 | Capacity improvements from I-70 to Rte. K. Potential Design-Build. Project involves bridges A1456 and A6754. | Federal | 39454 | 4384 | 0 | 43968 | 0 | NHPP |  | 130 | 500 | 1500 | 3468 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38370 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
914 | 5 | ST. CHARLES | IS 64 E | 6I3479 | 5.183 | Y | 6991E-20 | Pavement repair, pavement preservation treatment and upgrade guardrail from west of Rte. DD to Rte. 94. Potential-Design Build. | Federal | 2134 | 237 | 0 | 2431 | 0 | NHPP |  | 60 | 10 | 10 | 205 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
915 | 5 | ST. CHARLES | IS 64 E | 6I3550 | 1.853 | Y | 7171N-22 | Bridge rehabilitations at various locations in St. Louis District. Project involves bridges A6752, A6753, A4169, A5962, A5985, A6475, A6657, A7233, A7323, A6014, A6052, A6083, A6190, A7046, A7122, A7080, A7081, A8004, A8016, A8020, A8022, A8028, A8029, A8033 and A8036. | Federal | 6760 | 751 | 0 | 7611 | 0 | NHPP | 6I3540 | 100 | 659 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
916 | 5 | ST. CHARLES | IS 64 E | 6I3650 | 51.952 | Y | 7216G-22 | Replace structural signs from I-70 to the Mississippi River and on I-170 from I-270 to Eager Road. | Federal | 4819 | 535 | 0 | 5359 | 0 | NHPP |  | 5 | 5 | 650 | 567 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4132 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
917 | 5 | ST. CHARLES | IS 64 E | SL0057 | 6.571 | Y | 7229F-23 | Interchange improvements at I-64 and I-70 interchange (Phase 1). Potential Design-Build. | Federal | 83645 | 9294 | 0 | 92939 | 0 | NHPP |  | 0 | 1000 | 4000 | 5750 | 0 | 0 | 0 | 0 | 0 | 1030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 81159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
918 | 5 | ST. CHARLES | N OR 64 W | SL0013 | 10.693 | Y | 7227O-23 | Pavement resurfacing, upgrade guardrail and upgrade pedestrian facilities to comply with the ADA Transition Plan on disconnected sections from Warsen Avenue to Wolfrum Road and Rte. N from Spring Borough Drive to La Le Drive. | Adv. CN | 5919 | 1480 | 0 | 7399 | 0 | AC-STBG |  | 0 | 5 | 100 | 300 | 467 | 0 | 0 | 0 | 0 | 0 | 53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6474 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
919 | 5 | ST. CHARLES | N OR 64 W | SL0016 | 0.04 | Y | 7227R-23 | Bridge replacement over Peruque Creek. Project involves bridge J0991. | Adv. CN | 1878 | 469 | 0 | 2347 | 0 | AC-STBG |  | 0 | 5 | 50 | 50 | 70 | 158 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2014 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
920 | 5 | ST. CHARLES | N OR 64 W | SL0112 | 0.036 | Y | 7265C-23 | Bridge replacement over Dardenne Creek. Project involves bridge A1458. | Adv. CN | 1841 | 460 | 0 | 2301 | 0 | AC-STBG |  | 0 | 50 | 50 | 100 | 128 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1973 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
921 | 5 | ST. CHARLES | S OR 64 W | 6S3507 | 1.005 | Y | 6961A-20 | Payment to St. Charles County for construction of Interstate Drive from east of Quail Ridge Park to Prospect Road. $1,524,500 Cost Share funds. | Adv. CN | 1232 | 308 | 0 | 1540 | 0 | AC-STBG |  | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1525 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
922 | 5 | ST. CHARLES | US 67 S | 6P3414 | 0.188 | Y | 7216O-24 | Payment to IDOT for inspection of stay cables on the Clark Bridge. Project involves bridge A4278. | Federal | 601 | 150 | 0 | 751 | 0 | NHPP |  | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
923 | 5 | ST. CHARLES | US 67 S | 6P3570 | 6.117 | Y | 6992U-21 | Pavement repair, pavement resurfacing and replace signals from Rte. 367 to the Mississippi River bridge and outer road between Riverlands Way and the Mississippi River. | Federal | 5603 | 1401 | 0 | 7354 | 0 | NHPP | 6P3636 | 350 | 100 | 525 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6379 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
924 | 5 | ST. CHARLES | US 67 S | 6P3636 | 1.27 | Y | 7217N-22 | Add J-turns between Rte. 94 and the Missouri River. | Federal | 1886 | 210 | 0 | 2146 | 0 | SAFETY | 6P3570 | 50 | 75 | 197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
925 | 5 | ST. CHARLES | US 67 S | SL0088 | 0.419 | Y | 7230E-26 | Payback to IDOT for bridge deck sealing on the Clark Bridge over the Mississippi River. Project involves bridge A4278. | Federal | 129 | 32 | 0 | 161 | 0 | NHPP |  | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 0 | 0
926 | 5 | ST. CHARLES | US 67 S | SL0107 | 0.635 | Y | 7230M-23 | Bridge preventative maintenance and upgrade drainage on the Lewis Bridge. Project involves bridge A3047. | Federal | 796 | 199 | 0 | 995 | 0 | NHPP |  | 0 | 5 | 5 | 5 | 5 | 61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 914 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
927 | 5 | ST. CHARLES | IS 70 E | 6I3490 | 0.168 | Y | 6990E-20 | Bridge rehabilitation on various bridges on I-70 and outer roads between Rte. K and Spencer Road. Project involves bridges L0710, L0711, A0856, G0337, A5256, A5257, G0336 and L0481. $2,587,000 District Operation funds. | Federal | 9335 | 1037 | 0 | 10819 | 0 | NHPP | 6I3613 6P3548 6S3488 | 447 | 757 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9615 | 0 | 0 | 0 | 0 | 0 | 0 | 2587 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
928 | 5 | ST. CHARLES | IS 70 E | 6I3542 | 0.798 | Y | 7171M-22 | Bridge washing on I-70, I-64, Rte. 370 and Rte. 21. Project involves bridges A4017, A3292, A4557, L0561 and K0637. $30,000 District Operations funds. | Federal | 539 | 60 | 0 | 600 | 0 | NHPP |  | 1 | 63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 536 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
929 | 5 | ST. CHARLES | IS 70 E | 6I3613 | 4.61 | Y | 7171W-22 | Pavement resurfacing and upgrade guardrail from Rte. K to 0.3 mile east of Mid Rivers Mall Drive. | Federal | 4046 | 450 | 0 | 4696 | 0 | NHPP | 6I3490 6P3548 6S3488 | 200 | 372 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4124 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
930 | 5 | ST. CHARLES | IS 70 E | SL0115 | 52.802 | Y | 7230Z-23 | Striping upgrades in St. Charles and St. Louis Counties and St. Louis City. | Federal | 1124 | 125 | 0 | 1249 | 0 | SAFETY |  | 0 | 127 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
931 | 5 | ST. CHARLES | IS 70 W | 6I0624 | 1.591 | Y | 5905-13 | Road realignment from Wentzville Parkway to west of I-64/Rte. 61. Project involves bridges A4320 and A4323. | Federal | 33575 | 3731 | 0 | 43293 | 0 | NHPP |  | 4292 | 1500 | 2676 | 0 | 0 | 0 | 0 | 1695 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
932 | 5 | ST. CHARLES | N OR 70 W | 6I3337Z | 4.154 | Y | 6806EE-21 | Payback to St. Charles County for corridor improvements from Cave Springs to Fairgrounds, bridge rehabilitations over I70 at Zumbehl and Cave Springs and modify interchange configuration at First Capitol. $7,500,000 Cost Share funds. | Federal | 0 | 5000 | 0 | 7500 | 0 | STATE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 2500 | 2500 | 0 | 0 | 0 | 0
933 | 5 | ST. CHARLES | S OR 70 E | 6S3667 | 1.207 | Y | 7220Q-22 | Pavement rehabilitation from west of Executive Center Parkway to Cave Springs Road. | Adv. CN | 459 | 115 | 0 | 579 | 0 | AC-STBG | 6S3486 6S3487 SL0018 | 5 | 48 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 491 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
934 | 5 | ST. CHARLES | MO 79 N | SL0015 | 0.018 | Y | 7227Q-23 | Bridge rehabilitations at various locations in St. Charles County. Project involves bridges A4728, A7043, A2348, A8539, A6157, A6755, A7103 and H0141. | Federal | 895 | 224 | 0 | 1119 | 0 | NHPP |  | 0 | 5 | 5 | 50 | 103 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 956 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
935 | 5 | ST. CHARLES | MO 79 S | 6P3483 | 9.04 | Y | 6991G-20 | Pavement resurfacing and upgrade guardrail from Dyer Road to divided pavement. | Adv. CN | 2320 | 580 | 0 | 3100 | 0 | AC-STBG |  | 200 | 226 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2674 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
936 | 5 | ST. CHARLES | MO 79 S | 6P3548 | 0.097 | Y | 7216U-21 | Bridge rehabilitation over I-70 and over Norfolk Southern Railroad and Outer Road 70. Project involves bridges A4294, A3896 and A4293. | Federal | 3210 | 802 | 0 | 4093 | 0 | NHPP | 6I3490 6I3613 6S3488 | 81 | 328 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3684 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
937 | 5 | ST. CHARLES | MO 79 S | 6P3555 | 0.888 | Y | 6992P-20 | Upgrade signals at TR Hughes Boulevard. $9,819 O'Fallon and $1,474,000 Congestion Mitigation and Air Quality Program funds. | Federal | 1833 | 448 | 10 | 2422 | 0 | CMAQ |  | 121 | 179 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2112 | 0 | 0 | 0 | 0 | 0 | 0 | 1484 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
938 | 5 | ST. CHARLES | MO 94 E | 6S3302 | 21.403 | Y | 6806D-18 | Pavement resurfacing and upgrade guardrail from Warren County line to I-64. | Adv. CN | 3856 | 964 | 0 | 4945 | 0 | AC-STBG |  | 125 | 389 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4431 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
939 | 5 | ST. CHARLES | MO 94 E | SL0011 | 6.705 | Y | 7227M-23 | Pavement resurfacing and upgrade guardrail from BNSF Railway to Rte. H/J. | Adv. CN | 786 | 196 | 0 | 982 | 0 | AC-STBG |  | 0 | 50 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
940 | 5 | ST. CHARLES | RT A E | 6S3530 | 3.37 | Y | 7026B-21 | Payment to St. Charles County for additional lanes and pavement resurfacing from Rte. 61 to I-70. $3,500,000 Governor's Cost Share Program funds. | Adv. CN | 2808 | 702 | 0 | 3515 | 0 | AC-STBG |  | 5 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3500 | 0 | 0 | 0 | 0 | 0 | 0 | 3500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
941 | 5 | ST. CHARLES | CST BRYAN RD S | 6S3488 | 0.048 | Y | 6990H-20 | Bridge rehabilitation at Bryan Road. Project involves bridge A5045. | Adv. CN | 2198 | 549 | 0 | 2947 | 0 | AC-STBG | 6I3490 6I3613 6P3548 | 200 | 230 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2517 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
942 | 5 | ST. CHARLES | RT D E | 6S3480 | 18.148 | Y | 6991H-20 | Pavement preservation treatment from Rte. Z to Rte. 94 and Rte. H from Rte. 94 to Rte. J. | Adv. CN | 1614 | 403 | 0 | 2047 | 0 | AC-STBG |  | 30 | 10 | 140 | 121 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1746 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
943 | 5 | ST. CHARLES | RT D E | SL0004 | 0.02 | Y | 7220V-22 | Culvert replacement 0.4 mile east of Rte. T. Project involves culvert T0755. | Adv. CN | 547 | 137 | 0 | 689 | 0 | AC-STBG |  | 5 | 50 | 58 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 564 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
944 | 5 | ST. CHARLES | CST HUSTER RD S | SL0018 | 0.57 | Y | 7227T-23 | Pavement resurfacing from south of Fountain Lakes Boulevard to Hayford Road. | Federal | 0 | 250 | 0 | 250 | 0 | STATE | 6S3486 6S3487 6S3667 | 0 | 19 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
945 | 5 | ST. CHARLES | I-64 I-70 | SL0152 | 0 | Y |  | Payback to St. Charles County for 6I3527 to study interchange improvements at I-64 and I-70. | Adv. CN | 788 | 197 | 0 | 985 | 0 | AC-NHPP |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 985 | 0 | 0 | 0 | 0 | 0
946 | 5 | ST. CHARLES | RT K S | 6S3520 | 0.535 | Y | 7063BB-23 | Payment to O'Fallon to build one way outer roads, add U-turn ramps and relocate exit ramps between Woodlawn and Rte. K. $1,096,503 Cost Share funds. | Adv. CN | 890 | 222 | 0 | 1117 | 0 | AC-STBG |  | 5 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1097 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
947 | 5 | ST. CHARLES | RT K S | SL0051 | 32.23 | Y | 7229A-23 | Pavement repairs including on Rte. 79, I-70 OR, Salt River Road and I-64 in St. Charles County, I-270, I-44, I-64 OR, South Woods Mill Road, Rte. 370, Rte. 364, and Rte. 50 in St. Louis County. | Adv. CN | 1078 | 270 | 0 | 1348 | 0 | AC-STBG |  | 0 | 124 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1224 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
948 | 5 | ST. CHARLES | CST LAKE ST LOUIS BLVD E | SL0118 | 0.445 | Y |  | Payment to Lake Saint Louis for pavement resurfacing, drainage improvements and to add lanes and sidewalks from north of Hawk Ridge Crossing to south of Hawk Ridge Circle. $600,000 Cost Share funds. | Adv. CN | 508 | 127 | 0 | 635 | 0 | AC-STBG |  | 0 | 5 | 5 | 15 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
949 | 5 | ST. CHARLES | RT M S | 6S3486 | 1.002 | Y | 6991I-20 | Pavement resurfacing and repair from Rte. P (Pieper Road) to Rte. 79. | Adv. CN | 466 | 117 | 0 | 613 | 0 | AC-STBG | 6S3487 6S3667 SL0018 | 30 | 8 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 549 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
950 | 5 | ST. CHARLES | RT N E | 6S3312 | 2.392 | Y | 6798W-18 | Pavement resurfacing and upgrade pedestrian facilities to comply with the ADA Transition Plan from Bryan Road to Rte. K. | Federal | 266 | 66 | 0 | 418 | 0 | NHPP |  | 36 | 26 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 306 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
951 | 5 | ST. CHARLES | RT N E | 6S3668 | 1 | Y | 7223AA-22 | Payment to O'Fallon to construct dual left turn lanes at Rte. K. $645,000 Cost Share funds. | Adv. CN | 520 | 130 | 0 | 655 | 0 | AC-STBG |  | 5 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
952 | 5 | ST. CHARLES | N OR 70 E | SL0119 | 0 | Y |  | Construct new north outer road and relocate ramps from Rte. 94 to Zumbehl Road. $2,569,000 Cost Share and $7,931,000 St. Charles County funds. | Adv. CN | 3944 | 0 | 7931 | 11875 | 0 | AC-STBG |  | 0 | 0 | 1060 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10815 | 0 | 0 | 0 | 0 | 0 | 0 | 7931 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
953 | 5 | ST. CHARLES | N OR 70 E | SL0161 |  | Y |  | Payback to St. Charles County to construct new north outer road and relocate ramps from Rte. 94 to Zumbehl Road. $2,976,000 Cost Share funds. | Adv. CN | 2381 | 595 | 0 | 2976 | 0 | AC-STBG |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 476 | 0 | 0
954 | 5 | ST. CHARLES | CST OLD HWY N E | 6S3508 | 0.43 | Y | 7101A-20 | Payment to Lake St. Louis for pavement resurfacing and to add turn lanes, pedestrian facilities and lighting from Hawk Ridge Trail to Sommers Road. $460,000 Cost Share funds. | Adv. CN | 380 | 95 | 0 | 475 | 0 | AC-STBG |  | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 460 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
955 | 5 | ST. CHARLES | RT V S | 6S3487 | 4.048 | Y | 6991J-20 | Rebuild pavement and upgrade signage from Rte. 94 to end of state maintenance. | Federal | 0 | 1179 | 0 | 1334 | 0 | STATE |  | 155 | 60 | 96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1023 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
956 | 5 | ST. CHARLES | Various | 6P3457 | 0 | Y | 6989D-23 | Job Order Contracting for guardrail repair at various locations in St. Charles County. | Adv. CN | 689 | 172 | 0 | 861 | 0 | AC-STBG |  | 0 | 61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
957 | 5 | ST. CHARLES | Various | 6P3459 | 0 | Y | 6989F-20 | Job Order Contracting for guardrail repair at various locations in St. Charles County. | Adv. CN | 728 | 182 | 0 | 911 | 0 | AC-STBG |  | 1 | 0 | 0 | 61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 849 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
958 | 5 | ST. CHARLES | RT W N | 6S3564 | 0.041 | Y | 7219L-22 | Bridge rehabilitation over I-70. Project involves bridge A0795. | Federal | 378 | 94 | 0 | 477 | 0 | NHPP |  | 5 | 5 | 5 | 5 | 58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 399 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
959 | 5 | ST. CHARLES | RT Y E | 6S3607 | 6.043 | Y | 7219P-22 | Pavement resurfacing and pavement repairs from Flatwoods Road to Rte. 79. | Adv. CN | 1204 | 301 | 0 | 1506 | 0 | AC-STBG |  | 1 | 51 | 147 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1307 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
960 | 5 | ST. CHARLES | RT Z S | 6P3604 | 1.1 | Y | 7150-22 | Payment to Wentzville for additional lanes from Interstate Drive to Perry Cate Boulevard. Project involves bridge A2314. $3,975,000 Cost Share funds. | Adv. CN | 3900 | 975 | 0 | 5700 | 0 | AC-STBG |  | 10 | 13 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 815 | 4200 | 660 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
961 | 5 | ST. CHARLES | RT Z S | 6S3491 | 1.117 | Y | 6990G-20 | Pavement resurfacing from Perry Cate Boulevard to Rte. N. | Adv. CN | 526 | 131 | 0 | 717 | 0 | AC-STBG |  | 60 | 66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 591 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
962 | 5 | ST. CHARLES | RT Z S | SL0012 | 4.766 | Y | 7227N-23 | Pavement resurfacing and upgrade guardrail from Rte. N to Rte. D. | Adv. CN | 1212 | 303 | 0 | 1515 | 0 | AC-STBG |  | 0 | 10 | 50 | 126 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1329 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
963 | 5 | ST. LOUIS | MO 100 E | 6P3274 | 3.404 | Y | 6798T-18 | Pavement resurfacing, upgrade pedestrian facilities to comply with the ADA Transition Plan, bridge rehabilitations and bridge replacements from Rte. 141 to I-270. Project involves bridges A0960, A5016, F0181 and F0182. | Federal | 19479 | 4870 | 0 | 24791 | 0 | NHPP | 6P3274B | 442 | 500 | 1369 | 0 | 0 | 0 | 0 | 0 | 4561 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17919 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
964 | 5 | ST. LOUIS | MO 100 E | 6P3602 | 0.621 | Y | 7117A-22 | Payment to Manchester to upgrade pedestrian facilities to comply with the ADA Transition Plan from Baxter Road to Rte. 141. $1,119,125 Cost Share funds | Adv. CN | 903 | 226 | 0 | 1139 | 0 | AC-STBG |  | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1119 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
965 | 5 | ST. LOUIS | MO 100 E | SL0091 | 1.194 | Y |  | Payment to Wildwood to add J-turns at Rte. T and Pond Road. $1,495,000 Cost Share funds. | Federal | 1204 | 301 | 0 | 1505 | 0 | NHPP |  | 0 | 0 | 2 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 154 | 1341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
966 | 5 | ST. LOUIS | MO 100 E | SL0092 | 0.574 | Y | 7266-23 | Payment to Wildwood to construct left turn lanes at Booness Lane, Woodland Meadows Drive, Hencken Road and Windy Hollow Lane. $1,395,000 Cost Share funds. | Federal | 1124 | 281 | 0 | 1405 | 0 | NHPP |  | 0 | 8 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109 | 0 | 1286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
967 | 5 | ST. LOUIS | MO 100 W | 6P3274B | 0.018 | Y | 7216N-22 | Bridge rehabilitation on westbound lanes over I-270 and Des Peres Road. Project involves bridge A5682. | Federal | 1182 | 295 | 0 | 1509 | 0 | NHPP | 6P3274 | 32 | 80 | 181 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
968 | 5 | ST. LOUIS | MO 109 S | 6S3351 | 0.073 | Y | 6979B-20 | Add roundabout at Rte. CC. $3,222,000 Congestion Mitigation and Air Quality Improvement Program funds. | Federal | 3173 | 793 | 0 | 5208 | 0 | CMAQ |  | 376 | 259 | 0 | 0 | 0 | 0 | 0 | 866 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3707 | 0 | 0 | 0 | 0 | 0 | 1106 | 2116 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
969 | 5 | ST. LOUIS | MO 109 S | 6S3583 | 0.394 | Y | 7219Q-22 | Signal replacements at Lasalle Springs Middle School, on Big Bend Road at I-270 and on Rte. 141 at Old Gravois Road. | Adv. CN | 691 | 173 | 0 | 914 | 0 | AC-STBG |  | 50 | 138 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 725 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
970 | 5 | ST. LOUIS | MO 109 S | 6S3595 | 8.334 | Y | 7219S-22 | Pavement resurfacing, bridge deck sealing, upgrade guardrail and upgrade pedestrian facilities to comply with the ADA Transition Plan from Rte. 100 to Rte. FF. Project involves bridges A2955 and A4287. | Federal | 3650 | 912 | 0 | 4592 | 0 | NHPP | 6S3493 | 30 | 574 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3988 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
971 | 5 | ST. LOUIS | MO 109 S | SL0077 | 4.729 | Y | 7229V-23 | Pavement resurfacing from Rte. CC to Rte. 100. | Adv. CN | 1910 | 478 | 0 | 2388 | 0 | AC-STBG | SL0080 | 0 | 5 | 55 | 179 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2149 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
972 | 5 | ST. LOUIS | MO 115 S | 6S3416 | 1.288 | Y | 6936F-19 | Pavement resurfacing and upgrade signals, drainage and pedestrian facilities to comply with the ADA Transition Plan from Rte. U to St. Louis City limits. | Federal | 4090 | 1023 | 0 | 5606 | 0 | NHPP | 6S3416B | 493 | 50 | 310 | 0 | 0 | 0 | 0 | 0 | 245 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4508 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
973 | 5 | ST. LOUIS | MO 115 S | 6S3416B | 1.288 | Y | 7119-22 | Upgrade pedestrian facilities from Rte. U to the St. Louis City limits. $1,085,764 STBG-Urban and $272,000 Pine Lawn funds. | Adv. CN | 1065 | 6 | 260 | 1389 | 0 | AC-STBG | 6S3416 | 38 | 69 | 150 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1112 | 0 | 0 | 0 | 0 | 58 | 219 | 1080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
974 | 5 | ST. LOUIS | MO 115 S | 6S3417 | 1.257 | Y | 6936G-19 | Pavement resurfacing, upgrade signal, drainage and pedestrian facilities to comply with the ADA Transition Plan from I-170 to North Hanley Road and Engler Avenue to Wood Avenue. | Federal | 5335 | 1334 | 0 | 7279 | 0 | NHPP |  | 610 | 350 | 711 | 0 | 0 | 0 | 0 | 0 | 184 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5424 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
975 | 5 | ST. LOUIS | MO 141 S | 6P3062B | 0.117 | Y | 5967B-17 | Bridge replacement over flood control lake in Earth City. Project involves bridges A8123 and A8124. | Federal | 935 | 234 | 0 | 1452 | 0 | NHPP |  | 273 | 80 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1089 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
976 | 5 | ST. LOUIS | MO 141 S | SL0017 | 0.3 | Y | 7227S-23 | Drainage upgrades at Casino Center Drive intersection. | Federal | 280 | 70 | 0 | 350 | 0 | NHPP |  | 0 | 20 | 39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 291 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
977 | 5 | ST. LOUIS | MO 141 S | SL0025 | 0.234 | Y | 7228A-23 | Bridge rehabilitations and painting over Rte. 370 at Taussig Avenue, West St. Louis Mills Boulevard and Rte. 141. Project involves bridges A4920, A7015 and A4919. | Federal | 3912 | 978 | 0 | 4890 | 0 | NHPP |  | 0 | 25 | 165 | 473 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4227 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
978 | 5 | ST. LOUIS | MO 141 S | SL0026 | 2.821 | Y | 7228B-23 | Pavement resurfacing from Rte. 370 to I-70. | Federal | 1291 | 323 | 0 | 1614 | 0 | NHPP |  | 0 | 5 | 5 | 5 | 50 | 230 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1319 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
979 | 5 | ST. LOUIS | MO 141 S | SL0028 | 1.398 | Y | 7228D-23 | Pavement resurfacing from Rider Trail South to South Riverport Drive. | Federal | 1729 | 432 | 0 | 2161 | 0 | NHPP |  | 0 | 50 | 200 | 351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1560 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
980 | 5 | ST. LOUIS | MO 141 S | SL0078 | 0.941 | Y | 7229W-23 | Pavement resurfacing from 0.1 mile north of St. Luke's Hospital Road to I-64. | Federal | 360 | 90 | 0 | 450 | 0 | NHPP |  | 0 | 10 | 18 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 385 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
981 | 5 | ST. LOUIS | MO 141 S | SL0110 | 11.562 | Y | 7208-24 | Signal optimization from I-64 to Gravois Bluffs Blvd. $1,104,240 Congestion Mitigation and Air Quality Improvement Program funds. | Federal | 1106 | 276 | 0 | 1382 | 0 | CMAQ |  | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1380 | 0 | 0 | 0 | 0 | 0 | 0 | 1104 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
982 | 5 | ST. LOUIS | MO 141 S | SL0121 | 0.83 | Y |  | Widen interchange ramp, add turn lane and signal optimization at I-64. $1,717,040 Congestion Mitigation and Air Quality Improvement Program funds. | Federal | 1878 | 470 | 0 | 2348 | 0 | CMAQ |  | 0 | 203 | 1 | 255 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1889 | 0 | 0 | 0 | 0 | 162 | 0 | 1555 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
983 | 5 | ST. LOUIS | IS 170 E | 6I2339 | 0.049 | Y | 5309-11 | Construct access drive for St. Louis City Water north of Clayton Road. | Adv. CN | 74 | 19 | 0 | 197 | 0 | AC-STBG |  | 74 | 7 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
984 | 5 | ST. LOUIS | IS 170 E | 6I3567 | 0.265 | Y | 7171U-22 | Bridge rehabilitation over I-64 ramps, Ladue Road, Galleria Parkway, Clayton Road and Brentwood Boulevard and bridge replacement at Forest Park Parkway. Project involves bridges A2779, A2780, A2782, A2788, A2790, A8011, A8012 and A8015. | Federal | 9426 | 1047 | 0 | 10571 | 0 | NHPP |  | 98 | 102 | 200 | 300 | 677 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9194 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
985 | 5 | ST. LOUIS | IS 170 E | 6I3572 | 1.009 | Y | 7171R-22 | Bridge and culvert rehab and bridge paint over Page Ave, Woodson Rd and UP Railroad. Upgrade guardrail between Lackland and Midland. Sound abatement repairs near E Sherwood. Project involves bridges A3176, A2807, A2809 and culvert A2808.$50,000 District Operation funds. | Federal | 8735 | 971 | 0 | 9816 | 0 | NHPP |  | 110 | 550 | 609 | 0 | 0 | 0 | 0 | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8397 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
986 | 5 | ST. LOUIS | IS 170 E | 6I3624B | 0.161 | Y | 7227A-23 | Bridge replacement on ramp from eastbound I-270 to eastbound I-170. Project involves bridge A3808. | Federal | 2372 | 263 | 0 | 2635 | 0 | NHPP |  | 0 | 25 | 150 | 337 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2123 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
987 | 5 | ST. LOUIS | IS 170 E | SL0113 | 10.874 | Y | 7265B-23 | Striping upgrades from I-270 to I-64. | Federal | 126 | 14 | 0 | 140 | 0 | SAFETY |  | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
988 | 5 | ST. LOUIS | IS 170 W | 6I3535 | 0.471 | Y | 7171H | Bridge rehabilitations on and off westbound I-270. Project involves bridges A6370 and A6371. | Federal | 1345 | 149 | 0 | 1569 | 0 | NHPP | 6I3624 | 75 | 166 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1328 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
989 | 5 | ST. LOUIS | MO 180 E | 6S3311 | 0.097 | Y | 6811B-18 | Bridge replacement, ramp extensions and add sidewalk on St. Charles Rock Road at I-70. Project involves bridge L0887. | Federal | 7318 | 1830 | 0 | 9684 | 0 | NHPP |  | 511 | 450 | 150 | 100 | 593 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7855 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
990 | 5 | ST. LOUIS | MO 21 S | 6S3283 | 8.177 | Y | 6798R-18 | Pavement resurfacing, upgrade guardrail, signal and pedestrian facilities to comply with the ADA Transition Plan from Rte. 30 (Gravois Road) to the Meramec River. Project involves bridges A1156 and A1157. | Federal | 15786 | 3946 | 0 | 22586 | 0 | NHPP |  | 2854 | 344 | 1226 | 0 | 0 | 0 | 0 | 0 | 388 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17774 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
991 | 5 | ST. LOUIS | MO 231 S | 6S3597 | 12.491 | Y | 7134A-22 | Signal optimizations from Hoffmeister Avenue to Rte. 67, on Rte. 67 from Telegraph Road to Richardson Road and I-55 ramps at Richardson Road. $957,008 Congestion Mitigation and Air Quality Improvement Program funds. | Federal | 958 | 239 | 0 | 1198 | 0 | CMAQ |  | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1196 | 0 | 0 | 0 | 0 | 0 | 0 | 957 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
992 | 5 | ST. LOUIS | MO 231 S | 6S3631 | 2.855 | Y | 7220F-22 | Pavement and pedestrian improvements to comply with the ADA Transition Plan from St. Louis City limits to Franru Lane. | Adv. CN | 6335 | 1584 | 0 | 8019 | 0 | AC-STBG | 6S3632 SL0042 | 100 | 100 | 125 | 451 | 0 | 0 | 0 | 0 | 0 | 1917 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
993 | 5 | ST. LOUIS | MO 231 S | 6S3632 | 7.078 | Y | 7220G-22 | Pavement resurfacing and upgrade pedestrian facilities to comply with the ADA Transition Plan from Franru Lane to Meramec River. | Adv. CN | 8279 | 2070 | 0 | 10449 | 0 | AC-STBG | 6S3631 SL0042 | 100 | 200 | 181 | 699 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9264 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
994 | 5 | ST. LOUIS | IS 255 S | SL0074 | 3.373 | Y | 7229S-23 | Pavement preservation treatment from I-55 to the Mississippi River. | Federal | 4854 | 539 | 0 | 5393 | 0 | NHPP |  | 0 | 30 | 100 | 100 | 371 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
995 | 5 | ST. LOUIS | MO 267 N | 6S3397 | 3.902 | Y | 6892N-19 | Pavement resurfacing and upgrade pedestrian facilities to comply with the ADA Transition Plan from north of Lindbergh Boulevard to River City Boulevard. $1,917,000 Statewide Transportation Alternatives funds. | Adv. CN | 8224 | 2056 | 0 | 10836 | 0 | AC-STBG |  | 556 | 378 | 675 | 0 | 0 | 0 | 0 | 0 | 313 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8914 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
996 | 5 | ST. LOUIS | IS 270 E | 6I2090 | 0.253 | Y | 4414H-12 | Bridge replacement over Conway Road and bridge rehabilitation and pavement repair over I-64 ramp and Rte. AB (Ladue Road). Project involves bridges A1051, A1052 and A4657. | Federal | 24541 | 2727 | 0 | 29660 | 0 | NHPP |  | 2392 | 2268 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 24900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
997 | 5 | ST. LOUIS | IS 270 E | 6I3020C | 0.743 | Y | 6853E-18 | Modify interchange configuration at Riverview Boulevard in St. Louis City. Project involves bridges A1024 and A1025. | Federal | 21606 | 2401 | 0 | 27097 | 0 | NHPP |  | 2020 | 1556 | 0 | 0 | 0 | 0 | 0 | 1070 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22451 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
998 | 5 | ST. LOUIS | IS 270 E | 6I3020D | 1.426 | Y | 7171D-21 | Add lanes and bridge replacement from Lilac Avenue to Rte. H. Project involves bridge A0221. | Federal | 11337 | 1260 | 0 | 13047 | 0 | NHPP |  | 450 | 50 | 200 | 400 | 985 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
999 | 5 | ST. LOUIS | IS 270 E | 6I3580 | 3.209 | Y | 7171V-22 | Pavement resurfacing from Rte. 367 to Chain of Rocks Bridge. | Federal | 2302 | 256 | 0 | 2578 | 0 | NHPP |  | 20 | 10 | 10 | 75 | 235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2228 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1000 | 5 | ST. LOUIS | IS 270 E | 6I3616 | 2.096 | Y | 7171X-22 | Replace bridge approaches and upgrade guardrails at Rte. 180 and slide repair at Rte. 370. Project involves bridge A0180. $680,000 District Operation funds. | Federal | 2085 | 232 | 0 | 2327 | 0 | NHPP |  | 10 | 236 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2081 | 0 | 0 | 0 | 0 | 0 | 0 | 680 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1001 | 5 | ST. LOUIS | IS 270 E | 6I3618 | 0.022 | Y | 7171Z-22 | Culvert rehabilitation at Rte. AC. Project involves culvert J0888. | Adv. CN | 246 | 62 | 0 | 313 | 0 | AC-STBG |  | 5 | 5 | 5 | 15 | 31 | 0 | 0 | 0 | 0 | 0 | 74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1002 | 5 | ST. LOUIS | IS 270 E | 6I3653 | 3.958 | Y | 7216I-22 | Pavement repairs from Rte. AB to 0.4 mile south of Rte. 100. | Federal | 567 | 63 | 0 | 630 | 0 | NHPP | 6I3501 | 0 | 69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 561 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1003 | 5 | ST. LOUIS | IS 270 E | SL0021 | 6.089 | Y | 7227W-23 | Bridge replacements and rehabilitations, pavement resurfacing, upgrade signals and drainage and add pedestrian facilities from Rte. 367 to Lilac Avenue and Dunn Road from Rte. 367 to Riverview Drive. Project involves bridges J0847, L0749, A0241 and J0493. | Federal | 29449 | 3272 | 0 | 32721 | 0 | NHPP |  | 0 | 10 | 100 | 1500 | 3140 | 0 | 0 | 0 | 0 | 0 | 106 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1004 | 5 | ST. LOUIS | IS 270 E | SL0022 | 0.523 | Y | 7227X-23 | Bridge rehabilitations over Norfolk Southern Railway, on Rte. 370 over Norfolk Southern Railway, on ramp from Missouri Bottom to I-270 and on Missouri Bottom over I-270. Project involves bridges A1070, A4898, A4899 and A4277. | Federal | 3695 | 410 | 0 | 4105 | 0 | NHPP |  | 0 | 25 | 150 | 403 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3527 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1005 | 5 | ST. LOUIS | IS 270 E | SL0024 | 6.237 | Y | 7227Z-23 | Pavement resurfacing and median barrier replacement from I-70 to I-170. | Federal | 14499 | 1611 | 0 | 16110 | 0 | NHPP |  | 0 | 10 | 40 | 150 | 300 | 1180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14430 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1006 | 5 | ST. LOUIS | IS 270 E | SL0053 | 0.397 | Y | 7229C-23 | Bridge rehabilitations between I-44 and I-55. Project involves bridges A0967, A1033, A4876, A4877, A1026, A5082, A1235, A1234 and A1233. | Federal | 14849 | 1650 | 0 | 16499 | 0 | NHPP |  | 0 | 100 | 235 | 235 | 1035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14894 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1007 | 5 | ST. LOUIS | MO 30 E | 6S3532 | 0.25 | Y | 7219F-22 | Bridge rehabilitation over the Meramec River. Project involves bridge A2014. | Federal | 3863 | 966 | 0 | 4869 | 0 | NHPP |  | 40 | 290 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4539 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1008 | 5 | ST. LOUIS | MO 30 E | SL0081 | 9.125 | Y | 7229Y-23 | Pavement resurfacing from Rte. 141 to the St. Louis City limits. | Federal | 4668 | 1167 | 0 | 5835 | 0 | NHPP |  | 0 | 20 | 140 | 110 | 404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5161 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1009 | 5 | ST. LOUIS | MO 340 E | SL0076 | 7.712 | Y | 7229U-23 | Pavement resurfacing from I-270 to end of state maintenance. | Federal | 5006 | 1251 | 0 | 6257 | 0 | NHPP |  | 0 | 20 | 160 | 482 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5595 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1010 | 5 | ST. LOUIS | MO 364 E | SL0030 | 0.88 | Y | 7228F-23 | Bridge rehabilitation at Page Avenue over I-270. Project involves bridge A1243. | Federal | 3553 | 888 | 0 | 4441 | 0 | NHPP |  | 0 | 5 | 45 | 200 | 436 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3755 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1011 | 5 | ST. LOUIS | MO 364 W | SL0093 | 0 | Y | 7230G-22 | Upgrade drainage from the I-270 on ramp to the Bennington Place. $200,000 District Operation funds. | Federal | 344 | 86 | 0 | 455 | 0 | NHPP |  | 25 | 200 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 206 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1012 | 5 | ST. LOUIS | MO 366 E | 6S3582 | 6.666 | Y | 7171C-21 | Pavement resurfacing and upgrade pedestrian facilities to comply with the ADA Transition Plan from Geyer Road to St. Louis City limits and bridge replacement over Gravois Creek. Project involves bridge J0228. | Federal | 21860 | 5465 | 0 | 28133 | 0 | NHPP |  | 808 | 1510 | 1630 | 0 | 0 | 0 | 0 | 0 | 2426 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21759 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1013 | 5 | ST. LOUIS | MO 370 E | 6P3615 | 1.65 | Y | 7217K-22 | Bridge rehabilitation over Cowmire Creek, Ferguson Lane and Missouri Bottom Road. Project involves bridges A4895, A4896, A4886 and A5006. | Federal | 3540 | 885 | 0 | 4475 | 0 | NHPP |  | 50 | 50 | 131 | 352 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3892 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1014 | 5 | ST. LOUIS | IS 44 E | 6I3568 | 11.735 | Y | 7171P-22 | Pavement resurfacing and upgrade signals from 0.5 mile east of Rte. OO to Williams Road, 5th Street from Six Flags Road to Central Avenue, 4th Street from end of state maintenance to Central Avenue and Fox Creek Road from end of state maintenance to Six Flags Road. | Federal | 7299 | 811 | 0 | 8512 | 0 | NHPP |  | 401 | 568 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7542 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1015 | 5 | ST. LOUIS | IS 44 E | 6I3651 | 3.313 | Y | 7216H-22 | Bridge deck sealing on various bridges in St. Louis and Jefferson Counties and St. Louis City. Project involves bridges on I-44, I-55, I-70, I-255, I-270 and Rte. 21. $1,500,000 District Operations funds. | Federal | 1485 | 165 | 0 | 1670 | 0 | NHPP |  | 20 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1530 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1016 | 5 | ST. LOUIS | IS 44 E | SL0052 | 0.111 | Y | 7229B-23 | Bridge rehabilitations over Lindbergh Boulevard, Berry Road and Elm Avenue. Project involves bridges A1728, A1723 and A1715. | Federal | 6281 | 698 | 0 | 6979 | 0 | NHPP |  | 0 | 50 | 150 | 506 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6273 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1017 | 5 | ST. LOUIS | IS 44 E | SL0054 | 0.392 | Y | 7229D-23 | Bridge rehabilitations between Eureka and Fenton. Project involves bridges A3856, A0775, J0255, L0704, A3996, A3638, A1797, L0761, A4285, L0932 and A4288. | Federal | 18881 | 2098 | 0 | 20979 | 0 | NHPP |  | 0 | 120 | 160 | 220 | 250 | 1257 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18972 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1018 | 5 | ST. LOUIS | N OR 44 E | 6S3556 | 0.363 | Y | 7219I-22 | Bridge rehabilitation on Mattis Road over I-55, Geyer Road over I-44, Cragwold Road over I-270, pavement preservation treatment on I-270 over I-44 and bridge painting on the ramp from I-270 west to Rte. 67. Project involves bridges A1006, A4909, A5410, A5408 and A5082. | Federal | 1822 | 455 | 0 | 2337 | 0 | NHPP | 6I3534 | 60 | 305 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1972 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1019 | 5 | ST. LOUIS | IS 55 N | 6I3565 | 7.792 | Y | 7171O-22 | Bridge painting from 1.2 miles east of Lindbergh Boulevard to 0.4 mile south of Arsenal Street. Project involves bridges A0607, A0591, A1057, A1076, A1276 and A1085. | Federal | 6967 | 774 | 0 | 7743 | 0 | NHPP |  | 2 | 1 | 1 | 1 | 151 | 578 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7009 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1020 | 5 | ST. LOUIS | US 61 S | 6S3281 | 6.939 | Y | 6807W-18 | Pavement resurfacing, upgrade signal and pedestrian facilities to comply with the ADA Transition Plan from north of Big Bend Road to Barracksview Road. $2,232,000 District Operation funds. | Federal | 10955 | 2739 | 0 | 15618 | 0 | NHPP |  | 1578 | 881 | 0 | 0 | 0 | 0 | 0 | 346 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12813 | 0 | 0 | 0 | 0 | 0 | 0 | 2232 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1021 | 5 | ST. LOUIS | US 61 S | 6S3578 | 4.448 | Y | 7219O-22 | Pavement resurfacing and upgrade pedestrian facilities to comply with the ADA Transition Plan from the Meramec River to 0.1 mile north of Lindbergh Boulevard. | Federal | 10174 | 2544 | 0 | 12828 | 0 | NHPP |  | 110 | 250 | 614 | 774 | 0 | 0 | 0 | 0 | 0 | 356 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10724 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1022 | 5 | ST. LOUIS | IS 64 E | 6I0978Z | 9.01 | Y | 2606D-11 | Payback for project 6I0978 from west of Spoede Road to west of Sarah Street. Total cost of $189,800 with payments from 2011 to 2025. | Federal | 0 | 35055 | 0 | 189799 | 0 | STATE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 154744 | 11686 | 11686 | 11683 | 0 | 0 | 0
1023 | 5 | ST. LOUIS | IS 64 W | 6I3501 | 1.031 | Y | 6991M-20 | Bridge rehabilitations at I-270, over New Ballas Road, and ramp to New Ballas Road. Project involves bridges A4650, A4651, A4652, A4653, A4654, A4580, A4581 and A4657. | Federal | 11050 | 1228 | 0 | 13722 | 0 | NHFP | 6I3653 | 1444 | 1220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11058 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1024 | 5 | ST. LOUIS | IS 64 W | 6I3538 | 0.485 | Y | 7171J-23 | Bridge rehabilitation over the Missouri River. Project involves bridge A4017. | Federal | 5519 | 613 | 0 | 6232 | 0 | NHPP |  | 100 | 200 | 555 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5377 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1025 | 5 | ST. LOUIS | US 67 S | 6I3573 | 0.29 | Y | 6992X-21 | Culvert rehabilitations over Coldwater Creek, on Rte. N over Ball Creek and on Rte. AC over Maline Creek. Project involves culverts A1073, A1108 and L0269. | Adv. CN | 931 | 233 | 0 | 1254 | 0 | AC-STBG |  | 90 | 52 | 0 | 0 | 0 | 0 | 0 | 0 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 1079 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1026 | 5 | ST. LOUIS | US 67 S | 6P3623 | 3.935 | Y | 7217L-22 | Pavement resurfacing, replace signal, upgrade guardrail and upgrade pedestrian facilities to comply with the ADA Transition Plan from Rte. 367 to Rte. AC. | Federal | 5206 | 1302 | 0 | 6558 | 0 | NHPP |  | 50 | 150 | 678 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5680 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1027 | 5 | ST. LOUIS | US 67 S | 6S3280 | 7.04 | Y | 6798N-18 | Pavement resurfacing, bridge replacement and upgrade pedestrian facilities to comply with the ADA Transition Plan from Rte. D (Page Avenue) to Swan Drive. Project involves bridge H0989. | Federal | 8954 | 2239 | 0 | 12428 | 0 | NHPP |  | 846 | 82 | 689 | 0 | 0 | 0 | 0 | 389 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1028 | 5 | ST. LOUIS | US 67 S | 6S3521 | 0.267 | Y | 7106B-22 | Payment to Creve Coeur to signalize intersection and add turn lanes at Old Olive Street. $1,005,000 Cost Share and $575,100 Governor's Cost Share Program funds. | Adv. CN | 1276 | 319 | 0 | 1600 | 0 | AC-STBG |  | 5 | 13 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 710 | 870 | 0 | 0 | 0 | 0 | 0 | 575 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1029 | 5 | ST. LOUIS | US 67 S | 6S3557 | 3.438 | Y | 7219J-22 | Pavement resurfacing and upgrade pedestrian facilities to comply with the ADA Transition Plan from I-70 to Rte. D. | Federal | 7234 | 1809 | 0 | 9193 | 0 | NHPP |  | 150 | 300 | 250 | 607 | 0 | 0 | 0 | 0 | 0 | 52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7834 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1030 | 5 | ST. LOUIS | US 67 S | 6S3621 | 0.065 | Y | 7219Z-22 | Bridge rehabilitation over Rte. 180. Project involves bridge J0845. | Federal | 2023 | 506 | 0 | 2539 | 0 | NHPP |  | 10 | 100 | 335 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2094 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1031 | 5 | ST. LOUIS | US 67 S | 6S3625 | 3.795 | Y | 7220A-22 | Pavement resurfacing and upgrade pedestrian facilities to comply with the ADA Transition Plan from Rte. AC to Candle Light Lane. | Adv. CN | 6143 | 1536 | 0 | 7729 | 0 | AC-STBG |  | 50 | 150 | 100 | 200 | 521 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6708 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1032 | 5 | ST. LOUIS | US 67 S | 6S3669 | 0.163 | Y | 7220Z | Bridge rehabilitation over two locations of Coldwater Creek and over Lynn Haven Lane. Project involves bridges A1072, A1074 and A4514. | Federal | 6684 | 1671 | 0 | 8430 | 0 | NHPP |  | 75 | 100 | 250 | 200 | 532 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7273 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1033 | 5 | ST. LOUIS | US 67 S | SL0029 | 1.73 | Y | 7228E-23 | Pavement resurfacing and signal upgrades from I-270 to Missouri Bottom Road. | Federal | 3321 | 830 | 0 | 4151 | 0 | NHPP |  | 0 | 70 | 200 | 420 | 0 | 0 | 0 | 0 | 0 | 66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3395 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1034 | 5 | ST. LOUIS | IS 70 E | 6I3571 | 0.516 | Y | 7171Q-22 | Bridge painting at I-170 interchange. Project involves bridges A2999, A3000, A3001, A3002, A3003, A3004, A3005, A3007, A3008, A4226, L0810 and A4282. | Federal | 10612 | 1179 | 0 | 11851 | 0 | NHPP |  | 60 | 450 | 1158 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10183 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1035 | 5 | ST. LOUIS | IS 70 E | 6I3617 | 1.911 | Y | 7171Y-22 | Replace lighting at the I-270 interchange. | Federal | 2034 | 226 | 0 | 2280 | 0 | NHPP |  | 20 | 50 | 235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1036 | 5 | ST. LOUIS | IS 70 E | 6I3647 | 5.089 | Y | 7216F-22 | Pavement resurfacing from Rte. 180 to Springdale Avenue. | Federal | 8040 | 893 | 0 | 8983 | 0 | NHPP |  | 50 | 808 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1037 | 5 | ST. LOUIS | IS 70 E | 6I3654 | 0.2 | Y | 7216J-22 | Bridge replacement over I-270. Project involves bridge A0093. | Federal | 6674 | 741 | 0 | 7465 | 0 | NHFP |  | 50 | 50 | 100 | 200 | 700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6365 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1038 | 5 | ST. LOUIS | IS 70 E | SL0058 | 6.971 | Y | 7229G-23 | Corridor improvements from the Missouri River to Rte. 67. Potential Design-Build. Project involves various bridges. | Federal | 53034 | 5893 | 0 | 58927 | 0 | NHPP |  | 0 | 500 | 3000 | 2000 | 3250 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50156 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1039 | 5 | ST. LOUIS | IS 70 E | SL0075 | 2.337 | Y | 7229T-23 | Pavement resurfacing, pavement preservation treatment and upgrade guardrail from 0.24 mile west of Goodfellow Boulevard to Kingshighway Boulevard. | Federal | 1193 | 132 | 0 | 1325 | 0 | NHPP |  | 0 | 5 | 100 | 98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1040 | 5 | ST. LOUIS | RT AB E | 6S3633 | 3.229 | Y | 7220H-22 | Pavement resurfacing and upgrade pedestrian facilities to comply with the ADA Transition Plan from 0.1 mile west of Rte. 141 to I-270. | Adv. CN | 4601 | 1150 | 0 | 5851 | 0 | AC-STBG |  | 100 | 120 | 378 | 0 | 0 | 0 | 0 | 0 | 1176 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4077 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1041 | 5 | ST. LOUIS | RT AC N | 6I3573B | 0.153 | Y | 6992XX-23 | Bridge rehabilitation over Maline Creek. Project involves bridge A1109. | Adv. CN | 756 | 189 | 0 | 945 | 0 | AC-STBG |  | 0 | 0 | 35 | 109 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 801 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1042 | 5 | ST. LOUIS | RT AC S | 6S3569 | 2.417 | Y | 7219M-22 | Pavement resurfacing and upgrade pedestrian facilities to comply with the ADA Transition Plan from south of Pershall Road to north of St. Cyr Road. $1,831,000 Statewide Transportation Alternatives funds. | Federal | 8939 | 2235 | 0 | 11324 | 0 | NHPP |  | 150 | 200 | 315 | 892 | 0 | 0 | 0 | 0 | 0 | 622 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9145 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1043 | 5 | ST. LOUIS | RT AC S | 6S3648 | 3.295 | Y | 7220K-22 | Pavement resurfacing from I-270 to Lindberg Boulevard. | Adv. CN | 5017 | 1254 | 0 | 6296 | 0 | AC-STBG |  | 25 | 25 | 50 | 153 | 545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1044 | 5 | ST. LOUIS | RT BA S | SL0080 | 3.382 | Y | 7229X-23 | Pavement resurfacing from Rte. 109 north to Rte. 109 south. | Adv. CN | 1220 | 305 | 0 | 1525 | 0 | AC-STBG | SL0077 | 0 | 10 | 30 | 109 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1376 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1045 | 5 | ST. LOUIS | RT CC E | 6S3493 | 3.862 | Y | 7219E-22 | Pavement resurfacing from Rte. 109 to I-64. | Adv. CN | 3008 | 752 | 0 | 3787 | 0 | AC-STBG | 6S3595 | 27 | 429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3331 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1046 | 5 | ST. LOUIS | RT D E | 6S3215 | 2.23 | Y | 7227K-23 | Pavement resurfacing and upgrade pedestrian facilities to comply with the ADA Transition Plan from I-170 to west of Pennsylvania Avenue. | Federal | 8489 | 2122 | 0 | 12692 | 0 | NHPP | 6S3592 | 2081 | 390 | 641 | 0 | 0 | 0 | 0 | 0 | 104 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9476 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1047 | 5 | ST. LOUIS | RT D E | 6S3215B | 1.42 | Y | 7227K-23 | Pavement resurfacing and upgrade pedestrian facilities to comply with the ADA Transition Plan from west of Pennsylvania Avenue to St. Louis City limits. | Federal | 4849 | 1212 | 0 | 6061 | 0 | NHPP |  | 0 | 200 | 245 | 339 | 0 | 0 | 0 | 0 | 0 | 107 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5170 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1048 | 5 | ST. LOUIS | RT D E | 6S3438 | 5.777 | Y | 6990U-20 | Pavement resurfacing from St. Louis City limits to Tucker Boulevard. | Federal | 4288 | 1072 | 0 | 5377 | 0 | NHPP |  | 17 | 60 | 377 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4913 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049 | 5 | ST. LOUIS | RT D E | 6S3592 | 0.423 | Y | 7219R-22 | Bridge rehabilitations at various locations between Beltway Drive and Ogden Avenue. Project involves bridges A7109, A3885, A5328 and B0388. | Federal | 1890 | 473 | 0 | 2408 | 0 | NHPP | 6S3215 | 25 | 195 | 140 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050 | 5 | ST. LOUIS | RT D E | 6S3626 | 0.876 | Y | 7220B-22 | Bridge replacement over Rte. 67. Project involves bridge A0650. | Federal | 6788 | 1697 | 0 | 8685 | 0 | NHPP |  | 200 | 100 | 300 | 867 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7218 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051 | 5 | ST. LOUIS | RT D E | SL0027 | 3.19 | Y | 7228C-23 | Pavement resurfacing from Rte. 67 to I-170. | Federal | 3408 | 852 | 0 | 4260 | 0 | NHPP |  | 0 | 25 | 150 | 413 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3672 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052 | 5 | ST. LOUIS | RP IS170W TO IS270E E | 6I3624 | 0.292 | Y | 7216B-22 | Bridge rehabilitations on ramp from westbound I-170 to eastbound I-270. Project involves bridges A6372 and A6373. | Federal | 770 | 193 | 0 | 1013 | 0 | NHPP | 6I3535 | 50 | 127 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 836 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053 | 5 | ST. LOUIS | RP IS270E TO IS70W W | SL0086 | 0.055 | Y | 7230C-23 | Bridge replacements from I-270 eastbound to I-70 westbound and I-270 westbound to I-70 eastbound. Project involves bridges A3764 and A3766. | Federal | 20546 | 5137 | 0 | 25683 | 0 | NHPP |  | 0 | 50 | 250 | 1130 | 2496 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21757 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054 | 5 | ST. LOUIS | RP IS55N TO IS270E E | 6I3534 | 1.061 | Y | 7171G-22 | Bridge rehabilitation and painting at the I-55/I-270 interchange and at the I-44/I-270 interchange and crack filling on I-44 over the Meramec River. Project involves bridges A4881, A4882, A5411, A5412, A8231 and A8683. | Federal | 10081 | 2520 | 0 | 12846 | 0 | NHPP | 6S3556 | 245 | 819 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11782 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055 | 5 | ST. LOUIS | RP IS64E TO IS170W W | 6I3634 | 0.237 | Y | 7216C-22 | Bridge rehabilitation on ramps between I-170 and I-64. Project involves bridges A8013 and A8014. | Federal | 423 | 106 | 0 | 551 | 0 | NHPP |  | 22 | 40 | 40 | 5 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 413 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056 | 5 | ST. LOUIS | RP IS64W TO LONG RD S | SL0070 | 0.066 | Y | 7229Q-23 | Bridge replacement for Long Road over I-64. Project involves bridge A2170. | Federal | 2046 | 511 | 0 | 2557 | 0 | NHPP |  | 0 | 20 | 20 | 50 | 80 | 165 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2222 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057 | 5 | ST. LOUIS | CST JAMES S MCDONNELL BLVD S | 6I3326 | 0.143 | Y | 6811S-18 | Bridge rehabilitation at McDonnell Boulevard and Lambert International Boulevard ramp to I-70 eastbound. Project involves bridges A4226 and A4282. | Federal | 1690 | 422 | 0 | 2463 | 0 | NHPP |  | 351 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1972 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1058 | 5 | ST. LOUIS | RT N S | 6S3519 | 1.707 | Y | 6992F-20 | Pavement resurfacing and upgrade pedestrian facilities to comply with the ADA Transition Plan from Dunn Road to Thoroughman Avenue. | Adv. CN | 4245 | 1061 | 0 | 5856 | 0 | AC-STBG |  | 550 | 300 | 540 | 0 | 0 | 0 | 0 | 0 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4401 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1059 | 5 | ST. LOUIS | RT N S | 6S3599 | 1.949 | Y | 6992W-21 | Pavement resurfacing and upgrade pedestrian facilities to comply with the ADA Transition Plan from Hawkesbury Drive to Rte. 115. $56,882 DEMO ID MO116. | Adv. CN | 5841 | 1460 | 0 | 7551 | 0 | AC-STBG |  | 250 | 273 | 521 | 0 | 0 | 0 | 0 | 0 | 186 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6321 | 0 | 0 | 0 | 0 | 0 | 0 | 57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1060 | 5 | ST. LOUIS | CST NORTH HANLEY RD S | SL0023 | 0.079 | Y | 7227Y-23 | Bridge rehabilitation over I-70. Project involves bridge A6175. | Federal | 1161 | 290 | 0 | 1451 | 0 | NHPP |  | 0 | 5 | 5 | 10 | 65 | 149 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1217 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1061 | 5 | ST. LOUIS | RT U S | 6S3655 | 2.29 | Y | 7216P-22 | Pavement resurfacing from West Florissant Avenue to Woodrow Avenue. | Federal | 3452 | 863 | 0 | 4340 | 0 | NHPP |  | 25 | 50 | 50 | 75 | 439 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1062 | 5 | ST. LOUIS | Various | 6P3496B | 0 | Y | 6992S-21 | Safety improvements on various routes in St. Louis County. Potential Design-Build. $2,000,000 St. Louis County funds. | Federal | 2000 | 0 | 1850 | 4000 | 0 | SAFETY |  | 150 | 330 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3520 | 0 | 0 | 0 | 0 | 0 | 150 | 1850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1063 | 5 | ST. LOUIS CITY | MO 100 E | SL0073 | 6.759 | Y | 7229R-23 | Pavement resurfacing from the St. Louis City limits to I-44. | Adv. CN | 2691 | 673 | 0 | 3364 | 0 | AC-STBG |  | 0 | 5 | 100 | 256 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3003 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1064 | 5 | ST. LOUIS CITY | IS 270 W | 6I3264 | 0.423 | Y | 6446A-17 | Payment to IDOT for bridge replacement at Chain of Rocks Bridge over the Mississippi River. Project involves bridge A0890. | Federal | 100810 | 11201 | 0 | 112963 | 0 | NHPP |  | 952 | 10 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 112000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1065 | 5 | ST. LOUIS CITY | IS 270 W | 6I3481 | 39.782 | Y | 6991L-20 | Replace structural signs from the Mississippi River to I-55 and on I-255 from I-55 to the Mississippi River and on I-64 from 1st Street to Illinois State line and on I-55 from Park Avenue to Gratiot Street. | Federal | 4241 | 471 | 0 | 5117 | 0 | NHPP |  | 405 | 817 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3895 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066 | 5 | ST. LOUIS CITY | MO 367 S | 6S3279 | 2.162 | Y | 6798J-18 | Pavement resurfacing and upgrade pedestrian facilities to comply with the ADA Transition Plan from Halls Ferry Circle to I-70. $276,605 City of St. Louis funds. | Adv. CN | 2125 | 254 | 277 | 2705 | 0 | AC-STBG |  | 49 | 296 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 2335 | 0 | 0 | 0 | 0 | 0 | 0 | 277 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067 | 5 | ST. LOUIS CITY | IS 44 E | 6S3443 | 7.662 | Y | 6991T-20 | Bridge replacements at various locations over I-44 from Holmes Avenue to Shrewsbury Avenue and Macklind Avenue to Nebraska Avenue. Project involves bridges A2322, A3263, A2257, A1736, A1732, A1730, A2092, A1726, A1721, A1720, A1725 and A1729. | Federal | 33413 | 3713 | 0 | 37237 | 0 | NHPP |  | 111 | 400 | 700 | 710 | 2116 | 0 | 0 | 0 | 0 | 0 | 265 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32935 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068 | 5 | ST. LOUIS CITY | IS 55 S | 6I3427 | 15.131 | Y | 6990Q-19 | Pavement resurfacing, upgrade guardrail, upgrade pedestrian facilities to comply with the ADA Transition Plan and bridge rehabilitation from Lindbergh Blvd to I-44 and ADA on various locations on MoDOT owned right-of-way. Project involves bridge A7369, A7745 and A7746. | Federal | 26186 | 2909 | 0 | 30211 | 0 | NHPP |  | 1116 | 290 | 2646 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26134 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069 | 5 | ST. LOUIS CITY | IS 64 E | 6I3540 | 3.697 | Y | 7171K-22 | Bridge rehabilitation and preventative maintenance at Poplar St. double deck bridge, on Rte. 364 over the MO River and over Creve Coeur Lake, on Rte. 47 over the MO River and on I-44 on the Cole St. Viaduct. Project involves bridges A1501, A5585, A5584, A8141 and L0815. | Federal | 6615 | 735 | 0 | 7571 | 0 | NHPP | 6I3550 | 221 | 718 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6632 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070 | 5 | ST. LOUIS CITY | IS 64 E | SL0064 | 2.089 | Y | 7230D-23 | Pavement resurfacing, upgrade guardrail and upgrade pedestrian facilities to comply with the ADA Transition Plan from Sarah Street to 21st Street. | Federal | 1078 | 120 | 0 | 1198 | 0 | NHPP |  | 0 | 10 | 60 | 93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071 | 5 | ST. LOUIS CITY | IS 64 E | SL0087 | 2.547 | Y | 7230D-23 | Bridge rehabilitation and reconfigure ramps from Kingshighway to Jefferson (Partial). Project involves bridge A3651. | Federal | 16938 | 1882 | 0 | 18820 | 0 | NHPP |  | 0 | 100 | 400 | 800 | 1129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16391 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072 | 5 | ST. LOUIS CITY | IS 70 E | 6I0984Z | 0.755 | Y | 3479Z-11 | Payback for 6I0984 and 6U1086 to construct new Mississippi River Bridge. Payment of $11.939 million per year from 2011 to 2025. Project involves bridge A6500. | Federal | 0 | 35816 | 0 | 150772 | 0 | STATE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 114956 | 11939 | 11939 | 11938 | 0 | 0 | 0
1073 | 5 | ST. LOUIS CITY | IS 70 E | 6I3662 | 1.468 | Y | 7216M-22 | Bridge washing at various locations in the St. Louis District. Project involves bridges A1850, A4936, A5585 and A6500. $209,100 IDOT funds. | Federal | 575 | 209 | 0 | 785 | 0 | NHPP |  | 1 | 1 | 1 | 14 | 59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 709 | 0 | 0 | 0 | 0 | 0 | 0 | 209 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1074 | 5 | ST. LOUIS CITY | IS 70 E | SL0084 | 0.527 | Y | 7230A-23 | Bridge rehabilitation on the Stan Musial Veterans Memorial Bridge. Project involves bridge A6500. $466,000 IDOT funds. | Federal | 872 | 0 | 466 | 1338 | 0 | NHPP |  | 0 | 1 | 1 | 1 | 150 | 136 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1049 | 0 | 0 | 0 | 0 | 0 | 0 | 466 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1075 | 5 | ST. LOUIS CITY | IS 70 W | 6I3463 | 46.82 | Y | 6936M-19 | Replace structural signs from Warren County line to Mississippi River. | Federal | 2155 | 239 | 0 | 3154 | 0 | NHPP |  | 760 | 162 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2232 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1076 | 5 | ST. LOUIS CITY | CST DR MARTIN LUTHER KING BRG W | 6S3531 | 0.32 | Y | 7219G-24 | Payment to IDOT for deck sealing on the Martin Luther King Bridge. Project involves bridge A4856. | Federal | 69 | 17 | 0 | 86 | 0 | NHPP |  | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1077 | 5 | ST. LOUIS CITY | RT H S | 6S3278 | 3.65 | Y | 6798H-18 | Pavement resurfacing from Adelaide Avenue to west of Riverview Drive and Hall Street intersection. | Federal | 5039 | 1260 | 0 | 6669 | 0 | NHPP |  | 370 | 44 | 416 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5839 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1078 | 5 | ST. LOUIS CITY | RT H S | SL0065 | 3.544 | Y | 7229M-23 | Pavement resurfacing from I-270 to Hall Street. | Federal | 2647 | 662 | 0 | 3309 | 0 | NHPP |  | 0 | 1 | 1 | 50 | 52 | 233 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2972 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1079 | 5 | ST. LOUIS CITY | RP IS64E TO 14TH ST E | 6I3576 | 0.67 | Y | 7171T-22 | Signal replacements at various locations in St. Louis City and St. Louis County. | Federal | 1475 | 369 | 0 | 1875 | 0 | NHPP |  | 16 | 243 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1601 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1080 | 5 | ST. LOUIS CITY | CST WEBER RD E | 6S3442 | 0.132 | Y | 6991U-20 | Bridge replacements and ramp realignment on Weber Road, Loughborough Avenue over I-55, northbound I-55 exit and on ramp at Loughborough Avenue. Project involves bridges A0918 and A1077. | Federal | 9034 | 2258 | 0 | 11326 | 0 | NHPP |  | 34 | 1 | 340 | 340 | 330 | 593 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9677 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1081 | 5 | ST. LOUIS CITY | CST WEST FLORISSANT AVE S | 6S3552 | 0.393 | Y | 7219H-22 | Bridge rehabilitations over Terra West Belt Railroad and on Rte. 366 and Rte. 30 over the River Des Peres Drainage Channel. Project involves bridges A0482, A3208, A7167 and A7168. | Federal | 2017 | 504 | 0 | 2525 | 0 | NHPP |  | 4 | 21 | 176 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2324 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1082 | 5 | VARIOUS | Various | 5B0800U | 0 | Y | 4772-08 | Payback beginning in SFY 2008 for Safe and Sound bridges in the St. Louis District. | Federal | 0 | 6550 | 0 | 22098 | 5,001 - 10,000 | STATE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 15518 | 1310 | 1310 | 1310 | 1310 | 1310 | 0
1083 | 5 | VARIOUS | Various | 6I3644 | 0 | Y | 7216D-22 | Upgrade ITS dynamic message signs at various locations in the St Louis District. | Adv. CN | 742 | 186 | 0 | 933 | 0 | AC-STBG |  | 5 | 60 | 59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 809 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1084 | 5 | VARIOUS | Various | 6I3645 | 0 | Y | 7216E-22 | Upgrade ITS for CCTV, DMS and intersection detection at various routes in the St. Louis District. | Adv. CN | 725 | 181 | 0 | 911 | 0 | AC-STBG |  | 5 | 60 | 58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 788 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1085 | 5 | VARIOUS | Various | 6I3659 | 0 | Y | 7216K-22 | Replace pavement markers at various locations in the St. Louis District. | Federal | 444 | 111 | 0 | 595 | 0 | NHPP |  | 40 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 510 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1086 | 5 | VARIOUS | Various | 6P3221 | 0 | Y | 6758BB-18 | Payment to St. Charles County for engineering services contract for regional ITS Data Sharing Initiative and Phase 1 of data exchange between MoDOT and St. Charles County. | Federal | 0 | 154 | 0 | 154 | 0 | STATE |  | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1087 | 5 | VARIOUS | Various | 6P3332 | 0 | Y | 6807M-19 | Job Order Contracting for asphalt pavement improvements at various major route locations in the St. Louis District. | Adv. CN | 1994 | 499 | 0 | 2493 | 0 | AC-STBG |  | 0 | 93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1088 | 5 | VARIOUS | Various | 6P3428 | 0 | Y | 6936W-20 | Job Order Contracting for bridge repairs at various major route locations in the St. Louis District. | Adv. CN | 1888 | 472 | 0 | 2361 | 0 | AC-STBG |  | 1 | 160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1089 | 5 | VARIOUS | Various | 6P3447 | 0 | Y | 6936U-20 | Job Order Contracting for bridge repairs at various major route locations in the St. Louis District. | Adv. CN | 1995 | 499 | 0 | 2495 | 0 | AC-STBG |  | 1 | 0 | 0 | 160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2334 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1090 | 5 | VARIOUS | Various | 6P3448 | 0 | Y | 6936T-20 | Job Order Contracting for fence repair at various locations in the St. Louis District. | Federal | 0 | 501 | 0 | 502 | 0 | STATE |  | 1 | 0 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 464 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1091 | 5 | VARIOUS | Various | 6P3450 | 0 | Y | 6936R-20 | Job Order Contracting for guard cable repair at various locations in the St. Louis District. | Adv. CN | 796 | 199 | 0 | 996 | 0 | AC-STBG |  | 1 | 0 | 68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 927 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1092 | 5 | VARIOUS | Various | 6P3453 | 0 | Y | 6989B-20 | Job Order Contracting for guardrail repair at various locations in St. Louis City and St. Louis County. | Adv. CN | 3000 | 750 | 0 | 3753 | 0 | AC-STBG |  | 3 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1093 | 5 | VARIOUS | Various | 6P3454 | 0 | Y | 6936P-20 | Job Order Contracting for concrete pavement improvements at various major route locations in the St. Louis District. | Adv. CN | 1853 | 463 | 0 | 2323 | 0 | AC-STBG |  | 7 | 1 | 152 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2163 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1094 | 5 | VARIOUS | Various | 6P3460 | 0 | Y | 6989G-23 | Job Order Contracting for guardrail repair at various locations in Franklin and Jefferson Counties. | Adv. CN | 689 | 172 | 0 | 861 | 0 | AC-STBG |  | 0 | 61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1095 | 5 | VARIOUS | Various | 6P3462 | 0 | Y | 6989I-20 | Job Order Contracting for guardrail repair at various locations in Franklin and Jefferson Counties. | Adv. CN | 728 | 182 | 0 | 911 | 0 | AC-STBG |  | 1 | 0 | 0 | 61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 849 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1096 | 5 | VARIOUS | Various | 6P3496 | 0 | Y | 6989N-20 | Safety improvements on various locations in the St. Louis District. Potential Design-Build. $12,632,000 Open Container funds. | Federal | 38459 | 4273 | 0 | 43522 | 0 | SAFETY |  | 790 | 1463 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 41219 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1097 | 5 | VARIOUS | Various | 6P3510 | 0 | Y |  | Upgrade pedestrian facilities to comply with the ADA Transition Plan throughout the St. Louis District. Potential Design-Build. | Adv. CN | 17062 | 4266 | 0 | 22728 | 0 | AC-STBG |  | 1400 | 300 | 100 | 1500 | 0 | 0 | 0 | 0 | 0 | 3090 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16338 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1098 | 5 | VARIOUS | Various | 6P3510B | 0 | Y |  | Upgrade pedestrian facilities to comply with the ADA Transition Plan throughout the St. Louis District. Potential Design-Build. | Adv. CN | 6369 | 1592 | 0 | 8261 | 0 | AC-STBG |  | 300 | 401 | 880 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1099 | 5 | VARIOUS | Various | 6P3577 | 0 | Y | 7216Z-22 | On-call work zone enforcement at various locations in the St. Louis District. | Federal | 901 | 100 | 0 | 1002 | 0 | SAFETY |  | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1100 | 5 | VARIOUS | Various | 6P3639 | 0 | Y | 7217P-22 | Job Order Contracting for guardrail repair at various locations in St. Louis City and St. Louis County. | Adv. CN | 3172 | 793 | 0 | 3966 | 0 | AC-STBG |  | 1 | 1 | 1 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3713 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1101 | 5 | VARIOUS | Various | 6P3641 | 0 | Y | 7217Q-22 | On-call work zone enforcement at various locations in the St. Louis District. | Federal | 902 | 100 | 0 | 1003 | 0 | SAFETY |  | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1102 | 5 | VARIOUS | Various | 6P3642 | 0 | Y | 7217R-22 | On-call work zone enforcement at various locations in the St. Louis District. | Federal | 903 | 100 | 0 | 1004 | 0 | SAFETY |  | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1103 | 5 | VARIOUS | Various | 6P3643 | 0 | Y | 7217S-22 | Upgrade striping and signage for wrong way countermeasures at various locations in the St. Louis District. | Federal | 526 | 58 | 0 | 594 | 0 | SAFETY |  | 10 | 10 | 59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 515 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1104 | 5 | VARIOUS | Various | 6Q2025B | 0 | Y | 7217W-22 | Emergency response operations and staffing in the St. Louis District. | Adv. CN | 2282 | 571 | 0 | 2854 | 0 | AC-STBG |  | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1105 | 5 | VARIOUS | Various | 6Q2025C | 0 | Y | 7217X-22 | ITS operations, MoDOT staff, equipment maintenance and Transportation Management Center (TMC) operations at the TMC building in the St. Louis District. | Adv. CN | 642 | 161 | 0 | 804 | 0 | AC-STBG |  | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1106 | 5 | VARIOUS | Various | 6Q2025D | 0 | Y | 7217Z-22 | ITS operations, contract staffing and professional services at the Traffic Management Center building. | Adv. CN | 2842 | 711 | 0 | 3554 | 0 | AC-STBG |  | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1107 | 5 | VARIOUS | Various | 6Q2025E | 0 | Y | 7219A-22 | ITS asset management maintenance and operations at various locations in the St. Louis District. | Adv. CN | 1082 | 271 | 0 | 1354 | 0 | AC-STBG |  | 1 | 1 | 1 | 78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1273 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1108 | 5 | VARIOUS | Various | 6Q2025F | 0 | Y | 7219B-22 | ITS system preservation, repairs and upgrades throughout the St. Louis District. | Adv. CN | 762 | 191 | 0 | 954 | 0 | AC-STBG |  | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1109 | 5 | VARIOUS | Various | 6Q2025G | 0 | Y | 7219C-22 | Advanced Traffic Management System (ATMS) maintenance contract throughout the St. Louis District. | Adv. CN | 362 | 91 | 0 | 454 | 0 | AC-STBG |  | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1110 | 5 | VARIOUS | Various | 6Q2025H | 0 | Y | 7227B-23 | ITS network support throughout the St. Louis District. | Adv. CN | 858 | 215 | 0 | 1073 | 0 | AC-STBG |  | 0 | 1 | 1 | 71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1111 | 5 | VARIOUS | Various | 6Q2026B | 0 | Y | 7227C-23 | Emergency response operations and staffing in the St. Louis District. | Adv. CN | 2283 | 571 | 0 | 2855 | 0 | AC-STBG |  | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1112 | 5 | VARIOUS | Various | 6Q2026C | 0 | Y | 7227D-22 | ITS operations, MoDOT staff, equipment maintenance and Transportation Management Center (TMC) operations at the TMC building in the St. Louis District. | Adv. CN | 643 | 161 | 0 | 805 | 0 | AC-STBG |  | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1113 | 5 | VARIOUS | Various | 6Q2026D | 0 | Y | 7227E-22 | ITS operations, contract staffing and professional services at the TMC building. | Adv. CN | 2843 | 711 | 0 | 3555 | 0 | AC-STBG |  | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1114 | 5 | VARIOUS | Various | 6Q2026E | 0 | Y | 7227F-22 | ITS asset management maintenance and operations at various locations in the St. Louis District. | Adv. CN | 1025 | 256 | 0 | 1282 | 0 | AC-STBG |  | 1 | 1 | 1 | 1 | 78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1115 | 5 | VARIOUS | Various | 6Q2026F | 0 | Y | 7227G-22 | ITS system preservation, repairs and upgrades throughout the St. Louis District. | Adv. CN | 763 | 191 | 0 | 955 | 0 | AC-STBG |  | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1116 | 5 | VARIOUS | Various | 6Q2026G | 0 | Y | 7227H-22 | Advanced Traffic Management System (ATMS) maintenance contract throughout the St. Louis District. | Adv. CN | 363 | 91 | 0 | 455 | 0 | AC-STBG |  | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1117 | 5 | VARIOUS | Various | 6Q2026H | 0 | Y | 7227I-23 | ITS network support throughout the St. Louis District. | Adv. CN | 819 | 205 | 0 | 1024 | 0 | AC-STBG |  | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1020 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1118 | 5 | VARIOUS | Various | 6Q3174B | 0 | Y | 6989O-20 | Emergency response operations and staffing in the St. Louis District. These funds will be transferred to the District Operations budget. | Adv. CN | 2282 | 570 | 0 | 2855 | 0 | AC-STBG |  | 3 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1119 | 5 | VARIOUS | Various | 6Q3174C | 0 | Y | 6989P-20 | ITS operations, MoDOT Staff, equipment maintenance and Transportation Management Center (TMC) operations at TMC building. | Adv. CN | 642 | 160 | 0 | 805 | 0 | AC-STBG |  | 3 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1120 | 5 | VARIOUS | Various | 6Q3174D | 0 | Y | 6989Q-20 | ITS operations, contract staffing and professional services at the Transportation Management Center building. | Adv. CN | 2762 | 690 | 0 | 3455 | 0 | AC-STBG |  | 3 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1121 | 5 | VARIOUS | Various | 6Q3174E | 0 | Y | 6989R-20 | ITS asset management maintenance and operations at various locations in the St. Louis District. | Adv. CN | 990 | 248 | 0 | 1239 | 0 | AC-STBG |  | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1236 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1122 | 5 | VARIOUS | Various | 6Q3174F | 0 | Y | 6989S-20 | ITS system preservation, repairs and upgrades throughout the St. Louis District. These funds will be transferred to the District Operations budget. | Adv. CN | 762 | 190 | 0 | 955 | 0 | AC-STBG |  | 3 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1123 | 5 | VARIOUS | Various | 6Q3174G | 0 | Y | 6989T-24 | Advanced Traffic Management System (ATMS) maintenance contract throughout St. Louis District. Consultant services for upkeep of ATMS software for Transportation Management Center and central signal system. | Adv. CN | 362 | 90 | 0 | 453 | 0 | AC-STBG |  | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1124 | 5 | VARIOUS | Various | 6Q3174H | 0 | Y | 7227J-23 | ITS network support throughout the St. Louis District. | Adv. CN | 858 | 214 | 0 | 1072 | 0 | AC-STBG |  | 0 | 1 | 71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1125 | 5 | VARIOUS | Various | 6Q3386B | 0 | Y | 6892E-23 | Emergency response operations and staffing in the St. Louis District. These funds will be transferred to the District Operations Budget. | Adv. CN | 2281 | 570 | 0 | 2854 | 0 | AC-STBG |  | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1126 | 5 | VARIOUS | Various | 6Q3386C | 0 | Y | 6Q3386C | Transportation Management Center facility operations, key MoDOT staff salaries and utility payments for ITS network devices in the St. Louis District. | Adv. CN | 641 | 160 | 0 | 804 | 0 | AC-STBG |  | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1127 | 5 | VARIOUS | Various | 6Q3386D | 0 | Y | 6892G-23 | ITS operations, contract staffing and professional services at the Transportation Management Center building. | Adv. CN | 2601 | 650 | 0 | 3254 | 0 | AC-STBG |  | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1128 | 5 | VARIOUS | Various | 6Q3386E | 0 | Y | 6892H-23 | ITS asset management maintenance and operations at various locations in the St. Louis District. $250,000 District Operations funds. | Adv. CN | 1240 | 310 | 0 | 1551 | 0 | AC-STBG |  | 1 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1450 | 0 | 0 | 0 | 0 | 0 | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1129 | 5 | VARIOUS | Various | 6Q3386F | 0 | Y | 6892I-23 | ITS parts and services in the St. Louis District. | Adv. CN | 761 | 190 | 0 | 954 | 0 | AC-STBG |  | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1130 | 5 | VARIOUS | Various | 6Q3386G | 0 | Y | 6892J-23 | Advanced Traffic Management System (ATMS) maintenance contract throughout St. Louis District. Consultant services for upkeep of ATMS software for Traffic Management Center and central signal system. | Adv. CN | 361 | 90 | 0 | 452 | 0 | AC-STBG |  | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1131 | 5 | VARIOUS | Various | 6Q3470 | 0 | Y | 6989W-22 | ITS asset management and dynamic message signs at various locations in the St. Louis District. | Adv. CN | 1042 | 260 | 0 | 1303 | 0 | AC-STBG | 6Q3475 | 1 | 154 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1132 | 5 | VARIOUS | Various | 6Q3475 | 0 | Y | 6989Z-22 | ITS asset management and closed circuit television system cameras along various routes in the St. Louis District. | Adv. CN | 385 | 96 | 0 | 482 | 0 | AC-STBG | 6Q3470 | 1 | 63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 418 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1133 | 5 | VARIOUS | Various | SL0089 | 0 | Y | 7230F-22 | Upgrade lighting at various locations in Jefferson and Franklin Counties. | Adv. CN | 1785 | 446 | 0 | 2251 | 0 | AC-STBG |  | 20 | 171 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2060 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1134 | 5 | VARIOUS | Various | SL0096B | 0 | Y |  | Emergency response operations and staffing in the St. Louis District. | Adv. CN | 2284 | 571 | 0 | 2855 | 0 | AC-STBG |  | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1135 | 5 | VARIOUS | Various | SL0096C | 0 | Y |  | ITS operations, MoDOT staff, equipment maintenance and operations at the Traffic Management Center building in the St. Louis District. | Adv. CN | 644 | 161 | 0 | 805 | 0 | AC-STBG |  | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1136 | 5 | VARIOUS | Various | SL0096D | 0 | Y |  | ITS operations, contract staffing and professional services at the Traffic Management Center building. | Adv. CN | 2844 | 711 | 0 | 3555 | 0 | AC-STBG |  | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1137 | 5 | VARIOUS | Various | SL0096E | 0 | Y |  | ITS asset management and operations at various locations in the St. Louis District. | Adv. CN | 1085 | 271 | 0 | 1356 | 0 | AC-STBG |  | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1138 | 5 | VARIOUS | Various | SL0096F | 0 | Y |  | ITS system preservation, repairs and upgrades throughout the St. Louis District. | Adv. CN | 764 | 191 | 0 | 955 | 0 | AC-STBG |  | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1139 | 5 | VARIOUS | Various | SL0096G | 0 | Y |  | Advanced Traffic Management System maintenance contract throughout the St. Louis District. | Adv. CN | 364 | 91 | 0 | 455 | 0 | AC-STBG |  | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1140 | 5 | VARIOUS | Various | SL0096H | 0 | Y |  | ITS network support throughout the St. Louis District. | Adv. CN | 905 | 226 | 0 | 1131 | 0 | AC-STBG |  | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1126 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1141 | 5 | VARIOUS | Various | SL0097 | 0 | Y | 7230H-23 | Job Order Contracting for asphalt pavement improvements at various major route locations in the St. Louis District. | Adv. CN | 2236 | 559 | 0 | 2795 | 0 | AC-STBG |  | 0 | 1 | 1 | 1 | 169 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2623 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1142 | 5 | VARIOUS | Various | SL0098 | 0 | Y |  | Job Order Contracting for bridge repairs at various major route locations in the St. Louis District. | Adv. CN | 2108 | 527 | 0 | 2635 | 0 | AC-STBG |  | 0 | 1 | 1 | 1 | 1 | 155 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2476 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1143 | 5 | VARIOUS | Various | SL0099 | 0 | Y | 7230I-23 | Job Order Contracting for concrete pavement improvements at various major route locations in the St. Louis District. | Adv. CN | 1957 | 489 | 0 | 2446 | 0 | AC-STBG |  | 0 | 1 | 1 | 1 | 148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2295 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1144 | 5 | VARIOUS | Various | SL0100 | 0 | Y | 7230J-23 | Job Order Contracting for fence repair at various locations in the St. Louis District. | Federal | 0 | 528 | 0 | 528 | 0 | STATE |  | 0 | 1 | 1 | 1 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 492 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1145 | 5 | VARIOUS | Various | SL0101 | 0 | Y | 7230K-23 | Job Order Contracting for guard cable repair at various locations in the St. Louis District. | Adv. CN | 840 | 210 | 0 | 1050 | 0 | AC-STBG |  | 0 | 1 | 1 | 1 | 64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 983 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1146 | 5 | VARIOUS | Various | SL0102 | 0 | Y |  | Job Order Contracting for guardrail repair at various locations in St. Louis City and St. Louis County. | Adv. CN | 3351 | 838 | 0 | 4189 | 0 | AC-STBG |  | 0 | 1 | 1 | 1 | 1 | 246 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1147 | 5 | VARIOUS | Various | SL0103 | 0 | Y |  | Job Order Contracting for guardrail repair at various locations in Franklin and Jefferson Counties. | Adv. CN | 769 | 192 | 0 | 961 | 0 | AC-STBG |  | 0 | 1 | 1 | 1 | 1 | 57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1148 | 5 | VARIOUS | Various | SL0104 | 0 | Y |  | Job Order Contracting for guardrail repair at various locations in St. Charles County. | Adv. CN | 769 | 192 | 0 | 961 | 0 | AC-STBG |  | 0 | 1 | 1 | 1 | 1 | 57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1149 | 5 | VARIOUS | Various | SL0105 | 0 | Y | 7230L-23 | On-call work zone enforcement at various locations in the St. Louis District. | Federal | 967 | 107 | 0 | 1074 | 0 | SAFETY |  | 0 | 1 | 1 | 1 | 71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1150 | 6 | BARRY | MO 248 E | SR0119 | 0.083 | N |  | Bridge replacement over Flat Creek. Project involves bridge J0382. | Federal | 2370 | 593 | 0 | 2963 | 0 | NHPP |  | 0 | 150 | 490 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2323 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1151 | 6 | BARRY | BU 37 S | 7P3437 | 3.415 | N |  | Pavement resurfacing from Rte. 37 to 5th Street in Cassville. | Adv. CN | 583 | 146 | 0 | 737 | 0 | AC-STBG | 7S3447 | 8 | 3 | 58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 668 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1152 | 6 | BARRY | MO 37 S | 7P3455 | 0.425 | N |  | Pavement resurfacing from Central Avenue to Rte. 60 in Monett. | Adv. CN | 211 | 53 | 0 | 272 | 0 | AC-STBG |  | 8 | 2 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 238 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1153 | 6 | BARRY | MO 37 S | 7S2182 | 0.678 | N |  | Rebuild pavement and sidewalk and intersection reconfiguration on Central Ave from Cleveland St to Bond St and add roundabout at Broadway St in Monett. Design, right of way acquisition by Monett. $1,982,304 Cost Share, $1,994,000 Monett and $399,826 Trans. Alt. funds. | Federal | 2588 | 0 | 1994 | 4607 | 0 | STBG | 7P3455 7S3444 7S3472 | 25 | 15 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4507 | 0 | 0 | 0 | 0 | 0 | 0 | 2394 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1154 | 6 | BARRY | BU 60 E | 7S3472 | 2.092 | N |  | Upgrade pedestrian facilities to comply with the ADA Transition Plan from BNSF Railway to Bridle Lane, on Rte. 37 from Cleveland Street to Myrtle Street and on Rte. 60 from Eisenhower Street to Miller Way in Monett. | Adv. CN | 1141 | 285 | 0 | 1572 | 0 | AC-STBG |  | 146 | 172 | 216 | 0 | 0 | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 990 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1155 | 6 | BARRY | US 60 E | SR0021 | 18.745 | N |  | Pavement resurfacing, add roundabout at County Road 1100 and add turn lanes at County Roads 1160, 1180, 1200, 1235, 1247, 1250, 2000 and 2210 from Rte. 37 in Monett to Rte. 14 in Marionville. | Federal | 9090 | 2272 | 0 | 11362 | 0 | NHPP |  | 0 | 200 | 625 | 1187 | 0 | 0 | 0 | 0 | 0 | 116 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9234 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1156 | 6 | BARRY | MO 86 E | 7S3492 | 22.498 | N |  | Pavement resurfacing and add centerline rumblestripes from the Kings River to Rte. 13 in Stone County and from Rte. 13 to Rte. 65 in Taney County. | Adv. CN | 3073 | 768 | 0 | 3851 | 0 | AC-STBG | 7P3394 7P3533 7S3491 7S3500 | 10 | 151 | 263 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3427 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1157 | 6 | BARRY | MO 86 E | 7S3500 | 20.29 | N |  | Pavement resurfacing and add rumblestripes from Rte. 76 to the Kings River. | Adv. CN | 2553 | 638 | 0 | 3196 | 0 | AC-STBG | 7P3394 7P3533 7S3491 7S3492 | 5 | 74 | 273 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2844 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1158 | 6 | BARRY | RT BB E | 7S3493 | 5.766 | N |  | Pavement resurfacing from Rte. 37 to County Road 2060. | Adv. CN | 799 | 200 | 0 | 1009 | 0 | AC-STBG | 7S3494 | 10 | 13 | 87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 899 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1159 | 6 | BARRY | RT C E | 7S3242 | 2.657 | N |  | Upgrade pedestrian facilities to comply with the ADA Transition Plan in Purdy, on Rte. A and Rte. 86 in Wheaton, on Rte. DD in Seligman and on Bus. 37 in Cassville. | Adv. CN | 792 | 198 | 0 | 1162 | 0 | AC-STBG |  | 172 | 1 | 193 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 786 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1160 | 6 | BARRY | RT F E | 7S3491 | 5.221 | N |  | Pavement resurfacing and add rumblestripes from Rte. 112 to Rte. 86 and upgrade pedestrian facilities to comply with the ADA Transition Plan in Roaring River State Park. | Adv. CN | 814 | 204 | 0 | 1020 | 0 | AC-STBG | 7P3394 7P3533 7S3492 7S3500 | 2 | 22 | 88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 908 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1161 | 6 | BARRY | RT H S | 7S3431 | 0.273 | N |  | Pavement resurfacing from Rte. 86 to the Arkansas State line. | Adv. CN | 50 | 12 | 0 | 70 | 0 | AC-STBG | 7S3432 7S3436 | 8 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1162 | 6 | BARRY | RT P S | 7S3432 | 1.003 | N |  | Pavement resurfacing from Rte. 86 to the Arkansas State line. | Adv. CN | 102 | 25 | 0 | 135 | 0 | AC-STBG | 7S3431 7S3436 | 8 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 114 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1163 | 6 | BARRY | RT YY E | 7S3436 | 2.751 | N |  | Pavement resurfacing from Rte. 39 to Big Bay Road. | Adv. CN | 325 | 81 | 0 | 414 | 0 | AC-STBG | 7S3431 7S3432 | 8 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1164 | 6 | BARTON | MO 126 E | 7S3531 | 1.992 | N |  | Upgrade pedestrian facilities to comply with the ADA Transition Plan on Fourth Street and Rte. 97 (Main Street) in Lockwood, Rte. 126 in Golden City, Rte. W in Iantha and Rte. C in Irwin. | Adv. CN | 1458 | 365 | 0 | 1923 | 0 | AC-STBG |  | 100 | 200 | 248 | 171 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1199 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1165 | 6 | BARTON | US 160 E | 7S3531B | 1.45 | N |  | Upgrade pedestrian facilities to comply with the ADA Transition Plan on 12th Street in Lamar | Federal | 2150 | 538 | 0 | 2688 | 0 | STBG | 7S3506 | 0 | 300 | 570 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1813 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1166 | 6 | BARTON | US 160 E | SR0002 | 0.059 | N |  | Bridge replacement over North Fork Spring River north of Golden City. Project involves bridge H0901. | Federal | 1962 | 490 | 0 | 2482 | 0 | NHPP |  | 30 | 30 | 30 | 30 | 129 | 252 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1981 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1167 | 6 | BARTON | US 160 E | SR0042 | 30.338 | N |  | Pavement resurfacing and add rumblestripes from Rte. KK to Rte. 39 south of Greenfield and extend culverts from east of Lockwood to Rte. 39 south of Greenfield. | Adv. CN | 5338 | 1334 | 0 | 6672 | 0 | AC-STBG |  | 0 | 267 | 454 | 0 | 0 | 0 | 0 | 0 | 86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1168 | 6 | BARTON | MO 43 S | 7S3495 | 24.79 | Y |  | Pavement resurfacing from Rte. 160 to Rte. 171 in Airport Drive. | Adv. CN | 2686 | 672 | 0 | 3363 | 0 | AC-STBG |  | 5 | 45 | 297 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3016 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1169 | 6 | BARTON | RT K E | 7P3484B | 0.043 | N |  | Bridge replacement over Drywood Creek 2.8 miles east of Kansas State Line (State Line Road). Project involves bridge R0141. | Federal | 962 | 241 | 0 | 1262 | 0 | NHPP | 7S3379 7S3522 SR0172 | 59 | 24 | 144 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1170 | 6 | BARTON | RT NN N | 7S3441 | 5.05 | N |  | Pavement resurfacing from Rte. K in Liberal to Rte. 160. | Adv. CN | 312 | 78 | 0 | 392 | 0 | AC-STBG |  | 2 | 6 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1171 | 6 | BARTON | RT NN S | 7S3473 | 0.407 | N |  | Upgrade pedestrian facilities to comply with the ADA Transition Plan from Maple Street to Darwin Street in Liberal. | Adv. CN | 74 | 18 | 0 | 96 | 0 | AC-STBG |  | 4 | 12 | 17 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1172 | 6 | BARTON | RT O S | 7S3522 | 0.06 | N |  | Bridge replacement over West Fork Spring River 1.3 miles south of Rte. 160. Project involves bridge N0754. | Federal | 591 | 148 | 0 | 816 | 0 | NHPP | 7P3484B 7S3379 SR0172 | 77 | 9 | 90 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 638 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1173 | 6 | BARTON | RT V E | SR0096 | 0.702 | N |  | Bridge replacement and curve straightening over Little Drywood Creek 4.4 miles west of I-49. Project involves bridge P0343. | Adv. CN | 2305 | 576 | 0 | 2881 | 0 | AC-STBG |  | 0 | 10 | 10 | 10 | 335 | 246 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2265 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1174 | 6 | BARTON | RT W S | 7S3550 | 0.006 | N |  | Replace culverts and install guardrail over Buck's Run Creek 0.7 mile south of Rte. V. Project involves bridges T1067 and T1068. | Federal | 647 | 162 | 0 | 839 | 0 | NHPP |  | 30 | 61 | 91 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 653 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1175 | 6 | BATES | MO 18 E | 7P3511 | 2.314 | Y |  | Upgrade pedestrian facilities to comply with the ADA Transition Plan on Rte. 18 in Drexel and Adrian, Rte. Y in Merwin and Loop 49, Rte. 52 and Rte. H in Butler. | Adv. CN | 114 | 29 | 0 | 145 | 0 | AC-STBG |  | 2 | 17 | 20 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 104 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1176 | 6 | BATES | IS 49 N | 7P3485 | 0.65 | N |  | Bridge improvements on various routes including Benton, Cedar, Henry, St Clair and Vernon Counties. Potential Design-Build. Involves bridges A3694;A6930;H0258;J0534;K0232;L0179;R0272;S0979;T0467; X0190;X0742;A0490. Potential bridges A2135;A2620;A2820;P0210;A0842;A4071. | Federal | 26563 | 2951 | 0 | 29714 | 0 | NHPP |  | 200 | 1100 | 1100 | 124 | 0 | 0 | 0 | 0 | 0 | 90 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1177 | 6 | BATES | IS 49 S | 7I3385 | 18.498 | N |  | Pavement resurfacing from Rtes. A and B in Rich Hill to Rte. 54 in Nevada. | Federal | 8369 | 930 | 0 | 9425 | 0 | NHPP |  | 126 | 940 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8359 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1178 | 6 | BATES | IS 49 S | 7I3515 | 44.817 | N |  | Job Order Contracting for pavement repair from the Cass County line to Rte. 54 in Vernon County. | Adv. CN | 97 | 11 | 0 | 108 | 0 | AC-NHPP |  | 0 | 0 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1179 | 6 | BATES | IS 49 S | 7I3524 | 0.3 | N |  | Bridge rehabilitation over Loop 49 and Missouri and Northern Arkansas Railroad north of Butler. Project involves twin bridges A1992. | Federal | 2699 | 300 | 0 | 3204 | 0 | NHPP |  | 203 | 382 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2617 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1180 | 6 | BATES | IS 49 S | SR0154 | 180.959 | N |  | Striping upgrades from 0.5 mile south of Rtes. A/B in Archie to Rtes. A/B in Rich Hill, from Rte. 54 in Nevada to I-44, on Rte. 7 from 0.3 mile east of Rte. B in Creighton to Rte. 13 in Clinton and on Rte. 13 from 2nd Street in Clinton to Rte. WW in Greene County. | Federal | 998 | 111 | 0 | 1109 | 0 | SAFETY |  | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1059 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1181 | 6 | BATES | MO 52 E | SR0081 | 0.095 | N |  | Replace railroad underpass on Fort Scott Street in Butler. | Adv. CN | 11660 | 2915 | 0 | 14581 | 0 | AC-STBG |  | 6 | 300 | 300 | 400 | 300 | 1410 | 0 | 0 | 0 | 0 | 0 | 1967 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9898 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1182 | 6 | BENTON | MO 52 E | 7S3398 | 5.804 | N |  | Upgrade pedestrian facilities to comply with the ADA Transition Plan including on Rtes. F and U in Cole Camp, Rte. C in Lincoln, Rtes. J and C in Calhoun and Rte. N in Blairstown. | Adv. CN | 1451 | 363 | 0 | 1816 | 0 | AC-STBG |  | 2 | 379 | 243 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1183 | 6 | BENTON | MO 52 E | SR0158 | 12.342 | N |  | Pavement resurfacing and add shoulders from Rte. 65 to Haw Creek in Morgan County. | Adv. CN | 2859 | 715 | 0 | 3574 | 0 | AC-STBG |  | 0 | 178 | 165 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1184 | 6 | BENTON | US 65 S | 7P3212 | 4.05 | N |  | Pavement resurfacing from the Osage River in Warsaw to 0.4 mile south of Rte. MM. | Federal | 1002 | 250 | 0 | 1271 | 0 | NHPP | 7P3391 7P3449 7P3450 7P3451 7P3453 | 19 | 142 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1185 | 6 | BENTON | US 65 S | 7P3449 | 8.528 | N |  | Pavement resurfacing from 0.2 mile south of Rte. MM to Rte. AA. | Federal | 1350 | 337 | 0 | 1715 | 0 | NHPP | 7P3212 7P3391 7P3450 7P3451 7P3453 | 28 | 152 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1535 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1186 | 6 | BENTON | US 65 S | 7P3451 | 4.281 | N |  | Pavement resurfacing on southbound lanes from Rte. 52 north junction to 0.8 mile north of Rte. 52 south junction. | Federal | 466 | 117 | 0 | 593 | 0 | NHPP | 7P3212 7P3391 7P3449 7P3450 7P3453 | 10 | 54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1187 | 6 | BENTON | US 65 S | 7P3453 | 33.638 | N |  | Pavement resurfacing from Rte. AA to Rte. 32 in Dallas County and add southbound left turn lane at Victory Road north of Buffalo. | Federal | 3746 | 937 | 0 | 4806 | 0 | NHPP | 7P3212 7P3391 7P3449 7P3450 7P3451 | 123 | 402 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4281 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1188 | 6 | BENTON | MO 7 S | 7P3490 | 15.35 | N |  | Pavement resurfacing from Rte. 65 to Rte. AA. | Federal | 1600 | 400 | 0 | 2005 | 0 | NHPP | 5P3325 CD0138 | 5 | 27 | 173 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1189 | 6 | BENTON | MO 7 S | SR0062 | 0.406 | N |  | Bridge rehabilitation over Truman Reservoir. Project involves bridge A3465. | Federal | 244 | 61 | 0 | 305 | 0 | NHPP |  | 0 | 2 | 35 | 64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1190 | 6 | BENTON | MO 7 S | SR0109 | 15.76 | N |  | Add roundabout at Rte. 65 south junction and safety signage at various locations from Rte. 65 to 0.3 mile east of Rte. AA. | Adv. CN | 1318 | 329 | 0 | 1647 | 0 | AC-STBG |  | 0 | 150 | 185 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1191 | 6 | BENTON | MO 7 S | SR0110 | 20.905 | N |  | Add roundabout at Cold Spring Avenue, add pedestrian signal at Main Street in Warsaw and add safety signage at various locations from 0.3 mile west of Rte. C to Rte. 65 in Warsaw. | Federal | 1616 | 179 | 0 | 1795 | 0 | SAFETY |  | 0 | 50 | 50 | 64 | 184 | 0 | 0 | 0 | 0 | 0 | 106 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1192 | 6 | BENTON | RT AA E | SR0149 | 41.169 | N |  | Pavement resurfacing including Rte. VV from Rte. 7 to 1 mile south of Rte. AA and on Rtes. U, T, YY and Rte. E from Rte. 73 to Rte. T in Dallas County. | Federal | 0 | 5379 | 0 | 5620 | 0 | STATE |  | 241 | 261 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5118 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1193 | 6 | BENTON | RT KK S | SR0108 | 29.847 | N |  | Pavement resurfacing and add shoulders on Rte. KK from Rte. 7 to end of route, on Rte. Z from Rte. 13 to Rte. 7 and on Rte. T from Rte. C to Rte. 65. | Adv. CN | 4348 | 1087 | 0 | 5435 | 0 | AC-STBG |  | 0 | 15 | 15 | 100 | 317 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4988 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1194 | 6 | BENTON | RT P E | SR0111 | 15.598 | N |  | Pavement resurfacing from Rte. ZZ to Rte. 65 and on Main Street from 1st Street to 3rd Street in Ionia, Rte. F from Rte. 52 to end of state maintenance and Rte. U from Whiteman Road to Rte. 52 in Cole Camp. | Adv. CN | 1454 | 363 | 0 | 1817 | 0 | AC-STBG |  | 0 | 5 | 5 | 5 | 22 | 173 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1607 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1195 | 6 | CEDAR | MO 32 E | 7P3397 | 4.145 | N |  | Upgrade pedestrian facilities to comply with the ADA Transition Plan on East Street/West Street and Rte. 39 (South Street) in Stockton and on Rte. 97 (Ridge Street/Main Street) in Jericho Springs. | Adv. CN | 1234 | 308 | 0 | 1544 | 0 | AC-STBG |  | 2 | 2 | 136 | 265 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1118 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1196 | 6 | CEDAR | MO 32 E | SR0059 | 1.555 | N |  | Realign curves at Rte. CC, County Road 1350 and 2.3 miles west of Bolivar, bridge replacement over Barren Creek and add turn lanes at Rte. 245 and Rte. 123. Project involves bridge H0021. | Adv. CN | 4953 | 1238 | 0 | 6191 | 0 | AC-STBG |  | 0 | 250 | 250 | 778 | 0 | 0 | 0 | 0 | 0 | 103 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4810 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1197 | 6 | CEDAR | US 54 E | SR0033 | 25.067 | N |  | Pavement resurfacing from 0.1 mile east of Rte. 32 in El Dorado Springs to Rte. MM. | Federal | 4631 | 1158 | 0 | 5789 | 0 | NHPP |  | 0 | 37 | 57 | 484 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5211 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1198 | 6 | CEDAR | RT AA S | 7S3476 | 0.113 | N |  | Bridge replacement over South Fork Turkey Creek 4 miles north of Rte. M. Project involves bridge N0490. | Adv. CN | 774 | 193 | 0 | 1091 | 0 | AC-STBG | 7S0510 | 114 | 124 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 843 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1199 | 6 | CEDAR | RT M E | 7S0510 | 0.127 | N |  | Bridge replacement over Bear Creek 0.9 mile east of Rte. 32. Project involves bridge P0360. | Federal | 1142 | 285 | 0 | 1576 | 0 | NHPP | 7S3476 | 147 | 327 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1200 | 6 | CHRISTIAN | US 160 E | 7P3529 | 0.697 | Y |  | Replace signals in Highlandville including Rte. 52 in Butler, Rte. 54 in El Dorado Springs, Rte. 65 in Buffalo, Rte. 43 in Joplin, Rte. 60 and Loop 49 in Neosho, Rte. 39 in Aurora, Rte. 59 in Goodman and Anderson and Bus. 71 in Anderson and Pineville. | Adv. CN | 4117 | 1029 | 0 | 5346 | 0 | AC-STBG |  | 200 | 400 | 800 | 0 | 0 | 0 | 0 | 0 | 248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3698 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1201 | 6 | CHRISTIAN | US 60 E | 7P3470 | 2.939 | N |  | Upgrade pedestrian facilities to comply with the ADA Transition Plan in Billings, on Rte. ZZ in Marionville, on Rte. 14 and Rte. K in Clever and on Rte. 14 and Rte. PP in Sparta. | Adv. CN | 214 | 53 | 0 | 441 | 0 | AC-STBG |  | 174 | 51 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 196 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1202 | 6 | CHRISTIAN | US 65 S | SR0105 | 16.18 | N |  | Add climbing lanes, guard cable and safety signage at various locations and add northbound right turn lane at Saddlebrooke Drive from 0.4 mile north of Rte. EE in Christian County to 0.8 mile north of Rte. 76 in Taney County. | Federal | 6534 | 1633 | 0 | 8167 | 0 | NHPP |  | 0 | 500 | 500 | 1008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1203 | 6 | CHRISTIAN | RT EE E | SR0061 | 3.713 | N |  | Safety improvements at various locations from Rte. 160 in Highlandville to Rte. 65 and add roundabout at Rte. 160. | Adv. CN | 6826 | 1706 | 0 | 8532 | 0 | AC-STBG |  | 0 | 25 | 225 | 225 | 420 | 0 | 0 | 0 | 0 | 0 | 1061 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1204 | 6 | CHRISTIAN | RT P S | 7S3435 | 4.227 | N |  | Pavement resurfacing and add rumblestripes from County Road 194 in Republic to Rte. 14 in Clever. | Adv. CN | 545 | 136 | 0 | 689 | 0 | AC-STBG | 7P3433 7P3434 7S3442 8P3197 8P3198 8S3199 | 8 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 611 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1205 | 6 | CHRISTIAN | RT W S | SR0041 | 7.051 | N |  | Pavement resurfacing from 0.1 mile south of Timbercrest Road to end of state maintenance. | Adv. CN | 589 | 147 | 0 | 736 | 0 | AC-STBG |  | 0 | 7 | 8 | 64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 657 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1206 | 6 | DADE | US 160 E | SR0053 | 0.672 | Y |  | Bridge rehabilitations including I-49 in Jasper and McDonald Cos, Rte. 13 in St Clair Co, Rte. 7 in Henry Co and Rtes. 65, 76 and Bus. 65 in Taney Co. Bridges J0705, A2541, A3580, A5355, A5357, A5359, A5812, A5813, A6566, A6567, A6926, A6932, A7002, A7685, B0428, A6378. | Federal | 3635 | 909 | 0 | 4544 | 0 | NHPP |  | 0 | 2 | 148 | 537 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1207 | 6 | DADE | US 160 E | SR0104 | 0.573 | N |  | Curve realignment from County Road 114 to Rte. 245. | Adv. CN | 1635 | 409 | 0 | 2044 | 0 | AC-STBG |  | 0 | 10 | 190 | 220 | 0 | 0 | 0 | 0 | 0 | 109 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1515 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1208 | 6 | DADE | MO 215 S | 7S3480 | 0.349 | N |  | Bridge rehabilitation over Stockton Lake 1.3 miles west of Bona. Project involves bridge A2083. | Federal | 807 | 202 | 0 | 1077 | 0 | NHPP | 7S3479 7S3508 | 66 | 133 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 876 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1209 | 6 | DADE | RT D S | 7S3508 | 0.225 | N |  | Bridge replacement over Horse Creek. Project involves bridge P0844. | Federal | 925 | 231 | 0 | 1255 | 0 | NHPP | 7S3479 7S3480 | 97 | 270 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 886 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1210 | 6 | DADE | RT K E | 7S3479 | 0.123 | N |  | Bridge replacement over Jordan Creek near Everton. Project involves bridge N0280. | Federal | 1078 | 269 | 0 | 1416 | 0 | NHPP | 7S3480 7S3508 | 67 | 360 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 987 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1211 | 6 | DALLAS | MO 64 E | 7P3542 | 0.106 | N |  | Bridge replacement over the Niangua River near Bennett Spring State Park. Project involves bridge J0782. | Adv. CN | 4933 | 1233 | 0 | 6171 | 0 | AC-STBG |  | 5 | 10 | 655 | 635 | 0 | 0 | 0 | 0 | 0 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4831 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1212 | 6 | DALLAS | US 65 S | 7P3391 | 1.034 | N |  | Pavement resurfacing from north of Rte. 32 to north of Ash Street in Buffalo. | Federal | 221 | 55 | 0 | 286 | 0 | NHPP | 7P3212 7P3449 7P3450 7P3451 7P3453 | 10 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 251 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1213 | 6 | DALLAS | US 65 S | SR0089 | 6.41 | N |  | Add roundabouts at Rte. 73 and at Truman Road in Buffalo and add passing lane from Rte. D to Rte. 64 in Urbana. | Federal | 2638 | 659 | 0 | 3297 | 0 | NHPP |  | 0 | 100 | 168 | 375 | 0 | 0 | 0 | 0 | 0 | 72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2582 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1214 | 6 | DALLAS | US 65 S | SR0127 | 0.879 | N |  | Upgrade pedestrian facilities to comply with the ADA Transition Plan from Rte. 32 to 0.1 mile south of Truman Road in Buffalo. | Federal | 818 | 205 | 0 | 1023 | 0 | STBG | 8P3050C 8S3149 8S3162 8S3169 8S3172 8S3190 SU0085 | 0 | 101 | 181 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 727 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1215 | 6 | DALLAS | MO 73 N | SR0157 | 20.034 | N |  | Pavement resurfacing from Rte. 54 in Camden County to Rte. 65 near Buffalo. | Adv. CN | 1775 | 444 | 0 | 2219 | 0 | AC-STBG |  | 0 | 40 | 188 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1991 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1216 | 6 | GREENE | IS 44 E | SR0098 | 1.9 | N |  | Add high friction surface treatment on the eastbound lanes west of Rte. N in Greene County, the westbound lanes 1.5 miles west of Rte. 38 (Spur Drive) in Marshfield and on Rte. 39 south of Rte. P in Lawrence County. | Federal | 1145 | 127 | 0 | 1272 | 0 | SAFETY |  | 0 | 5 | 5 | 79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1183 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1217 | 6 | GREENE | US 60 E | 7P3271 | 2.905 | N |  | Pavement resurfacing from 0.5 mile east of Rte. 125 to 0.2 mile west of Rte. VV in Rogersville. | Federal | 803 | 201 | 0 | 1027 | 0 | NHPP | 8P3122B | 23 | 93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 911 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1218 | 6 | GREENE | US 65 N | 7P3393 | 6.998 | N |  | Pavement resurfacing on northbound lanes from Rtes. KK and A to north of Rte. AA in Dallas County. | Federal | 795 | 199 | 0 | 1000 | 0 | NHPP | 8P3164 | 6 | 17 | 87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 890 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1219 | 6 | GREENE | US 65 S | 7P2212D | 5.187 | N |  | Pavement improvements from Pomme de Terre River to Rte. KK. | Federal | 2422 | 605 | 0 | 3036 | 0 | NHPP |  | 9 | 1 | 1 | 1 | 3 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2846 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1220 | 6 | GREENE | RT BB E | 7P3107M | 0.067 | N |  | Bridge replacement over the Little Sac River 3.4 miles west of Rte. 13. Project involves bridge K0818. | Federal | 1568 | 392 | 0 | 2286 | 0 | NHPP |  | 324 | 237 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1723 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1221 | 6 | GREENE | RT K S | SR0023 | 0.507 | N |  | Pavement resurfacing from Rte. 266 to I-44. | Adv. CN | 136 | 34 | 0 | 170 | 0 | AC-STBG | SR0025 SR0026 SR0035 | 0 | 4 | 4 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1222 | 6 | GREENE | OR 60 | 7S3488 | 1.13 | N |  | Add outer roads from Rte. 125 to County Road 243 in Rogersville. | Adv. CN | 1946 | 487 | 0 | 2533 | 0 | AC-STBG | 8P0683E | 100 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 805 | 0 | 0 | 0 | 0 | 0 | 0 | 1428 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1223 | 6 | GREENE | RT V S | 7S3486 | 0.06 | N |  | Bridge replacement over Clear Creek north of Ash Grove. Project involves bridge T0493. | Adv. CN | 1801 | 450 | 0 | 2291 | 0 | AC-STBG |  | 40 | 196 | 259 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1794 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1224 | 6 | GREENE | RT V S | SR0025 | 8.026 | N |  | Pavement resurfacing from Rte. 123 in Walnut Grove to Rte. 160 in Ash Grove. | Adv. CN | 446 | 111 | 0 | 557 | 0 | AC-STBG | SR0023 SR0026 SR0035 | 0 | 4 | 4 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 501 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1225 | 6 | HENRY | MO 13 N | SR0029 | 12.407 | N |  | Pavement resurfacing from north of NW 1400 Road to Rte. 7 in Clinton. | Federal | 1798 | 450 | 0 | 2248 | 0 | NHPP |  | 0 | 15 | 20 | 189 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1226 | 6 | HENRY | MO 13 N | SR0130 | 0.217 | N |  | Bridge deck sealing on northbound bridge over the Truman Reservoir 3.1 miles south of Rte. 7. Project involves bridge A5385. | Federal | 976 | 244 | 0 | 1220 | 0 | NHPP |  | 0 | 5 | 5 | 5 | 55 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1227 | 6 | HENRY | MO 13 S | 7I3525 | 31.281 | N |  | Concrete repairs including St. Clair County and on Rte. 65 in Benton County, Rte. 32 in Cedar County, Rte. 54 in Vernon County and on interchange ramps at I-49 and Rte. B in Bates County. | Adv. CN | 1195 | 299 | 0 | 1504 | 0 | AC-STBG |  | 10 | 257 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1237 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1228 | 6 | HENRY | MO 13 S | 7P3465 | 0.376 | N |  | Add turn lanes, sidewalk, and pavement resurfacing at Rtes. 7 and 18 south junction and pavement resurfacing at Rte. 7 north junction in Clinton. | Federal | 748 | 187 | 0 | 1117 | 0 | NHPP |  | 132 | 111 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1229 | 6 | HENRY | MO 13 S | 7P3484C | 1.403 | N |  | Bridge replacement on southbound bridges over Deepwater Creek and Menson Creek near Deepwater. Project involves bridges A0488 and A0489. | Federal | 8218 | 2055 | 0 | 10773 | 0 | NHPP |  | 500 | 697 | 1134 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1230 | 6 | HENRY | MO 13 S | SR0031 | 7.658 | N |  | Pavement resurfacing from 0.2 mile south of Rte. 7 in Clinton to Rte. 52. | Federal | 2006 | 502 | 0 | 2508 | 0 | NHPP |  | 0 | 15 | 25 | 211 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2257 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1231 | 6 | HENRY | MO 18 E | SR0028 | 2.079 | N |  | Pavement resurfacing on Ohio Street from Montgomery Street to Rte. 13 in Clinton. | Federal | 633 | 158 | 0 | 791 | 0 | NHPP |  | 0 | 4 | 7 | 68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 712 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1232 | 6 | HENRY | BU 52 E | 7S3399 | 5.659 | N |  | Upgrade pedestrian facilities to comply with the ADA Transition Plan at various locations in Deepwater, on Rte. BB in Brownington, on Rte. D in Lowry City and on Rtes. 52, KK and P in Appleton City. | Adv. CN | 675 | 169 | 0 | 846 | 0 | AC-STBG |  | 2 | 2 | 95 | 111 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 634 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1233 | 6 | HENRY | MO 52 E | 7P3499 | 0.06 | N |  | Bridge replacement over the Katy Trail in Windsor. Project involves bridge K0930. | Federal | 814 | 204 | 0 | 1122 | 0 | NHPP |  | 102 | 202 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 816 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1234 | 6 | HENRY | MO 7 S | 7P3528 | 0.383 | N |  | Bridge replacements on the southbound bridges over Big River Overflow. Project involves bridges A3700 and A3701. | Federal | 3142 | 785 | 0 | 3977 | 0 | NHPP |  | 50 | 385 | 425 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3117 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1235 | 6 | HENRY | MO 7 S | SR0024 | 20.928 | N |  | Pavement resurfacing from east of Rte. B to 0.2 mile south of Rte. 18 (Ohio Street) in Clinton. | Federal | 3210 | 802 | 0 | 4012 | 0 | NHPP |  | 0 | 30 | 33 | 323 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3626 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1236 | 6 | HENRY | MO 7 S | SR0027 | 0.323 | N |  | Pavement resurfacing from Rte. 13 to 0.1 mile east of Vansant Road in Clinton. | Federal | 187 | 47 | 0 | 234 | 0 | NHPP |  | 0 | 4 | 4 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 206 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1237 | 6 | HENRY | RT C E | SR0090 | 17.511 | N |  | Pavement resurfacing and add shoulders from Rte. 7 to Rte. 65. | Adv. CN | 3289 | 822 | 0 | 4111 | 0 | AC-STBG |  | 0 | 20 | 20 | 110 | 275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3686 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1238 | 6 | HICKORY | US 54 E | 7P3450 | 8.27 | N |  | Pavement and bridge resurfacing from west of Rte. D to 1.8 miles east of Rte. BB. Project involves bridge K0091. | Federal | 1434 | 358 | 0 | 1821 | 0 | NHPP | 7P3212 7P3391 7P3449 7P3451 7P3453 | 29 | 176 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1616 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1239 | 6 | HICKORY | MO 64 E | 7P3503 | 83.395 | N |  | Pavement preservation treatment including Rte. 83; Rtes. T and 83 in Polk County; Rtes. M and 76 in Stone County; Rtes. 76, E and BB in McDonald County; Rte. CC in Webster County and Rte. W in Barry County. | Adv. CN | 2082 | 521 | 0 | 2629 | 0 | AC-STBG | SU0065 | 26 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2403 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1240 | 6 | HICKORY | RT P E | 7S3504 | 1.665 | N |  | Upgrade pedestrian facilities to comply with the ADA Transition Plan in Cross Timbers, Flemington, Hermitage, Humansville, Pittsburg, Urbana, Weaubleau and various Frisco Highline Trail crossings in Polk County. $329,000 Statewide Transportation Alternatives funds. | Adv. CN | 1087 | 272 | 0 | 1379 | 0 | AC-STBG |  | 20 | 255 | 218 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 876 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1241 | 6 | JASPER | MO 249 S | 7P3372C | 2.495 | Y | 10HS-22 | Repair slide at Rte. 171 in Carterville. | Adv. CN | 2413 | 603 | 0 | 3203 | 0 | AC-STBG |  | 187 | 363 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2653 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1242 | 6 | JASPER | MO 43 N | SR0073 | 0.196 | N |  | Bridge rehabilitations 0.4 mile south of Pine Road over North Fork Spring River and 0.6 mile south of Pecan Road over Spring River. Project involves bridges A2690 and A2691. | Adv. CN | 2082 | 521 | 0 | 2603 | 0 | AC-STBG |  | 0 | 20 | 40 | 293 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1243 | 6 | JASPER | MO 43 S | SR0008 | 0.221 | Y |  | Bridge replacements on Main Street over Kansas City Southern railroad and Turkey Creek and add sidewalk from F Street to Murphy Boulevard in Joplin. Project involves bridges K0415 and J0339. | Federal | 7388 | 1847 | 0 | 9335 | 0 | NHPP |  | 100 | 50 | 50 | 50 | 697 | 884 | 0 | 0 | 0 | 0 | 0 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7481 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1244 | 6 | JASPER | MO 43 S | SR0017 | 2.879 | Y |  | Pavement resurfacing from 0.1 mile south of Rte. 171 in Airport Drive to 0.1 mile south of Murphy Boulevard in Joplin. Project involves bridge J0339. | Federal | 757 | 189 | 0 | 946 | 0 | NHPP | SR0016 | 0 | 6 | 8 | 81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 851 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1245 | 6 | JASPER | MO 43 S | SR0048 | 0.022 | Y |  | Replace signal on Main Street Road at Fountain Road in Airport Drive. | Federal | 385 | 96 | 0 | 481 | 0 | NHPP |  | 0 | 36 | 96 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 347 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1246 | 6 | JASPER | IS 44 E | SR0102 | 4.08 | N |  | Roadway improvements at the I-49 and Rte. 59 interchange in Fidelity. | Federal | 25961 | 2885 | 0 | 28846 | 0 | NHPP |  | 0 | 244 | 1000 | 1000 | 3061 | 0 | 0 | 0 | 0 | 0 | 1095 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1247 | 6 | JASPER | IS 44 E | SR0150 | 99.992 | Y |  | Striping upgrades from 1 mile east of Prigmor Avenue in Joplin to Rte. 360 in Greene County and from 2 miles east of Rte. 125 to 3 miles east of Sampson Road in Webster County and on I-49 from Rte. 175 in Newton County to Rte. EE near Pineville. | Federal | 713 | 79 | 0 | 792 | 0 | SAFETY | SR0152 SR0153 SU0151 | 0 | 68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 724 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1248 | 6 | JASPER | LP 44 E | 7S3440 | 1.454 | N |  | Pavement resurfacing on High Street from Rte. 37 to I-44 and upgrade pedestrian facilities to comply with the ADA Transition Plan at the 5th Street and 9th Street intersections in Sarcoxie. | Adv. CN | 309 | 77 | 0 | 394 | 0 | AC-STBG | 7S3454 SR0036 SR0037 | 8 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1249 | 6 | JASPER | LP 49 S | 7S3430 | 0.148 | Y |  | Payment to Joplin for intersection improvements at Range Line Road and 15th Street in Joplin. $432,443 Cost Share funds. | Adv. CN | 366 | 91 | 0 | 457 | 0 | AC-STBG |  | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1250 | 6 | JASPER | MO 66 E | 7S2185B | 0.992 | Y | 11HS-21 | Pavement and operational improvements on 7th Street from Rte. P (Schifferdecker Avenue) to Maiden Lane in Joplin. | Adv. CN | 5640 | 1410 | 0 | 7850 | 0 | AC-STBG |  | 800 | 800 | 1199 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1251 | 6 | JASPER | MO 66 E | 7S2185C | 0.975 | Y | 07HS-21 | Pavement, operational improvements and upgrade pedestrian facilities to comply with the ADA Transition Plan on 7th Street from Maiden Lane to Rte. 43 (Main Street) in Joplin. $500,000 Statewide Transportation Alternatives funds. | Adv. CN | 9512 | 2378 | 0 | 11940 | 0 | AC-STBG |  | 50 | 2455 | 1512 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7873 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1252 | 6 | JASPER | MO 66 E | 7S2185D | 1.015 | Y | 08HS-21 | Pavement, operational improvements and upgrade pedestrian facilities to comply with the ADA Transition Plan on 7th Street from Rte. 43 (Main Street) to St. Louis Avenue in Joplin. $300,000 Statewide Transportation Alternatives funds. | Adv. CN | 9505 | 2376 | 0 | 12900 | 0 | AC-STBG |  | 1019 | 1792 | 1721 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8318 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1253 | 6 | JASPER | MO 66 E | 7S2185E | 0.988 | Y | 12HS-21 | Pavement and operational improvements on 7th Street from St. Louis Avenue to Loop 49 (Rangeline Road) in Joplin. | Adv. CN | 6188 | 1547 | 0 | 8535 | 0 | AC-STBG |  | 800 | 825 | 1401 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5459 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1254 | 6 | JASPER | MO 66 E | 7S2185F | 0.992 | Y | 09HS-21 | Upgrade pedestrian facilities to comply with the ADA Transition Plan on 7th Street from Rte. P (Schifferdecker Avenue) to Maiden Lane Avenue in Joplin. | Adv. CN | 2175 | 544 | 0 | 2869 | 0 | AC-STBG |  | 150 | 466 | 445 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1758 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1255 | 6 | JASPER | MO 66 E | 7S2185G | 0.988 | Y | 10HS-21 | Upgrade pedestrian facilities to comply with the ADA Transition Plan on 7th Street from St. Louis Avenue to Loop 49 (Range Line Road) in Joplin. | Adv. CN | 2525 | 631 | 0 | 3356 | 0 | AC-STBG |  | 200 | 527 | 494 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2085 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1256 | 6 | JASPER | MO 96 E | 7S3501 | 0.08 | N |  | Bridge replacement over Rte. 171 west of Carthage. Project involves bridge A3227. | Federal | 2485 | 621 | 0 | 3490 | 0 | NHPP |  | 384 | 4 | 366 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2736 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1257 | 6 | JASPER | MO 96 E | 7S3506B | 1.12 | N |  | Upgrade pedestrian facilities to comply with the ADA Transition Plan on Central Avenue from I-49 to Garrison Avenue in Carthage. | Adv. CN | 1821 | 455 | 0 | 2301 | 0 | AC-STBG | 7P3386B SR0060 | 25 | 484 | 299 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1443 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1258 | 6 | JASPER | MO 96 E | SR0060 | 1.12 | N |  | Pavement and operational improvements on Central Avenue from I-49 to Rte. 571 (Garrison Street) in Carthage. | Federal | 6771 | 1693 | 0 | 8464 | 0 | NHPP | 7P3386B 7S3506B | 0 | 264 | 1027 | 0 | 0 | 0 | 0 | 0 | 240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6933 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1259 | 6 | JASPER | RT BB S | SR0037 | 6.645 | N |  | Pavement resurfacing and add rumblestripes from Rte. N to Rte. 96. | Adv. CN | 1229 | 307 | 0 | 1536 | 0 | AC-STBG | 7S3440 7S3454 SR0036 | 0 | 174 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1362 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1260 | 6 | JASPER | RT FF E | 7S3059 | 0.4 | Y | 19HS-22 | Add railroad overpass on 32nd Street at Kansas City Southern Railway in Joplin. | Adv. CN | 8994 | 2249 | 0 | 11263 | 0 | AC-NHPP |  | 20 | 20 | 20 | 24 | 190 | 472 | 0 | 0 | 0 | 0 | 0 | 3278 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7239 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1261 | 6 | JASPER | RT FF E | 7S3059B | 0.4 | Y |  | Relocate Davis Boulevard intersection and add signal on 32nd Street in Joplin. | Adv. CN | 2056 | 514 | 0 | 2570 | 0 | AC-NHPP |  | 0 | 81 | 138 | 0 | 0 | 0 | 0 | 0 | 98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2253 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1262 | 6 | JASPER | RT HH E | 7S3378 | 0.328 | N |  | Payment to Carthage for addition of roundabout at I-49 southbound exit ramp and Dr. Russell Smith Way in Carthage. $1,333,841 Cost Share funds. | Adv. CN | 1072 | 268 | 0 | 1345 | 0 | AC-STBG |  | 5 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1334 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1263 | 6 | JASPER | RT M E | SR0036 | 6.9 | N |  | Pavement resurfacing and add rumblestripes from Rte. 171 to Rte. 43. | Adv. CN | 1658 | 415 | 0 | 2073 | 0 | AC-STBG | 7S3440 7S3454 SR0037 | 0 | 234 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1839 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1264 | 6 | JASPER | RT M E | SR0074 | 0.019 | N |  | Bridge rehabilitation 0.7 mile east of Rte. 43 over Duval Creek. Project involves bridge A2862. | Adv. CN | 296 | 74 | 0 | 370 | 0 | AC-STBG |  | 0 | 10 | 10 | 43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 307 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1265 | 6 | LAWRENCE | MO 39 S | SR0019 | 2.729 | N | SP1812-18 | Pavement resurfacing from west of Lewis Shaw Avenue to Rte. 60 in Aurora. | Federal | 604 | 151 | 0 | 755 | 0 | NHPP |  | 0 | 2 | 8 | 63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 682 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1266 | 6 | LAWRENCE | BU 60 E | 7P3527 | 4.848 | N |  | Upgrade pedestrian facilities to comply with the ADA Transition Plan on Bus. 60 and Rte. 39 in Aurora, on Rte. H in Freistatt, on Rte. DD and Rte. 39 in Miller, on Loop 44 in Mt. Vernon, on Rte. 37 and Rte. 97 in Pierce City and on Rte. P in Verona. | Adv. CN | 2077 | 519 | 0 | 3104 | 0 | AC-STBG | 8S3200 | 498 | 631 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1267 | 6 | LAWRENCE | BU 60 E | 7S3442 | 4.461 | N |  | Pavement resurfacing and add rumblestripes from Rte. 60 in Verona to west of Cowan Drive in Aurora. | Adv. CN | 714 | 179 | 0 | 904 | 0 | AC-STBG | 7P3433 7P3434 7S3435 8P3197 8P3198 8S3199 | 11 | 90 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 803 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1268 | 6 | LAWRENCE | BU 60 E | 7S3444 | 4.057 | N |  | Pavement resurfacing and add rumblestripes from Rte. H in Monett to Rte. 60. | Adv. CN | 571 | 143 | 0 | 759 | 0 | AC-STBG |  | 45 | 2 | 52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 660 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1269 | 6 | LAWRENCE | BU 60 E | SR0022 | 3.528 | N |  | Pavement resurfacing from west of Cowan Drive to Rte. 60 in Aurora. | Federal | 458 | 115 | 0 | 573 | 0 | NHPP |  | 0 | 2 | 6 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 515 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1270 | 6 | LAWRENCE | US 60 E | 7P3433 | 10.693 | N |  | Railroad crossing safety improvements at various locations from Western Avenue in Marionville to County Road 194 west of Republic. $1,689,000 Consolidated Rail Infrastructure and Safety Improvements Program and $1,519,000 Grade Crossing Safety Account. | Adv. CN | 1519 | 1347 | 0 | 3263 | 0 | AC-STBG | 7P3434 7S3435 7S3442 8P3197 8P3198 8S3199 | 309 | 171 | 0 | 0 | 0 | 0 | 0 | 88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2695 | 0 | 0 | 0 | 0 | 0 | 336 | 2864 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1271 | 6 | LAWRENCE | US 60 E | 7P3434 | 10.598 | N |  | Pavement resurfacing and add turn lanes at various locations from 0.1 mile east of Western Avenue in Marionville to County Road 194 west of Republic. | Federal | 2978 | 744 | 0 | 3798 | 0 | NHPP | 7P3433 7S3435 7S3442 8P3197 8P3198 8S3199 | 74 | 602 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1272 | 6 | LAWRENCE | MO 97 S | 7S3381 | 0.606 | N |  | Bridge replacement and culvert replacement over the Spring River and Spring Creek. Project involves bridges L0180 and Y0134. | Federal | 1928 | 482 | 0 | 2674 | 0 | NHPP |  | 264 | 331 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2077 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1273 | 6 | LAWRENCE | RT P S | 7S3494 | 5.59 | N |  | Pavement resurfacing and add rumblestripes from Rte. 39 to Bus. 60 in Verona. | Adv. CN | 693 | 173 | 0 | 868 | 0 | AC-STBG | 7S3493 | 2 | 18 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 773 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1274 | 6 | MCDONALD | MO 43 S | 7S3379 | 0.33 | N |  | Bridge replacement and streambank stabilization over the Elk River. Project involves bridge A0826. | Federal | 3646 | 912 | 0 | 4987 | 0 | NHPP |  | 429 | 136 | 518 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3902 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1275 | 6 | MCDONALD | IS 49 S | 7I3517 | 15.978 | Y | 7I3517 | Job Order Contracting for pavement repair from Rte. 59 to Arkansas State line. | Adv. CN | 142 | 16 | 0 | 158 | 0 | AC-NHPP |  | 0 | 0 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 124 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1276 | 6 | MCDONALD | IS 49 S | SR0016 | 6.637 | N |  | Pavement resurfacing from Rte. 59 near Goodman to 2.1 miles south of Rte. 76. | Federal | 3234 | 359 | 0 | 3593 | 0 | NHPP | SR0017 | 0 | 10 | 48 | 301 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3234 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1277 | 6 | MCDONALD | IS 49 S | SR0153 | 7.809 | Y |  | Striping upgrades from Rte. EE near Pineville to the Arkansas State line. | Federal | 165 | 18 | 0 | 183 | 0 | SAFETY | SR0150 SR0152 SU0151 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1278 | 6 | MCDONALD | MO 59 S | 7P3428 | 0.322 | N |  | Streambank stabilization and add sidewalk from Rte. 90 west junction to Rte. 90 east junction (Main Street) in Noel. | Adv. CN | 1402 | 351 | 0 | 2183 | 0 | AC-STBG |  | 405 | 312 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1441 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1279 | 6 | MCDONALD | MO 59 S | 7S3519 | 1.226 | Y |  | Upgrade pedestrian facilities to comply with the ADA Transition Plan in Lanagan and on Rte. 90 in Noel, Rte. W in Pineville and Rte. 76 in Anderson. | Adv. CN | 578 | 145 | 0 | 919 | 0 | AC-STBG |  | 196 | 2 | 125 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 584 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1280 | 6 | MCDONALD | US 71 S | 7P3260 | 8.996 | Y | 7P3260 | Pavement resurfacing from south of Goodin Hollow Road to the Arkansas State line, construct offset right turn lane at Rains Road and close median opening west of Wolf Den Road. | Federal | 3034 | 758 | 0 | 4040 | 0 | NHPP | 7S3443 | 243 | 328 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3464 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1281 | 6 | MCDONALD | MO 76 E | 7S3438 | 0.23 | N |  | Pavement resurfacing from Rte. 59 to 0.3 mile west of Patterson Street in Anderson. | Adv. CN | 137 | 34 | 0 | 179 | 0 | AC-STBG | 7S3445 7S3448 | 8 | 51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1282 | 6 | MCDONALD | MO 76 E | 7S3447 | 16.733 | N |  | Pavement resurfacing and add rumblestripes from Rte. U to 0.2 mile east of Old Exeter Road and on Bus. 37 (Main Street) from east of County Road 2182 to 5th Street in Cassville. | Adv. CN | 2781 | 695 | 0 | 3631 | 0 | AC-STBG | 7P3437 | 155 | 1 | 303 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1283 | 6 | MCDONALD | MO 76 E | 7S3448 | 0.66 | N |  | Pavement resurfacing from the Oklahoma State line to Rte. 43. | Adv. CN | 70 | 17 | 0 | 95 | 0 | AC-STBG | 7S3438 7S3445 | 8 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1284 | 6 | MCDONALD | MO 90 E | 7S0532 | 0.08 | Y | 7S0532 | Bridge replacement over Little Sugar Creek 1.3 miles east of Jane. Project involves bridge P0973. | Federal | 2966 | 742 | 0 | 3714 | 0 | NHPP | 7S3523 | 6 | 249 | 627 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2822 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1285 | 6 | MCDONALD | MO 90 E | SR0097 | 0.4 | N |  | Add safety signage at Slate Gap Lane, on Rte. 59 0.1 mile south of Mount Shira Road in Ginger Blue and on Rte. O south of Queen's Lace Drive near Stella. | Federal | 59 | 7 | 0 | 66 | 0 | SAFETY |  | 0 | 2 | 6 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1286 | 6 | MCDONALD | RT C E | 7S3523 | 0.234 | N |  | Bridge rehabilitation over Indian Creek. Project involves bridge R0567. | Federal | 806 | 201 | 0 | 1059 | 0 | NHPP | 7S0532 | 52 | 19 | 120 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 866 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1287 | 6 | MCDONALD | RT F E | 7S3445 | 8.23 | N |  | Pavement resurfacing from end of state maintenance to Rte. 59 in Anderson. | Adv. CN | 529 | 132 | 0 | 674 | 0 | AC-STBG | 7S3438 7S3448 | 13 | 64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 597 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1288 | 6 | MCDONALD | RT OO S | 7S3443 | 0.307 | Y | 7S3443 | Pavement resurfacing from Rte. 71 to the Arkansas State line. | Adv. CN | 90 | 23 | 0 | 121 | 0 | AC-STBG | 7P3260 | 8 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 101 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1289 | 6 | NEWTON | MO 43 S | SR0075 | 0.072 | Y |  | Replace culverts from Thurman Street to Cleveland Street in Seneca and at Rte. NN 0.1 mile north of Freeburg Road. Project involves culverts T1059, T1060, T1061 and T1062. | Federal | 0 | 978 | 0 | 978 | 0 | STATE |  | 0 | 160 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 816 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1290 | 6 | NEWTON | MO 43 S | SR0092 | 0.19 | Y |  | Intersection improvement at 34th Street and signal improvement at Loop 49 (Range Line Road) and Rte. TT (Newman Road) in Joplin. | Federal | 494 | 55 | 0 | 549 | 0 | SAFETY | SR0048 | 0 | 31 | 105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 413 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1291 | 6 | NEWTON | IS 44 E | 7I3514 | 69.112 | Y | 01HS-24 | Job Order Contracting for pavement repair from the Oklahoma State line to Rte. 360 in Greene County. | Adv. CN | 452 | 50 | 0 | 502 | 0 | AC-NHPP |  | 0 | 0 | 90 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 412 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1292 | 6 | NEWTON | IS 44 E | SR0152 | 21.548 | Y |  | Striping upgrades from the Oklahoma State line to 1 mile east of Prigmor Avenue in Joplin and on I-49 from I-44 west junction in Joplin to Rte. 175. | Federal | 356 | 39 | 0 | 395 | 0 | SAFETY | SR0150 SR0153 SU0151 | 0 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 361 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1293 | 6 | NEWTON | IS 49 N | SR0045 | 0.178 | Y |  | Bridge improvements over Shoal Creek and on Rte. 66 over Rte. 249 in Duenweg. Project involves bridges A5224, A5225 and A6147. | Federal | 1443 | 160 | 0 | 1603 | 0 | NHPP |  | 0 | 24 | 199 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1380 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1294 | 6 | NEWTON | MO 59 S | 7S3446 | 23.488 | N |  | Pavement resurfacing including the culvert on Splitlog Road, add rumblestripes from Loop 49 in Neosho to the Arkansas State line and curve widening at Rte. EE west intersection. Project involves culvert A4335. | Adv. CN | 4303 | 1076 | 0 | 5453 | 0 | AC-STBG |  | 74 | 1713 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3666 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1295 | 6 | NEWTON | BU 60 E | 7S3390 | 6.996 | N |  | Pavement resurfacing from Rtes. 60 and 59 north junction 2.2 miles west of Granby to Rtes. 60 and 59 south junction in Neosho. | Federal | 1001 | 250 | 0 | 1264 | 0 | NHPP |  | 13 | 17 | 109 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1296 | 6 | NEWTON | BU 60 E | SR0113 | 1.149 | N |  | Rebuild pavement from Stadium Drive to north of Daugherty Road in Neosho. | Federal | 3504 | 876 | 0 | 4380 | 0 | NHPP |  | 0 | 10 | 10 | 60 | 368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3932 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1297 | 6 | NEWTON | US 60 E | 7P3386 | 41.773 | N |  | Pavement resurfacing and bridge rehabilitations from the Oklahoma State line to Rte. 37 in Monett. Project involves bridges A0333 and A0334. | Federal | 6063 | 1516 | 0 | 7587 | 0 | NHPP |  | 8 | 162 | 629 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6788 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1298 | 6 | NEWTON | US 60 E | 7P3386B | 5.902 | N |  | Concrete pavement repairs from 0.1 mile east of I-49 to Rte. 59 in Neosho and from 0.8 mile west of Rtes. W and M to Vixen Road east of Granby. | Federal | 246 | 61 | 0 | 307 | 0 | NHPP | 7S3506B SR0060 | 0 | 10 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1299 | 6 | NEWTON | US 60 E | SR0095 | 0.442 | N |  | Add roundabout at Rte. HH in Neosho and at Rte. 97 in Yonkerville and add turn lanes at Rtes. Y and CC, Hammer Road and Oak Ridge Drive. $2,624,000 Open Container funds. | Federal | 5378 | 598 | 0 | 5976 | 0 | SAFETY |  | 0 | 500 | 1093 | 0 | 0 | 0 | 0 | 0 | 260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4123 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1300 | 6 | NEWTON | MO 86 E | 7S3454 | 8.28 | Y | 06HS-22 | Pavement resurfacing and add rumblestripes from I-44 in Joplin to Rte. BB (Iris Road). | Adv. CN | 1898 | 475 | 0 | 2467 | 0 | AC-STBG | 7S3440 SR0036 SR0037 | 94 | 222 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2151 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1301 | 6 | NEWTON | MO 86 E | 7S3487 | 0.1 | N |  | Add roundabout on Loop 49 at Hammer Road. Design, right of way acquisition and inspection by Neosho. $843,947 Neosho and $1,159,696 Cost Share funds. | Adv. CN | 1236 | 0 | 844 | 2085 | 0 | AC-STBG |  | 5 | 3 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2064 | 0 | 0 | 0 | 0 | 0 | 0 | 844 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1302 | 6 | NEWTON | RT B S | 7S3496 | 2.628 | N |  | Pavement resurfacing from Rte. 60 in Granby to Rte. 86. | Adv. CN | 234 | 58 | 0 | 294 | 0 | AC-STBG | 7S3497 | 2 | 6 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 259 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1303 | 6 | NEWTON | RT E S | 7S3497 | 5.266 | N |  | Pavement resurfacing from Rte. J east of Diamond to Rte. 60 in Granby. | Adv. CN | 386 | 96 | 0 | 484 | 0 | AC-STBG | 7S3496 | 2 | 8 | 43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 431 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1304 | 6 | NEWTON | RT T S | 7S3506 | 0.72 | N |  | Upgrade pedestrian facilities to comply with the ADA Transition Plan in Fairview and on Rtes. E and 60 in Granby, Bus. 60 in Neosho, Rte. A in Stella, Rte. 37 in Wentworth and Rte. U in La Russell. | Adv. CN | 646 | 161 | 0 | 832 | 0 | AC-STBG | 7S3531B | 25 | 156 | 111 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 530 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1305 | 6 | POLK | MO 123 S | SR0055 | 0.036 | N |  | Repair culverts at Spring Creek, on Rte. 83 at Mile Creek and on Rte. O at Ashlock Creek. Project includes bridges H0406, L0341 and P0984. | Adv. CN | 1220 | 305 | 0 | 1525 | 0 | AC-STBG |  | 0 | 5 | 5 | 5 | 90 | 137 | 0 | 0 | 0 | 0 | 0 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1306 | 6 | POLK | MO 83 S | SR0035 | 14.23 | N |  | Pavement resurfacing and add rumblestripes from Rte. V to Rte. 32 in Bolivar. | Adv. CN | 1694 | 423 | 0 | 2117 | 0 | AC-STBG | SR0023 SR0025 SR0026 | 0 | 20 | 64 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1893 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1307 | 6 | POLK | RT D S | 7S3509 | 0.074 | N |  | Bridge rehabilitation over Piper Creek 2 miles north of Bolivar. Project involves bridge A2638. | Federal | 590 | 147 | 0 | 749 | 0 | NHPP |  | 12 | 38 | 84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 615 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1308 | 6 | POLK | RT U S | SR0026 | 5.12 | N |  | Pavement resurfacing and add rumblestripes from Rte. 13 in Bolivar to end of state maintenance. $436,000 Open Container funds. | Adv. CN | 942 | 235 | 0 | 1177 | 0 | AC-STBG |  | 0 | 15 | 23 | 87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1052 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1309 | 6 | POLK | RT Z E | 7S3368B | 0.018 | N |  | Culvert replacement over Pratter Branch 0.2 mile west of Rock Prairie. Project involves culvert W0507. | Federal | 0 | 558 | 0 | 562 | 0 | STATE |  | 4 | 2 | 2 | 2 | 0 | 102 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1310 | 6 | ST. CLAIR | MO 13 S | 7P3034B | 1.27 | N |  | Pavement improvements on the southbound lanes from SE 1100 Road to NE 201 Road. | Federal | 724 | 181 | 0 | 912 | 0 | NHPP |  | 7 | 1 | 1 | 1 | 42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 860 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1311 | 6 | ST. CLAIR | MO 82 E | 7P3477 | 0.14 | N |  | Bridge rehabilitation over the Sac River at Truman Lake. Project involves bridge A3905. | Federal | 1483 | 371 | 0 | 1983 | 0 | NHPP |  | 129 | 227 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1627 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1312 | 6 | ST. CLAIR | MO 82 E | 7P3534 | 0.093 | N |  | Bridge rehabilitation over Truman Reservoir. Project involves bridge A4070. | Federal | 608 | 152 | 0 | 762 | 0 | NHPP |  | 2 | 49 | 85 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 624 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1313 | 6 | ST. CLAIR | RT V S | 7S3475 | 0.374 | N |  | Bridge rehabilitation over Coon Creek 4.7 miles north of Rte. 54. Project involves bridge A3911. | Adv. CN | 712 | 178 | 0 | 948 | 0 | AC-STBG |  | 58 | 116 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 774 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1314 | 6 | STONE | MO 13 S | 7P3394 | 11.09 | N |  | Pavement resurfacing from south of the Kimberling City Bridge to the Arkansas State line in Blue Eye. | Federal | 1510 | 377 | 0 | 1905 | 0 | NHPP | 7P3533 7S3491 7S3492 7S3500 | 18 | 28 | 164 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1695 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1315 | 6 | STONE | MO 13 S | 7P3457 | 0.643 | N |  | Bridge washing over Table Rock Lake in Kimberling City and on Rte. 39 over Table Rock Lake in Shell Knob. Project involves bridges A0585 and A0260. | Federal | 86 | 22 | 0 | 110 | 0 | NHPP |  | 2 | 2 | 3 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1316 | 6 | STONE | MO 13 S | SR0094 | 0.088 | N |  | Add roundabout at Rte. 160 near Reeds Spring. | Federal | 3038 | 338 | 0 | 3376 | 0 | SAFETY |  | 0 | 200 | 434 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2722 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1317 | 6 | STONE | MO 13 S | SR0132 | 0.363 | N |  | Bridge rehabilitation over Table Rock Lake. Project involves bridge A0585. | Federal | 511 | 128 | 0 | 639 | 0 | NHPP |  | 0 | 5 | 5 | 75 | 95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 459 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1318 | 6 | STONE | US 160 E | 7P3533C | 9.239 | N |  | Pavement resurfacing and add rumblestripes from Rte. 13 to 0.4 mile east of Rte. 65. | Adv. CN | 3870 | 968 | 0 | 4840 | 0 | AC-STBG |  | 2 | 393 | 455 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3988 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1319 | 6 | STONE | MO 265 S | SR0010 | 1.421 | N |  | Upgrade pedestrian facilities to comply with the ADA Transition Plan from North Hemphill Avenue to Rte. D and on Rte. D from Rte. 265 to Pirate Lane in Crane. | Adv. CN | 354 | 89 | 0 | 469 | 0 | AC-STBG |  | 26 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 376 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1320 | 6 | STONE | MO 76 E | 7S3234 | 7.482 | N |  | Pavement resurfacing from Rte. 13 in Branson West to Rte. 376 and on Rte. 376 from the Ozark Mountain Highroad to 76 Country Boulevard/Shepherd of the Hills Expressway in Branson. | Federal | 2083 | 521 | 0 | 2637 | 0 | NHPP |  | 33 | 834 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1321 | 6 | STONE | MO 76 E | 7S3395 | 1.516 | N |  | Upgrade pedestrian facilities to comply with the ADA Transition Plan at various locations from Bus. 13 in Branson West to Rte. 376 and on Rte. 376 from Rte. 76 to Shepherd of the Hills Expressway in Branson. $1,000,000 Statewide Transportation Alternatives Funds. | Federal | 942 | 236 | 0 | 1684 | 0 | STBG |  | 506 | 53 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 1075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1322 | 6 | STONE | MO 76 E | 8P2360B | 0.628 | N |  | Payback to Silver Dollar City to add lanes and replace signal at Indian Point Road. Design, right-of-way acquisition and construction by Silver Dollar City. $1,192,033 Cost Share funds. | Adv. CN | 1040 | 260 | 0 | 1315 | 0 | AC-STBG |  | 15 | 15 | 93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1192 | 0 | 0 | 0 | 0
1323 | 6 | STONE | MO 76 E | SR0050 | 1.127 | Y |  | Bridge painting including Rte. 248, Rte. 65, I-49, Rte. 171 and Rte. B over I-49, Rte. 171, Rte. 65 and I-44. Project involves bridges A2728, A2729, A3020, A3065, A3070, A3477, A3564, A3821, A4258, A4820, A5812, A5813, X0793, A0588 and A0337. | Adv. CN | 4679 | 1170 | 0 | 5849 | 0 | AC-STBG |  | 0 | 45 | 45 | 100 | 641 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5018 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1324 | 6 | TANEY | US 160 E | 7P3507 | 0.176 | N |  | Replace signals and roadway realignment at Rte. 39 and Hadley Street in Aurora, replace signals at Rte. 76 and Main Street in Branson and replace signals and add right turn lane at Rte. 160 and Coy Boulevard in Forsyth. | Adv. CN | 2046 | 512 | 0 | 2583 | 0 | AC-STBG |  | 25 | 25 | 25 | 245 | 340 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1873 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1325 | 6 | TANEY | US 160 E | SR0011 | 0.092 | N |  | Bridge replacement over Beaver Creek. Project involves bridge L0382. | Federal | 4502 | 1125 | 0 | 5627 | 0 | STBG |  | 0 | 50 | 50 | 100 | 200 | 743 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4482 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1326 | 6 | TANEY | US 160 E | SR0087 | 8.282 | N |  | Add high friction surface treatment near Merriam Woods including Rte. 76 east of Branson, Rte. 265 in Branson, Rte. 65 in Hollister, Rte. 13 in Stone County, I-49 in Nevada and Rte. 59 in McDonald County. $307,000 Open Container funds. | Federal | 2669 | 297 | 0 | 2966 | 0 | SAFETY |  | 0 | 47 | 345 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2574 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1327 | 6 | TANEY | US 160 E | SR0121 | 0.085 | N |  | Bridge replacement over Swan Creek in Forsyth. Project involves bridge J0952. | Federal | 4010 | 1002 | 0 | 5012 | 0 | NHPP |  | 0 | 100 | 100 | 250 | 598 | 0 | 0 | 0 | 0 | 0 | 106 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3858 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1328 | 6 | TANEY | MO 248 E | 7P3533B | 6.668 | N |  | Pavement resurfacing and add rumblestripes from Rte. 160 to Shepherd of the Hills Expressway in Branson. | Adv. CN | 905 | 226 | 0 | 1141 | 0 | AC-STBG |  | 10 | 36 | 79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1016 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1329 | 6 | TANEY | MO 248 E | SR0056 | 6.357 | N |  | Upgrade pedestrian facilities to comply with the ADA Transition Plan from Branson Commerce Parkway to Rte. 65 and on Rte. 376 from Rte. 265 to Old Shepherd's Trail. | Adv. CN | 4512 | 1128 | 0 | 5640 | 0 | AC-STBG |  | 0 | 100 | 100 | 402 | 0 | 0 | 0 | 0 | 0 | 788 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1330 | 6 | TANEY | MO 376 E | 7P3533 | 1.738 | N |  | Pavement resurfacing from Rte. 265 to Shepherd of the Hills Expressway in Branson. | Adv. CN | 926 | 231 | 0 | 1159 | 0 | AC-STBG | 7P3394 7S3491 7S3492 7S3500 | 2 | 25 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1032 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1331 | 6 | TANEY | BU 65 S | SR0039 | 0.99001 | N |  | Pavement resurfacing from east of Blue Sky Lane to Rte. 65 in Hollister. | Adv. CN | 516 | 129 | 0 | 645 | 0 | AC-STBG |  | 0 | 4 | 4 | 54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1332 | 6 | TANEY | BU 65 S | SR0122 | 0.044 | N |  | Bridge improvement over Missouri and Northern Arkansas Railroad in Hollister. Project involves bridge J0710. | Federal | 2742 | 686 | 0 | 3428 | 0 | NHPP |  | 0 | 150 | 189 | 5 | 312 | 0 | 0 | 0 | 0 | 0 | 42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2730 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1333 | 6 | TANEY | US 65 S | SR0091 | 0.401 | N |  | Intersection improvements at Rte. 265. | Federal | 2683 | 671 | 0 | 3354 | 0 | NHPP |  | 0 | 100 | 100 | 383 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2771 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1334 | 6 | TANEY | MO 76 E | 7P3548 | 0.117 | N |  | Bridge rehabilitation over Roark Creek and Missouri and Northern Arkansas Railroad near Branson. Project involves bridges A5434 and A5435. | Federal | 1457 | 364 | 0 | 1871 | 0 | NHPP |  | 50 | 320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1501 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1335 | 6 | TANEY | MO 76 E | SR0099 | 28.88 | N |  | Add safety signage at various locations on Rtes. 39, 76, 160, 90, 176 and 248 in Barry, Lawrence, Stone, Taney and Webster Counties. $678,000 Open Container funds. | Federal | 794 | 88 | 0 | 882 | 0 | SAFETY |  | 0 | 20 | 74 | 69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 719 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1336 | 6 | TANEY | CST 76 COUNTRY BLVD E | 8O2373 | 4.504 | N |  | Payment to Branson for Phase I multimodal improvements on 76 Country Boulevard from Rte. 376 to 6th Street in Branson. $413,000 Statewide Transportation Alternatives funds. | Federal | 640 | 160 | 0 | 929 | 0 | STBG |  | 129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800 | 0 | 0 | 0 | 0 | 0 | 0 | 413 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1337 | 6 | TANEY | CST 76 COUNTRY BLVD E | 8O2373B | 4.335 | N |  | Payment to Branson for road relinquishment of Rte. 76 from Shepherd of the Hills Expressway to Sunshine Street. $3,746,574 over 10 years from SFY 2019 through SFY 2028. | Federal | 0 | 1953 | 0 | 3648 | 1 - 300 | STATE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1695 | 368 | 379 | 390 | 402 | 414 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1338 | 6 | TANEY | MO 86 E | SR0155 | 1.226 | N |  | Payment to private entity to add lanes and pavement resurfacing from Jones Road to Rte. 65, add roundabout at Jones Road, add lanes at Devil's Pool Road, and add lanes at roundabout at Ridgedale Road. $9,540,000 Governor's Cost Share Program funds. | Federal | 0 | 9630 | 0 | 9630 | 0 | STATE |  | 0 | 90 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9540 | 0 | 0 | 0 | 0 | 0 | 0 | 9540 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1339 | 6 | TANEY | RT BB S | SR0040 | 3.608 | N |  | Pavement resurfacing and add rumblestripes from Bus. 65 in Hollister to Layton Road. | Adv. CN | 578 | 145 | 0 | 723 | 0 | AC-STBG |  | 0 | 14 | 20 | 57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 632 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1340 | 6 | TANEY | RT F E | SR0038 | 3.349 | N |  | Pavement resurfacing and add rumblestripes from 0.1 mile east of Rte. 65 to Rte. 160 in Merriam Woods. | Adv. CN | 844 | 211 | 0 | 1055 | 0 | AC-STBG |  | 0 | 10 | 32 | 72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 941 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1341 | 6 | TANEY | RT F E | SR0115 | 0.7 | N |  | High friction surface treatment at various locations from Rte. 65 to Rte. 160. | Federal | 265 | 29 | 0 | 294 | 0 | SAFETY |  | 0 | 5 | 10 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1342 | 6 | VARIOUS | Various | 5B0800W | 0 | Y |  | Payback beginning in SFY 2008 for Safe and Sound bridges in the rural Southwest District. | Federal | 0 | 38840 | 0 | 105345 | 25,001 - 50,000 | STATE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 59 | 0 | 0 | 0 | 0 | 0 | 0 | 66446 | 7768 | 7768 | 7768 | 7768 | 7768 | 0
1343 | 6 | VARIOUS | Various | 7I3467 | 0 | Y | 21HS-22, 7I3467 | Job Order Contracting for bridge repairs at various locations in the rural Southwest District. | Adv. CN | 1972 | 493 | 0 | 2470 | 0 | AC-STBG |  | 5 | 3 | 402 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2060 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1344 | 6 | VARIOUS | Various | 7I3471 | 0 | Y | 32HS-22 | On-call work zone enforcement at various locations in the rural Southwest District. | Federal | 90 | 10 | 0 | 100 | 0 | SAFETY |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1345 | 6 | VARIOUS | Various | 7I3512 | 0 | Y | 01HS-23 | On-call work zone enforcement at various locations in the rural Southwest District. | Federal | 90 | 10 | 0 | 100 | 0 | SAFETY |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1346 | 6 | VARIOUS | Various | 7P3468 | 0 | Y | 24HS-22, 7P3468 | Job Order Contracting for guard cable and guardrail repair in the rural Southwest District. | Adv. CN | 3285 | 821 | 0 | 4108 | 0 | AC-STBG |  | 2 | 959 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3147 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1347 | 6 | VARIOUS | Various | 7Q3466 | 0 | Y | 33HS-22, 7Q3466 | Operations and management of Ozarks Traffic ITS in the rural Southwest District. | Adv. CN | 217 | 54 | 0 | 271 | 0 | AC-STBG |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 271 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1348 | 6 | VARIOUS | Various | 7Q3513 | 0 | Y | 02HS-23, 7Q3513 | Operations and management of Ozarks Traffic ITS in the rural Southwest District. | Adv. CN | 302 | 75 | 0 | 377 | 0 | AC-STBG |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 377 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1349 | 6 | VARIOUS | Various | SR0067 | 0 | Y |  | On-call work zone enforcement at various locations in the rural Southwest District. | Federal | 90 | 10 | 0 | 100 | 0 | SAFETY |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1350 | 6 | VARIOUS | Various | SR0069 | 0 | Y |  | Operations and management of Ozarks Traffic ITS in the rural Southwest District. | Adv. CN | 217 | 54 | 0 | 271 | 0 | AC-STBG |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 271 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1351 | 6 | VARIOUS | Various | SR0071 | 0 | Y |  | Job Order Contracting for guard cable and guardrail repair in the rural Southwest District. | Adv. CN | 3060 | 765 | 0 | 3835 | 0 | AC-STBG |  | 10 | 10 | 10 | 234 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1352 | 6 | VARIOUS | Various | SR0117 | 0 | Y |  | Job Order Contracting for concrete repairs in the rural Southwest District. | Adv. CN | 921 | 230 | 0 | 1151 | 0 | AC-STBG |  | 0 | 30 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1051 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1353 | 6 | VARIOUS | Various | SR0145 | 0 | Y |  | Pavement preservation treatment at various locations in the rural Southwest District. | Adv. CN | 2714 | 678 | 0 | 3392 | 0 | AC-STBG |  | 0 | 20 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3152 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1354 | 6 | VERNON | MO 43 S | 7P3518 | 3.498 | N |  | Upgrade pedestrian facilities to comply with the ADA Transition Plan in Bronaugh, on Spur 71 (Main Street) in Milo, Rte. F in Moundville, Loop 49 in Nevada, Rte. H in Richards, Rte. AA in Schell City and Rte. EE in Walker. | Adv. CN | 877 | 219 | 0 | 1098 | 0 | AC-STBG |  | 2 | 2 | 124 | 144 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1355 | 6 | VERNON | IS 49 N | SR0064 | 0.068 | N |  | Bridge rehabilitation over Rte. K in Nevada. Project involves twin bridges A1775. | Federal | 1340 | 149 | 0 | 1489 | 0 | NHPP |  | 0 | 2 | 32 | 168 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1287 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1356 | 6 | VERNON | IS 49 S | 7I3489 | 25.352 | N |  | Pavement resurfacing from Rte. 54 in Nevada to Rte. 160 in Lamar. | Federal | 11637 | 1293 | 0 | 12980 | 0 | NHPP |  | 50 | 278 | 1101 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11551 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1357 | 6 | VERNON | IS 49 S | 7I3516 | 55.938 | N |  | Job Order Contracting for pavement repair from Rte. 54 in Vernon County to I-44 in Jasper County. | Adv. CN | 341 | 38 | 0 | 379 | 0 | AC-NHPP |  | 0 | 0 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 309 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1358 | 6 | VERNON | IS 49 S | SR0063 | 0.06 | N |  | Bridge rehabilitation over Missouri and Northern Arkansas Railroad in Nevada. Project involves twin bridges A1774. | Federal | 2278 | 253 | 0 | 2531 | 0 | NHPP |  | 0 | 2 | 193 | 256 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1359 | 6 | VERNON | US 54 E | 7P3452 | 18.311 | N |  | Pavement resurfacing from east of I-49 in Nevada to east of Rte. 32 in El Dorado Springs. | Federal | 2930 | 733 | 0 | 3719 | 0 | NHPP |  | 56 | 364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1360 | 6 | VERNON | US 54 E | 7P3521 | 0.088 | N |  | Bridge rehabilitation over Little Dry Wood Creek west of Nevada. Project involves twin bridges A2948. | Federal | 1255 | 314 | 0 | 1571 | 0 | NHPP |  | 2 | 36 | 182 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1349 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1361 | 6 | VERNON | RT KK E | 7S3478 | 0.095 | N |  | Bridge rehabilitation over Drywood Creek 4 miles west of Rte. 43. Project involves bridge N0960. | Adv. CN | 550 | 138 | 0 | 733 | 0 | AC-STBG |  | 43 | 120 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 568 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1362 | 6 | VERNON | RT T S | 7S3535 | 8.16 | N |  | Rebuild pavement from Rte. 54 to 0.6 mile south of Rte. 54 and pavement resurfacing from 0.6 mile south of Rte. 54 to Rte. FF. | Adv. CN | 3622 | 905 | 0 | 4571 | 0 | AC-STBG |  | 44 | 1140 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 3385 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1363 | 6 | WEBSTER | IS 44 E | 7I3010 | 20.228 | N |  | Pavement resurfacing from 2.8 miles east of Rte. 125 in Strafford to 2 miles west of Rtes. J and Y in Conway, realign curve 3.5 miles east of Rte. 125 in Strafford and extend exit ramps at Rte. B, Rte. 38, Sampson Road and Conway Rest Area. | Federal | 23216 | 2579 | 0 | 25820 | 0 | NHPP | SU0146 | 25 | 4342 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21453 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1364 | 6 | WEBSTER | IS 44 E | 7I3510 | 20.757 | N |  | Job Order Contracting for pavement repair in Webster County. | Adv. CN | 230 | 26 | 0 | 256 | 0 | AC-NHPP |  | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 206 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1365 | 6 | WEBSTER | IS 44 E | SR0015 | 20.778 | N |  | Pavement resurfacing from Greene County line to Webster County line and on westbound lanes from Webster County line to 2.3 miles east of Rtes. J and Y in Conway. | Federal | 8447 | 938 | 0 | 9385 | 0 | NHPP |  | 0 | 10 | 136 | 791 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8448 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1366 | 6 | WEBSTER | BU 60 W | SR0034 | 3.056 | N |  | Pavement resurfacing from 0.1 mile south of Rte. 60 to 0.1 mile east of White Oak Road in Rogersville. | Adv. CN | 610 | 152 | 0 | 762 | 0 | AC-STBG |  | 0 | 30 | 30 | 130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 572 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1367 | 6 | WEBSTER | US 60 E | 7P3425C | 4.755 | N |  | Railroad crossing improvements from 0.2 mile west of Rte. Z in Fordland to Rte. O in Diggins and add interchange at Rte. A. $10,357,239 CRISI, $4,000,000 STBG-Rail, $1,500,000 Grade Crossing Safety Account, $1,500,000 BNSF Railway and $1,010,168 Webster County funds. | Adv. CN | 21165 | 2781 | 2510 | 27271 | 0 | AC-STBG |  | 815 | 500 | 890 | 2987 | 0 | 0 | 0 | 0 | 0 | 1854 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20225 | 0 | 0 | 0 | 0 | 500 | 2300 | 15567 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1368 | 6 | WEBSTER | US 60 E | SR0112 | 2.55 | N |  | Remove at-grade intersections and add access roads in Seymour. | Federal | 27820 | 6955 | 0 | 34775 | 0 | NHPP |  | 0 | 500 | 550 | 800 | 800 | 2600 | 0 | 0 | 0 | 0 | 0 | 1421 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28104 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1369 | 6 | WEBSTER | RT B S | SR0030 | 5.257 | N |  | Pavement resurfacing and add rumblestripes from Rte. AD to 1.8 miles north of Rte. 60 in Rogersville. | Adv. CN | 670 | 168 | 0 | 838 | 0 | AC-STBG |  | 0 | 8 | 8 | 74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 748 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1370 | 6 | WEBSTER | RT FF S | 7P3533D | 1.694 | N |  | Pavement resurfacing on Rtes. FF and PP from Rte. 60 west junction to Rte. 60 east junction in Fordland and on Bus. 60 from Rte. 60 west junction to County Line Road in Rogersville. | Adv. CN | 160 | 40 | 0 | 202 | 0 | AC-STBG |  | 2 | 4 | 2 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 176 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1371 | 6 | WEBSTER | RT PP E | SR0032 | 5.847 | N |  | Pavement resurfacing from Rte. KK to Rte. FF in Fordland. | Adv. CN | 365 | 91 | 0 | 456 | 0 | AC-STBG | 7P3533D SR0030 SR0034 | 0 | 4 | 4 | 41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 407 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1372 | 6 | CHRISTIAN | MO 125 S | SU0103 | 0.13 | Y |  | Add safety signage 0.1 mile north of Lindenlure Drive. | Federal | 14 | 2 | 0 | 16 | 0 | SAFETY |  | 0 | 1 | 1 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1373 | 6 | CHRISTIAN | MO 14 E | 8P0583B | 0.513 | Y | OK2201 | Roadway improvements on South Street from 6th Avenue to 14th Avenue in Ozark. | Adv. CN | 4689 | 1172 | 0 | 5886 | 0 | AC-STBG |  | 25 | 25 | 50 | 412 | 390 | 0 | 0 | 0 | 0 | 0 | 1578 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3406 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1374 | 6 | CHRISTIAN | US 160 E | 8S3138 | 0.314 | Y | CC1802 | Add intersection turn lanes, replace signals and upgrade striping and signage at Rte. CC near Nixa. | Federal | 4334 | 1083 | 0 | 6381 | 0 | NHPP | 8S3138B SU0020 | 664 | 662 | 0 | 0 | 0 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4755 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1375 | 6 | CHRISTIAN | US 160 W | 8S3138B | 0.414 | Y | CC2102-20A | Bridge rehabilitation on northbound bridge over the James River and add turn lanes and replace signal at Rte. AA. Project involves bridge A1198. | Federal | 4096 | 1024 | 0 | 5666 | 0 | NHPP | 8S3138 SU0020 | 536 | 692 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4428 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1376 | 6 | CHRISTIAN | US 65 S | 8P0605I | 3.271 | Y | CC1901-19 | Add lanes from Rte. CC to Rte. 14 in Ozark. | Federal | 10294 | 2573 | 0 | 12878 | 0 | NHPP | 8P0605J | 11 | 917 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1377 | 6 | CHRISTIAN | US 65 S | 8P0605J | 1.439 | Y | CC1902-19 | Add lanes from Rte. 14 to Rte. F and bridge rehabilitation over the Finley River in Ozark. Project involves bridges A0646 and A3110. | Federal | 8220 | 2055 | 0 | 10291 | 0 | NHPP | 8P0605I | 16 | 737 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9538 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1378 | 6 | CHRISTIAN | RT AA E | SU0065 | 7.21 | Y | CC2303-23 | Pavement preservation treatment from Rte. 160 to Blue Springs Road (end of state maintenance) and on Rte. JJ from Rte. 125 to Rte. 14. | Adv. CN | 178 | 44 | 0 | 222 | 0 | AC-STBG | 7P3503 | 0 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 193 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1379 | 6 | CHRISTIAN | RT CC E | 8S0736D | 0.805 | Y | OK2102-20A | Capital improvements from Fremont Road to 22nd Street in Ozark. Design, right of way acquisition and utility relocation by Ozark. $2,021,449 Cost Share, $2,128,397 STBG-Urban and $532,099 Ozark funds. | Adv. CN | 4385 | 564 | 532 | 5581 | 0 | AC-STBG |  | 100 | 10 | 20 | 484 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4967 | 0 | 0 | 0 | 0 | 0 | 0 | 2660 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1380 | 6 | CHRISTIAN | RT CC E | 8S0736E | 0.18 | Y | OK2202-22 | Intersection improvements at 22nd Street in Ozark. Project involves culvert A3861. | Adv. CN | 2714 | 678 | 0 | 3442 | 0 | AC-STBG |  | 50 | 100 | 222 | 418 | 0 | 0 | 0 | 0 | 0 | 311 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1381 | 6 | CHRISTIAN | RT CC E | 8S0736F | 0.225 | Y | NX2202-22 | Add roundabout at Main Street in Nixa. | Adv. CN | 1704 | 426 | 0 | 2140 | 0 | AC-STBG |  | 10 | 245 | 291 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1494 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1382 | 6 | CHRISTIAN | RT CC E | 8S0736H | 0.805 | Y |  | Payment to Ozark for design, right-of-way and utility relocations for capital improvements from Fremont Road to 22nd Street. $825,768 Cost Share funds. | Adv. CN | 676 | 169 | 0 | 845 | 0 | AC-STBG |  | 0 | 10 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 418 | 407 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1383 | 6 | CHRISTIAN | RT J E | 8S3245 | 0.062 | Y | OK2203-22 | Ramp and intersection improvements at Rtes. CC and J and bridge rehabilitation on eastbound bridge over Rte. 65 in Ozark. Project involves bridge A3860. | Federal | 629 | 157 | 0 | 788 | 0 | NHPP |  | 2 | 2 | 53 | 87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 644 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1384 | 6 | CHRISTIAN | RT W S | SU0012 | 1.011 | Y |  | Pavement resurfacing from Rte. 14 to south of Timbercrest Road near Ozark. | Adv. CN | 130 | 32 | 0 | 162 | 0 | AC-STBG |  | 0 | 2 | 6 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 139 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1385 | 6 | GREENE | MO 125 S | 8S3238 | 1.098 | Y | ST2201-22 | Intersection improvements at various locations from 0.2 mile north of Evergreen Street to 0.1 mile west of Washington Avenue in Strafford. | Adv. CN | 3948 | 987 | 0 | 5055 | 0 | AC-STBG |  | 120 | 530 | 537 | 0 | 0 | 0 | 0 | 0 | 155 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3713 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1386 | 6 | GREENE | CRD 127 W | 8S3156 | 0.069 | Y | SP1911-19A | Bridge improvement on Melville Road over I-44 in Springfield. Project involves bridge A0441. | Federal | 2875 | 719 | 0 | 3708 | 0 | NHPP |  | 114 | 150 | 140 | 367 | 0 | 0 | 0 | 0 | 0 | 46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2891 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1387 | 6 | GREENE | MO 13 S | 8P3087E | 0.367 | Y | SP1816-20A | Add lanes, improve pedestrian access and replace signal on Kansas Expressway at Sunset Street in Springfield. $278,200 Springfield and $1,112,800 STBG-Urban funds. | Federal | 1664 | 165 | 251 | 2782 | 0 | STBG | 8P3087F 8S3165 8S3173 | 507 | 313 | 0 | 0 | 0 | 0 | 0 | 195 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1767 | 0 | 0 | 0 | 0 | 0 | 133 | 1258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1388 | 6 | GREENE | MO 13 S | 8P3087F | 0.453 | Y | SP1817-20A | Add lanes, improve pedestrian access and replace signal on Kansas Expressway at Walnut Lawn Street in Springfield. $404,500 Springfield and $1,324,800 STBG-Urban funds. | Federal | 2182 | 186 | 359 | 3457 | 0 | STBG | 8P3087E 8S3165 8S3173 | 366 | 411 | 0 | 0 | 0 | 0 | 0 | 364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2316 | 0 | 0 | 0 | 0 | 0 | 230 | 1499 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1389 | 6 | GREENE | MO 13 S | 8S3165 | 7.62 | Y | GR2007-20 | Pavement resurfacing on Kansas Expressway from north of I-44 to Rte. 60 (James River Freeway). $3,839.99 DEMO ID MO250. | Federal | 2605 | 651 | 0 | 3308 | 0 | NHPP | 8P3087E 8P3087F 8S3173 | 52 | 322 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2934 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1390 | 6 | GREENE | MO 13 S | 8S3173 | 7.617 | Y | EN2003-20A | Upgrade pedestrian facilities to comply with the ADA Transition Plan and add sidewalks at various locations on Kansas Expressway from north of I-44 to Rte. 60 (James River Freeway). $149,703 Springfield, $598,809 STBG-Urban and $329,000 Statewide Trans. Alt. funds. | Adv. CN | 3260 | 665 | 150 | 5470 | 0 | AC-STBG | 8P3087E 8P3087F 8S3165 | 1345 | 741 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3334 | 0 | 0 | 0 | 0 | 0 | 0 | 749 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1391 | 6 | GREENE | MO 13 S | SU0079 | 0.203 | Y |  | Interchange improvements at I-44 in Springfield. | Federal | 24042 | 6011 | 0 | 30053 | 0 | NHPP |  | 0 | 500 | 500 | 840 | 2738 | 0 | 0 | 0 | 0 | 0 | 4986 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20489 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1392 | 6 | GREENE | MO 13 S | SU0093 | 1.009 | Y |  | Capital improvement on Kansas Expressway from Grand Street to Rte. 413 (Sunshine Street) in Springfield. | Federal | 7881 | 1970 | 0 | 9851 | 0 | NHPP |  | 0 | 40 | 40 | 300 | 600 | 1055 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7784 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1393 | 6 | GREENE | US 160 E | SU0051 | 0.248 | Y | SP2304-23 | Bridge painting over Rte. 60 (James River Freeway), on Republic Street over Rte. 60 and on Rte. 266 (Chestnut Expressway) over I-44 in Springfield. Project involves bridges A4146, A4184 and A0598. | Federal | 1237 | 309 | 0 | 1546 | 0 | NHPP |  | 0 | 10 | 24 | 40 | 168 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1394 | 6 | GREENE | US 160 W | SU0020 | 0.155 | Y | SP2213-22 | Bridge deck sealing on northbound bridge over James River Overflow south of Springfield. Project involves bridge A1199. | Federal | 133 | 33 | 0 | 166 | 0 | NHPP | 8S3138 8S3138B | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 136 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1395 | 6 | GREENE | MO 266 E | SU0080 | 0.096 | Y |  | Add roundabout at Rte. AB and at Rte. B west of Springfield. | Adv. CN | 4271 | 1068 | 0 | 5339 | 0 | AC-STBG |  | 0 | 300 | 450 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4089 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1396 | 6 | GREENE | MO 360 E | SU0014 | 3.679 | Y | SP2309-23 | Pavement resurfacing from I-44 to Rte. 60 in Springfield. | Federal | 522 | 130 | 0 | 652 | 0 | NHPP |  | 0 | 9 | 59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 584 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1397 | 6 | GREENE | MO 413 S | 8S3157 | 0.607 | Y | SP1908-19A | Bridge replacement, add sidewalks and upgrade pedestrian facilities to comply with the ADA Transition Plan on Sunshine Street from 0.1 mile east of Scenic Avenue to Rte. 13 (Kansas Expressway) in Springfield. Project involves bridge H0945. | Federal | 3854 | 963 | 0 | 5888 | 0 | NHPP |  | 733 | 609 | 0 | 0 | 0 | 0 | 0 | 338 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4208 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1398 | 6 | GREENE | IS 44 E | 8I3044C | 2.083 | Y | SP2203 | Add lanes from Rte. H (Glenstone Avenue) to Rte. 65 in Springfield. | Federal | 9647 | 1072 | 0 | 11123 | 0 | NHPP | 8I3225 | 404 | 100 | 64 | 588 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9967 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1399 | 6 | GREENE | IS 44 E | 8I3225 | 15.519 | Y | GR2201 | Pavement resurfacing from 0.6 mile west of Rte. 266 (Chestnut Expressway) to Rte. H (Glenstone Avenue) in Springfield and from Rte. 65 in Springfield to 0.5 mile east of Rte. 125 in Strafford. | Federal | 6313 | 701 | 0 | 7064 | 0 | NHPP | 8I3044C | 50 | 73 | 50 | 585 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6306 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1400 | 6 | GREENE | IS 44 E | 8I3232 | 37.255 | Y | MO2401 | Job Order Contracting for pavement repair in the urban Southwest District. | Adv. CN | 452 | 50 | 0 | 502 | 0 | AC-NHPP |  | 0 | 0 | 90 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 412 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1401 | 6 | GREENE | IS 44 E | SU0013 | 1.539 | Y | ST2301-23 | Pavement resurfacing from 0.5 mile east of Rte. 125 in Strafford to the Webster County line. | Federal | 405 | 45 | 0 | 450 | 0 | NHPP |  | 0 | 2 | 6 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 402 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1402 | 6 | GREENE | IS 44 E | SU0076 | 2.648 | Y |  | Add lanes and replace bridges from Rte. 13 (Kansas Expressway) to Rte. H (Glenstone Avenue) in Springfield. Project involves bridges A0444, A0445, A0446 and A0447. | Federal | 25073 | 2786 | 0 | 27859 | 0 | NHPP |  | 0 | 800 | 800 | 2800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23459 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1403 | 6 | GREENE | IS 44 E | SU0114 | 2.275 | Y |  | Sound abatement at various locations from Rte. 13 (Kansas Expressway) to Rte. 65 in Springfield. | Adv. CN | 5406 | 1352 | 0 | 6758 | 0 | AC-STBG |  | 0 | 150 | 50 | 50 | 200 | 510 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5796 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1404 | 6 | GREENE | IS 44 E | SU0151 | 21.835 | Y |  | Striping upgrades from 0.1 mile east of Rte. 360 to 2 miles east of Rte. 125 in Strafford. | Federal | 237 | 26 | 0 | 263 | 0 | SAFETY | SR0150 SR0152 SR0153 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 239 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1405 | 6 | GREENE | IS 44 W | SU0058 | 3.36 | Y | MO2309-23 | Add high friction surface treatment on westbound lanes in Strafford, Rte. 60 in Springfield, Rtes. NN and 125 in Christian County and pavement resurfacing on Rte. 60 auxiliary lanes from Kansas Expressway to Campbell Avenue in Springfield. | Federal | 3725 | 414 | 0 | 4139 | 0 | SAFETY |  | 0 | 66 | 481 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3592 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1406 | 6 | GREENE | IS 44 W | SU0146 | 1.369 | Y |  | Rebuild pavement on the westbound lanes from 2.1 miles east of Rte. 125 to 0.7 mile east of Rte. 125 near Strafford. | Federal | 4237 | 471 | 0 | 4708 | 0 | NHPP | 7I3010 | 0 | 320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4388 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1407 | 6 | GREENE | LP 44 E | 8P3144 | 9.213 | Y | SP1812-22A | Safety improvements on Chestnut Expressway from I-44 to Rte. 65 in Springfield. | Federal | 1522 | 169 | 0 | 1779 | 0 | SAFETY |  | 88 | 325 | 160 | 0 | 0 | 0 | 0 | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1056 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1408 | 6 | GREENE | LP 44 E | 8P3192 | 50.8 | Y | EN2002-20A | Upgrade pedestrian facilities to comply with the ADA Transition Plan at various locations on Loop 44, Rte. EE, Rte. YY, Outer Road 65, Rte. 160 in Springfield, Rte. 14, Rte. CC, Rte. J and Rte. NN in Ozark and Rte. M in Nixa. | Adv. CN | 1636 | 409 | 0 | 2130 | 0 | AC-STBG |  | 85 | 312 | 380 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1338 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1409 | 6 | GREENE | LP 44 E | 8S3166 | 1.101 | Y | SP2013-20 | Pavement resurfacing on Chestnut Expressway from Scenic Avenue to west of Rte. 13 (Kansas Expressway). | Federal | 410 | 103 | 0 | 519 | 0 | NHPP | 8S3167 8S3171 8S3224 | 6 | 5 | 46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 462 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1410 | 6 | GREENE | LP 44 E | 8S3167 | 3.182 | Y | SP2002-20 | Pavement resurfacing on Chestnut Expressway from 0.1 mile west of Bus. 65 (Glenstone Avenue) to 0.1 mile east of Eastgate Avenue and on Eastgate Avenue from 0.1 mile north of Cherry Street to 0.3 mile north of Chestnut Expressway in Springfield. | Federal | 1042 | 261 | 0 | 1316 | 0 | NHPP | 8S3166 8S3171 8S3224 | 13 | 18 | 112 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1173 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1411 | 6 | GREENE | LP 44 E | 8S3224 | 5.156 | Y | SP2206-22 | Pavement resurfacing on Chestnut Expressway from Lullwood Avenue to Scenic Avenue and from east of Rte. 13 (Kansas Expressway) to 0.1 mile east of Delaware Avenue in Springfield. | Federal | 1678 | 420 | 0 | 2103 | 0 | NHPP | 8S3166 8S3167 8S3171 | 5 | 46 | 178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1874 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1412 | 6 | GREENE | LP 44 E | SU0088 | 2.081 | Y |  | Add ITS equipment and software on Chestnut Expressway from Rte. 160 (West Bypass) to Rte. 13 (Kansas Expressway) in Springfield. | Adv. CN | 351 | 88 | 0 | 444 | 0 | AC-STBG |  | 5 | 10 | 68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 361 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1413 | 6 | GREENE | LP 44 W | 8P3050B | 3.19 | Y | SP1710 | Pavement resurfacing on Glenstone Avenue from Evergreen Street to BNSF Railway and on Rte. H from north of Stoneridge Street to McClernon Street in Springfield. | Federal | 936 | 234 | 0 | 1212 | 0 | NHPP | 8S3112 8S3117 8S3160 8S3175 | 42 | 106 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1064 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1414 | 6 | GREENE | S OR 60 E | 8S3175 | 0.816 | Y | EN1914-19A | Upgrade pedestrian facilities to comply with the ADA Transition Plan on Nature Center Way from 0.1 mile east of Republic Road to end of route. | Adv. CN | 332 | 83 | 0 | 508 | 0 | AC-STBG | 8P3050B 8S3112 8S3117 8S3160 | 84 | 74 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1415 | 6 | GREENE | US 60 E | 8P0683G | 1.433 | Y | GR140318A1 | Capital improvements from Rte. 65 to Rtes. NN and J. | Federal | 15802 | 3951 | 0 | 19904 | 0 | NHPP |  | 151 | 300 | 300 | 300 | 440 | 1307 | 0 | 0 | 0 | 0 | 0 | 612 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16494 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1416 | 6 | GREENE | US 60 E | 8P3122B | 4.944 | Y | GR1907-19 | Pavement resurfacing from Highland Springs Boulevard east of Springfield to west of Rte. 125 in Rogersville. | Federal | 1785 | 446 | 0 | 2266 | 0 | NHPP | 7P3271 | 35 | 221 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2010 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1417 | 6 | GREENE | US 60 E | 8P3197 | 1.817 | Y | GR2011-20A | Railroad crossing safety improvements at various locations from County Rd. 194 west of Republic to O'Neal St. and at BNSF Railway crossings on Main St., Hampton Ave., Hines St. and Rte. 174 in Republic. $394,000 CRISI Program and $395,000 GCSA funds. | Federal | 347 | 343 | 0 | 850 | 0 | OTHER | 7P3433 7P3434 7S3435 7S3442 8P3198 8S3199 | 136 | 44 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 646 | 0 | 0 | 0 | 0 | 0 | 103 | 686 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1418 | 6 | GREENE | US 60 E | 8P3198 | 0.937 | Y | RP2202-22 | Pavement resurfacing from County Road 194 to 0.2 mile west of Illinois Street in Republic. | Federal | 190 | 47 | 0 | 245 | 0 | NHPP | 7P3433 7P3434 7S3435 7S3442 8P3197 8S3199 | 8 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 214 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1419 | 6 | GREENE | US 60 E | SU0078 | 1.058 | Y |  | Capital improvement from west of County Road 103 to Rte. 360 (James River Freeway) in Republic. | Federal | 5302 | 1326 | 0 | 6628 | 0 | NHPP |  | 0 | 50 | 50 | 100 | 223 | 343 | 0 | 0 | 0 | 0 | 0 | 1098 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4764 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1420 | 6 | GREENE | US 60 W | 8P0683E | 0.966 | Y | RG0901 | Add interchange at Rte. 125 in Rogersville. $4,008,000 Open Container, $1,000,000 Rogersville and $1,000,000 Greene County funds. | Federal | 19498 | 166 | 2000 | 25133 | 0 | SAFETY | 7S3488 | 2266 | 1320 | 0 | 0 | 0 | 0 | 0 | 1203 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20344 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1421 | 6 | GREENE | BU 65 S | 8S3112 | 1.548 | Y | SP1903-19 | Pavement resurfacing on Glenstone Avenue from Battlefield Road to Rte. 60 (James River Freeway) and on Nature Center Way at Reed Avenue in Springfield. | Federal | 687 | 172 | 0 | 888 | 0 | NHPP | 8P3050B 8S3117 8S3160 8S3175 | 29 | 78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 781 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1422 | 6 | GREENE | BU 65 S | 8S3117 | 3.689 | Y | SP1904-19 | Pavement resurfacing on Glenstone Avenue from BNSF Railway south of Loop 44 (Chestnut Expressway) to Battlefield Road in Springfield. | Federal | 1154 | 288 | 0 | 1493 | 0 | NHPP | 8P3050B 8S3112 8S3160 8S3175 | 51 | 130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1312 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1423 | 6 | GREENE | BU 65 S | 8S3160 | 8.097 | Y | SP2003-20A | Modify access, signals, ADA Transition Plan improvements and replace bus stop pads from Valley Water Mill Rd. to Rte. 60 in Springfield. $677,000 Open Container, $315,000 Statewide Trans. Alt., $315,434 STBG-Urban, $78,859 Springfield and $67,500 CU Transit funds. | Federal | 5630 | 1261 | 147 | 9137 | 0 | STBG | 8P3050B 8S3112 8S3117 8S3175 | 1878 | 1251 | 0 | 0 | 0 | 0 | 0 | 221 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5787 | 0 | 0 | 0 | 0 | 0 | 0 | 462 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1424 | 6 | GREENE | BU 65 S | 8S3171 | 1.663 | Y | EN2007-20 | Upgrade pedestrian facilities to comply with the ADA Transition Plan at various locations on Chestnut Expressway from east of Bus. 65 (Glenstone Avenue) to east of Belcrest Avenue in Springfield. $79,000 Statewide Transportation Alternatives funds. | Adv. CN | 922 | 231 | 0 | 1159 | 0 | AC-STBG | 8S3166 8S3167 8S3224 | 6 | 230 | 186 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 727 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1425 | 6 | GREENE | BU 65 S | SU0003 | 8.097 | Y | SP2218-22A | Operational and pedestrian improvements on Glenstone Avenue from Valley Water Mill Road to Rte. 60 (James River Freeway) in Springfield. | Adv. CN | 3930 | 983 | 0 | 4923 | 0 | AC-STBG |  | 10 | 967 | 830 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3112 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1426 | 6 | GREENE | E OR 65 S | 8S3158 | 0.024 | Y | SP1910-19A | Bridge replacement on Eastgate Avenue over BNSF Railway in Springfield. Project involves bridge W0574. | Federal | 2198 | 550 | 0 | 2865 | 0 | NHPP |  | 117 | 159 | 263 | 0 | 0 | 0 | 0 | 0 | 206 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1427 | 6 | GREENE | US 65 N | 8I3246 | 0.218 | Y | MO2206 | Bridge improvements northbound over S. Dry Sac Creek, Republic Road over Rte. 60 in Springfield, Rte. 14 over Rte. 65 in Ozark and Rte. M over McCaferty Branch. Project involves bridges A3361, A4181, A3109 and A3514. | Federal | 1000 | 250 | 0 | 1252 | 0 | NHPP |  | 2 | 21 | 152 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1077 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1428 | 6 | GREENE | US 65 N | 8P3164 | 6.594 | Y | GR2003-20 | Pavement resurfacing on northbound lanes from north of I-44 in Springfield to Rtes. KK and A. | Federal | 1061 | 265 | 0 | 1338 | 0 | NHPP | 7P3393 | 12 | 20 | 115 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1191 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1429 | 6 | GREENE | US 65 S | 8P3043 | 0.522 | Y | SP2208 | Pavement resurfacing on various sections at the Rte. D (Sunshine Street) interchange. | Adv. CN | 318 | 79 | 0 | 405 | 0 | AC-NHPP | 8S3212 | 8 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 359 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1430 | 6 | GREENE | US 65 S | 8P3242 | 48.964 | Y | MO2212-22 | Concrete repairs at various locations from Rtes. A and KK to 0.9 mile south of Rte. F in Ozark and on Rte. 60 at various locations from County Road 194 near Republic to Rte. 125 in Rogersville. | Adv. CN | 502 | 126 | 0 | 633 | 0 | AC-STBG |  | 5 | 107 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 521 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1431 | 6 | GREENE | US 65 S | SU0046 | 0.289 | Y | MO2306-23 | Bridge deck sealing over County Road 197 and James River Freeway including Bus. 65 (Glenstone Avenue) and National Avenue over James River Freeway in Springfield and Rte. MM over Rte. 360 in Republic. Project involves bridges A3360, A2072, A4175, A4177 and A5907. | Federal | 2533 | 633 | 0 | 3166 | 0 | NHPP |  | 0 | 60 | 396 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2710 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1432 | 6 | GREENE | US 65 S | SU0101 | 0.192 | Y |  | Add J-turn at Bluegrass Road (County Road 94). $840,000 Open Container funds. | Federal | 1594 | 177 | 0 | 1771 | 0 | SAFETY |  | 0 | 100 | 303 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1340 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1433 | 6 | GREENE | MO 744 E | 8I3243 | 74.588 | Y | MO2205 | Replace signs at various locations on Rte. 744 (Kearney Street), Loop 44 (Chestnut Expressway), Bus. 65 (Glenstone Avenue), Rte. 13 (Kansas Expressway), Rte. 413 (Sunshine Street) and Rte. 160 (West Bypass) in Greene and Christian Counties. | Adv. CN | 334 | 83 | 0 | 447 | 0 | AC-STBG |  | 30 | 58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 359 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1434 | 6 | GREENE | MO 744 E | 8P3050C | 2.64 | Y | SP1708 | Pavement resurfacing on Kearney Street from Rte. 13 (Kansas Expressway) to Loop 44 (Glenstone Avenue). | Federal | 639 | 160 | 0 | 816 | 0 | NHPP | 8S3149 8S3162 8S3169 8S3172 8S3190 SR0127 SU0085 | 17 | 2 | 71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 726 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1435 | 6 | GREENE | MO 744 E | 8P3236 | 0.217 | Y | MO2209-22 | Replace signals on Kearney St at Mayfair Ave, on Loop 44 at Haseltine Rd, on Evans Rd at Rte. 65 ramps, on Bus. 65 at Seminole St, Portland St and Barataria St, on Rte. D at Oak Grove Ave and Ventura Ave in Springfield and on Rte. 60 at Rte. MM in Republic. | Adv. CN | 3890 | 972 | 0 | 4912 | 0 | AC-STBG |  | 50 | 603 | 718 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1436 | 6 | GREENE | MO 744 E | 8P3237 | 0.155 | Y | MO2210-22 | Replace signals on Kearney St at National Ave, Summit Ave, Grant Ave and Broadway Ave, on Bus. 65 at Patterson Ave and Cedarbrook Ave, on Bus. 65 at Sunset Ave in Springfield, on Rte. FF at Rte. MM in Battlefield and on Rte. CC at Cheyenne Rd in Christian County. | Adv. CN | 2842 | 710 | 0 | 3562 | 0 | AC-STBG |  | 10 | 10 | 10 | 416 | 511 | 0 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2592 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1437 | 6 | GREENE | MO 744 E | 8S3149 | 2.693 | Y | EN1901-19 | Upgrade pedestrian facilities to comply with the ADA Transition Plan on Kearney Street at various locations between Rte. 13 (Kansas Expressway) and Loop 44 (Glenstone Avenue) in Springfield. | Adv. CN | 1801 | 450 | 0 | 2934 | 0 | AC-STBG | 8P3050C 8S3162 8S3169 8S3172 8S3190 SR0127 SU0085 | 579 | 1 | 377 | 0 | 0 | 0 | 0 | 104 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1873 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1438 | 6 | GREENE | MO 744 E | 8S3162 | 4.657 | Y | GR2004-20 | Pavement resurfacing from east of Loop 44 (Glenstone Avenue) to Mulroy Road and on Mulroy Road from Rte. OO to I-44. | Federal | 1329 | 332 | 0 | 1690 | 0 | NHPP | 8P3050C 8S3149 8S3169 8S3172 8S3190 SR0127 SU0085 | 29 | 9 | 147 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1505 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1439 | 6 | GREENE | MO 744 E | 8S3169 | 3.733 | Y | SP2006-20 | Pavement resurfacing on Kearney Street from Springfield-Branson National Airport to west of Rte. 13 (Kansas Expressway) in Springfield. | Adv. CN | 727 | 182 | 0 | 932 | 0 | AC-STBG | 8P3050C 8S3149 8S3162 8S3172 8S3190 SR0127 SU0085 | 23 | 1 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 828 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1440 | 6 | GREENE | MO 744 E | 8S3172 | 2.44 | Y | EN2005-20 | Upgrade pedestrian facilities to comply with the ADA Transition Plan at various locations on Kearney Street from east of Loop 44 (Glenstone Avenue) to LeCompte Road. | Adv. CN | 1495 | 374 | 0 | 2310 | 0 | AC-STBG | 8P3050C 8S3149 8S3162 8S3169 8S3190 SR0127 SU0085 | 391 | 44 | 316 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1509 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1441 | 6 | GREENE | MO 744 E | SU0085 | 9.047 | Y | SP2307 | Add lanes and modify signals on Kearney Street from Springfield-Branson National Airport to LeCompte Avenue. | Federal | 1855 | 464 | 0 | 2319 | 0 | NHPP | 8P3050C 8S3149 8S3162 8S3169 8S3172 8S3190 SR0127 | 0 | 355 | 355 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1607 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1442 | 6 | GREENE | MO 744 W | 8S3190 | 1.942 | Y | EN2006-20 | Upgrade pedestrian facilities to comply with the ADA Transition Plan on Kearney Street from Rte. 160 (West Bypass) to Rte. 13 (Kansas Expressway) in Springfield. | Adv. CN | 1582 | 395 | 0 | 2570 | 0 | AC-STBG | 8P3050C 8S3149 8S3162 8S3169 8S3172 SR0127 SU0085 | 486 | 1 | 387 | 0 | 0 | 0 | 0 | 107 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1589 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1443 | 6 | GREENE | CST BATTLEFIELD RD E | 8S3212 | 0.70401 | Y | SP2209 | Pavement resurfacing from Moulder Avenue to Ruskin Avenue in Springfield. $416,098 Springfield funds. | Federal | 344 | 0 | 416 | 768 | 0 | NHPP | 8P3043 | 8 | 222 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 538 | 0 | 0 | 0 | 0 | 0 | 0 | 416 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1444 | 6 | GREENE | RT C E | 8S3226 | 3.674 | Y | GR2202-22 | Pavement resurfacing from Rte. 65 to Rte. 125 north of Strafford. | Adv. CN | 218 | 54 | 0 | 274 | 0 | AC-STBG | 8S3227 8S3228 | 2 | 6 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 241 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1445 | 6 | GREENE | CST CHERRY ST E | 8S3221 | 0.173 | Y | SP2210-22 | Pavement resurfacing, upgrade pedestrian facilities to comply with the ADA Transition Plan and bridge rehabilitation over Rte. 65 from Ingram Mill Avenue to Eastgate Avenue in Springfield. Project involves bridge A1652. | Federal | 210 | 53 | 0 | 269 | 0 | NHPP |  | 4 | 45 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 218 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1446 | 6 | GREENE | RT D E | 8S0745 | 2.617 | Y | SP1906-19 | Pavement resurfacing on Sunshine Street from Bus. 65 (Glenstone Avenue) to Blackman Road in Springfield. | Adv. CN | 1062 | 266 | 0 | 1378 | 0 | AC-STBG | 8S3211 8S3215 | 50 | 20 | 114 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1194 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1447 | 6 | GREENE | RT D E | 8S3133 | 4.533 | Y | SP1802-22A | Safety and operational improvements on Sunshine Street from Bus. 65 (Glenstone Avenue) to 0.3 mile east of County Road 199. | Federal | 3024 | 756 | 0 | 3838 | 0 | NHPP |  | 58 | 335 | 617 | 0 | 0 | 0 | 0 | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2678 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1448 | 6 | GREENE | RT D E | 8S3153 | 2.557 | Y | SP1413-19 | Upgrade pedestrian facilities to comply with the ADA Transition Plan on Sunshine Street from Bus. 65 (Glenstone Avenue) to Blackman Road in Springfield. $252,000 Transportation Alternatives | Adv. CN | 1063 | 266 | 0 | 1587 | 0 | AC-STBG |  | 258 | 92 | 202 | 0 | 0 | 0 | 0 | 0 | 53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 982 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1449 | 6 | GREENE | RT D E | 8S3215 | 5.47 | Y | GR2203 | Pavement resurfacing from east of Blackman Road to Rte. 125 east of Springfield. | Adv. CN | 1090 | 273 | 0 | 1385 | 0 | AC-STBG | 8S0745 8S3211 | 22 | 2 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1241 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1450 | 6 | GREENE | RT DD E | 8S3228 | 2.752 | Y | GR2204-22 | Pavement resurfacing from Rte. 125 in Strafford to the Webster County line. | Adv. CN | 169 | 42 | 0 | 213 | 0 | AC-STBG | 8S3226 8S3227 | 2 | 6 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 185 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1451 | 6 | GREENE | RT EE E | SU0066 | 0.048 | Y |  | Bridge improvement over I-44 in Springfield. Project involves bridge A0713. | Federal | 883 | 221 | 0 | 1104 | 0 | NHPP |  | 0 | 30 | 33 | 124 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 917 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1452 | 6 | GREENE | RT FF S | SU0018 | 3.055 | Y | BA2301-23 | Pavement resurfacing from Weaver Road in Battlefield to end of route at Haseltine Road. | Adv. CN | 355 | 89 | 0 | 444 | 0 | AC-STBG |  | 0 | 2 | 2 | 4 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 398 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1453 | 6 | GREENE | RT J S | 8S3211 | 5.504 | Y | GR2205-22 | Pavement resurfacing from Rte. D to 0.3 mile north of Rte. 60 east of Springfield. | Adv. CN | 403 | 101 | 0 | 512 | 0 | AC-STBG | 8S0745 8S3215 | 8 | 3 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 456 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1454 | 6 | GREENE | RT MM S | 8S0836B | 1.511 | Y | RP1703-22A | Add lanes on Brookline Avenue from I-44 to Rte. 360 (James River Freeway) in Republic. Design, right-of-way and inspection by Republic. $6,000,000 Cost Share, $2,296,000 STBG-Urban and $581,247 Republic funds. | Adv. CN | 6932 | 1152 | 581 | 8991 | 0 | AC-STBG |  | 326 | 82 | 338 | 0 | 0 | 0 | 0 | 0 | 691 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7554 | 0 | 0 | 0 | 0 | 0 | 0 | 2877 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1455 | 6 | GREENE | RT MM S | 8S0836D | 0.154 | Y | RP1704-20A | Relocate Brookline Avenue, add railroad grade separation and sidewalks from County Road 160 to Rte. 60 in Republic. $564,000 Open Container and $374,000 Statewide Transportation Alternatives funds. | Adv. CN | 26531 | 6633 | 0 | 33764 | 0 | AC-STBG |  | 600 | 1000 | 1173 | 1879 | 0 | 0 | 0 | 0 | 0 | 2945 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1456 | 6 | GREENE | RT MM S | 8S3239 | 0.125 | Y | RP2201-22 | Add signals at ramps and reconfigure lanes at I-44. | Adv. CN | 962 | 241 | 0 | 1253 | 0 | AC-STBG |  | 50 | 30 | 88 | 0 | 0 | 0 | 0 | 0 | 674 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1457 | 6 | GREENE | RT P S | 8S3199 | 1.15 | Y | RP2203-22 | Pavement resurfacing from Rte. 60 to County Road 194 in Republic. | Adv. CN | 152 | 38 | 0 | 198 | 0 | AC-STBG | 7P3433 7P3434 7S3435 7S3442 8P3197 8P3198 | 8 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 171 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1458 | 6 | GREENE | RT P S | 8S3200 | 1.451 | Y | EN2202-22 | Upgrade pedestrian facilities to comply with the ADA Transition Plan from Rte. 60 to Grace Street and on Rte. 174 from Lindsey Avenue to Walnut Avenue in Republic. | Adv. CN | 238 | 59 | 0 | 352 | 0 | AC-STBG | 7P3527 | 53 | 73 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 224 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1459 | 6 | GREENE | CST REPUBLIC ST E | 8S3240 | 0.078 | Y | SP2211-22 | Bridge rehabilitation over Rte. 60 (James River Freeway) 0.5 mile east of Rte. 13 (Kansas Expressway) in Springfield. Project involves bridge A4184. | Federal | 1364 | 341 | 0 | 1709 | 0 | NHPP |  | 4 | 114 | 188 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1401 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1460 | 6 | GREENE | RT WW E | 8S3227 | 3.499 | Y | GR2207-22 | Pavement resurfacing and add shoulders from Rte. 13 to Rte. H. | Adv. CN | 449 | 112 | 0 | 563 | 0 | AC-STBG | 8S3226 8S3228 | 2 | 20 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 501 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1461 | 6 | GREENE | RT ZZ N | SU0054 | 0 | Y | EN2205-22A | Add bicycle and pedestrian trail from Rte. M to County Road 182 in Republic. $1,246,730 Coronavirus Response and Relief Supplemental Appropriations Act, $169,400 STBG Large Urban and $42,350 Ozark Greenways funds. | Adv. CN | 1498 | 332 | 42 | 1872 | 0 | AC-STBG |  | 0 | 414 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | 0 | 0 | 0 | 0 | 0 | 0 | 1458 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1462 | 6 | GREENE | RT ZZ S | 8S3194 | 0.336 | Y | GR2010-20A | Add roundabout on Wilson's Creek Boulevard at County Road 182. $870,000 Federal Lands Access Program and $100,000 National Parks Service funds. | Adv. CN | 1236 | 309 | 0 | 1717 | 0 | AC-OTHER |  | 172 | 194 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1351 | 0 | 0 | 0 | 0 | 0 | 0 | 970 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1463 | 6 | VARIOUS | Various | 5B0800X | 0 | Y | MO1105 | Payback beginning in SFY 2008 for Safe and Sound bridges in the urban Southwest District. | Federal | 0 | 1460 | 0 | 4921 | 1,001 - 2,000 | STATE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 3454 | 292 | 292 | 292 | 292 | 292 | 0
1464 | 6 | VARIOUS | Various | 8I3214 | 0 | Y | MO2302 | On-call work zone enforcement at various locations in the urban Southwest District. | Federal | 198 | 22 | 0 | 220 | 0 | SAFETY |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1465 | 6 | VARIOUS | Various | 8I3230 | 0 | Y | MO2404 | On-call work zone enforcement at various locations in the urban Southwest District. | Federal | 198 | 22 | 0 | 220 | 0 | SAFETY |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1466 | 6 | VARIOUS | Various | 8P3213 | 0 | Y | MO2207-22 | Job Order Contracting for guard cable and guardrail repair in the urban Southwest District. | Adv. CN | 1146 | 286 | 0 | 1438 | 0 | AC-STBG |  | 6 | 237 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1195 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1467 | 6 | VARIOUS | Various | 8P3234 | 0 | Y | MO2213-22 | Job Order Contracting for bridge repairs at various locations in the urban Southwest District. | Adv. CN | 208 | 52 | 0 | 260 | 0 | AC-STBG |  | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 210 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1468 | 6 | VARIOUS | Various | 8Q3208 | 0 | Y | MO2301-22A | Operations and management of Ozarks Traffic ITS in the urban Southwest District. | Adv. CN | 612 | 153 | 0 | 765 | 0 | AC-STBG |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 765 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1469 | 6 | VARIOUS | Various | 8Q3231 | 0 | Y | MO2402-22 | Operations and management of Ozarks Traffic ITS in the urban Southwest District. | Adv. CN | 734 | 184 | 0 | 918 | 0 | AC-STBG |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 918 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1470 | 6 | VARIOUS | Various | SU0068 | 0 | Y | MO2501 | On-call work zone enforcement at various locations in the urban Southwest District. | Federal | 212 | 23 | 0 | 235 | 0 | SAFETY |  | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1471 | 6 | VARIOUS | Various | SU0070 | 0 | Y | MO2502 | Operations and management of Ozarks Traffic ITS in the urban Southwest District. | Adv. CN | 655 | 164 | 0 | 819 | 0 | AC-STBG |  | 0 | 0 | 0 | 54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 765 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1472 | 6 | VARIOUS | Various | SU0072 | 0 | Y | MO2307 | Job Order Contracting for guard cable and guardrail repair in the urban Southwest District. | Adv. CN | 1116 | 279 | 0 | 1395 | 0 | AC-STBG |  | 0 | 4 | 4 | 88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1473 | 6 | VARIOUS | Various | SU0118 | 0 | Y | MO2308 | Job Order Contracting for concrete repairs in the urban Southwest District. | Adv. CN | 562 | 140 | 0 | 702 | 0 | AC-STBG |  | 0 | 15 | 57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 630 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1474 | 7 | BOLLINGER | MO 34 E | 9P3668 | 9.083 | N |  | Pavement resurfacing from County Road 808 to 0.6 mile south of Rte. B. | Federal | 1446 | 361 | 0 | 1815 | 0 | NHPP |  | 8 | 131 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1676 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1475 | 7 | BOLLINGER | MO 34 E | 9P3745 | 0.08 | N |  | Intersection improvements at the south intersection of Rte. 51 in Marble Hill. | Federal | 1353 | 338 | 0 | 1723 | 0 | NHPP |  | 32 | 31 | 85 | 0 | 0 | 0 | 0 | 0 | 417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1158 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1476 | 7 | BOLLINGER | MO 34 E | SE0057 | 15.2 | Y |  | Pavement resurfacing from Rte. B to Rte. 72. | Federal | 2678 | 669 | 0 | 3347 | 0 | NHPP |  | 0 | 15 | 20 | 248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3064 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1477 | 7 | BOLLINGER | MO 34 E | SE0067 | 0.2 | N |  | Intersection improvements at the north intersection of Rte. 51 in Marble Hill. | Federal | 1123 | 281 | 0 | 1404 | 0 | NHPP |  | 0 | 5 | 5 | 20 | 20 | 120 | 0 | 0 | 0 | 0 | 0 | 90 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1478 | 7 | BOLLINGER | MO 51 S | SE0113 | 36.019 | N |  | Pavement resurfacing from Rte. 91 to Rte. 60. | Adv. CN | 5066 | 1267 | 0 | 6333 | 0 | AC-STBG |  | 0 | 7 | 10 | 20 | 20 | 455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5821 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1479 | 7 | BOLLINGER | MO 72 E | 9P3842 | 0.1 | N |  | Intersection improvements at Rte. 51. | Federal | 850 | 94 | 0 | 964 | 0 | SAFETY |  | 20 | 39 | 74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 831 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1480 | 7 | BOLLINGER | RT FF E | SE0098 | 7.318 | N |  | Pavement resurfacing from Rte. H to Rte. 51 and on Spur N from Rte. N to end of state maintenance. | Federal | 0 | 725 | 0 | 725 | 0 | STATE |  | 0 | 3 | 5 | 53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 664 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1481 | 7 | BOLLINGER | RT N E | 9S3716 | 17.4 | N |  | Pavement preservation treatment and add rumblestripes from Rte. 51 to Rte. 25 in Delta. | Adv. CN | 2879 | 720 | 0 | 3601 | 0 | AC-STBG |  | 2 | 48 | 78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3473 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1482 | 7 | BOLLINGER | RT UU E | SE0064 | 7.524 | N |  | Pavement resurfacing from Rte. B to Rte. 34. | Adv. CN | 654 | 164 | 0 | 818 | 0 | AC-STBG |  | 0 | 0 | 5 | 5 | 5 | 51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 752 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1483 | 7 | BOLLINGER | RT ZZ E | 9S3646 | 0.223 | N |  | Bridge replacement over Little Crooked Creek. Project involves bridge N0987. | Adv. CN | 1055 | 264 | 0 | 1331 | 0 | AC-STBG |  | 12 | 44 | 159 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1107 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1484 | 7 | BUTLER | MO 142 E | 9S3557 | 0.02 | N |  | Bridge replacement over Cane Creek. Project involves bridge S0524. | Adv. CN | 709 | 177 | 0 | 944 | 0 | AC-STBG | 9P3758 | 49 | 93 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 793 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1485 | 7 | BUTLER | MO 142 E | 9S3673 | 13.12 | N |  | Pavement improvements from Rte. HH to Rte. 53. | Adv. CN | 1461 | 365 | 0 | 1831 | 0 | AC-STBG |  | 5 | 10 | 119 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1697 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1486 | 7 | BUTLER | MO 158 E | 9S3672 | 5.22 | N |  | Pavement improvements from Rte. 67 to Rte. 142. | Adv. CN | 414 | 104 | 0 | 519 | 0 | AC-STBG |  | 1 | 2 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 481 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1487 | 7 | BUTLER | MO 158 W | SE0115 | 0.2 | N |  | Bridge replacement over Craven Drainage Ditch. Project involves bridge T0170. | Adv. CN | 667 | 167 | 0 | 834 | 0 | AC-STBG |  | 0 | 3 | 40 | 93 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 668 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1488 | 7 | BUTLER | US 160 W | SE0060 | 0.1 | N |  | Intersection improvements at Rte. C and Rte. V. | Adv. CN | 1565 | 391 | 0 | 1956 | 0 | AC-STBG |  | 0 | 25 | 26 | 139 | 0 | 0 | 0 | 0 | 0 | 397 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1369 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1489 | 7 | BUTLER | MO 51 N | SE0118 | 0.164 | N |  | Bridge replacement over St. Francis River. Project involves bridge J0092. | Adv. CN | 2863 | 716 | 0 | 3579 | 0 | AC-STBG |  | 0 | 2 | 90 | 100 | 100 | 283 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1490 | 7 | BUTLER | MO 53 S | 9P3524 | 33.962 | N |  | Pavement resurfacing from Bus. 67 to Rte. 25. | Adv. CN | 5682 | 1420 | 0 | 7182 | 0 | AC-STBG |  | 80 | 493 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6609 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1491 | 7 | BUTLER | MO 53 S | SE0061 | 2.043 | N |  | Add turn lane from Rte. 142 to Rte. UU. | Federal | 5648 | 1412 | 0 | 7060 | 0 | NHPP |  | 0 | 50 | 50 | 290 | 0 | 0 | 0 | 0 | 0 | 4187 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2483 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1492 | 7 | BUTLER | BU 60 E | 9S3603 | 5.095 | N |  | Pavement resurfacing from Rte. W to 0.2 mile west of Rte. B in Poplar Bluff. Project involves bridges A3267 and A3266. | Adv. CN | 2138 | 535 | 0 | 2685 | 0 | AC-STBG |  | 12 | 23 | 188 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2462 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1493 | 7 | BUTLER | N OR 60 E | 9S3587 | 2.08 | N |  | Pavement resurfacing from Short Leaf Drive to Rte. W. | Adv. CN | 186 | 47 | 0 | 240 | 0 | AC-STBG | 9P3700 9P3702 9P3704 9S3588 | 7 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 213 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1494 | 7 | BUTLER | S OR 60 E | 9S3588 | 1.222 | N |  | Pavement resurfacing from Township Line Road to end of state maintenance. | Adv. CN | 100 | 25 | 0 | 132 | 0 | AC-STBG | 9P3700 9P3702 9P3704 9S3587 | 7 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 112 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1495 | 7 | BUTLER | US 60 E | 9P3681 | 1.532 | N |  | Pavement improvements from 0.4 mile west of County Road 411 to 0.5 mile to west of County Road 411 includes ramps at Rte. 60/67. | Federal | 374 | 94 | 0 | 470 | 0 | NHPP |  | 2 | 3 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 435 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1496 | 7 | BUTLER | US 60 W | 9P3700 | 2.64 | N |  | Pavement resurfacing westbound from 0.8 mile west of Rte. PP to 0.3 mile east of Rte. V and eastbound from 0.8 mile east of Rte. 21 south to Rte. V at Ellsinore. | Adv. CN | 1878 | 469 | 0 | 2373 | 0 | AC-STBG | 9P3702 9P3704 9S3587 9S3588 | 26 | 176 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2171 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1497 | 7 | BUTLER | US 60 W | 9P3704 | 16.449 | N |  | Shoulder resurfacing from Rte. 60/67 interchange to 2.3 miles east of Rte. 51 and on Bus. 60 from Rte. 60 to Rte. B. | Adv. CN | 2766 | 692 | 0 | 3478 | 0 | AC-STBG | 9P3700 9P3702 9S3587 9S3588 | 20 | 244 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3214 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1498 | 7 | BUTLER | BU 67 N | SE0106 | 0.05 | N |  | Bridge rehabilitation over Pike Creek. Project involves bridge A0595. | Federal | 702 | 175 | 0 | 877 | 0 | NHPP |  | 0 | 1 | 5 | 20 | 20 | 95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 736 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1499 | 7 | BUTLER | BU 67 S | 9S3602 | 4.669 | N |  | Pavement resurfacing from Bus. 60 to Rte. M and on Rte. M from 0.5 mile west of Bus. 67 to Bus. 67 in Poplar Bluff. Project involves bridge A0595. | Adv. CN | 1366 | 341 | 0 | 1717 | 0 | AC-STBG |  | 10 | 10 | 115 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1582 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1500 | 7 | BUTLER | US 67 S | 9P3514 | 11.769 | N |  | Pavement resurfacing from Arkansas State line to Rte. 160. | Federal | 1969 | 492 | 0 | 2492 | 0 | NHPP |  | 31 | 148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2313 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1501 | 7 | BUTLER | US 67 S | 9P3751 | 2.003 | N |  | Add lanes and outer roads to upgrade corridor to freeway standards from County Road 338 south to County Road 352. $5,085,253 Cost Share and $6,868,213 Poplar Bluff funds. | Federal | 6268 | 0 | 5946 | 13736 | 0 | NHPP | 9P3764 | 600 | 1183 | 0 | 0 | 0 | 0 | 0 | 922 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11031 | 0 | 0 | 0 | 0 | 0 | 922 | 5946 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1502 | 7 | BUTLER | US 67 S | 9P3764 | 1.001 | N |  | Add lanes and outer roads to upgrade corridor to freeway standards from County Road 360 to County Road 338. $2,631,917 Governor's Cost Share Program, $507,271 Cost Share Program and $3,622,456 Poplar Bluff funds. | Federal | 481 | 2632 | 2770 | 7245 | 0 | NHPP | 9P3751 | 72 | 411 | 0 | 0 | 0 | 0 | 0 | 1290 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5472 | 0 | 0 | 0 | 0 | 0 | 853 | 5402 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1503 | 7 | BUTLER | US 67 S | SE0126 | 6.126 | N |  | Pavement resurfacing from northbound lane Rte. 60 to County Road 402 and southbound lane County Road 521 to Rte. 60. | Federal | 3152 | 788 | 0 | 3940 | 0 | NHPP |  | 0 | 1 | 1 | 4 | 40 | 271 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3623 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1504 | 7 | BUTLER | US 67 S | SE0140 | 0.6 | N |  | Bridge replacements over Harviell Drainage Ditch, Hart Drainage Ditch and Neelyville Drainage Ditch. Project involves bridges F0665, K0982 and K0983. | Federal | 3235 | 809 | 0 | 4044 | 0 | NHPP |  | 0 | 50 | 100 | 100 | 100 | 305 | 0 | 0 | 0 | 0 | 0 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3366 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1505 | 7 | BUTLER | W OR 67 S | SE0091 | 2.415 | N |  | Pavement resurfacing from Rte. M to Rte. 67. | Federal | 0 | 363 | 0 | 363 | 0 | STATE |  | 0 | 2 | 2 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 332 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1506 | 7 | BUTLER | W OR 67 S | SE0092 | 1.409 | N |  | Pavement resurfacing from Rte. 67 to end of state maintenance. | Federal | 0 | 300 | 0 | 300 | 0 | STATE |  | 0 | 2 | 2 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 274 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1507 | 7 | BUTLER | RT AA S | 9S3677 | 0.4 | N |  | Bridge replacements over Drainage Ditch 1 and 10. Project involves bridges X0789 and X0790. | Federal | 1386 | 346 | 0 | 1757 | 0 | NHPP |  | 25 | 79 | 134 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1505 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1508 | 7 | BUTLER | RT B E | 9S3606 | 0.215 | N |  | Bridge replacement over Drainage Ditch 1. Project involves bridge G0277. | Federal | 820 | 205 | 0 | 1032 | 0 | NHPP |  | 7 | 50 | 108 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 867 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1509 | 7 | BUTLER | RT EE N | SE0109 | 0.2 | N |  | Bridge rehabilitation over Cane Creek Overflow. Project involves bridge N0884. | Federal | 0 | 587 | 0 | 587 | 0 | STATE |  | 0 | 2 | 2 | 20 | 20 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 493 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1510 | 7 | BUTLER | RT M E | 9S3453 | 0.773 | N |  | Intersection improvements at County Road 459. | Adv. CN | 810 | 202 | 0 | 1068 | 0 | AC-STBG |  | 56 | 33 | 47 | 0 | 0 | 0 | 0 | 0 | 349 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1511 | 7 | BUTLER | RT M W | SE0090 | 8.182 | N |  | Pavement resurfacing from Rte. 67 to end of state maintenance. | Federal | 757 | 189 | 0 | 946 | 0 | NHPP |  | 0 | 2 | 2 | 76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 866 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1512 | 7 | BUTLER | RT MM E | SE0114 | 0.2 | N |  | Bridge replacement over Harviell Drainage Ditch. Project involves bridge N0686. | Adv. CN | 782 | 195 | 0 | 977 | 0 | AC-STBG |  | 0 | 11 | 25 | 127 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 803 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1513 | 7 | BUTLER | RT PP E | SE0066 | 2.76 | N |  | Pavement resurfacing from roundabout to Bus. 60. | Adv. CN | 1199 | 300 | 0 | 1499 | 0 | AC-STBG |  | 0 | 1 | 5 | 5 | 5 | 104 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1379 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1514 | 7 | BUTLER | RT U E | 9S3608 | 0.263 | N |  | Bridge rehabilitation over St. Francis River. Project involves bridge A2470. | Federal | 1267 | 317 | 0 | 1617 | 0 | NHPP |  | 33 | 72 | 157 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1348 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1515 | 7 | BUTLER | RT U E | 9S3779 | 11.77 | N |  | Pavement resurfacing from Rte. CC to Rte. 25. | Adv. CN | 923 | 231 | 0 | 1156 | 0 | AC-STBG |  | 2 | 5 | 5 | 5 | 67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1072 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1516 | 7 | BUTLER | RT W S | 9S3781 | 4.09 | N |  | Pavement resurfacing from Rte. O to Bus. 60. | Adv. CN | 491 | 123 | 0 | 616 | 0 | AC-STBG |  | 2 | 2 | 2 | 2 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1517 | 7 | BUTLER | RT WW S | SE0131 | 0.93 | N |  | Signal replacement at Rte. WW and Henry Street in Poplar Bluff at Bus. 60 and 9th Street in Poplar Bluff and at Rte. 160 and Rte. Y in Doniphan. | Adv. CN | 1609 | 402 | 0 | 2011 | 0 | AC-STBG |  | 0 | 68 | 165 | 0 | 0 | 0 | 0 | 0 | 202 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1518 | 7 | CAPE GIRARDEAU | MO 177 S | 9S3590 | 11.919 | N |  | Pavement resurfacing from Rte. J to end of state maintenance. Add rumblestripes from Ute Lane to Lexington Avenue. | Adv. CN | 2402 | 600 | 0 | 3011 | 0 | AC-STBG |  | 9 | 10 | 165 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2827 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1519 | 7 | CAPE GIRARDEAU | MO 25 S | 9P3772 | 0.2 | N |  | Bridge replacement over Drainage Ditch 25. Project involves bridge H0431. | Federal | 630 | 157 | 0 | 788 | 0 | NHPP |  | 1 | 10 | 20 | 21 | 61 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 669 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1520 | 7 | CAPE GIRARDEAU | MO 25 S | 9S3706 | 0.25 | N |  | Bridge rehabilitation over Diversion Channel. Project involves bridge A4817. | Federal | 653 | 163 | 0 | 821 | 0 | NHPP |  | 5 | 5 | 5 | 54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 752 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1521 | 7 | CAPE GIRARDEAU | MO 25 S | 9S3841 | 0.1 | N |  | Add roundabout at Rte. K. | Federal | 755 | 84 | 0 | 859 | 0 | SAFETY |  | 20 | 117 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 702 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1522 | 7 | CAPE GIRARDEAU | MO 25 S | SE0072 | 0.2 | N |  | Add roundabout at Rte. 74 and Rte. A. | Federal | 1008 | 112 | 0 | 1120 | 0 | SAFETY |  | 0 | 9 | 30 | 113 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 968 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1523 | 7 | CAPE GIRARDEAU | MO 25 S | SE0117 | 15.638 | N |  | Pavement resurfacing from Rte. 77 to Rte. 91. | Adv. CN | 3226 | 807 | 0 | 4033 | 0 | AC-STBG |  | 0 | 3 | 50 | 289 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3691 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1524 | 7 | CAPE GIRARDEAU | MO 25 S | SE0128 | 11.18 | Y |  | Pavement resurfacing from Rte. 61 to Rte. 77 and add turn lanes at Rte. Z and County Roads 325, 324 and 318. | Adv. CN | 2888 | 722 | 0 | 3610 | 0 | AC-STBG |  | 0 | 4 | 20 | 223 | 0 | 0 | 0 | 0 | 0 | 692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2671 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1525 | 7 | CAPE GIRARDEAU | MO 25 S | SE0164 | 0.551 | N |  | Scour repair over the Diversion Channel. Project involves bridge A4817. | Adv. CN | 281 | 70 | 0 | 351 | 0 | AC-STBG |  | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 306 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1526 | 7 | CAPE GIRARDEAU | MO 34 E | 9P3812 | 0.4 | N |  | Bridge replacement over Dillard Creek. Project involves bridge J0883. | Federal | 2140 | 535 | 0 | 2680 | 0 | NHPP |  | 5 | 29 | 100 | 79 | 171 | 0 | 0 | 0 | 0 | 0 | 41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2255 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1527 | 7 | CAPE GIRARDEAU | IS 55 N | SE0073 | 9.408 | N |  | Pavement resurfacing from Rte. FF to Rte. KK. | Federal | 2324 | 258 | 0 | 2582 | 0 | NHPP |  | 0 | 14 | 10 | 10 | 179 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2369 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1528 | 7 | CAPE GIRARDEAU | IS 55 S | 9I3838 | 12.38 | Y |  | Pavement resurfacing on southbound lanes from Rte. 61 to Rte. 74 and on northbound lanes from Rte. M to Rte. 61. | Federal | 9593 | 1066 | 0 | 10709 | 0 | NHPP |  | 50 | 100 | 676 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1529 | 7 | CAPE GIRARDEAU | US 61 N | 9P3735 | 0.247 | Y |  | Bridge replacement at Hubble Creek and add turn lanes at Mary Street in Jackson. Project involves bridge H0144. | Federal | 3990 | 998 | 0 | 5122 | 0 | NHPP |  | 134 | 299 | 0 | 0 | 0 | 0 | 0 | 0 | 1302 | 0 | 0 | 0 | 0 | 0 | 0 | 3387 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1530 | 7 | CAPE GIRARDEAU | US 61 S | 9P3122 | 0.08 | Y |  | Bridge replacement over I-55 and capacity improvements at Exit 93. Project involves bridge A0628. | Federal | 7601 | 1900 | 0 | 10238 | 0 | NHPP |  | 737 | 200 | 100 | 100 | 415 | 0 | 0 | 0 | 0 | 0 | 106 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8580 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1531 | 7 | CAPE GIRARDEAU | US 61 S | 9P3575 | 10.764 | Y |  | Drainage improvements in Cape Girardeau County. | Federal | 1158 | 289 | 0 | 1474 | 0 | NHPP |  | 27 | 5 | 88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1354 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1532 | 7 | CAPE GIRARDEAU | US 61 S | 9S3782 | 1.4 | Y |  | Pavement resurfacing from Rte. 177 to Drury Lane. | Adv. CN | 653 | 163 | 0 | 817 | 0 | AC-STBG |  | 1 | 1 | 1 | 1 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 758 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1533 | 7 | CAPE GIRARDEAU | US 61 S | 9S3810 | 0.3 | N |  | Bridge replacement over Erlide Creek. Project involves bridge G0027. | Federal | 528 | 132 | 0 | 665 | 0 | NHPP |  | 5 | 10 | 15 | 21 | 38 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 566 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1534 | 7 | CAPE GIRARDEAU | US 61 S | SE0071 | 0.2 | Y |  | Add intersection turn lanes and upgrade signals at Donna Drive. | Federal | 1432 | 358 | 0 | 1790 | 0 | NHPP |  | 0 | 1 | 2 | 10 | 20 | 57 | 0 | 0 | 0 | 0 | 0 | 1096 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 604 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1535 | 7 | CAPE GIRARDEAU | MO 72 E | 9P3121B | 3.49 | Y |  | Pavement resurfacing from Rte. 34 to Rte. 25/61 in Jackson. | Federal | 1202 | 300 | 0 | 1526 | 0 | NHPP |  | 24 | 74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1428 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1536 | 7 | CAPE GIRARDEAU | MO 74 E | 9P3308 | 0.326 | Y |  | Bridge rehabilitation over Mississippi River "Emerson bridge". Project involves bridge A5076. $6,500,000 from IDOT. | Federal | 8224 | 0 | 6500 | 14756 | 0 | NHPP |  | 32 | 10 | 60 | 862 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13792 | 0 | 0 | 0 | 0 | 0 | 0 | 6500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1537 | 7 | CAPE GIRARDEAU | MO 74 E | 9P3862 | 0.25 | Y |  | Payback to Cape Girardeau for eastbound intersection modification at Minnesota Avenue and construct westbound intersection at Minnesota Avenue. Design, right of way and construction by Cape Girardeau. $296,000 Cost Share funds. | Adv. CN | 242 | 61 | 0 | 306 | 0 | AC-NHPP |  | 3 | 1 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 296 | 0 | 0 | 0 | 0
1538 | 7 | CAPE GIRARDEAU | MO 74 W | 9P3840 | 0.243 | Y |  | Intersection improvements at I-55 interchange. | Federal | 518 | 57 | 0 | 577 | 0 | SAFETY |  | 2 | 15 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 524 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1539 | 7 | CAPE GIRARDEAU | MO 77 S | 9S3549 | 13.328 | N |  | Pavement resurfacing and add rumblestripes from Rte. 25 to Rte. 61. Resurface only from County Road 264 to Rte. 61. | Adv. CN | 1783 | 446 | 0 | 2252 | 0 | AC-STBG | 9S3825 | 23 | 245 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1984 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1540 | 7 | CAPE GIRARDEAU | RT BB E | 9S3776 | 0.2 | N |  | Bridge rehabilitation over Caney Creek. Project involves bridge R0071. | Federal | 0 | 667 | 0 | 668 | 0 | STATE |  | 1 | 10 | 10 | 23 | 57 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 562 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1541 | 7 | CAPE GIRARDEAU | RT D S | 9S3645 | 0.233 | N |  | Bridge replacement over Byrd Creek. Project involves bridge P0734. | Federal | 1175 | 294 | 0 | 1481 | 0 | NHPP |  | 12 | 40 | 164 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1247 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1542 | 7 | CAPE GIRARDEAU | RT D S | 9S3773 | 0.2 | N |  | Bridge replacement over Cane Creek. Project involves bridge P0714. | Adv. CN | 831 | 208 | 0 | 1044 | 0 | AC-STBG |  | 5 | 20 | 20 | 27 | 69 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 892 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1543 | 7 | CAPE GIRARDEAU | RT EE E | 9S3477 | 4.3 | N |  | Pavement resurfacing from Rte. 25 in Delta to Rte. 77 in Chaffee. | Adv. CN | 511 | 128 | 0 | 642 | 0 | AC-STBG |  | 3 | 2 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 589 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1544 | 7 | CAPE GIRARDEAU | RT K E | 9S3847 | 2.6 | Y |  | Roadway widening and adding signals from Greenbriar Drive to 0.2 mile west of I-55 in Cape Girardeau. $2,606,000 Open Container funds and $585,560 repurposed earmarks DEMO ID MO234. | Adv. CN | 3796 | 949 | 0 | 4845 | 0 | AC-STBG |  | 100 | 105 | 356 | 0 | 0 | 0 | 0 | 0 | 336 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3948 | 0 | 0 | 0 | 0 | 0 | 0 | 586 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1545 | 7 | CAPE GIRARDEAU | RT KK E | SE0047 | 35.096 | N |  | Pavement preservation treatment from Rte. BB to Rte. 61, Rte. T from Rte. BB to Rte. 51 and Rte. N from Rte. M to end of state maintenance. | Adv. CN | 794 | 198 | 0 | 992 | 0 | AC-STBG |  | 0 | 5 | 8 | 67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 912 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1546 | 7 | CAPE GIRARDEAU | RT N E | SE0044 | 0.023 | N |  | Bridge replacement over Whitewater River. Project involves bridge S0291. | Adv. CN | 605 | 151 | 0 | 756 | 0 | AC-STBG |  | 0 | 9 | 9 | 9 | 34 | 68 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 603 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1547 | 7 | CAPE GIRARDEAU | RT N E | SE0045 | 0.09 | N |  | Bridge replacement over Small Creek. Project involves bridge S0532. | Adv. CN | 370 | 92 | 0 | 462 | 0 | AC-STBG |  | 0 | 5 | 5 | 5 | 22 | 41 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1548 | 7 | CAPE GIRARDEAU | RT OO E | SE0030 | 0.026 | N |  | Bridge replacement over Whitewater River. Project involves bridge N0690. | Adv. CN | 2426 | 607 | 0 | 3033 | 0 | AC-STBG |  | 0 | 77 | 158 | 314 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2463 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1549 | 7 | CAPE GIRARDEAU | RT W S | 9S3826 | 9.7 | Y |  | Pavement resurfacing from Rte. 177 to Rte. 61. | Adv. CN | 1395 | 349 | 0 | 1746 | 0 | AC-STBG | 9S3525 | 2 | 20 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1550 | 7 | CAPE GIRARDEAU | RT Y E | 9S3589 | 0.2 | N |  | Bridge replacement over Little Indian Creek. Project involves bridge N0198. | Federal | 761 | 190 | 0 | 968 | 0 | NHPP |  | 17 | 27 | 72 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 832 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1551 | 7 | CAPE GIRARDEAU | RT Z E | 9S3738 | 0.35 | N |  | Bridge replacements over Hubble Creek and Hubble Creek Overflow. Project involves bridges T0788 and T0842. | Federal | 2537 | 634 | 0 | 3221 | 0 | NHPP |  | 50 | 107 | 208 | 0 | 0 | 0 | 0 | 0 | 42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2814 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1552 | 7 | CARTER | BU 60 E | SE0022 | 2.067 | N |  | Pavement resurfacing on Bus. 60 in Van Buren. | Adv. CN | 304 | 76 | 0 | 380 | 0 | AC-STBG |  | 0 | 1 | 1 | 1 | 2 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1553 | 7 | CARTER | US 60 W | 9P3758 | 0.44 | N |  | Bridge rehabilitation in the westbound lane over Current River in Van Buren. Project involves bridge A5000. | Federal | 423 | 106 | 0 | 551 | 0 | NHPP | 9S3557 | 22 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 464 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1554 | 7 | CARTER | RT A E | 9S3609 | 0.209 | N |  | Bridge replacement over Cane Creek in Ellsinore. Project involves bridge G0348. | Federal | 694 | 174 | 0 | 890 | 0 | NHPP |  | 22 | 52 | 93 | 0 | 0 | 0 | 0 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 706 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1555 | 7 | CARTER | RT A E | 9S3717 | 8.325 | N |  | Pavement preservation treatment from Rte. 60 near Ellsinore to Rte. 49. | Adv. CN | 194 | 48 | 0 | 243 | 0 | AC-STBG |  | 1 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 227 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1556 | 7 | CARTER | RT B E | 9S3612 | 0.236 | N |  | Bridge replacement over Ten Mile Creek. Project involves bridge R0240. | Federal | 946 | 237 | 0 | 1205 | 0 | NHPP |  | 22 | 55 | 118 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1005 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1557 | 7 | CARTER | RT B E | 9S3761 | 110.623 | N |  | Bridge rail and guardrail upgrades at various locations in the Southeast District. | Adv. CN | 1442 | 361 | 0 | 1868 | 0 | AC-STBG |  | 65 | 149 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1654 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1558 | 7 | CARTER | RT D S | SE0149 | 2.062 | N |  | Add rumblestripes from County Road 123 to Bus. 60. | Adv. CN | 615 | 154 | 0 | 769 | 0 | AC-STBG |  | 0 | 10 | 20 | 64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 675 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1559 | 7 | CARTER | RT N E | SE0051 | 0.141 | N |  | Bridge replacement over Middle Brushy Creek. Project involves bridge G0770. | Federal | 0 | 1085 | 0 | 1085 | 0 | STATE |  | 0 | 27 | 59 | 113 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 882 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1560 | 7 | CHRISTIAN | RT T E | SE0014 | 8.383 | N |  | Pavement resurfacing from Rte. UU to Rte. 76 in Douglas County. | Adv. CN | 658 | 165 | 0 | 823 | 0 | AC-STBG |  | 0 | 2 | 2 | 2 | 5 | 52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 760 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1561 | 7 | DENT | MO 72 E | 9P3843 | 33.763 | N |  | Pavement resurfacing from the east intersection of Rte. 32 to the west intersection of Rte. 21. | Adv. CN | 2989 | 747 | 0 | 3743 | 0 | AC-STBG |  | 7 | 8 | 8 | 27 | 244 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3449 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1562 | 7 | DOUGLAS | MO 14 E | 9P3701 | 20.336 | N |  | Pavement resurfacing from Rte. 181 south to Rte. 63. | Adv. CN | 1332 | 333 | 0 | 1668 | 0 | AC-STBG |  | 3 | 4 | 14 | 113 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1534 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1563 | 7 | DOUGLAS | MO 14 E | 9P3747 | 0.1 | N |  | Modify roundabout at Springfield Road and Jefferson Street. | Adv. CN | 668 | 167 | 0 | 861 | 0 | AC-STBG |  | 26 | 71 | 0 | 0 | 0 | 0 | 0 | 0 | 104 | 0 | 0 | 0 | 0 | 0 | 0 | 660 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1564 | 7 | DOUGLAS | MO 14 E | 9P3808 | 12.552 | N |  | Pavement resurfacing from Rte. Z to Rte. 5. | Adv. CN | 1401 | 350 | 0 | 1754 | 0 | AC-STBG |  | 3 | 3 | 4 | 13 | 115 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1616 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1565 | 7 | DOUGLAS | MO 14 E | SE0013 | 31.367 | N |  | Pavement resurfacing from Bus. 5 to Rte. 181. | Adv. CN | 2519 | 630 | 0 | 3149 | 0 | AC-STBG |  | 0 | 6 | 6 | 7 | 22 | 199 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1566 | 7 | DOUGLAS | BU 5 S | SE0016 | 2.359 | N |  | Pavement resurfacing on Bus. 5 loop in Ava. | Adv. CN | 450 | 113 | 0 | 563 | 0 | AC-STBG |  | 0 | 1 | 1 | 1 | 4 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 520 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1567 | 7 | DOUGLAS | MO 76 E | SE0012 | 33.111 | N |  | Pavement resurfacing from Rte. 5 to Rte. 181. Project involves bridges P0351 and T0609. | Adv. CN | 3221 | 805 | 0 | 4026 | 0 | AC-STBG |  | 0 | 8 | 8 | 9 | 28 | 255 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3718 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1568 | 7 | DOUGLAS | MO 76 E | SE0025 | 0.047 | N |  | Bridge rehabilitation over Indian Creek. Project involves bridge T0972. | Adv. CN | 634 | 158 | 0 | 792 | 0 | AC-STBG |  | 0 | 9 | 9 | 10 | 37 | 73 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 647 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1569 | 7 | DOUGLAS | MO 95 S | SE0020 | 9.499 | N |  | Pavement resurfacing from Rte. 76 to Rte. 14. | Adv. CN | 752 | 188 | 0 | 940 | 0 | AC-STBG |  | 0 | 1 | 2 | 2 | 7 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 868 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1570 | 7 | DUNKLIN | MO 108 E | 9S3465 | 5.704 | N |  | Pavement resurfacing from Arkansas State line to Rte. 412. | Adv. CN | 431 | 108 | 0 | 551 | 0 | AC-STBG | 9S3337 9S3339 | 12 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 499 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1571 | 7 | DUNKLIN | MO 153 S | 9S3517 | 0.3 | N |  | Bridge replacement over Taylor Slough. Project involves bridge J0842. | Federal | 177 | 44 | 0 | 251 | 0 | NHPP | 9S3530 | 19 | 23 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 198 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1572 | 7 | DUNKLIN | MO 153 S | SE0070 | 0.1 | N |  | Bridge replacement over Drainage Slough. Project involves bridge J0854. | Adv. CN | 444 | 111 | 0 | 555 | 0 | AC-STBG |  | 0 | 4 | 10 | 10 | 10 | 52 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 439 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1573 | 7 | DUNKLIN | MO 162 E | 9S3326 | 16.489 | N |  | Pavement resurfacing from Rte. 25 near Clarkton to Rte. 61 near Portageville. | Adv. CN | 2031 | 508 | 0 | 2567 | 0 | AC-STBG | 9S3403 9S3528 SE0084 | 28 | 178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2361 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1574 | 7 | DUNKLIN | MO 164 E | 9P3678 | 0.4 | N |  | Bridge replacement over Deering Drainage Ditch and Lateral Ditch 4. Project involves bridges L0305 and L0304. | Federal | 1531 | 383 | 0 | 1939 | 0 | NHPP |  | 25 | 25 | 31 | 152 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1690 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1575 | 7 | DUNKLIN | MO 164 E | 9S3780 | 29.15 | N |  | Pavement resurfacing and add rumblestripes from Rte. 412 to Rte. 61. | Adv. CN | 7439 | 1860 | 0 | 9301 | 0 | AC-STBG |  | 2 | 20 | 20 | 20 | 234 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9005 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1576 | 7 | DUNKLIN | BU 25 S | SE0144 | 1.405 | N |  | Add center turn lane from Rte. 25 to Broadwater Road. | Adv. CN | 1306 | 327 | 0 | 1633 | 0 | AC-STBG |  | 0 | 10 | 10 | 118 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1495 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1577 | 7 | DUNKLIN | MO 25 S | 9P3721 | 22.039 | N |  | Pavement resurfacing and add shoulders from 1.8 miles south of Rte. 62 near Malden to 0.3 mile north of Rte. 153. Add shoulders only from 0.3 mile north of Rte. 153 to 0.1 mile north of Rte. E in Kennett. | Federal | 7646 | 1911 | 0 | 9657 | 0 | NHPP |  | 100 | 996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8561 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1578 | 7 | DUNKLIN | US 412 E | 9P3766 | 0.239 | N |  | Payment to ARDOT for bridge repair on St. Francis River bridge. Project involves bridge A4554. | Federal | 401 | 100 | 0 | 502 | 0 | NHPP |  | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1579 | 7 | DUNKLIN | US 412 E | SE0058 | 1.4 | N |  | Pavement resurfacing from Rte. VV to Rte. 84. | Federal | 570 | 142 | 0 | 712 | 0 | NHPP |  | 0 | 3 | 5 | 52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 652 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1580 | 7 | DUNKLIN | MO 53 S | 9P3768 | 0.27 | N |  | Bridge replacement over Drainage Ditch 2 and Lateral Ditch 2. Project involves bridges G0423 and G0424. | Federal | 2182 | 546 | 0 | 2753 | 0 | NHPP | SE0086 SE0088 | 25 | 152 | 302 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2246 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1581 | 7 | DUNKLIN | US 62 E | 9P3667 | 10.291 | N |  | Pavement resurfacing from Arkansas State line to Rte. 53 and from Rte. 53 to Rte. 25. Add rumblestripes from Arkansas State line to Rte. 53. | Adv. CN | 2003 | 501 | 0 | 2509 | 0 | AC-STBG |  | 5 | 10 | 10 | 142 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2342 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1582 | 7 | DUNKLIN | MO 84 E | 9P3839 | 2.72 | N |  | Pavement resurfacing from Rte. O to Rte. 412 through Kennett. | Federal | 673 | 168 | 0 | 843 | 0 | NHPP |  | 2 | 2 | 2 | 5 | 51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 781 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1583 | 7 | DUNKLIN | MO 84 E | SE0132 | 1.2 | Y |  | Signal replacement at Rte. 84 and Kennett Street in Kennett, Rte. 84 and Main Street in Kennett, Rte. 61 and Cape Rock Drive in Cape Girardeau and at Rte. 62 and Rte. 105 in Charleston. | Adv. CN | 2045 | 511 | 0 | 2556 | 0 | AC-STBG |  | 0 | 32 | 85 | 204 | 0 | 0 | 0 | 0 | 0 | 71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2164 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1584 | 7 | DUNKLIN | RT A S | 9S3676 | 0.6 | N |  | Bridge replacements over Drainage Ditch 5, Main Drainage Ditch and Levee Ditch. Project involves bridges S0973, S0974 and S0975. | Federal | 1323 | 331 | 0 | 1750 | 0 | NHPP |  | 96 | 31 | 123 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1476 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1585 | 7 | DUNKLIN | RT D E | SE0079 | 22.242 | N |  | Pavement preservation from Rte. 25 to Rte. 61. | Adv. CN | 537 | 134 | 0 | 671 | 0 | AC-STBG |  | 0 | 1 | 1 | 43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 626 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1586 | 7 | DUNKLIN | RT DD W | SE0095 | 0.257 | N |  | Bridge painting over Saint Francis River and over Rte. 60 at Marble Hill Road and Rte. T in Butler County. Project involves bridges A2382, A3723 and A3681. | Federal | 0 | 874 | 0 | 874 | 0 | STATE |  | 0 | 2 | 4 | 10 | 30 | 95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 733 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1587 | 7 | DUNKLIN | RT F N | SE0055 | 5.701 | N |  | Pavement preservation treatment from Rte. 412 to Arkansas State line. | Federal | 0 | 187 | 0 | 187 | 0 | STATE |  | 0 | 1 | 1 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 171 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1588 | 7 | DUNKLIN | RT H S | SE0088 | 0.2 | N |  | Bridge improvement over Lateral Ditch No. 2. Project involves bridge X0586. | Adv. CN | 645 | 161 | 0 | 906 | 0 | AC-STBG | 9P3768 SE0086 | 100 | 10 | 3 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 773 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1589 | 7 | DUNKLIN | RT J E | 9S3403 | 11.503 | N |  | Pavement resurfacing and add rumblestripes from Bus. 25 in Malden to Rte. 53. | Adv. CN | 2708 | 677 | 0 | 3408 | 0 | AC-STBG | 9S3326 9S3528 SE0084 | 23 | 108 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3277 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1590 | 7 | DUNKLIN | RT J E | SE0086 | 0.2 | N |  | Bridge improvement over Drainage Ditch. Project involves bridge S0375. | Adv. CN | 436 | 109 | 0 | 610 | 0 | AC-STBG | 9P3768 SE0088 | 65 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 515 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1591 | 7 | DUNKLIN | RT J E | SE0163 | 0.035 | N |  | Urgent bridge rehabilitation over Drainage Ditch 12. Project involves bridge A2383. | Federal | 1006 | 251 | 0 | 1257 | 0 | NHPP |  | 0 | 237 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1020 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1592 | 7 | DUNKLIN | RT M S | 9S3337 | 2.514 | N |  | Pavement resurfacing from Rte. 25 to Rte. 153. | Adv. CN | 258 | 64 | 0 | 336 | 0 | AC-STBG | 9S3339 9S3465 | 14 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 295 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1593 | 7 | DUNKLIN | RT MM N | SE0130 | 0.2 | N |  | Bridge replacement over Lateral Ditch 1. Project involves bridge N0626. | Adv. CN | 993 | 248 | 0 | 1241 | 0 | AC-STBG |  | 0 | 1 | 2 | 5 | 25 | 162 | 0 | 0 | 0 | 0 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1594 | 7 | DUNKLIN | RT N E | SE0054 | 6.924 | N |  | Pavement preservation treatment from Rte. 412 to Rte. 164. | Federal | 168 | 42 | 0 | 210 | 0 | STBG |  | 0 | 1 | 1 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 193 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1595 | 7 | DUNKLIN | RT N E | SE0101 | 0.2 | N |  | Bridge replacement over Drainage Ditch 35. Project involves bridge P0876. | Adv. CN | 542 | 136 | 0 | 678 | 0 | AC-STBG |  | 0 | 6 | 20 | 85 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 546 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1596 | 7 | DUNKLIN | RT P E | 9S3339 | 4.299 | N |  | Pavement resurfacing from Rte. C in Senath to Rte. Y. | Adv. CN | 441 | 110 | 0 | 565 | 0 | AC-STBG | 9S3337 9S3465 | 14 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 514 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1597 | 7 | DUNKLIN | RT TT S | SE0158 | 26.861 | N |  | Pavement resurfacing from Rte. 164 to the Arkansas State line, Rte. U Reynolds County, Rte. AA Cape Girardeau County, Rte. V Madison County, Rte. NN Madison County and Rte. NN in Scott and Mississippi County. | Federal | 0 | 3455 | 0 | 3534 | 0 | STATE |  | 79 | 224 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3231 | 0 | 0 | 0 | 0 | 0 | 0 | 3231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1598 | 7 | DUNKLIN | RT UU E | SE0065 | 0.4 | N |  | Bridge replacement over Lateral Ditch 78 and Lateral Ditch 79. Project involves bridges P0663 and P0664. | Federal | 0 | 1448 | 0 | 1448 | 0 | STATE |  | 0 | 5 | 5 | 20 | 20 | 115 | 0 | 0 | 0 | 0 | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1239 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1599 | 7 | DUNKLIN | RT WW N | SE0053 | 5.579 | N |  | Pavement preservation treatment from Rte. 53 to Rte. J. | Federal | 147 | 37 | 0 | 184 | 0 | STBG |  | 0 | 1 | 1 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 168 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1600 | 7 | DUNKLIN | RT Y S | SE0102 | 9.129 | N |  | Pavement resurfacing from Rte. 412 to Rte. 164. | Adv. CN | 742 | 185 | 0 | 927 | 0 | AC-STBG |  | 0 | 2 | 5 | 61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 859 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1601 | 7 | DUNKLIN | RT YY S | SE0103 | 0.517 | N |  | Pavement resurfacing from Rte. 164 to end of state maintenance. | Federal | 0 | 29 | 0 | 29 | 0 | STATE |  | 0 | 1 | 1 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1602 | 7 | DUNKLIN | RT Z S | 9S3774 | 0.2 | N |  | Bridge replacement over Main Drainage Ditch. Project involves bridge S0924. | Federal | 658 | 165 | 0 | 828 | 0 | NHPP |  | 5 | 13 | 20 | 22 | 57 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 706 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1603 | 7 | HOWELL | MO 137 S | 9S3801 | 0.223 | N |  | Bridge replacement over BNSF Railway. Project involves bridge K0789. | Federal | 4197 | 1049 | 0 | 5296 | 0 | NHPP |  | 50 | 50 | 50 | 182 | 381 | 0 | 0 | 0 | 0 | 0 | 1306 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3277 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1604 | 7 | HOWELL | MO 142 E | 9S3684 | 0.2 | N |  | Bridge replacement over Myatt Creek. Project involves bridge P0058. | Federal | 1343 | 336 | 0 | 1700 | 0 | NHPP |  | 21 | 21 | 22 | 76 | 161 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1389 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1605 | 7 | HOWELL | MO 142 E | 9S3846 | 26.175 | N |  | Pavement resurfacing from Rte. E to Bus. 63 in Thayer. | Adv. CN | 1853 | 463 | 0 | 2320 | 0 | AC-STBG |  | 4 | 5 | 5 | 17 | 151 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2138 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1606 | 7 | HOWELL | US 160 E | 9P3614 | 20.961 | N |  | Pavement resurfacing from Rte. 63 to Rte. 99. Rumblestripes from Allen Street to Rte. 99. Add southbound turn lane at intersection at Rte. BB. Project involves bridges S0270 and S0271. | Adv. CN | 4822 | 1205 | 0 | 6068 | 0 | AC-STBG |  | 41 | 6 | 362 | 0 | 0 | 0 | 0 | 0 | 222 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5437 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1607 | 7 | HOWELL | US 160 E | SE0006 | 0.593 | N |  | Pavement resurfacing from County Road 6070 to Rte. 63. | Federal | 221 | 55 | 0 | 276 | 0 | NHPP |  | 0 | 1 | 1 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 254 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1608 | 7 | HOWELL | MO 17 S | 9S3692 | 17.865 | N |  | Pavement resurfacing from Rte. 63 to Arkansas State line. | Adv. CN | 1932 | 483 | 0 | 2420 | 0 | AC-STBG |  | 5 | 5 | 20 | 165 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1609 | 7 | HOWELL | MO 17 S | 9S3731 | 17.414 | N |  | Add rumblestripes from 0.4 mile south of Rte. WW to Rte. 160. $2,683,000 Open Container funds. | Federal | 2849 | 317 | 0 | 3278 | 0 | SAFETY | 9S3191 | 112 | 308 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2858 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1610 | 7 | HOWELL | US 60 W | 9P3615 | 13 | N |  | Pavement resurfacing in the westbound lanes from 0.1 mile west of Rte. 63 south to 0.2 mile east of Rte. 63 north. | Federal | 5370 | 1342 | 0 | 6789 | 0 | NHPP | 9P3617 | 77 | 502 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6210 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1611 | 7 | HOWELL | BU 63 S | SE0133 | 0.451 | N |  | Signal replacement at Bus. 63 and Missouri Avenue in West Plains and at Porter Wagoner Boulevard and Broadway in West Plains. | Adv. CN | 1249 | 312 | 0 | 1561 | 0 | AC-STBG |  | 0 | 8 | 8 | 48 | 102 | 0 | 0 | 0 | 0 | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1115 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1612 | 7 | HOWELL | US 63 S | 9P3617 | 14.909 | N |  | Pavement resurfacing from 0.1 mile south of South Bus. 63 to 0.5 mile south of Rte. F. Project involves bridge F0372. | Federal | 6334 | 1584 | 0 | 8009 | 0 | NHPP | 9P3615 | 91 | 592 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1613 | 7 | HOWELL | US 63 S | 9P3683 | 0.6 | N |  | Bridge replacement over BNSF Railway. Project involves bridge F0373. | Federal | 3866 | 966 | 0 | 5106 | 0 | NHPP |  | 274 | 555 | 0 | 0 | 0 | 0 | 0 | 0 | 116 | 0 | 0 | 0 | 0 | 0 | 0 | 4161 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1614 | 7 | HOWELL | US 63 S | SE0004 | 4.705 | N |  | Pavement resurfacing from south of Rte. 60 to north of Rte. P. | Federal | 898 | 224 | 0 | 1122 | 0 | NHPP |  | 0 | 4 | 10 | 77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1615 | 7 | HOWELL | RT DD E | SE0009 | 3.726 | N |  | Pavement resurfacing from Rte. 137 to end of state maintenance. | Federal | 0 | 320 | 0 | 320 | 0 | STATE |  | 0 | 1 | 3 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 294 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1616 | 7 | HOWELL | RT JJ S | SE0011 | 13.289 | N |  | Pavement resurfacing from Rte. 160 to Arkansas State line. | Adv. CN | 1041 | 260 | 0 | 1301 | 0 | AC-STBG |  | 0 | 2 | 2 | 4 | 9 | 82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1202 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1617 | 7 | HOWELL | RT JJ S | SE0034 | 0.061 | N |  | Bridge replacement over South Fork Spring River. Project involves bridge P0797. | Adv. CN | 1278 | 319 | 0 | 1597 | 0 | AC-STBG |  | 0 | 19 | 19 | 19 | 71 | 148 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1306 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1618 | 7 | HOWELL | RT WW S | SE0008 | 3.777 | N |  | Pavement resurfacing from Rte. 17 to end of state maintenance. | Federal | 0 | 331 | 0 | 331 | 0 | STATE |  | 0 | 1 | 3 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1619 | 7 | HOWELL | RT ZZ E | 9S3565 | 0.024 | N |  | Bridge replacement over Howell Creek. Project involves bridge N0497. | Federal | 802 | 201 | 0 | 1083 | 0 | NHPP |  | 80 | 125 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 869 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1620 | 7 | HOWELL | RT ZZ E | 9S3845 | 7.579 | N |  | Pavement resurfacing from Rte. 63 to end of state maintenance. | Adv. CN | 560 | 140 | 0 | 701 | 0 | AC-STBG |  | 1 | 1 | 1 | 5 | 47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 646 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1621 | 7 | IRON | MO 143 S | 9S3783 | 17.4 | N |  | Pavement preservation treatment from Rte. 49 to Rte 34. | Adv. CN | 399 | 100 | 0 | 501 | 0 | AC-STBG | 9P3784 9P3785 9S3786 9S3787 9S3788 9S3789 9S3790 9S3797 | 2 | 1 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 471 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1622 | 7 | IRON | MO 21 S | 9P3548 | 8.06 | N |  | Pavement and bridge resurfacing and safety improvements from Rte. E to Rte. 49. Project involves bridges A4450, A4379 and A4380. | Adv. CN | 3121 | 780 | 0 | 4041 | 0 | AC-STBG |  | 140 | 100 | 261 | 0 | 0 | 0 | 0 | 0 | 83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3457 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1623 | 7 | IRON | MO 21 S | 9P3570 | 6.81 | N |  | Pavement resurfacing from Rte. 32 to Rte. N. | Adv. CN | 1179 | 295 | 0 | 1475 | 0 | AC-STBG |  | 1 | 2 | 6 | 104 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1362 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1624 | 7 | IRON | MO 32 E | SE0038 | 0.085 | N |  | Bridge replacement over Reid Creek. Project involves bridge G0269. | Adv. CN | 407 | 102 | 0 | 509 | 0 | AC-STBG |  | 0 | 6 | 6 | 6 | 24 | 44 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 391 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1625 | 7 | IRON | MO 32 E | SE0039 | 0.059 | N |  | Bridge replacement over Richardson Creek. Project involves bridge G0270. | Adv. CN | 171 | 43 | 0 | 214 | 0 | AC-STBG |  | 0 | 2 | 2 | 2 | 12 | 19 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 162 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1626 | 7 | IRON | MO 32 E | SE0040 | 0.326 | N |  | Bridge replacement over Keesling Creek. Project involves bridge G0272. | Adv. CN | 248 | 62 | 0 | 310 | 0 | AC-STBG |  | 0 | 3 | 3 | 4 | 16 | 28 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 242 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1627 | 7 | IRON | MO 32 E | SE0148 | 8.22 | N |  | Pavement preservation treatment, add shoulders, curve widening and curve relocation from Rte. KK to Rte. Z. | Adv. CN | 3882 | 970 | 0 | 4852 | 0 | AC-STBG |  | 0 | 29 | 30 | 120 | 383 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4230 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1628 | 7 | IRON | MO 49 S | 9P3796 | 28.8 | N |  | Pavement preservation treatment from Rte. 21 to Rte. 34 and add rumblestripes from Rte. 143 to Rte. 34. | Adv. CN | 2426 | 606 | 0 | 3053 | 0 | AC-STBG |  | 21 | 21 | 84 | 126 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2801 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1629 | 7 | IRON | MO 49 S | 9P3849 | 0.091 | N |  | Bridge replacement over Branch Creek near Vulcan. Project involves bridge G0633. | Federal | 955 | 239 | 0 | 1226 | 0 | NHPP |  | 32 | 69 | 130 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 990 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1630 | 7 | IRON | MO 72 E | 9P3736 | 17.745 | N |  | Pavement resurfacing and add rumblestripes from Rte. 21 to Rte. 67. | Adv. CN | 4383 | 1096 | 0 | 5480 | 0 | AC-STBG |  | 1 | 5 | 330 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1631 | 7 | IRON | RT KK S | 9S3613 | 20.43 | N |  | Pavement and bridge resurfacing from Rte. 32 to Rte. 72. Project involves bridge A2342. | Adv. CN | 2375 | 594 | 0 | 3019 | 0 | AC-STBG | 9S3371 9S3468 | 50 | 10 | 190 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1632 | 7 | IRON | RT M E | SE0120 | 0.2 | N |  | Bridge box culvert extension over Mill Dam Creek. Project involves bridge X0524. | Adv. CN | 235 | 59 | 0 | 294 | 0 | AC-STBG |  | 0 | 10 | 10 | 28 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 238 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1633 | 7 | IRON | RT N S | 9S3371 | 18.96 | N |  | Pavement and bridge resurfacing from Rte. 21 north to Rte. 21 south. Project involves bridge A2205. | Adv. CN | 1705 | 426 | 0 | 2158 | 0 | AC-STBG | 9S3468 9S3613 | 27 | 10 | 142 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1634 | 7 | LACLEDE | MO 5 S | 9P3697 | 30.86 | N |  | Pavement resurfacing from Rte. J to Rte. 60. | Adv. CN | 3122 | 781 | 0 | 3911 | 0 | AC-STBG |  | 8 | 9 | 33 | 266 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3595 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1635 | 7 | LACLEDE | MO 95 S | 9S3696 | 28.66 | N |  | Pavement and bridge resurfacing from Rte. 32 to Rte. 60. Project involves bridge A2113. | Adv. CN | 2054 | 513 | 0 | 2572 | 0 | AC-STBG |  | 5 | 6 | 22 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1636 | 7 | MADISON | BU 67 S | SE0018 | 4.481 | N |  | Pavement resurfacing from Rte. 72 to Rte. E. | Federal | 578 | 145 | 0 | 723 | 0 | NHPP |  | 0 | 1 | 2 | 2 | 5 | 46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1637 | 7 | MADISON | E OR 67 S | SE0017 | 0.695 | N |  | Pavement resurfacing from Rte. 72 to end of state maintenance. | Federal | 0 | 108 | 0 | 108 | 0 | STATE |  | 0 | 1 | 1 | 1 | 1 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1638 | 7 | MADISON | US 67 S | SE0069 | 1.4 | N |  | Intersection improvements at Rte. A and Rte. C. | Federal | 1327 | 332 | 0 | 1659 | 0 | NHPP |  | 0 | 9 | 10 | 10 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1510 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1639 | 7 | MADISON | MO 72 E | SE0043 | 2.155 | N |  | Pavement resurfacing from Rte. 67 to Rte. OO. | Federal | 521 | 130 | 0 | 651 | 0 | NHPP |  | 0 | 2 | 6 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 598 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1640 | 7 | MADISON | MO 72 W | SE0085 | 0.2 | N |  | Bridge replacement over Turkey Creek. Project involves bridge G0328. | Adv. CN | 2047 | 512 | 0 | 2559 | 0 | AC-STBG |  | 0 | 40 | 100 | 285 | 0 | 0 | 0 | 0 | 0 | 42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2092 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1641 | 7 | MADISON | RT C E | SE0035 | 0.048 | N |  | Bridge replacement over Leatherwood Creek. Project involves bridge T0763. | Adv. CN | 772 | 193 | 0 | 965 | 0 | AC-STBG |  | 0 | 11 | 11 | 12 | 44 | 89 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1642 | 7 | MADISON | RT C E | SE0160 | 0.07 | N |  | Slope repairs 0.1 mile west of Saint Francis River. | Federal | 346 | 86 | 0 | 432 | 0 | STBG |  | 0 | 121 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 306 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1643 | 7 | MADISON | RT M S | SE0036 | 0.088 | N |  | Bridge replacement over Shetley Creek. Project involves bridge T0092. | Adv. CN | 995 | 249 | 0 | 1244 | 0 | AC-STBG |  | 0 | 15 | 15 | 15 | 56 | 115 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1017 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1644 | 7 | MADISON | RT M S | SE0037 | 0.046 | N |  | Bridge replacement over Big Creek. Project involves bridge T0093. | Adv. CN | 748 | 187 | 0 | 935 | 0 | AC-STBG |  | 0 | 11 | 11 | 14 | 40 | 86 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 762 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1645 | 7 | MISSISSIPPI | MO 102 E | 9S3680 | 0.2 | N |  | Bridge replacement over Black Bayou. Project involves bridge T0545. | Adv. CN | 824 | 206 | 0 | 1050 | 0 | AC-STBG |  | 20 | 20 | 22 | 73 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 910 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1646 | 7 | MISSISSIPPI | MO 105 S | 9S3714 | 10.645 | N |  | Pavement resurfacing from Rte. 62 in Charleston to Rte. 80 in East Prairie. | Adv. CN | 2429 | 607 | 0 | 3041 | 0 | AC-STBG |  | 5 | 10 | 202 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1647 | 7 | MISSISSIPPI | IS 57 N | 9I3730 | 1.728 | N |  | Pavement resurfacing in the northbound lane from east of Rte. B to west of Rte. 105 and from Rte. 105 to Rte. 60 and on I-55 in the southbound lane from 0.6 mile north of Rte. O to the Arkansas State line. | Adv. CN | 7046 | 1761 | 0 | 8812 | 0 | AC-STBG |  | 5 | 5 | 5 | 5 | 177 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8615 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1648 | 7 | MISSISSIPPI | IS 57 S | 9I3583 | 0.5 | N |  | Payment to IDOT for bridge painting on Mississippi River "Cairo bridge." Project involves bridge A2000. | Federal | 13503 | 1500 | 0 | 15006 | 0 | NHPP |  | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1649 | 7 | MISSISSIPPI | IS 57 S | 9I3666 | 0.3 | N |  | Payment to IDOT for deck sealing on Mississippi River "Cairo bridge." Project involves bridge A2000. | Federal | 69 | 8 | 0 | 78 | 0 | NHPP |  | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1650 | 7 | MISSISSIPPI | IS 57 S | 9I3765 | 0.3 | N |  | Payment to IDOT for replacing approach pavement on Mississippi River "Cairo bridge." Project involves bridge A2000. | Federal | 452 | 50 | 0 | 503 | 0 | NHPP |  | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1651 | 7 | MISSISSIPPI | US 60 E | 9S3665 | 0.149 | N |  | Payment to IDOT for expansion joint repairs on Mississippi River "Old Cairo bridge." Project involves bridge K0950. | Federal | 1001 | 250 | 0 | 1252 | 0 | NHPP |  | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1652 | 7 | MISSISSIPPI | US 60 E | 9S3707 | 4.841 | N |  | Add rumblestripes from Rte. EE to Mississippi River Bridge. | Adv. CN | 530 | 133 | 0 | 673 | 0 | AC-STBG |  | 10 | 10 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 593 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1653 | 7 | MISSISSIPPI | US 62 E | 9S3325 | 0.6 | N |  | Bridge rehabilitation and pavement replacement at I-57. Project involves bridge A2024. | Adv. CN | 1631 | 408 | 0 | 2071 | 0 | AC-STBG | 9S3740 | 32 | 134 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1905 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1654 | 7 | MISSISSIPPI | US 62 E | 9S3740 | 0.9 | N |  | Add center turn lane from 0.5 mile west of I-57 to 0.4 mile east of I-57 in Charleston. | Adv. CN | 3012 | 753 | 0 | 3785 | 0 | AC-STBG | 9S3325 | 20 | 261 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 3501 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1655 | 7 | MISSISSIPPI | MO 75 S | 9S3769 | 0.2 | N |  | Bridge replacement over Drainage Ditch 14. Project involves bridge F0757. | Federal | 426 | 107 | 0 | 534 | 0 | NHPP |  | 1 | 27 | 65 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 434 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1656 | 7 | MISSISSIPPI | MO 77 S | 9S3405 | 25.574 | N |  | Pavement resurfacing from Rte. 60/62 to end of state maintenance. | Adv. CN | 1837 | 459 | 0 | 2332 | 0 | AC-STBG |  | 36 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1657 | 7 | MISSISSIPPI | MO 77 S | SE0062 | 0.8 | N |  | Bridge replacements over Lateral Ditch 3, Main Ditch, Lateral Ditch 4 and Lateral Ditch 7. Project involves bridges T0418, T0419, T0542 and T0543. | Adv. CN | 3786 | 946 | 0 | 4732 | 0 | AC-STBG |  | 0 | 50 | 100 | 100 | 100 | 397 | 0 | 0 | 0 | 0 | 0 | 87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3898 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1658 | 7 | MISSISSIPPI | MO 80 E | SE0077 | 0.4 | N |  | Bridge replacements over Drainage Ditch 23 and Drainage Ditch 29. Project involves bridges F0786 and F0788. | Adv. CN | 1229 | 307 | 0 | 1536 | 0 | AC-STBG |  | 0 | 1 | 5 | 10 | 50 | 177 | 0 | 0 | 0 | 0 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1271 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1659 | 7 | MISSISSIPPI | RT D W | SE0076 | 0.2 | N |  | Bridge replacement over Governor's Diversion Ditch. Project involves bridge Z0757. | Adv. CN | 756 | 189 | 0 | 945 | 0 | AC-STBG |  | 0 | 6 | 50 | 100 | 0 | 0 | 0 | 0 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 767 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1660 | 7 | MISSISSIPPI | RT DD E | 9S3679 | 0.1 | N |  | Bridge replacement over Drainage Ditch 31. Project involves bridge X0396. | Federal | 0 | 761 | 0 | 776 | 0 | STATE |  | 15 | 15 | 18 | 57 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 666 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1661 | 7 | MISSISSIPPI | RT DD W | SE0078 | 0.2 | N |  | Bridge replacement over Drainage Ditch 23. Project involves bridge X0395. | Federal | 0 | 873 | 0 | 873 | 0 | STATE |  | 0 | 8 | 40 | 96 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 708 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1662 | 7 | MISSISSIPPI | RT UU S | 9S3715 | 5.42 | N |  | Pavement resurfacing from Rte. 62 in Charleston to Rte. D. | Adv. CN | 480 | 120 | 0 | 601 | 0 | AC-STBG |  | 1 | 2 | 42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 556 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1663 | 7 | NEW MADRID | MO 162 E | 9S3718 | 6.59 | N |  | Pavement preservation treatment from I-55 near Portageville to Rte. M. | Adv. CN | 156 | 39 | 0 | 196 | 0 | AC-STBG |  | 1 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 183 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1664 | 7 | NEW MADRID | IS 55 S | 9I3844 | 20.14 | N |  | Pavement resurfacing on southbound lanes from Rte. 61 north to north of Rte. A and on northbound lanes from Rte. A to Rte. 61 North. | Federal | 13824 | 1536 | 0 | 15460 | 0 | NHPP |  | 100 | 100 | 987 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14273 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1665 | 7 | NEW MADRID | BU 60 E | 9S3722 | 1.302 | N |  | Pavement resurfacing and add rumblestripes from Rte. 60 to Rte. 114 near Sikeston. | Adv. CN | 1063 | 266 | 0 | 1339 | 0 | AC-STBG | 9S3741 9S3743 | 10 | 60 | 123 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1666 | 7 | NEW MADRID | US 60 E | 9P3584 | 1 | N |  | Add overpass 1 mile east of Rte. 61. $1,375,000 Governor's Cost Share Program funds and $1,475,000 Sikeston funds. | Adv. CN | 1725 | 0 | 1475 | 3830 | 0 | AC-NHPP |  | 630 | 350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2850 | 0 | 0 | 0 | 0 | 0 | 0 | 2850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1667 | 7 | NEW MADRID | US 61 S | 9S3516 | 21.36 | N |  | Pavement resurfacing from 0.1 mile north of Rte. 60 in Sikeston to 0.3 mile south of I-55 at exit 44. | Adv. CN | 4089 | 1022 | 0 | 5112 | 0 | AC-STBG |  | 1 | 1 | 10 | 356 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4744 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1668 | 7 | NEW MADRID | US 61 S | 9S3767 | 0.763 | N |  | Payment to Sikeston to add lanes from Larcel Lane to County Road 824 and install signals at the entrance to the South Industrial Park. $2,024,000 Cost Share funds. | Adv. CN | 1743 | 436 | 0 | 2179 | 0 | AC-STBG |  | 0 | 155 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1669 | 7 | NEW MADRID | US 61 S | 9S3798 | 2.221 | N |  | Upgrade pedestrian facilities to comply with the ADA Transition Plan at various locations in Lilbourn, Cooter, Hayti, Portageville, Parma, Matthews and Vanduser. $1,216,000 Statewide Transportation Alternative funds. | Adv. CN | 1390 | 347 | 0 | 1739 | 0 | AC-STBG |  | 2 | 20 | 146 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 1566 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1670 | 7 | NEW MADRID | US 62 E | SE0089 | 0.2 | N |  | Bridge replacement over Drain Ditch 44. Project involves bridge F0204. | Adv. CN | 562 | 140 | 0 | 792 | 0 | AC-STBG |  | 90 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 670 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1671 | 7 | NEW MADRID | RT D E | 9S3641 | 0.233 | N |  | Bridge replacement over Drainage Ditch 1. Project involves bridge L0224. | Federal | 1307 | 327 | 0 | 1656 | 0 | NHPP |  | 22 | 56 | 191 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1381 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1672 | 7 | NEW MADRID | RT D E | 9S3724 | 0.214 | N |  | Bridge replacement over Drainage Ditch 1. Project involves bridge L0226. | Federal | 556 | 139 | 0 | 700 | 0 | NHPP |  | 5 | 24 | 84 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 582 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1673 | 7 | NEW MADRID | RT E N | SE0127 | 0.2 | N |  | Bridge replacement over Little River Ditch 251. Project involves bridge T0254. | Adv. CN | 706 | 177 | 0 | 883 | 0 | AC-STBG |  | 0 | 9 | 40 | 96 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 717 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1674 | 7 | NEW MADRID | RT E S | 9S3723 | 0.214 | N |  | Bridge replacement over Otter Slough Ditch. Project involves bridge S0443. | Federal | 610 | 153 | 0 | 768 | 0 | NHPP |  | 5 | 22 | 95 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 641 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1675 | 7 | NEW MADRID | RT J N | SE0059 | 3.97 | N |  | Pavement resurfacing from Rte. 62 to Rte. 153. | Adv. CN | 326 | 81 | 0 | 407 | 0 | AC-STBG |  | 0 | 2 | 3 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 373 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1676 | 7 | NEW MADRID | RT T E | 9S3800 | 8.6 | N |  | Pavement preservation treatment from Rte. 61 to end of state maintenance. | Adv. CN | 205 | 51 | 0 | 257 | 0 | AC-STBG | 9S3794 9S3795 | 1 | 1 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 241 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1677 | 7 | NEW MADRID | RT U W | SE0080 | 4.46 | N |  | Pavement preservation treatment from Rte. D to Rte. 61. | Adv. CN | 128 | 32 | 0 | 160 | 0 | AC-STBG |  | 0 | 1 | 2 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 145 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1678 | 7 | NEW MADRID | RT W E | SE0124 | 8.229 | N |  | Pavement resurfacing from Rte. Z to Rte. 61. | Adv. CN | 662 | 165 | 0 | 827 | 0 | AC-STBG |  | 0 | 1 | 2 | 2 | 5 | 56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 761 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1679 | 7 | NEW MADRID | RT ZZ W | SE0107 | 0.2 | N |  | Bridge replacement over Drainage Ditch 52. Project involves bridge T0783. | Federal | 0 | 842 | 0 | 842 | 0 | STATE |  | 0 | 5 | 5 | 20 | 20 | 91 | 0 | 0 | 0 | 0 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 679 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1680 | 7 | OREGON | MO 142 E | 9P3686 | 0.961 | N |  | Bridge replacement over Eleven Point River and raise roadway from bridge east 0.6 mile. Project involves bridge T0395. | Adv. CN | 5234 | 1308 | 0 | 6872 | 0 | AC-STBG |  | 330 | 570 | 0 | 0 | 0 | 0 | 0 | 0 | 83 | 0 | 0 | 0 | 0 | 0 | 0 | 5889 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1681 | 7 | OREGON | US 160 E | 9S3802 | 0.2 | N |  | Bridge replacement over Cox Creek. Project involves bridge H0173. | Federal | 978 | 244 | 0 | 1237 | 0 | NHPP |  | 15 | 15 | 16 | 57 | 117 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1006 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1682 | 7 | OREGON | US 160 E | SE0021 | 28.747 | N |  | Pavement resurfacing from Rte. FF to Rte. 21 and add rumblestripes from Rte. C to Rte. 21. | Adv. CN | 3836 | 959 | 0 | 4795 | 0 | AC-STBG |  | 0 | 17 | 17 | 17 | 60 | 326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4358 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1683 | 7 | OREGON | US 160 E | SE0041 | 0.041 | N |  | Bridge replacement over Barren Fork Creek. Project involves bridge H0458. | Adv. CN | 1238 | 309 | 0 | 1547 | 0 | AC-STBG |  | 0 | 18 | 18 | 19 | 69 | 143 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1265 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1684 | 7 | OREGON | MO 19 S | SE0033 | 0.102 | N |  | Bridge replacement over Eleven Point River. Project involves bridge K0344. | Adv. CN | 2886 | 722 | 0 | 3608 | 0 | AC-STBG |  | 0 | 44 | 44 | 45 | 157 | 335 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2976 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1685 | 7 | OREGON | RT A E | SE0159 | 14.699 | N |  | Pavement resurfacing from Rte. 19 to Rte. E, Rte. OO from Rte. 63 to end of state maintenance in Oregon County, Rte. VV in Douglas County from Rte. 14 to end of state maintenance and Rte. KK in Douglas County from Rte. 76 to end of state maintenance. | Federal | 0 | 1892 | 0 | 1935 | 0 | STATE |  | 43 | 123 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1769 | 0 | 0 | 0 | 0 | 0 | 0 | 1769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1686 | 7 | OREGON | RT AA E | 9S3809 | 9.179 | N |  | Pavement resurfacing from Rte. 19 to end of state maintenance. | Adv. CN | 650 | 162 | 0 | 813 | 0 | AC-STBG |  | 1 | 1 | 1 | 7 | 54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 749 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1687 | 7 | OREGON | RT E S | 9S3191 | 12.419 | N |  | Pavement and bridge resurfacing from Rte. 142 to Rte. 19. Project involves bridge R0541. | Adv. CN | 1013 | 253 | 0 | 1287 | 0 | AC-STBG | 9S3731 | 21 | 94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1688 | 7 | OREGON | RT M S | SE0108 | 9.636 | N |  | Add rumblestripes from Rte. 160 to Rte. 63. $1,836,000 Open Container funds. | Adv. CN | 1815 | 454 | 0 | 2269 | 0 | AC-STBG |  | 0 | 10 | 18 | 153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2088 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1689 | 7 | OZARK | US 160 E | 9P3728 | 0.5 | N |  | Bridge washing over Bull Shoals Lake. Project involves bridge K0817. | Federal | 40 | 10 | 0 | 51 | 0 | NHPP |  | 1 | 1 | 1 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1690 | 7 | OZARK | MO 181 S | 9S3379 | 18.153 | N |  | Pavement resurfacing from Rte. H to Rte. 160. | Adv. CN | 1310 | 327 | 0 | 1659 | 0 | AC-STBG | 9P3599 | 22 | 119 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1691 | 7 | OZARK | MO 5 S | 9P3599 | 8.703 | N |  | Pavement resurfacing and add rumblestripes from Rte. 160 to Arkansas State line and pavement resurfacing on Rte. T from 0.1 miles east of county road 527 to 0.1 miles west of county road 512. | Adv. CN | 1810 | 453 | 0 | 2343 | 0 | AC-STBG | 9S3379 | 80 | 219 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1692 | 7 | OZARK | RT PP S | SE0015 | 5.308 | N |  | Pavement resurfacing from Rte. H to Rte. 160. | Adv. CN | 418 | 105 | 0 | 523 | 0 | AC-STBG |  | 0 | 1 | 1 | 1 | 4 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 483 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1693 | 7 | PEMISCOT | IS 155 S | 9I3729 | 0.956 | N |  | Bridge washing over the Mississippi River and Rte. 74 over the Mississippi River in Cape Girardeau County. Project involves bridges A1700 and A5076. | Federal | 108 | 12 | 0 | 121 | 0 | NHPP |  | 1 | 1 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 107 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1694 | 7 | PEMISCOT | MO 164 E | 9S3795 | 5.31 | N |  | Pavement preservation treatment from I-55 to Rte. D. | Adv. CN | 134 | 33 | 0 | 168 | 0 | AC-STBG | 9S3794 9S3800 | 1 | 1 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 156 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1695 | 7 | PEMISCOT | US 412 E | 9P3586 | 16.234 | N |  | Pavement resurfacing from Rte. 25 to I-155. | Adv. CN | 1254 | 314 | 0 | 1626 | 0 | AC-STBG |  | 58 | 186 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1382 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1696 | 7 | PEMISCOT | MO 84 E | 9S3528 | 2.884 | N |  | Pavement resurfacing from Rte. 412 to I-55. | Adv. CN | 929 | 232 | 0 | 1166 | 0 | AC-STBG | 9S3326 9S3403 SE0084 | 5 | 85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1076 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1697 | 7 | PEMISCOT | MO 84 E | SE0167 | 0.2 | N |  | Payment to Pemiscot County for bridge replacement over Drainage Ditch No. 6. Project involves bridge J0291. $822,834 Governor's Cost Share Program funds. | Federal | 0 | 825 | 0 | 825 | 0 | STATE |  | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 823 | 0 | 0 | 0 | 0 | 0 | 0 | 823 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1698 | 7 | PEMISCOT | RT A E | 9S3530 | 0.2 | N |  | Bridge replacement over Drainage Ditch 72. Project involves bridge T0536. | Federal | 306 | 76 | 0 | 411 | 0 | NHPP | 9S3517 | 24 | 45 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 337 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1699 | 7 | PEMISCOT | RT A E | 9S3734 | 3.647 | N |  | Upgrade pedestrian facilities to comply with the ADA Transition Plan at various locations in Arbyrd, Cabool, Marble Hill, Morehouse, Puxico and Wardell. $1,421,000 Statewide Transportation Alternatives funds. | Adv. CN | 1566 | 392 | 0 | 1959 | 0 | AC-STBG |  | 1 | 176 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 1776 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1700 | 7 | PEMISCOT | RT A E | 9S3778 | 10.95 | N |  | Pavement resurfacing from Rte. 412 to Rte. EE. | Adv. CN | 734 | 183 | 0 | 922 | 0 | AC-STBG |  | 5 | 5 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1701 | 7 | PEMISCOT | RT A E | 9S3794 | 10.34 | N |  | Pavement preservation treatment from Rte. EE to I-55. | Adv. CN | 246 | 62 | 0 | 309 | 0 | AC-STBG | 9S3795 9S3800 | 1 | 1 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 290 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1702 | 7 | PEMISCOT | RT B S | SE0104 | 0.2 | N |  | Bridge replacement over Drainage Ditch 66. Project involves bridge L0349. | Adv. CN | 898 | 225 | 0 | 1123 | 0 | AC-NHPP |  | 0 | 7 | 20 | 159 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 913 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1703 | 7 | PEMISCOT | RT C S | 9S3770 | 0.2 | N |  | Bridge replacement over Drainage Ditch 4. Project involves bridge S0712. | Federal | 472 | 118 | 0 | 595 | 0 | NHPP |  | 5 | 5 | 20 | 21 | 42 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1704 | 7 | PEMISCOT | RT C S | SE0084 | 10.976 | N |  | Pavement resurfacing from Rte. 412 to Rte.164. | Adv. CN | 1812 | 453 | 0 | 2345 | 0 | AC-STBG | 9S3326 9S3403 9S3528 | 80 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2255 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1705 | 7 | PEMISCOT | RT D S | SE0075 | 6.07 | N |  | Pavement resurfacing and add rumblestripes from Rte. U to Rte. 164. | Adv. CN | 2083 | 521 | 0 | 2604 | 0 | AC-STBG |  | 0 | 3 | 10 | 10 | 20 | 166 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2395 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1706 | 7 | PEMISCOT | RT DD S | SE0074 | 6.469 | N |  | Pavement resurfacing from Rte. 164 to Arkansas State line. | Adv. CN | 562 | 140 | 0 | 702 | 0 | AC-STBG |  | 0 | 1 | 1 | 1 | 4 | 49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 646 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1707 | 7 | PEMISCOT | RT E E | 9S3675 | 7.736 | N |  | Pavement improvements from Rte. 61 to Rte. DD. | Adv. CN | 638 | 160 | 0 | 800 | 0 | AC-STBG |  | 2 | 3 | 51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 744 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1708 | 7 | PEMISCOT | RT HH E | 9S3593 | 0.2 | N |  | Bridge replacement over Drainage Ditch 85. Project involves bridge X0939. | Federal | 0 | 659 | 0 | 694 | 0 | STATE |  | 35 | 68 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 589 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1709 | 7 | PEMISCOT | RT J E | SE0105 | 4.965 | N |  | Pavement resurfacing from Rte. 84 to Rte. K. | Adv. CN | 404 | 101 | 0 | 505 | 0 | AC-STBG |  | 0 | 2 | 2 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 468 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1710 | 7 | PEMISCOT | RT K E | 9S3595 | 0.2 | N |  | Bridge replacement over Main Ditch 8. Project involves bridge T0142. | Federal | 0 | 1131 | 0 | 1185 | 0 | STATE |  | 54 | 108 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 1021 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1711 | 7 | PEMISCOT | RT O E | 9S3669 | 0.2 | N |  | Bridge replacement over Pemiscot Bayou. Project involves bridge P0132. | Federal | 526 | 131 | 0 | 667 | 0 | NHPP |  | 10 | 39 | 57 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 556 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1712 | 7 | PERRY | MO 51 S | 9P3459 | 15.887 | N |  | Pavement resurfacing 0.4 mile south of I-55 in Perryville to Rte. 72. | Adv. CN | 1487 | 372 | 0 | 1866 | 0 | AC-STBG | 9P3392 9P3644 9P3650 9S3431 9S3478 | 7 | 156 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1703 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1713 | 7 | PERRY | MO 51 S | 9P3857 | 0.306 | N |  | Bridge replacement over the Mississippi River "Chester Bridge." Design-Build. Project involves bridge L0135. $117,262,000 IDOT funds. | Federal | 120333 | 0 | 114864 | 240227 | 0 | NHPP | 9P3857B 9P3857C | 5005 | 5495 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 229702 | 0 | 0 | 0 | 0 | 0 | 2398 | 127864 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1714 | 7 | PERRY | MO 51 S | 9P3857B | 0.498 | N |  | Bridge replacement over Horse Island Chute and construct new two-lane roadway on the Missouri approach to the Mississippi River "Chester Bridge." Design-Build. Project involves bridge L1004. | Federal | 17871 | 4468 | 0 | 23604 | 0 | NHPP | 9P3857 9P3857C | 715 | 483 | 0 | 0 | 0 | 0 | 0 | 550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21856 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1715 | 7 | PERRY | MO 51 S | SE0146 | 107.286 | Y |  | Install signage at various locations in Southeast District. | Federal | 1062 | 118 | 0 | 1180 | 0 | SAFETY |  | 0 | 160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1020 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1716 | 7 | PERRY | RT A E | 9S3792 | 12.88 | N |  | Pavement preservation treatment from Rte. 61 to end of state maintenance. | Adv. CN | 299 | 75 | 0 | 375 | 0 | AC-STBG | 9S3791 9S3793 9S3799 | 1 | 1 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 352 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1717 | 7 | PERRY | RT B S | 9S3821 | 11.29 | N |  | Pavement resurfacing from National Guard Drive to Rte. KK. | Adv. CN | 914 | 229 | 0 | 1145 | 0 | AC-STBG |  | 2 | 2 | 2 | 10 | 57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1072 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1718 | 7 | PERRY | RT C S | 9S3431 | 23.693 | N |  | Pavement resurfacing from Rte. 51 to Rte. A in Frohna. | Adv. CN | 1660 | 415 | 0 | 2095 | 0 | AC-STBG | 9P3392 9P3459 9P3644 9P3650 9S3478 | 20 | 138 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1937 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1719 | 7 | PERRY | RT C S | 9S3793 | 12.1 | N |  | Pavement preservation treatment from Rte. A to Rte. 61. | Adv. CN | 286 | 71 | 0 | 358 | 0 | AC-STBG | 9S3791 9S3792 9S3799 | 1 | 1 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 336 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1720 | 7 | PERRY | RT C S | SE0056 | 0.017 | N |  | Bridge replacement over Apple Creek. Project involves bridge P0803. | Adv. CN | 1698 | 425 | 0 | 2123 | 0 | AC-STBG |  | 0 | 50 | 92 | 213 | 0 | 0 | 0 | 0 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1746 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1721 | 7 | PERRY | RT K S | 9S3671 | 0.2 | N |  | Bridge rehabilitation over Apple Creek. Project involves bridge N0877. | Federal | 501 | 125 | 0 | 631 | 0 | NHPP | 9S3670 | 5 | 15 | 22 | 49 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 534 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1722 | 7 | PERRY | RT K S | 9S3791 | 5.7 | N |  | Pavement preservation treatment from Rte. B to Rte. O. | Adv. CN | 142 | 35 | 0 | 178 | 0 | AC-STBG | 9S3792 9S3793 9S3799 | 1 | 1 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 166 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1723 | 7 | PERRY | RT NN E | 9S3771 | 0.2 | N |  | Bridge replacement over Saline Creek. Project involves bridge N0062. | Federal | 0 | 1733 | 0 | 1738 | 0 | STATE |  | 5 | 32 | 50 | 51 | 138 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1460 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1724 | 7 | PERRY | RT P E | 9S3799 | 6.67 | N |  | Pavement preservation treatment from Rte. 61 to Rte. C. | Adv. CN | 163 | 41 | 0 | 205 | 0 | AC-STBG | 9S3791 9S3792 9S3793 | 1 | 1 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 191 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1725 | 7 | PERRY | Rte. 150 | 9P3857C | 0 | N |  | Pavement improvements on the approach to the Mississippi River "Chester Bridge." in Randolph County Illinois. Design-Build. Project involves bridge L0135. $1,923,000 IDOT funds. | Adv. CN | 0 | 0 | 1703 | 1923 | 0 | AC-STBG | 9P3857 9P3857B | 195 | 132 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1571 | 0 | 0 | 0 | 0 | 0 | 220 | 1703 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1726 | 7 | PERRY | RT T E | 9S3670 | 0.2 | N |  | Bridge replacement over Saline Creek. Project involves bridge S0734. | Adv. CN | 1730 | 433 | 0 | 2188 | 0 | AC-STBG | 9S3671 | 25 | 50 | 79 | 146 | 0 | 0 | 0 | 0 | 0 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1859 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1727 | 7 | REYNOLDS | MO 34 E | SE0003 | 9.214 | N |  | Pavement resurfacing from Rte. 21 to near Wayne County line. | Federal | 967 | 242 | 0 | 1209 | 0 | NHPP |  | 0 | 6 | 10 | 82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1728 | 7 | REYNOLDS | RT AA E | 9S3786 | 6.9 | N |  | Pavement preservation treatment from end of state maintenance to Rte. 49. | Adv. CN | 168 | 42 | 0 | 211 | 0 | AC-STBG | 9P3784 9P3785 9S3783 9S3787 9S3788 9S3789 9S3790 9S3797 | 1 | 1 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1729 | 7 | REYNOLDS | RT B S | 9S3688 | 0.2 | N |  | Bridge replacement over Logan Creek. Project involves bridge S0851. | Federal | 1345 | 336 | 0 | 1726 | 0 | NHPP |  | 45 | 93 | 183 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1401 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1730 | 7 | REYNOLDS | RT K E | 9S3455 | 21.745 | N |  | Curve improvements from Rte. 21 to Rte. 49. | Federal | 1060 | 118 | 0 | 1222 | 0 | SAFETY |  | 44 | 113 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 1053 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1731 | 7 | REYNOLDS | RT TT S | 9S3468 | 3.675 | N |  | Pavement resurfacing from Rte. KK to Rte. 72. | Adv. CN | 351 | 88 | 0 | 444 | 0 | AC-STBG | 9S3371 9S3613 | 5 | 3 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 407 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1732 | 7 | RIPLEY | MO 142 E | 9P3749 | 0.2 | N |  | Bridge replacement over Mill Creek. Project involves bridge X0394. | Adv. CN | 660 | 165 | 0 | 892 | 0 | AC-STBG |  | 67 | 109 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1733 | 7 | RIPLEY | MO 142 E | 9S3685 | 0.2 | N |  | Bridge replacement over Drainage Ditch 2. Project involves bridge T0758. | Federal | 443 | 111 | 0 | 561 | 0 | NHPP |  | 7 | 8 | 32 | 57 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 449 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1734 | 7 | RIPLEY | MO 142 E | SE0031 | 0.038 | N |  | Bridge replacement over Harris Creek. Project involves bridge S0814. | Adv. CN | 632 | 158 | 0 | 790 | 0 | AC-STBG |  | 0 | 22 | 46 | 83 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1735 | 7 | RIPLEY | MO 142 E | SE0032 | 0.043 | N |  | Bridge replacement over Logan Creek. Project involves bridge S0889. | Adv. CN | 1066 | 267 | 0 | 1333 | 0 | AC-STBG |  | 0 | 15 | 16 | 16 | 60 | 123 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1088 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1736 | 7 | RIPLEY | US 160 E | 9S3806 | 9.126 | N |  | Pavement and bridge resurfacing from south intersection of Rte. 21 to Rte. JJ. Project involves bridge A3087. | Adv. CN | 2137 | 534 | 0 | 2676 | 0 | AC-STBG |  | 5 | 6 | 6 | 19 | 174 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2466 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1737 | 7 | RIPLEY | RT W S | 9S3817 | 0.2 | N |  | Bridge replacement over Drainage Ditch 1. Project involves bridge P0676. | Federal | 907 | 227 | 0 | 1148 | 0 | NHPP |  | 14 | 15 | 61 | 118 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 933 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1738 | 7 | RIPLEY | RT W S | 9S3848 | 0.2 | N |  | Bridge replacement over Drainage Ditch 3. Project involves bridge P0677. | Federal | 906 | 227 | 0 | 1147 | 0 | NHPP |  | 14 | 15 | 60 | 118 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 933 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1739 | 7 | SCOTT | IS 55 N | SE0166 | 14.756 | N |  | Pavement resurfacing from I-57 to Rte. 77. | Federal | 2007 | 223 | 0 | 2230 | 0 | NHPP |  | 0 | 190 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1740 | 7 | SCOTT | US 61 S | 9S3777 | 11.03 | N |  | Pavement resurfacing from Rte. 77 to Rte. Y. | Adv. CN | 1946 | 486 | 0 | 2433 | 0 | AC-STBG |  | 1 | 10 | 10 | 10 | 143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2259 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1741 | 7 | SCOTT | MO 91 S | 9S3525 | 10.174 | N |  | Pavement resurfacing from Rte. P to Rte. 61 and Rte. 61 to Kelly Street in Morley. | Adv. CN | 3014 | 753 | 0 | 3780 | 0 | AC-STBG | 9S3826 | 13 | 20 | 98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3649 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1742 | 7 | SCOTT | RT A E | 9S3827 | 9.02 | N |  | Pavement resurfacing from Rte. 77 to Rte. 61. | Adv. CN | 812 | 203 | 0 | 1017 | 0 | AC-STBG |  | 2 | 2 | 2 | 8 | 59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 944 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1743 | 7 | SCOTT | RT BB S | 9S3741 | 3.869 | N |  | Pavement resurfacing and add rumblestripes from Rte. ZZ to Rte. 114 near Sikeston. | Adv. CN | 1278 | 319 | 0 | 1624 | 0 | AC-STBG | 9S3722 9S3743 | 27 | 40 | 129 | 0 | 0 | 0 | 0 | 0 | 99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1329 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1744 | 7 | SCOTT | RT C E | 9S3727 | 0.228 | N |  | Bridge rehabilitation over St. Johns Drainage Ditch. Project involves bridge N0761. | Federal | 451 | 113 | 0 | 565 | 0 | NHPP |  | 1 | 5 | 18 | 56 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 478 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1745 | 7 | SCOTT | RT E E | SE0082 | 8.008 | N |  | Pavement preservation treatment from Rte. 77 to Commerce. | Adv. CN | 202 | 50 | 0 | 252 | 0 | AC-STBG |  | 0 | 1 | 1 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 232 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1746 | 7 | SCOTT | RT H S | SE0081 | 5.77 | N |  | Pavement preservation treatment from Rte. 77 to Rte. U. | Adv. CN | 151 | 38 | 0 | 189 | 0 | AC-STBG |  | 0 | 1 | 1 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 173 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1747 | 7 | SCOTT | RT H S | SE0123 | 8.09 | N |  | Pavement resurfacing from Rte. U to Rte. 62. | Adv. CN | 1089 | 272 | 0 | 1361 | 0 | AC-STBG |  | 0 | 5 | 10 | 101 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1245 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1748 | 7 | SCOTT | RT HH E | 9S3744 | 0.341 | N |  | Add intersection turn lanes at Ingram Road and County Road 473 near Sikeston. | Adv. CN | 350 | 87 | 0 | 444 | 0 | AC-STBG |  | 7 | 14 | 35 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 381 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1749 | 7 | SCOTT | RT M E | 9S3813 | 7.46 | N |  | Pavement resurfacing from Rte. A to I-55. | Adv. CN | 997 | 249 | 0 | 1247 | 0 | AC-STBG |  | 1 | 1 | 5 | 10 | 73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1157 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1750 | 7 | SCOTT | RT N N | SE0143 | 0.1 | N |  | Intersection improvements at Rte. K. | Adv. CN | 370 | 92 | 0 | 462 | 0 | AC-STBG |  | 0 | 5 | 5 | 34 | 0 | 0 | 0 | 0 | 0 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 278 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1751 | 7 | SCOTT | RT N S | 9S3811 | 10.09 | N |  | Pavement resurfacing from Rte. E to Rte. D. | Adv. CN | 678 | 170 | 0 | 849 | 0 | AC-STBG |  | 1 | 2 | 2 | 5 | 52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1752 | 7 | SCOTT | RT Y E | SE0150 | 0.5 | N |  | Intersection improvements at Rte. BB. | Federal | 1169 | 130 | 0 | 1299 | 0 | SAFETY |  | 0 | 10 | 50 | 145 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1082 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1753 | 7 | SCOTT | RT Z S | 9S3640 | 0.214 | N |  | Bridge replacement over Drainage Ditch 1. Project involves bridge S0971. | Federal | 622 | 155 | 0 | 784 | 0 | NHPP |  | 7 | 19 | 102 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1754 | 7 | SCOTT | RT Z S | 9S3825 | 13.58 | N |  | Pavement resurfacing from Rte. 61 to Rte. 114. | Adv. CN | 890 | 222 | 0 | 1114 | 0 | AC-STBG | 9S3549 | 2 | 87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1755 | 7 | SCOTT | RT ZZ E | 9S3743 | 4.345 | N |  | Pavement resurfacing and add rumblestripes from beginning of state maintenance to Rte. 61 near Sikeston. Rumblestripes only from Rte. BB to 0.5 mile west of Rte. 61. | Adv. CN | 964 | 241 | 0 | 1228 | 0 | AC-STBG | 9S3722 9S3741 | 23 | 13 | 66 | 0 | 0 | 0 | 0 | 0 | 138 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 988 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1756 | 7 | SHANNON | MO 19 S | 9P3687 | 0.2 | N |  | Bridge replacement over Hurricane Creek. Project involves bridge K0358. | Federal | 1478 | 369 | 0 | 1896 | 0 | NHPP |  | 49 | 103 | 202 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1537 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1757 | 7 | SHANNON | MO 19 S | 9P3785 | 25.8 | N |  | Pavement preservation treatment from Rte. 60 to Rte. 160. | Adv. CN | 582 | 146 | 0 | 730 | 0 | AC-STBG | 9P3784 9S3783 9S3786 9S3787 9S3788 9S3789 9S3790 9S3797 | 2 | 2 | 39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 687 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1758 | 7 | SHANNON | MO 19 S | 9P3814 | 0.259 | N |  | Bridge replacement over Spring Valley. Project involves bridge J0420. | Federal | 6409 | 1602 | 0 | 8015 | 0 | NHPP |  | 4 | 10 | 12 | 353 | 772 | 0 | 0 | 0 | 0 | 0 | 467 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6397 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1759 | 7 | ST. FRANCOIS | MO 221 S | 9S3610 | 16.187 | N |  | Pavement resurfacing and roadway improvements from Rte. 67 to Rte. 21 in Farmington. | Adv. CN | 4039 | 1010 | 0 | 5440 | 0 | AC-STBG |  | 173 | 100 | 362 | 0 | 0 | 0 | 0 | 218 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4587 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1760 | 7 | ST. FRANCOIS | MO 221 S | 9S3853 | 0.082 | N |  | Box culvert replacement over Brewers Creek. Project involves bridge Y0935. | Federal | 468 | 117 | 0 | 588 | 0 | NHPP |  | 3 | 4 | 4 | 12 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 520 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1761 | 7 | ST. FRANCOIS | MO 32 E | 9P3644 | 3.646 | N |  | Pavement resurfacing from Maple Valley Drive to 1.3 miles east of Rte. OO in Farmington. | Federal | 1480 | 370 | 0 | 1861 | 0 | NHPP | 9P3392 9P3459 9P3650 9S3431 9S3478 | 11 | 144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1706 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1762 | 7 | ST. FRANCOIS | MO 32 E | 9P3650 | 19.814 | N |  | Pavement and bridge resurfacing from 1.3 miles east of Rte. OO near Farmington to 0.3 mile east of I-55 and add left turn lane at I-55 intersection. Project involves bridges K0251 and J0911. | Federal | 4923 | 1231 | 0 | 6372 | 0 | NHPP | 9P3392 9P3459 9P3644 9S3431 9S3478 | 218 | 598 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5556 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1763 | 7 | ST. FRANCOIS | MO 32 E | 9P3852 | 6.954 | N |  | Pavement and bridge resurfacing from High Street in Bismark to the south intersection of Bus. 32. Project involves bridges A2668 and A2670. | Adv. CN | 1822 | 455 | 0 | 2282 | 0 | AC-STBG |  | 5 | 5 | 5 | 16 | 148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2103 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1764 | 7 | ST. FRANCOIS | BU 67 S | 9S3851 | 0.911 | N |  | Pavement resurfacing from Rte 8. to Main Street through Park Hills. | Adv. CN | 438 | 110 | 0 | 549 | 0 | AC-STBG |  | 1 | 1 | 1 | 7 | 29 | 0 | 0 | 0 | 0 | 0 | 95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 415 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1765 | 7 | ST. FRANCOIS | US 67 N | 9P3547 | 0.072 | N |  | Bridge rehabilitation over Union Pacific Railroad. Project involves bridge L0666. | Federal | 454 | 113 | 0 | 608 | 0 | NHPP |  | 22 | 54 | 0 | 0 | 0 | 0 | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 513 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1766 | 7 | ST. FRANCOIS | US 67 N | SE0099 | 0.158 | N |  | Installation of Closed Circuit TV along Rtes. 32, 67 and 72. | Federal | 906 | 226 | 0 | 1132 | 0 | NHPP |  | 0 | 5 | 76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1051 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1767 | 7 | ST. FRANCOIS | US 67 S | SE0002 | 21.48 | N |  | Pavement resurfacing from Jefferson County line to Rte. 221. | Federal | 9369 | 2342 | 0 | 11711 | 0 | NHPP |  | 0 | 49 | 100 | 796 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10766 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1768 | 7 | ST. FRANCOIS | US 67 S | SE0068 | 0.4 | N |  | Interchange improvements and bridge replacement at Rte. 32 in Leadington. Project involves bridge A0144. | Federal | 12831 | 3208 | 0 | 16039 | 0 | NHPP |  | 0 | 251 | 250 | 250 | 500 | 1317 | 0 | 0 | 0 | 0 | 0 | 66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13405 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1769 | 7 | ST. FRANCOIS | MO 8 E | 9P3448 | 0.15 | N |  | Add intersection turn lanes and upgrade signals at State Street in Desloge. | Federal | 1292 | 323 | 0 | 1877 | 0 | NHPP |  | 262 | 60 | 143 | 0 | 0 | 0 | 0 | 0 | 173 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1239 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1770 | 7 | ST. FRANCOIS | MO 8 E | SE0010 | 6.85 | N |  | Pavement resurfacing from Washington County line to RR Bridge (Bus. 67) and add shoulders from east of Rte. P to RR Bridge (Bus. 67). | Federal | 1420 | 355 | 0 | 1775 | 0 | NHPP |  | 0 | 5 | 5 | 5 | 17 | 116 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1627 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1771 | 7 | ST. FRANCOIS | RT B S | SE0152 | 7.253 | N |  | Add rumblestripes from Rte. 32 to Rte. 221. | Adv. CN | 1235 | 309 | 0 | 1544 | 0 | AC-STBG |  | 0 | 7 | 13 | 105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1419 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1772 | 7 | ST. FRANCOIS | RT BB S | 9S3789 | 6.38 | N |  | Pavement preservation treatment from Rte. M to Rte. 32. | Adv. CN | 159 | 40 | 0 | 200 | 0 | AC-STBG | 9P3784 9P3785 9S3783 9S3786 9S3787 9S3788 9S3790 9S3797 | 1 | 1 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 186 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1773 | 7 | ST. FRANCOIS | CRD BERRY RD S | SE0168 | 0.1 | N |  | Payment to St. Francois County to construct new bridge over Big River. $1,825,000 Governor's Cost Share Program funds. | Federal | 0 | 1827 | 0 | 1827 | 0 | STATE |  | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1825 | 0 | 0 | 0 | 0 | 0 | 0 | 1825 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1774 | 7 | ST. FRANCOIS | RT C E | 9S3788 | 12.8 | N |  | Pavement preservation treatment from Rte. D to Rte. 32. | Adv. CN | 297 | 74 | 0 | 372 | 0 | AC-STBG | 9P3784 9P3785 9S3783 9S3786 9S3787 9S3789 9S3790 9S3797 | 1 | 1 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1775 | 7 | ST. FRANCOIS | RT D S | 9S3478 | 12.696 | N |  | Pavement resurfacing from Rte. Y to Rte. EE in Farmington. | Adv. CN | 1135 | 284 | 0 | 1441 | 0 | AC-STBG | 9P3392 9P3459 9P3644 9P3650 9S3431 | 22 | 106 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1313 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1776 | 7 | ST. FRANCOIS | RT D S | SE0050 | 0.52 | N |  | Rebuild pavement and add turn lanes from Rte. EE to Rte. 32. | Adv. CN | 2275 | 569 | 0 | 2844 | 0 | AC-STBG |  | 0 | 32 | 149 | 201 | 0 | 0 | 0 | 0 | 0 | 321 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2141 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1777 | 7 | ST. FRANCOIS | RT F E | 9S3797 | 11.88 | N |  | Pavement preservation treatment from Rte. OO to Rte. WW. | Adv. CN | 276 | 69 | 0 | 346 | 0 | AC-STBG | 9P3784 9P3785 9S3783 9S3786 9S3787 9S3788 9S3789 9S3790 | 1 | 1 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1778 | 7 | ST. FRANCOIS | RT K E | SE0019 | 6.953 | N |  | Pavement and bridge resurfacing from Rte. 47 to Rte. D. Project involves bridge A0968. | Adv. CN | 1064 | 266 | 0 | 1330 | 0 | AC-STBG |  | 0 | 3 | 3 | 3 | 9 | 84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1228 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1779 | 7 | ST. FRANCOIS | RT K E | SE0154 | 0.135 | N |  | Intersection improvements at North Wood Drive. | Adv. CN | 1630 | 407 | 0 | 2037 | 0 | AC-STBG |  | 0 | 8 | 8 | 8 | 56 | 98 | 0 | 0 | 0 | 0 | 0 | 715 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1780 | 7 | ST. FRANCOIS | RT NN E | 9S3787 | 4.3 | N |  | Pavement preservation treatment from Rte. N to Rte. 221. | Adv. CN | 110 | 28 | 0 | 139 | 0 | AC-STBG | 9P3784 9P3785 9S3783 9S3786 9S3788 9S3789 9S3790 9S3797 | 1 | 1 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1781 | 7 | ST. FRANCOIS | RT OO S | 9S3490 | 16.76 | N |  | Pavement and bridge resurfacing and add rumblestripes from 0.1 mile south of Rte. 32 in Farmington to Rte. 72 in Fredericktown. Project involves bridges H0488, J0081, J0080, H0500, J0079 and H0501. | Adv. CN | 5504 | 1376 | 0 | 6918 | 0 | AC-STBG |  | 38 | 36 | 145 | 543 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6156 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1782 | 7 | STE. GENEVIEVE | MO 32 E | 9P3392 | 5.226 | N |  | Pavement resurfacing from I-55 to Gerard Street in Ste. Genevieve. | Adv. CN | 948 | 237 | 0 | 1224 | 0 | AC-STBG | 9P3459 9P3644 9P3650 9S3431 9S3478 | 39 | 90 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1095 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1783 | 7 | STE. GENEVIEVE | MO 32 E | 9S3854 | 0.8 | N |  | Drainage improvements 0.25 mile east of Rte. 61 and at Siebert Rd. | Adv. CN | 2741 | 685 | 0 | 3476 | 0 | AC-STBG |  | 50 | 50 | 50 | 25 | 239 | 0 | 0 | 0 | 0 | 0 | 53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3009 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1784 | 7 | STE. GENEVIEVE | MO 32 E | SE0121 | 1.606 | Y |  | Installation of Closed Circuit TV including Rtes. 60, 61, 51, 67, 72 and I-55. | Federal | 860 | 215 | 0 | 1080 | 0 | NHPP |  | 5 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1785 | 7 | STE. GENEVIEVE | IS 55 S | 9I3619 | 198.095 | Y |  | Job Order Contracting for concrete pavement repair from the Jefferson County line to the Arkansas State line and all of I-57 and all of I-155. | Adv. CN | 243 | 27 | 0 | 278 | 0 | AC-NHPP |  | 8 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1786 | 7 | STE. GENEVIEVE | IS 55 S | 9I3828 | 198.095 | Y |  | Job Order Contracting for concrete pavement repair from the Jefferson County line to the Arkansas State line and all of I-57 and I-155. | Federal | 499 | 55 | 0 | 555 | 0 | NHPP |  | 1 | 54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1787 | 7 | STE. GENEVIEVE | IS 55 S | 9I3830 | 198.095 | Y |  | Job Order Contracting for concrete pavement repair from the Jefferson County line to the Arkansas State line and all of I-57 and I-155. | Federal | 257 | 28 | 0 | 286 | 0 | NHPP |  | 1 | 1 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1788 | 7 | STE. GENEVIEVE | IS 55 S | 9I3831 | 198.095 | Y |  | Job Order Contracting for asphalt pavement repair from the Jefferson County line to the Arkansas State line and all of I-57 and I-155. | Federal | 257 | 28 | 0 | 286 | 0 | NHPP |  | 1 | 1 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1789 | 7 | STE. GENEVIEVE | IS 55 S | SE0112 | 198.091 | Y |  | Job Order Contracting for asphalt pavement repair from the Jefferson County line to the Arkansas State line and all of I-57 and all of I-155. | Federal | 262 | 29 | 0 | 291 | 0 | NHPP |  | 0 | 0 | 1 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 265 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1790 | 7 | STE. GENEVIEVE | IS 55 S | SE0134 | 198.085 | Y |  | Job Order Contracting for concrete pavement repair from the Jefferson County line to the Arkansas State line and all of I-57 and all of I-155. | Federal | 264 | 29 | 0 | 293 | 0 | NHPP |  | 0 | 0 | 1 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 265 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1791 | 7 | STE. GENEVIEVE | IS 55 S | SE0142 | 198.085 | Y |  | Replace signage along I-55, I-57 and I-155. | Federal | 2016 | 224 | 0 | 2240 | 0 | NHPP |  | 0 | 240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1792 | 7 | STE. GENEVIEVE | IS 55 S | SE0162 | 198 | Y |  | Striping upgrades from Jefferson County line to Arkansas State line and includes all of I-57 and I-155. | Federal | 1877 | 209 | 0 | 2086 | 0 | SAFETY |  | 0 | 167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1919 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1793 | 7 | STE. GENEVIEVE | US 61 S | 9P3739 | 0.2 | N |  | Add turn lane at intersection at Industrial River Road. | Adv. CN | 355 | 89 | 0 | 465 | 0 | AC-STBG |  | 21 | 10 | 30 | 0 | 0 | 0 | 0 | 0 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 377 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1794 | 7 | STE. GENEVIEVE | US 61 S | 9P3855 | 0.8 | N |  | Intersection improvements at Rte. Y. | Adv. CN | 605 | 151 | 0 | 806 | 0 | AC-STBG |  | 50 | 5 | 5 | 38 | 0 | 0 | 0 | 0 | 0 | 266 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 442 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1795 | 7 | STE. GENEVIEVE | RT B S | 9S3698 | 13.73 | N |  | Pavement and bridge resurfacing from Rte. 32 to Rte. WW. Project involves bridges R0535 and R0536. | Adv. CN | 1314 | 328 | 0 | 1650 | 0 | AC-STBG |  | 8 | 14 | 115 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1513 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1796 | 7 | STE. GENEVIEVE | RT M S | 9S3449B | 0.69 | N |  | Upgrade pedestrian facilities to comply with the ADA Transition Plan in the City of Ste. Genevieve. | Adv. CN | 142 | 35 | 0 | 191 | 0 | AC-STBG |  | 9 | 13 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 164 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1797 | 7 | STE. GENEVIEVE | RT M S | 9S3790 | 7.13 | N |  | Pavement preservation treatment from Rte. 61 to Rte. J. | Adv. CN | 174 | 43 | 0 | 218 | 0 | AC-STBG | 9P3784 9P3785 9S3783 9S3786 9S3787 9S3788 9S3789 9S3797 | 1 | 1 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1798 | 7 | STE. GENEVIEVE | RT N S | SE0026 | 0.064 | N |  | Bridge replacement over Saline Creek. Project involves bridge P0631. | Adv. CN | 951 | 238 | 0 | 1189 | 0 | AC-STBG |  | 0 | 30 | 63 | 122 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 953 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1799 | 7 | STE. GENEVIEVE | RT O S | 9S3699 | 6.2 | N |  | Pavement resurfacing from Rte. 61 to Rte. 32. | Adv. CN | 527 | 132 | 0 | 661 | 0 | AC-STBG |  | 2 | 2 | 4 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 608 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1800 | 7 | STE. GENEVIEVE | RT Z E | SE0094 | 0.12 | N |  | Bridge painting over I-55 at Rte. Z, Rte. M, county road Eisenbeis Bottom and Rte. 32. Project involves bridges A2460, A2420, A2417 and A2406. | Adv. CN | 1223 | 306 | 0 | 1529 | 0 | AC-STBG |  | 0 | 2 | 5 | 10 | 50 | 178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1284 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1801 | 7 | STE. GENEVIEVE | RT Z E | SE0100 | 4.32 | N |  | Add rumblestripes from Rte. N to Rte. 61. | Adv. CN | 768 | 192 | 0 | 960 | 0 | AC-STBG |  | 0 | 5 | 78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 877 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1802 | 7 | STODDARD | MO 114 E | 9S3725 | 0.457 | N |  | Bridge improvements over Drainage Ditch 5 and Little River Drainage Ditch. Project involves bridges J0740 and F0565. | Adv. CN | 1947 | 487 | 0 | 2435 | 0 | AC-STBG | 9S3726 9S3775 | 1 | 10 | 69 | 272 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2069 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1803 | 7 | STODDARD | MO 114 E | 9S3726 | 0.229 | N |  | Bridge replacement over Dexter Creek. Project involves bridge K0031. | Adv. CN | 1726 | 432 | 0 | 2159 | 0 | AC-STBG | 9S3725 9S3775 | 1 | 10 | 44 | 231 | 0 | 0 | 0 | 0 | 0 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1842 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1804 | 7 | STODDARD | MO 114 E | 9S3775 | 0.2 | N |  | Bridge replacement over Union Pacific Railroad. Project involves bridge K0032. | Adv. CN | 1822 | 456 | 0 | 2288 | 0 | AC-STBG | 9S3725 9S3726 | 10 | 50 | 55 | 144 | 0 | 0 | 0 | 0 | 0 | 107 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1922 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1805 | 7 | STODDARD | MO 114 E | SE0087 | 14.904 | N |  | Pavement resurfacing from Rte. 25 to Rte. 60. | Adv. CN | 3053 | 763 | 0 | 3826 | 0 | AC-STBG |  | 10 | 101 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3715 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1806 | 7 | STODDARD | MO 25 S | 9P3674 | 5.301 | N |  | Pavement improvements from Rte. Z to Bus. 25. | Adv. CN | 1110 | 278 | 0 | 1391 | 0 | AC-STBG |  | 3 | 5 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1328 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1807 | 7 | STODDARD | US 60 E | 9P3702 | 6.284 | N |  | Pavement resurfacing on the eastbound lanes from 2 miles east of Rte. 51 to Rte. F and shoulder resurfacing at various locations from Rte. DD to west of Rte. F. | Federal | 2083 | 521 | 0 | 2619 | 0 | NHPP | 9P3700 9P3704 9S3587 9S3588 | 15 | 178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2426 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1808 | 7 | STODDARD | US 60 E | SE0063 | 6.937 | N |  | Pavement resurfacing from Rte. F to Rte. 25. | Federal | 1378 | 345 | 0 | 1723 | 0 | NHPP |  | 0 | 1 | 1 | 10 | 10 | 117 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1584 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1809 | 7 | STODDARD | US 60 W | 9P3703 | 6.833 | N |  | Shoulder resurfacing from County Road 531 to Rte. 60/61 interchange. | Federal | 960 | 240 | 0 | 1205 | 0 | NHPP |  | 5 | 5 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1810 | 7 | STODDARD | MO 91 S | 9S3824 | 6.59 | N |  | Pavement resurfacing from Rte. 25 to Rte. P. | Adv. CN | 580 | 145 | 0 | 727 | 0 | AC-STBG |  | 2 | 2 | 2 | 5 | 42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 674 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1811 | 7 | STODDARD | RT AB E | 9S3526 | 11.596 | N |  | Pavement resurfacing from Rte. 25 to Rte. Y. | Adv. CN | 796 | 199 | 0 | 1008 | 0 | AC-STBG |  | 13 | 71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 924 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1812 | 7 | STODDARD | RT AB E | SE0093 | 0.2 | N |  | Bridge replacement over Drainage Ditch 24. Project involves bridge N0380. | Adv. CN | 1544 | 386 | 0 | 1930 | 0 | AC-STBG |  | 0 | 1 | 10 | 50 | 50 | 198 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1612 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1813 | 7 | STODDARD | RT BB N | SE0122 | 10.771 | N |  | Pavement resurfacing from Rte. C to Rte. M. | Adv. CN | 706 | 176 | 0 | 882 | 0 | AC-STBG |  | 0 | 2 | 10 | 62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 808 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1814 | 7 | STODDARD | RT J E | SE0097 | 19.093 | N |  | Pavement resurfacing from Rte. T to Rte. 25. | Adv. CN | 1430 | 358 | 0 | 1788 | 0 | AC-STBG |  | 0 | 1 | 2 | 10 | 10 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1815 | 7 | STODDARD | RT M E | 9S3485 | 9.354 | N |  | Pavement resurfacing from Rte. K to Rte. 25 in Aquilla. | Adv. CN | 757 | 189 | 0 | 949 | 0 | AC-STBG |  | 3 | 3 | 64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 879 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1816 | 7 | STODDARD | RT O E | SE0116 | 0.2 | N |  | Bridge replacement over Drainage Ditch 287. Project involves bridge X0730. | Adv. CN | 554 | 138 | 0 | 692 | 0 | AC-STBG |  | 0 | 7 | 30 | 76 | 0 | 0 | 0 | 0 | 0 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 556 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1817 | 7 | STODDARD | RT P S | 9S3642 | 0.216 | N |  | Bridge replacement over Drainage Ditch 35. Project involves bridge R0185. | Federal | 434 | 109 | 0 | 550 | 0 | NHPP |  | 7 | 14 | 54 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 471 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1818 | 7 | STODDARD | RT PP E | SE0125 | 10.034 | N |  | Pavement resurfacing from Rte. 51 to Rte. M. | Adv. CN | 674 | 169 | 0 | 843 | 0 | AC-STBG |  | 0 | 1 | 10 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 772 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1819 | 7 | STODDARD | RT Y E | SE0052 | 10.981 | N |  | Pavement preservation treatment from 0.8 mile north of Rte. P to Kingshighway in Sikeston. | Adv. CN | 276 | 69 | 0 | 345 | 0 | AC-STBG |  | 0 | 1 | 1 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 317 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1820 | 7 | STODDARD | RT ZZ N | SE0119 | 0.2 | N |  | Bridge replacement over Main Drainage Ditch. Project involves bridge N0899. | Adv. CN | 782 | 196 | 0 | 978 | 0 | AC-STBG |  | 0 | 1 | 1 | 3 | 50 | 99 | 0 | 0 | 0 | 0 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 802 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1821 | 7 | TEXAS | MO 137 S | 9S3693 | 23.966 | N |  | Pavement resurfacing from Rte. 17 to Bus. 60 | Adv. CN | 1698 | 424 | 0 | 2131 | 0 | AC-STBG |  | 9 | 19 | 149 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1954 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1822 | 7 | TEXAS | MO 137 S | SE0027 | 0.076 | N |  | Bridge replacement over Pine Creek. Project involves bridge S0528. | Adv. CN | 982 | 246 | 0 | 1228 | 0 | AC-STBG |  | 0 | 32 | 65 | 126 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 991 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1823 | 7 | TEXAS | MO 137 S | SE0028 | 0.052 | N |  | Bridge replacement over Big Creek. Project involves bridge S0607. | Adv. CN | 711 | 178 | 0 | 889 | 0 | AC-STBG |  | 0 | 22 | 48 | 91 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1824 | 7 | TEXAS | MO 137 S | SE0029 | 0.078 | N |  | Bridge replacement over South Prong Jacks Fork. Project involves bridge S0529. | Adv. CN | 1370 | 343 | 0 | 1713 | 0 | AC-STBG |  | 0 | 44 | 90 | 177 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1388 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1825 | 7 | TEXAS | MO 17 S | 9P3604 | 7.67 | N |  | Pavement resurfacing from Rte. 38 to Rte. 63. | Federal | 968 | 242 | 0 | 1225 | 0 | NHPP |  | 15 | 4 | 83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1123 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1826 | 7 | TEXAS | MO 17 S | 9P3607 | 14.882 | N |  | Pavement resurfacing from Rte. 32 to Rte. 38. | Federal | 3834 | 958 | 0 | 4855 | 0 | NHPP |  | 63 | 99 | 386 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4307 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1827 | 7 | TEXAS | MO 17 S | 9P3690 | 0.2 | N |  | Bridge rehabilitation over Roubidoux Creek. Project involves bridge L0713. | Federal | 1442 | 360 | 0 | 1822 | 0 | NHPP |  | 20 | 27 | 96 | 189 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1485 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1828 | 7 | TEXAS | US 60 E | SE0096 | 1.4 | N |  | Upgrading dynamic message signs at various locations including I-55 and I-57. | Federal | 858 | 214 | 0 | 1082 | 0 | STBG |  | 10 | 72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1829 | 7 | TEXAS | US 63 S | 9P3819 | 6.07 | N |  | Pavement resurfacing from Rte. CC to Rte. 32. | Federal | 2939 | 735 | 0 | 3718 | 0 | NHPP |  | 44 | 139 | 283 | 0 | 0 | 0 | 0 | 0 | 333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2919 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1830 | 7 | TEXAS | US 63 S | 9P3820 | 2.669 | N |  | Pavement resurfacing from Rte. E to Rte. B. | Federal | 1118 | 280 | 0 | 1405 | 0 | NHPP |  | 7 | 7 | 8 | 55 | 91 | 0 | 0 | 0 | 0 | 0 | 205 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1032 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1831 | 7 | TEXAS | RT B E | 9S3803 | 23.209 | N |  | Pavement resurfacing from Rte. 63 to end of state maintenance. | Adv. CN | 1671 | 418 | 0 | 2093 | 0 | AC-STBG |  | 4 | 4 | 5 | 15 | 136 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1929 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1832 | 7 | TEXAS | RT K S | SE0042 | 4.95 | N |  | Pavement resurfacing from Rte. KK to Rte. 17. | Adv. CN | 388 | 97 | 0 | 485 | 0 | AC-STBG |  | 0 | 1 | 1 | 1 | 3 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 448 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1833 | 7 | TEXAS | RT VV E | SE0007 | 9.826 | N |  | Pavement resurfacing from Rte. 137 to end of state maintenance in Dent County. | Adv. CN | 738 | 184 | 0 | 922 | 0 | AC-STBG |  | 0 | 4 | 8 | 63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 847 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1834 | 7 | VARIOUS | VARIOUS | SE0169 |  | Y |  | Add island lighting at various locations throughout the Southeast District. | Federal | 1835 | 204 | 0 | 2039 | 0 | SAFETY |  | 0 | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 1879 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1835 | 7 | VARIOUS | Various | 5B0800Z | 0 | N |  | Payback beginning in SFY 2008 for Safe and Sound bridges in the Southeast District. | Federal | 0 | 30830 | 0 | 94966 | 25,001 - 50,000 | STATE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 99 | 0 | 0 | 0 | 0 | 0 | 0 | 64037 | 6166 | 6166 | 6166 | 6166 | 6166 | 0
1836 | 7 | VARIOUS | Various | 9P3624 | 0 | Y |  | Job Order Contracting for guard cable and guardrail repair for St. Francois, Ste. Genevieve, Madison, Perry, Cape Girardeau, Wayne, Bollinger, Stoddard, Scott, Butler, New Madrid, Mississippi, Pemiscot and Dunklin Counties. | Adv. CN | 1962 | 490 | 0 | 2458 | 0 | AC-STBG |  | 6 | 1 | 133 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2318 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1837 | 7 | VARIOUS | Various | 9P3631 | 0 | Y |  | Job Order Contracting for asphalt pavement repair on all major highways except interstates. | Adv. CN | 230 | 57 | 0 | 287 | 0 | AC-STBG |  | 0 | 1 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1838 | 7 | VARIOUS | Various | 9P3632 | 0 | Y |  | Job Order Contracting for asphalt pavement repair on all major highways except interstates. | Adv. CN | 235 | 59 | 0 | 294 | 0 | AC-STBG |  | 0 | 0 | 1 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 265 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1839 | 7 | VARIOUS | Various | 9P3635 | 0 | Y |  | Job Order Contracting for concrete pavement repair on all major highways except interstates. | Adv. CN | 418 | 104 | 0 | 528 | 0 | AC-STBG |  | 6 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1840 | 7 | VARIOUS | Various | 9P3733 | 0 | N |  | Conversion to low profile islands in various locations throughout the Southeast District. | Federal | 475 | 53 | 0 | 538 | 0 | SAFETY |  | 10 | 103 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 425 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1841 | 7 | VARIOUS | Various | 9P3753 | 0 | Y |  | Job Order Contracting for erosion control repairs at various locations within the Southeast District. | Adv. CN | 838 | 210 | 0 | 1049 | 0 | AC-STBG |  | 1 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1842 | 7 | VARIOUS | Various | 9P3754 | 0 | N |  | Job Order Contracting for guard cable and guardrail repair for Wright, Douglas, Ozark, Texas, Howell, Shannon, Reynolds, Iron, Carter, Oregon and Ripley Counties. | Adv. CN | 259 | 65 | 0 | 325 | 0 | AC-STBG |  | 1 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1843 | 7 | VARIOUS | Various | 9P3755 | 0 | Y |  | Job Order Contracting for guard cable and guardrail repair for St. Francois, Ste. Genevieve, Madison, Perry, Cape Girardeau, Wayne, Bollinger, Stoddard, Scott, Butler, New Madrid, Mississippi, Pemiscot and Dunklin Counties. | Adv. CN | 1902 | 476 | 0 | 2379 | 0 | AC-STBG |  | 1 | 128 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1844 | 7 | VARIOUS | Various | 9P3756 | 0 | Y |  | Job Order Contracting for asphalt pavement repair on all major highways except interstates. | Adv. CN | 217 | 54 | 0 | 272 | 0 | AC-STBG |  | 1 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1845 | 7 | VARIOUS | Various | 9P3757 | 0 | Y |  | Job Order Contracting for concrete pavement repair on all major highways except interstates. | Adv. CN | 443 | 111 | 0 | 555 | 0 | AC-STBG |  | 1 | 1 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 515 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1846 | 7 | VARIOUS | Various | 9P3759 | 0 | Y |  | On-call work zone enforcement at various locations in the Southeast District. | Federal | 38 | 4 | 0 | 42 | 0 | SAFETY |  | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1847 | 7 | VARIOUS | Various | 9P3823 | 0 | Y |  | On-call work zone enforcement at various locations in the Southeast District. | Federal | 38 | 4 | 0 | 42 | 0 | SAFETY |  | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1848 | 7 | VARIOUS | Various | 9P3832 | 0 | N |  | Job Order Contracting for guard cable and guardrail repair for Wright, Douglas, Ozark, Texas, Howell, Shannon, Reynolds, Iron, Carter, Oregon and Ripley Counties. | Adv. CN | 267 | 67 | 0 | 335 | 0 | AC-STBG |  | 1 | 2 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 309 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1849 | 7 | VARIOUS | Various | 9P3834 | 0 | Y |  | Job Order Contracting for erosion control repairs at various locations within the Southeast District. | Federal | 0 | 1079 | 0 | 1080 | 0 | STATE |  | 1 | 1 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1850 | 7 | VARIOUS | Various | 9P3835 | 0 | N |  | Erosion control repairs at various locations along Rtes. 60 and 67. | Adv. CN | 906 | 227 | 0 | 1143 | 0 | AC-NHPP |  | 10 | 12 | 71 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1851 | 7 | VARIOUS | Various | 9P3837 | 0 | N |  | Erosion control repairs at various locations along Rtes. 60 and 67. | Federal | 0 | 544 | 0 | 545 | 0 | STATE |  | 1 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1852 | 7 | VARIOUS | Various | 9P3850 | 0 | Y |  | Wrong way striping and signing at various freeway and expressway interchange locations in Southeast District. | Federal | 1057 | 117 | 0 | 1179 | 0 | SAFETY |  | 5 | 15 | 147 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1012 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1853 | 7 | VARIOUS | Various | 9S3752 | 0 | Y |  | Job Order Contracting for ADA Transition Plan Improvements at various locations in the Southeast District. | Adv. CN | 90 | 22 | 0 | 115 | 0 | AC-STBG |  | 3 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1854 | 7 | VARIOUS | Various | 9S3833 | 0 | Y |  | Job Order Contracting for ADA Transition Plan Improvements at various locations in the Southeast District. | Adv. CN | 94 | 24 | 0 | 120 | 0 | AC-STBG |  | 2 | 3 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 103 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1855 | 7 | VARIOUS | Various | SE0110 | 0 | Y |  | Job Order Contracting for erosion control repairs at various locations within the Southeast District. | Federal | 871 | 218 | 0 | 1089 | 0 | NHPP |  | 0 | 1 | 2 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1061 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1856 | 7 | VARIOUS | Various | SE0129 | 0 | Y |  | Replace signage on major highways in the Southeast District. | Federal | 1970 | 492 | 0 | 2462 | 0 | NHPP |  | 0 | 0 | 100 | 240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1857 | 7 | VARIOUS | Various | SE0135 | 0 | Y |  | Job Order Contracting for concrete pavement repair on all major highways except interstates. | Federal | 442 | 111 | 0 | 553 | 0 | NHPP |  | 0 | 1 | 2 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 530 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1858 | 7 | VARIOUS | Various | SE0136 | 0 | Y |  | Replace signage on major highways in the Southeast District. | Federal | 1920 | 480 | 0 | 2400 | 0 | NHPP |  | 0 | 100 | 240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2060 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1859 | 7 | VARIOUS | Various | SE0137 | 0 | N |  | Job Order Contracting for guard cable and guardrail repair for Wright, Douglas, Ozark, Texas, Howell, Shannon, Reynolds, Iron, Carter, Oregon and Ripley Counties. | Adv. CN | 275 | 69 | 0 | 344 | 0 | AC-STBG |  | 0 | 1 | 1 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 318 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1860 | 7 | VARIOUS | Various | SE0138 | 0 | Y |  | Job Order Contracting for guard cable and guardrail repair for St. Francois, Ste. Genevieve, Madison, Perry, Cape Girardeau, Wayne, Bollinger, Stoddard, Scott, Butler, New Madrid, Mississippi, Pemiscot and Dunklin Counties. | Adv. CN | 2050 | 512 | 0 | 2562 | 0 | AC-STBG |  | 0 | 1 | 6 | 168 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2387 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1861 | 7 | VARIOUS | Various | SE0139 | 0 | N |  | Erosion control repairs at various locations along Rtes. 60 and 67. | Federal | 0 | 576 | 0 | 576 | 0 | STATE |  | 0 | 1 | 1 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 530 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1862 | 7 | VARIOUS | Various | SE0151 |  | Y |  | On-call work zone enforcement at various locations in the Southeast District. | Federal | 39 | 4 | 0 | 43 | 0 | SAFETY |  | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1863 | 7 | WAYNE | MO 34 E | 9P3784 | 24.235 | N |  | Pavement preservation treatment from Rte. 67 to County Road 808. | Federal | 552 | 138 | 0 | 692 | 0 | NHPP | 9P3785 9S3783 9S3786 9S3787 9S3788 9S3789 9S3790 9S3797 | 2 | 2 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 651 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1864 | 7 | WAYNE | MO 34 E | 9P3816 | 0.2 | N |  | Bridge rehabilitation over Clark Creek. Project involves bridge A1300. | Federal | 1662 | 415 | 0 | 2103 | 0 | NHPP |  | 26 | 26 | 27 | 95 | 200 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1727 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1865 | 7 | WAYNE | MO 34 E | SE0049 | 12.245 | N |  | Pavement resurfacing from Wayne County line to Rte. 49 north. | Federal | 2315 | 579 | 0 | 2894 | 0 | NHPP |  | 0 | 6 | 6 | 6 | 20 | 183 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2673 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1866 | 7 | WAYNE | MO 34 E | SE0141 | 3.836 | N |  | Upgrade pedestrian facilities to comply with the ADA Transition Plan at various locations in Bloomfield, Glenallen and Piedmont. $1,201,000 Statewide Transportation Alternative funds. | Federal | 1455 | 364 | 0 | 1819 | 0 | NHPP |  | 0 | 20 | 80 | 125 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1592 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1867 | 7 | WAYNE | US 67 N | SE0083 | 0.2 | N |  | Bridge replacement over Otter Creek. Project involves bridge L0210. | Federal | 2333 | 583 | 0 | 2916 | 0 | NHPP |  | 0 | 20 | 115 | 356 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2415 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1868 | 7 | WAYNE | US 67 S | 9P3822 | 7.42 | N |  | Pavement resurfacing from Rte. 49 to south of Rte. JJ, Rte. 172 to south of F and Rte. A to north of Rte. F. | Federal | 3889 | 972 | 0 | 4864 | 0 | NHPP |  | 3 | 10 | 20 | 30 | 288 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4513 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1869 | 7 | WAYNE | RT A E | 9S3815 | 0.2 | N |  | Bridge rehabilitation over Otter Creek. Project involves bridge A0518. | Federal | 1325 | 331 | 0 | 1676 | 0 | NHPP |  | 20 | 21 | 21 | 75 | 159 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1366 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1870 | 7 | WAYNE | RT A E | SE0147 | 0.087 | N |  | Bridge replacement over Small Creek. Project involves bridge S0497. | Federal | 0 | 1182 | 0 | 1182 | 0 | STATE |  | 0 | 30 | 64 | 123 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 962 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1871 | 7 | WAYNE | RT FF S | 9S3568 | 0.028 | N |  | Bridge replacement over Rings Creek. Project involves bridge N0205. | Federal | 949 | 237 | 0 | 1277 | 0 | NHPP |  | 91 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 1027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1872 | 7 | WRIGHT | MO 38 E | 9S3689 | 0.2 | N |  | Bridge replacement over Dove Creek. Project involves bridge A1812. | Federal | 1494 | 373 | 0 | 1890 | 0 | NHPP |  | 23 | 24 | 24 | 85 | 179 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1549 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1873 | 7 | WRIGHT | MO 38 E | SE0046 | 72.175 | N |  | Pavement preservation treatment from Rte. 95 to Rte. 17, Rte. 19 from Riverview Drive to north of Rte. 60, Rte. W from Rte. 17 to Mtn. View, Rte. CC from Rte. 181 to Rte. 63 and Rte. B from Rte. 160 to Rte. 142. | Adv. CN | 1710 | 427 | 0 | 2137 | 0 | AC-STBG |  | 0 | 9 | 18 | 145 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1874 | 7 | WRIGHT | MO 5 S | 9P3605 | 17.851 | N |  | Pavement resurfacing from Rte. 60 to Rte. A in Douglas County. | Adv. CN | 4612 | 1153 | 0 | 5772 | 0 | AC-STBG |  | 7 | 57 | 415 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5293 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1875 | 7 | WRIGHT | US 60 E | SE0023 | 20.001 | N |  | Pavement and bridge resurfacing east of Rte. C to east of Cabool. Project involves bridge A2647. | Federal | 5051 | 1263 | 0 | 6314 | 0 | NHPP |  | 0 | 12 | 12 | 13 | 45 | 401 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5831 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1876 | 7 | WRIGHT | US 60 E | SE0161 | 317.702 | N |  | Striping upgrades from Webster County line to I-55, on Rte. 67 from Jefferson County line to Rte. 160 and on Rte. 63 from east intersection of Rte. 60 to Rte. 14. | Federal | 1372 | 152 | 0 | 1524 | 0 | SAFETY |  | 0 | 143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1381 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1877 | 7 | WRIGHT | US 60 W | SE0024 | 23.619 | N |  | Pavement resurfacing from Rte. 95 to Webster County line. | Federal | 6269 | 1567 | 0 | 7836 | 0 | NHPP |  | 0 | 16 | 16 | 16 | 55 | 496 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7237 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1878 | 7 | WRIGHT | MO 95 S | SE0145 | 1.623 | N |  | Add center turn lane from Red Springs Road to Bus. 60. | Adv. CN | 11240 | 2810 | 0 | 14050 | 0 | AC-STBG |  | 0 | 149 | 399 | 741 | 0 | 0 | 0 | 0 | 0 | 5811 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1879 | 7 | WRIGHT | RT A E | 9S3805 | 6.002 | N |  | Pavement resurfacing from Bus. 60 in Mansfield to Rte. K. | Adv. CN | 463 | 116 | 0 | 580 | 0 | AC-STBG |  | 1 | 1 | 2 | 4 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 534 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1880 | 7 | WRIGHT | RT AF S | 9S3691 | 0.2 | N |  | Bridge replacement over Beaver Creek. Project involves bridge N0675. | Federal | 1828 | 457 | 0 | 2315 | 0 | NHPP |  | 30 | 30 | 121 | 240 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1889 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1881 | 7 | WRIGHT | RT F S | 9S3695 | 23.3 | N |  | Pavement and bridge resurfacing from Rte. 5 to Rte. EE. Project involves bridges A2260 and A2259. | Adv. CN | 1674 | 419 | 0 | 2099 | 0 | AC-STBG |  | 6 | 20 | 148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1925 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1882 | 7 | WRIGHT | RT M E | 9S3611 | 0.2 | N |  | Box culvert replacement at Parks Creek. Project involves bridge X0164. | Federal | 573 | 143 | 0 | 725 | 0 | NHPP |  | 9 | 33 | 77 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 603 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1883 | 7 | WRIGHT | RT PP S | SE0005 | 2.427 | N |  | Pavement resurfacing from Rte. C to end of state maintenance. | Federal | 0 | 226 | 0 | 226 | 0 | STATE |  | 0 | 1 | 1 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 208 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1884 | 7 | WRIGHT | RT U S | 9S3818 | 0.2 | N |  | Bridge replacement over BNSF Railway. Project involves bridge H0290. | Federal | 1365 | 341 | 0 | 1727 | 0 | NHPP |  | 21 | 21 | 21 | 80 | 163 | 0 | 0 | 0 | 0 | 0 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1398 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1885 | 7 | WRIGHT | RT V E | 9S3804 | 7.287 | N |  | Pavement resurfacing from Rte. F to Rte. 5. | Adv. CN | 542 | 135 | 0 | 678 | 0 | AC-STBG |  | 1 | 1 | 2 | 5 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1886 | 99 | VARIOUS | Various | ST0001 |  | N |  | Safety Circuit Rider statewide liaison for state fiscal year 2024. | Federal | 60 | 0 | 15 | 75 | 0 | SAFETY |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1887 | 99 | VARIOUS | Various | ST0002 |  | N |  | Safety Circuit Rider statewide liaison for state fiscal year 2025. | Federal | 60 | 0 | 15 | 75 | 0 | SAFETY |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1888 | 99 | VARIOUS | Various | ST0011 |  | N |  | Safety Circuit Rider statewide liaison for state fiscal year 2023. | Federal | 60 | 0 | 15 | 75 | 0 | SAFETY |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0