## 2024_08_Major_Projects
FY 25 |  | FY 24 | [11 empty] | FY 25 | [11 empty] | FY 26 Start | [11 empty] | FY 27 Start | [11 empty] | FY 28 Start | [11 empty] | FY 29 Start
2025-2029 STIP Large Project Look Ahead | $ | time axis 2023-07-01 to 2029-07-01
Improve I-70 ST0020 Package 2 East | 500 | 2024-09-01: Technical Meetings; 2024-10-01: Technical Meetings; 2024-11-01: Award/Commission Meeting
SE US 67 Butler Co. J9P3764/J9P3751/ST0062B (FY 25) | 40.9 | 2024-09-01: Award/Commission Meeting
MO 366 Corridor 6S3582 (FY25) | 30.5 | 2024-10-01: Award/Commission Meeting
SW US 60 RR Webster 7P3425C (FY 25) | 37.1 | 2024-10-01: Award/Commission Meeting
I-35 Corridor NW0133 (FY25) | 38.2 | 2024-11-01: Award/Commission Meeting
MO 21 Corridor 6S3283 (FY25) | 30.3 | 2024-11-01: Award/Commission Meeting
US-63 + MO-AC Interchange 5P3433 (FY25) | 21.7 | 2024-11-01: Award/Commission Meeting
Daniel Boone Bridge Rehab 6I3538 (FY25) | 25.1 | 2024-11-01: Award/Commission Meeting
MO-1 Corridor 8I3044C (FY25) | 20.1 | 2024-12-01: Award/Commission Meeting
I-44 Corridor SU0076;8I3044C, SU0114, 8I3225, 8S3238, ST0088B (FY 25) | 105.2 | 2024-12-01: Award/Commission Meeting
SW Bridge Bundle 7P3485 (FY 25) | 37.9 | 2024-09-01: RFQ/SOQ; 2024-10-01: Technical Meetings; 2024-11-01: Technical Meetings; 2024-12-01: Technical Meetings; 2025-01-01: Technical Meetings; 2025-02-01: Technical Meetings; 2025-03-01: Award/Commission Meeting
MO-231 Corridor 6S3632 (FY25) | 22 | 2025-04-01: Award/Commission Meeting
MO-13 Corridor 4P2333 and 3P3019 (FY25) | 31.1 | 2025-04-01: Award/Commission Meeting
RT MM Corridor 8S0836D (FY25) | 34.4 | 2025-05-01: Award/Commission Meeting
US50-RT291 Oldham Parkway 4P3196 (FY25) | 29.5 | 2025-05-01: Award/Commission Meeting
Improve I-70 ST0019 Package 3 West (FY 25) | 350 | 2024-12-01: Advertise; 2025-01-01: RFQ/SOQ; 2025-02-01: Technical Meetings; 2025-03-01: Technical Meetings; 2025-04-01: Technical Meetings; 2025-05-01: Award/Commission Meeting
Route 30 Project 6S3435 (FY25) | 29.1 | 2025-06-01: Award/Commission Meeting
FY 26 | bar: 2023-07-01; 2024-06-01 to 2024-07-01; 2024-11-01 to 2024-12-01; 2025-06-01 to 2025-07-01; 2026-06-01 to 2026-07-01; 2027-06-01 to 2027-07-01; 2028-06-01 to 2028-07-01; 2029-06-01
I-44 Corridor ST0088 and ST0089 (ST0120 and ST0116) (and SU0013, SU0297, SU0169, SU0066, SU0079, SR0015, SR0102) (SU0146 and 7I3010) (FY 26) | 539.7 | 2025-08-01: Potential Advertise; 2025-09-01: Potential RFQ/SOQ; 2025-10-01: Potential Technical Meetings; 2025-11-01: Potential Technical Meetings; 2025-12-01: Potential Technical Meetings; 2026-01-01: Potential Award/Commission Meeting
Improve I-70 ST0017 Package 4A Rocheport to Columbia (FY 26) | 490 | 2026-03-01: Potential Advertise; 2026-04-01: Potential RFQ/SOQ; 2026-05-01: Potential Technical Meetings; 2026-06-01: Potential Technical Meetings; 2026-07-01: Potential Technical Meetings; 2026-08-01: Potential Award/Commission Meeting
I-29 Corridor KU0017 (FY26) | 23.1 | 2025-07-01: Award/Commission Meeting
Joachim Creek Bridge 6S3289 and K0294(FY26) | 26.4 | 2025-07-01: Award/Commission Meeting
SL MO 370 Discovery Bridge Rehab 6P3554 (FY26) | 70.1 | 2025-10-01: Award/Commission Meeting
MO-47 Corridor NE0003 (FY26) | 26.7 | 2025-11-01: Award/Commission Meeting
US 169 Bridge over BNSF Rail KU0099 (FY26) | 22.2 | 2025-11-01: Award/Commission Meeting
KC Mo 291 Liberty Bend Bridge Replace/Rehab 4P3471 (FY 26) | 87.5 | 2026-01-01: Potential Advertise; 2026-02-01: Potential RFQ/SOQ; 2026-03-01: Potential Technical Meetings; 2026-04-01: Potential Technical Meetings; 2026-05-01: Potential Technical Meetings; 2026-06-01: Potential Award/Commission Meeting
SE US 67 Butler Co. ST0062 (FY 26) | 44.2 | 2026-03-01: Award/Commission Meeting
Improve I-70 ST0018B 4C High Hill Realignment (FY 26) | 76.2 | 2026-04-01: Award/Commission Meeting
Improve I-70 4B ST0017B Booneville to Rocheport DBB (FY 26) | 150 | 2026-05-01: Award/Commission Meeting
I-270 North Gap SL0021 (FY 26) | 37 | 2026-06-01: Award/Commission Meeting
FY 27 | bar: 2023-07-01; 2024-06-01 to 2024-07-01; 2025-06-01 to 2025-07-01; 2025-11-01 to 2025-12-01; 2026-06-01 to 2026-07-01; 2027-06-01 to 2027-07-01; 2028-06-01 to 2028-07-01; 2029-06-01
I-44 Phelps/Laclede Co. ST0121, ST0122, ST0123, ST0118, ST0119 (FY 27) | 104.8 | 2027-01-01: Potential Advertise; 2027-02-01: Potential RFQ/SOQ; 2027-03-01: Potential Technical Meetings; 2027-04-01: Potential Technical Meetings; 2027-05-01: Potential Technical Meetings; 2027-06-01: Potential Award/Commission Meeting
I-44 St. Louis Rt. 141 to 109 and 100 to 30 ST0117 and ST0115 (FY 27) | 63.7 | 2026-07-01: Potential Advertise; 2026-08-01: Potential RFQ/SOQ; 2026-09-01: Potential Technical Meetings; 2026-10-01: Potential Technical Meetings; 2026-11-01: Potential Technical Meetings; 2026-12-01: Potential Award/Commission Meeting
Improve I-70 4D ST0018 Kingdom City to Warrenton (FY 27) | 440.5 | 2026-11-01: Potential Advertise; 2026-12-01: Potential RFQ/SOQ; 2027-01-01: Potential Technical Meetings; 2027-02-01: Potential Technical Meetings; 2027-03-01: Potential Technical Meetings; 2027-04-01: Potential Award/Commission Meeting
Improve I-70 4E ST0016 Odessa to Booneville (FY 27) | 661.5 | 2027-05-01: Potential Advertise; 2027-06-01: Potential RFQ/SOQ; 2027-07-01: Potential Technical Meetings; 2027-08-01: Potential Technical Meetings; 2027-09-01: Potential Technical Meetings; 2027-10-01: Potential Award
US 63 Westphalia Corridor CD0108 (FY27) | 88.1 | 2027-03-01: Award/Commission Meeting
I-44 Six Flags to ElmAv SL0054 (FY27) | 31.8 | 2026-07-01: Award/Commission Meeting
I-270 over Bellefontaine Improvement SL0021 (FY27) | 35.7 | 2026-07-01: Award/Commission Meeting
Lincoln County US 61 Corridor NE0004 (FY27) | 27.1 | 2026-07-01: Award/Commission Meeting
I-64 over Vandaventer Br. Replacement J6I3502 (J6I3574) | 113.7 | 2027-01-01: Potential Advertise; 2027-02-01: Potential RFQ/SOQ; 2027-03-01: Potential Technical Meetings; 2027-04-01: Potential Technical Meetings; 2027-05-01: Potential Technical Meetings; 2027-06-01: Potential Award/Commission Meeting
Blue River Bridge Rehab 4S3490 (FY27) | 28.4 | bar: 2027-01-01
SL Bridge Bundle 6S3443, SL0052, SL0054 (I44 &I55) (FY 27) | 75.5 | 2026-11-01: Potential Advertise; 2026-12-01: Potential RFQ/SOQ; 2027-01-01: Potential Technical Meetings; 2027-02-01: Potential Technical Meetings; 2027-03-01: Potential Technical Meetings; 2027-04-01: Potential Technical Meetings; 2027-05-01: Potential Technical Meetings; 2027-06-01: Potential Award/Commission Meeting
US 61 64/Lincoln SL0083 (FY 27) | 49.6 | 2026-11-01: Potential Advertise; 2026-12-01: Potential RFQ/SOQ; 2027-01-01: Potential Technical Meetings; 2027-02-01: Potential Technical Meetings; 2027-03-01: Potential Technical Meetings; 2027-04-01: Potential Technical Meetings; 2027-05-01: Potential Technical Meetings; 2027-06-01: Potential Award/Commission Meeting
Improve I-70 4D ST0018 Kingdom City to Warrenton (FY 27) | 440.5 | 2026-10-01: Potential Advertise; 2026-11-01: Potential RFQ/SOQ; 2026-12-01: Potential Technical Meetings; 2027-01-01: Potential Technical Meetings; 2027-02-01: Potential Technical Meetings; 2027-03-01: Potential Award/Commission Meeting
FY 28
US 61 Rt B&E Intersection NE0144 (FY28) | 25 | 2027-10-01: Award/Commission Meeting
I-35 Clinton Co. Resurfacing I-29, I-35, 169 ST0094 (FY 28) | 32.1 | 2028-02-01: Award/Commission Meeting
KC IS 29 Bridge 4I3458 (FY 28) | 228.9 | 2027-12-01: Potential Advertise; 2028-01-01: Potential RFQ/SOQ; 2028-02-01: Potential Technical Meetings; 2028-03-01: Potential Technical Meetings; 2028-04-01: Potential Technical Meetings; 2028-05-01: Potential Technical Meetings; 2028-06-01: Potential Award/Commission Meeting
MO 47 Franklin SL0082 (FY 28) | 85.6 | 2027-07-01: Potential Advertise; 2027-08-01: Potential RFQ/SOQ; 2027-09-01: Potential Technical Meetings; 2027-10-01: Potential Technical Meetings; 2027-11-01: Potential Technical Meetings; 2027-12-01: Potential Technical Meetings; 2028-01-01: Potential Award/Commission Meeting
Railroad Overpass 32nd St. in Joplin 7S3059 (FY28) | 27.9 | 2028-03-01: Award/Commission Meeting
KC IS 49 AddLane 155th to 58 KU0028 and ST0091 (FY28) | 57.4 | 2027-07-01: Potential Advertise; 2027-08-01: Potential RFQ/SOQ; 2027-09-01: Potential Technical Meetings; 2027-10-01: Potential Technical Meetings; 2027-11-01: Potential Technical Meetings; 2027-12-01: Potential Technical Meetings; 2028-01-01: Potential Award/Commission Meeting
US-60 Seymour Corridor SR0112 (FY 28) | 36.6 | 2028-03-01: Award/Commission Meeting
FY 29 | bar: 2023-07-01; 2024-06-01 to 2024-07-01; 2025-06-01 to 2025-07-01; 2026-06-01 to 2026-07-01; 2027-06-01; 2027-08-01 to 2027-09-01; 2028-06-01 to 2028-07-01; 2029-06-01
US 65 Benton Co. Passing Lanes ST0093 (and SR0089 FY29) | 53.4 | 2028-10-01: Award/Commission Meeting
MO 180 and I-70 Interchange 6S3311 (FY29) | 20.2 | 2028-07-01: Award/Commission Meeting
I-70 over Rte. 40 KU0114 (FY 29) | 32.9 | 2028-12-01: Potential Advertise; 2029-01-01: Potential RFQ/SOQ; 2029-02-01: Potential Technical Meetings; 2029-03-01: Potential Technical Meetings; 2029-04-01: Potential Technical Meetings; 2029-05-01: Potential Technical Meetings; 2029-06-01: Potential Award/Commission Meeting
I-70 MO River to 67 SL0058 (FY 29) | 65 | 2028-07-01: Potential Advertise; 2028-08-01: Potential RFQ/SOQ; 2028-09-01: Potential Technical Meetings; 2028-10-01: Potential Technical Meetings; 2028-11-01: Potential Technical Meetings; 2028-12-01: Potential Technical Meetings; 2029-01-01: Potential Award/Commission Meeting
US 60 Seymour Corridor SR0112 (FY29) | 34.8 | 2028-10-01: Award/Commission Meeting
Heart of America Bridge Rehab KU0270 (FY29) | 41.4 | 2028-12-01: Award/Commission Meeting
Capital Improvements MO 60&65 8P0683G (FY29) | 28.7 | 2029-03-01: Award/Commission Meeting
NW I-229 Project NW0134 | TBD | 2028-12-01: Potential Advertise; 2029-01-01: Potential RFQ/SOQ; 2029-02-01: Potential Technical Meetings; 2029-03-01: Potential Technical Meetings; 2029-04-01: Potential Technical Meetings; 2029-05-01: Potential Technical Meetings; 2029-06-01: Potential Award/Commission Meeting
MO370 : Pave Elm to 270 6P3649 (FY29) | 20.7 | 2029-03-01: Award/Commission Meeting
Color Keys | bar: 2023-07-01; 2024-06-01; 2025-06-01 to 2025-07-01; 2026-06-01 to 2026-07-01; 2027-06-01; 2027-08-01 to 2027-09-01; 2028-06-01 to 2028-07-01; 2029-06-01
Advertise
RFQ/SOQ
One on One meetings
Award/Commission Meeting
Project Type Key
Contracts Underway
Corridor | bar: 2023-09-01 to 2024-05-01
Interchange | bar: 2023-09-01 to 2024-05-01
Bridge | bar: 2023-09-01 to 2024-05-01
Bridge Bundle | bar: 2023-09-01 to 2024-05-01
Improve I-70 | bar: 2023-09-01 to 2024-05-01
Forward I-44