## Sheet1
A7024
2023-07-13 |  | Bridge Length | 1387.5 | ft
Updated 10-14-24 |  | Bridge Width | 40.7 | ft
|  | Unit Cost $/ sq. ft | 51.9751
Item | Name | Quantity | (units) | Unit Cost | Estimated Cost
206-55.00 | Temporary Shoring | 1 | lump sum | 100000 | 100000 | in addition to jacking frames
216-45.00 | Removal of Existing Expansion Joint and Adjacent Concrete | 76 | lin. Ft. | 1000 | 76000 | Added 10/13/2024 following inspection*
216-99.02 | Removal Existing Bearings | 24 | each | 5000 | 120000
703-42.14 | Class B-2 Concrete | 20 | Cu. Yd | 5000 | 100000 | Added 10/13/2024 following inspection*
703-42-15 | Barrier Curb | 40 | lin. Ft. | 500 | 20000 | Added 10/13/2024 following inspection*
706.10.60 | Reinforcing Steel | 2400 | lbs | 6 | 14400 | Added 10/13/2024 following inspection*
711-02.00 | Protective Coating - Concrete Bents and Piers (Epoxy) | 5000 | sq. ft. | 8 | 40000
704-01.01 | Substructure Repair (Formed) | 150 | sq. ft. | 250 | 37500
| Beam Cap modification for Bearings | 4 | each | 125000 | 500000 | Build Geometry for new Bearings and anchor bolt edge distance
712-09.00 | Expansion Device (Finger Plate) | 76 | lin. Ft. | 4200 | 319200 | Added 10/13/2024 following inspection*
712-10.00 | Fabricated Structural Steel | 20000 | lbs | 22 | 440000 | Jacking frames at 2, 3(SPAN 2,3), 6 (SPAN 5,6) AND 7 (18 @ abt 1100# PER FRAME -exterior girder only jacked from 1 side) includes stiffener modification
716-99.02 | High Load Multi-Rotational Bearings (Guided Expansion) | 16 | each | 52000 | 832000 | replace all expansion bearings - 8 need replaced as of July 2023
716-99.02 | High Load Multi-Rotational Bearings (Fixed) | 8 | each | 42000 | 336000 | replace fixed bearings with problems documented July 2023
|  |  |  | Bridge TOTAL | 2935100
| Traffic Control | 1 | lump sum | 80000 | 80000
| Mobilzation | 1 | lump sum | 12% | 361812
|  |  |  | TOTAL | 3376912
bearing prices increased for anchor bolt installation
Notes 7-13-23
Bent | Condition
1 integral end bt | No problems documented
2 fixed | Diagonal Crack in restraint block, Bearing have section loss, large bearing tilt all bearings - Need Replaced July 2023
3 exp (joint) | Section loss in bearings - open v cracks in cap | (Bearing curled up slightly 10-10-2024)
4 fixed | No problems documented
5 fixed | No problems documented
6 exp (joint) | cap open v cracks, broken anchor bolts, bearing tilt and debonding - Need Replaced July 2023
7 fixed | bearing tilt - spalls under bearing, broken anchor bolts - major spall under bearing girder 4 Need Replaced July 2023
8 integral end bt | No problems documented
not room on cap to install jacking stiffener and jack directly from girders
District provided traffic control estimate of $18,000 - See John Sanders email 7-22-23 (Leave as is)
UPDATES 10-13-24
* Per Matt Geiger October 2024 inspection - Finger Plate support beams need repaired.
Increased traffic control for staging finger removal 10-13-24.
Include shoring towers in estimate due to condition of bearings and cap modification bent 7 if needed