## Earthwork
200 EARTHWORK CHECKLIST |  |  |  | Date:
Contractor: |  | Contract:
Route: |  | Project:
Item and Location:
Section 201 CLEARING AND GRUBBING
No. | Items |  | Yes | No | N/A
1 | Environmental clearances met and Endangered Species requirements considered.
2 | Limits agreed upon and disposal plan meets specifications.
3 | Engineer has designated all items to be preserved. (Plants, trees, shrubs, & misc.)
4 | Waste Disposal Agreement signed and copy provided to QA
5 | - HOLD POINT
6 | Roots/stumps removed and holes compacted within 10' of construction limits.
Section 202 REMOVAL OF ROADWAYS AND BUILDINGS
No. | Items |  | Yes | No | N/A
10 | Follows all specification and government regulations.
Section 203 BORROW, CLASS A EXCAVATION, and EMBANKMENT IN PLACE
No. | Items |  | Yes | No | N/A
20 | Environmental and Cultural clearances obtained, and erosion control plan established for Borrow/Excavation areas.
21 | Waste Disposal Agreement signed and copy provided to QA
22 | - HOLD POINT
23 | Borrow or Excavated material is suitable and approved for use. Free of trees, stumps, and rubbish.
24 | Proctor completed on each soil type.
25 | Initial measurements taken of site to be excavated.
26 | - HOLD POINT
27 | Daily truck counts provided to MoDOT for estimates of payment.
28 | Final measurements taken of site excavated from.
29 | Erosion Control established and applied according to Section 800.
30 | All road crossings kept clean and free of material. Dust is managed.
Section 203 CLASS C EXCAVATION, BLASTING REQUIREMENTS
No. | Items |  | Yes | No | N/A
50 | Blasting Plan submitted 14 days in advance, complies with Sec 107.7.
51 | Notification made for any road closures made 2 weeks in advance.
52 | Initial measurements taken, and quantity agreed upon by QC and QA, of the area to require Class C Excavation.
53 | - HOLD POINT
54 | Final measurements taken of Class C Excavation area.
Comments:
Section 203 COMPACTING EMBANKMENT, COMPACTING IN CUT
No. | Items |  | Yes | No | N/A
60 | Removed subgrade material to a depth of 12" below the bottom of the lowest base course in Compact in Cut areas.
61 | 6" scarification of the exposed 12" depth surface in the Compact in Cut areas.
62 | Maximum of 8" loose lift thickness in common fill areas.
63 | 8" to 12" occasional stones or rock fragments may be incorporated into embankment outside mainline limits, lifts may be increased to 12" loose in these areas.
64 | If excavated material is mostly large rock, material shall be placed according to specs in lifts as thick as the average size of the rock, not exceeding 24". (Rock Emb.)
65 | In Rock Emb. Areas, the rock will be dozed into place, not just dumped.
66 | Lifts are leveled, moisture conditioned and compacted uniformly. Shale and heavy clay will be reduced accordingly.
67 | Material is at or above Optimum Moisture (for material with Liquid Limit of 40 or above) within 5' of subgrade. Soil in a rocky fill should be in a plastic state.
68 | Periodic moisture checks performed during lift placement as needed.
69 | All compaction and density testing completed according to Specifications.
70 | Embankment not placed on or with frozen material.
71 | Section 209 Compliant (see subgrade checklist)
72 | - HOLD POINT
Section 214 ROCK FILL
No. |  |  | Yes | No | N/A
80 | Used durable stone or broken concrete with <10% earth, sand, or non durable rock.
81 | 25% of the material stone pieces will have a volume of 1.0 cubic foot or more.
82 | Maximum lift thickness is 24".
83 | Lefts are spread per 203.4.16 and compaction is performed per 203.5.
OTHER CONSIDERATIONS
90 | All Subgrade Stabilization lab testing completed (Section 205)
91 | Visual Inspection / Proof Rolling as approved by the engineer is complete for Subgrade Stabilization. (Section 205)
92 | Roadway graded to correct slopes, profiles, cross sections, etc. according to plans and cross sections.
93 | Linear Grading areas have been visually inspected. (Section 207)
94 | Interception ditches visually inspected rainfall event. (Section 208)
95 | All work complies with all specifications and requirements not listed above.
Comments:
QC Inspector Print Name: |  | QC Inspector Signature:
Company: