## Permeable Base & Rock Base
300 PERMEABLE BASE AND ROCK BASE CHECKLIST |  |  |  | Date:
Contractor: |  | Contract:
Route: |  | Project:
Item and Location:
ROADWAY SUBGRADE (18" Section)
No. | Items |  | Yes | No | N/A
1 | Existing Embankment has been accepted for use by the Earthwork Inspector. Fill more than 18" below subgrade was appropriately inspected and tested.
2 | - HOLD POINT
3 | The roadway section in common fill areas within 18" below finished subgrade meets density requirements (95% RC Standard Proctor, 1 density test per 500' of roadway)
4 | Untestable roadway subgrades (rock/rubble/soil mixes) have been compacted with roller method. (Cannot density test if >20% is retained on the 3/4" sieve.)
Section 302 PEARMEABLE BASE
No. | Items |  | Yes | No | N/A
10 | Method of placement approved and subgrade is Sec 209 and Sec 203 compliant.
11 | - HOLD POINT
12 | Constructed per plans and typical section.
13 | Correct thickness, width, locations, daylighted to drain or edge drains installed.
14 | Drainage capability is unaffected by contamination. Contaminated material removed.
15 | Asphalt permeable base: discharge temperature is 250-300 F, compaction completed before 100 F, Minimum of 3 passes with a 5 - 10 ton roller, and maximum 4" compacted layer.
16 | Cement Stabilized base: Minimize segregation, consolidate with pavement vibrators, and cure for 48 hours per Sec 502.6, and mist during cure.
17 | - HOLD POINT
Comments:
Section 303 ROCK BASE
No. | Items |  | Yes | No | N/A
30 | Method of placement approved and subgrade is Sec 209 and Sec 203 compliant.
31 | - HOLD POINT
32 | Constructed per plans and typical section.
33 | Correct thickness, width, locations, daylighted to drain or edge drains installed.
34 | Rock or broken concrete/composite less than 10% soil. No asphalt particles used, except for small amounts adhering to concrete.
35 | Correct particle size and lift thickness adhered to as stated in Sec 303.2.2, 303.2.3, and 303.3.3.
36 | All applicable provisions in Sec 203 for the handling and placement of roadway excavation material apply. Compacted in accordance with Sec 203.5.5. (Use 4 passes with a tamping roller (250 psi) or 2 passes with a Vibratory Roller (16 - 20 tons)
37 | Material is bladed or dozed in place, not dumped, with equipment routed over the entire area for each lift.
38 | The top 2" of the Rock Base section are within +/- 1/2" of plan elevation and consist of 2" maximum rock fragments,spalls, reclaimed asphalt, or concrete. The 2" max sized material has a PI of <10, and a gradation such that at least 50% of the material is retained on the #4 sieve. Reclaimed asphalt or concrete graded to meet Sec 1007.
39 | - HOLD POINT
Comments:
QC Inspector Print Name: |  | QC Inspector Signature:
Company: