## 620
620 PAVEMENT MARKING |  |  |  | Date:
Contractor: |  | Contract:
Route: |  | Project:
Item and Location:
Materials
No. | Items |  | Yes | No | N/A
1 | Do all materials meet specification and is proper documentation supplied to MoDOT? (Marking Tape, Paint, Beads, Temp. Raised Pvmt. Markers, Epoxy)
General Requirements
No. | Items |  | Yes | No | N/A
10 | Does application equipment meet the specifications for the specific material to be placed?
11 | Does the surface preparation meet the specifications for the specific material to be placed?
12 | Is pavement marking installed in accordance with manufacturer's recommendations as supplied to the engineer?
13 | Are all pavement markings uniform in appearance with crisp, well- defined edges, and uniform in width and thickness?
14 | Are surface beads uniformly distributed?
15 | Are longitudinal pavement marking placed on longitudinal joints?
16 | Has liquid pavement marking been protected until marking has reached a "no- track" state?
Permanent Pavement Markings
No. | Items |  | Yes | No | N/A
30 | Were all pavement markings in place no later than five days after final paving operations, except where marking is placed within the rumble strip?
31 | Was permanent striping in rumble strip placed no later than five days after the completion of the rumble strip?
32 | Was intermittent pavement marking started with gap, immediately after the last existing intermittent pavement marking?
33 | Were retroreflectivity measurements taken no sooner than seven days after application, and did pavement markings meet minimum retroreflectivity and visual acceptance?
34 | Were non acceptable pavement markings repaired or replaced within 30 days?
Comments:
Temporary Pavement Markings
No. | Items |  | Yes | No | N/A
40 | Were short term marking tape or temporary raised pavement markers installed on pavements undergoing milling, grinding, or resurfacing at the completion of each day's operation, or before leaving the work zone unattended?
41 | Were temporary markings and temporary raised pavement markers installed according to the specifications?
42 | Was temporary marking placed on the higher layer at the centerline of the roadway or lane when the adjacent layer of resurfacing has not been placed and the existing centerline or lane line has been obliterated?
43 | Did temporary paint meet minimum retroreflectivity and, was it maintained at minimum retroreflectivity and % stripe in place?
44 | If temporary paint was used on final pavement surface, and permanent pavement markings to be done by others, was any paint outside of the final pavement marking footprint removed?
45 | Was preformed marking tape, preformed removable marking tape, and preformed short term marking tape installed according to the manufacturers recommendations, and a copy of the installation specifications provided to the engineer?
Paint for Pavement Marking
No. | Items |  | Yes | No | N/A
50 | Did pavement surface temperatures meet the specifications?
51 | Was paint applied in accordance with the specifications?
52 | Were glass beads applied in accordance with the specifications?
Pavement Marking Removal
No. | Items |  | Yes | No | N/A
60 | Were pavement markings removed in accordance with the specifications?
Temporary Raised Pavement Markings
No. | Items |  | Yes | No | N/A
70 | Were temporary raised pavement markers installed in accordance with the specifications?
71 | Were temporary raised pavement markers removed when it was the contractors responsibility?
Comments:
QC Inspector Print Name: |  | QC Inspector Signature:
Company: