## Sheet1
701 DRILLED SHAFT CHECKLIST |  |  |  | Date:
Contractor: |  | Contract:
Route: |  | Project:
Item and Location:
Submittals and Materials
No. | Items |  | Yes | No | N/A
1 | Installation plan signed, sealed and delivered to MoDOT 30 days prior to construction?
2 | All materials documentation (rebar, roller spacers, mechanical bar splices, permanent casing, CSL tubes, slurry, etc.) meet specification?
3 | - HOLD POINT
Drilling
No. | Items |  | Yes | No | N/A
10 | Shaft locations staked and referenced?
11 | Shaft excavation within tolerances for vertical alignment and horizontal position?
12 | TV camera inspection of shaft performed and video taped?
13 | Excavated material logged?
14 | If rock socket required, were NX cores taken and meet requirements?
15 | Drilled hole free of water and/or debris?
16 | Drilled hole at proper elevation, diameter, and minimum embedment?
Casing and Slurry
No. | Items |  | Yes | No | N/A
30 | Steel casing condition and size per plan? (diameter & length)
31 | Temporary casing removed properly?
32 | Permanent casing installed to proper depth?
33 | Casing splices approved by Engineer?
34 | Slurry used is the correct type, density, viscosity, sand content, and pH?
Reinforcing Cage
No. | Items |  | Yes | No | N/A
40 | Is the rebar the correct sizes and configured per plan.
41 | Is the rebar properly tied?
42 | Are necessary splices constructed per specification?
43 | Are proper spacers and amount installed per specification?
44 | Proper number of CSL tubes installed per plan?
45 | Steel cage adequately supported and checked for final bottom and side clearances?
46 | Top elevation of reinforcing cage checked?
47 | - HOLD POINT
Comments:
Concrete Placement
No. | Items |  | Yes | No | N/A
60 | Concrete mix design and class to be used are correct and approved for the project?
61 | CSL tubes filled with water prior to pour
62 | Information on the concrete batch ticket indicates conformance with mix design and specifications?
63 | If dry method, is drop chute used with free fall less than 80 ft?
64 | If wet method, is tremie used and discharge end kept immersed in concrete no less than 5 ft. at all times?
65 | Concrete sampled and tested per Section 501?
66 | Concrete placement continuous and within time limitations?
67 | Concrete dropped straight down without striking side walls?
68 | Joints per plan and rebar continuous through joint?
69 | Concrete expelled at least 18" above pour line?
70 | Finished concrete true to design grade and elevation?
71 | Concrete cured per Section 502?
72 | - HOLD POINT
Post Concrete Placement
No. | Items |  | Yes | No | N/A
80 | Final location of projecting reinforcing steel has been checked in all directions including splice length?
81 | Projecting steel adequately cleaned?
82 | Cross-hole sonic logging (CSL) performed per specification?
83 | Shafts with poor CSL results cored and filled per specification?
84 | If required, load tests performed per specification?
Drilled Shaft Summary
No. | Items |  | Yes | No | N/A
90 | Were the materials tested at the required frequency?
91 | Did this work meet the project specifications?
Comments:
QC Inspector Print Name: |  | QC Inspector Signature:
Company: