## Sheet1
703 CONCRETE MASONRY CONSTRUCTION (STRUCTURES) CHECKLIST |  |  |  | Date:
Contractor: |  | Contract:
Route: |  | Project:
Item and Location:
Materials
No. | Items |  | Yes | No | N/A
1 | All materials (reinforcing steel, forms, ties, supports, curing compound, etc.) meet specifications?
Formwork
No. | Items |  | Yes | No | N/A
10 | Forms mortar tight and sufficiently rigid to prevent excessive deflections?
11 | Forms of sound material and designed to remain true to shape?
12 | Forms present a smooth surface and joints align properly?
13 | Forms are correct dimension and elevation?
14 | Inside of forms cleaned of dirt, mortar, and foreign materials?
15 | Dirt, chips, sawdust, water, and other foreign material removed from within forms?
17 | Forms lubricated to ensure removal?
Reinforcing Steel
No. | Items |  | Yes | No | N/A
30 | Bars proper size, length, grade, and epoxy coated as required?
31 | Proper number and spacing of bars?
32 | Proper procedures followed for field bending or cutting of bars?
33 | If cut, epoxy bar ends coated with approved material?
34 | Does reinforcement have required clearance or depth of cover from surface of concrete?
35 | Mechanical bar splices appropriate length for size and type of bar?
36 | Supports and ties plastic or epoxy coated as required?
37 | All bars tied at intersections or as required?
38 | Bar splices correct length?
39 | Bar placement, clearance, and tying checked?
40 | All bars clean and free of oil, dirt, and rust?
41 | - HOLD POINT
Comments:
Concrete Placing and Curing
No. | Items |  | Yes | No | N/A
50 | Concrete mix design and class to be used are correct and approved for the project?
51 | Reinforcing steel checked and approved prior to concrete placement?
52 | Construction joints cleaned?
53 | Drainage and weep holes at proper location and elevation?
54 | Does ambient temperature for placing concrete meet specifications?
55 | Vibrators have a minimum frequency 0f 4500 impulses/minute?
56 | - HOLD POINT
57 | Information on the concrete batch ticket indicates conformance with mix design and specifications?
58 | Concrete sampled and tested per section 501?
59 | Concrete placed continuously to prevent cold joints?
60 | Concrete placed to avoid segregation?
61 | Concrete consolidated properly?
62 | If tremie or bucket used was free fall drop < 5ft?
63 | Joints constructed per locations on plans?
64 | Reinforcing dowels required in adjacent concrete?
65 | Proper finishing methods performed?
66 | Forms removed after concrete reaches minimum strength?
67 | Proper curing method performed?
68 | Approved curing compound applied at proper rate?
Concrete (Structures) Summary
No. | Items |  | Yes | No | N/A
80 | Were the materials tested at the required frequency?
81 | Did this work meet the project specifications?
Comments:
QC Inspector Print Name: |  | QC Inspector Signature:
Company: