## Sheet1
712 STRUCTURAL STEEL CHECKLIST (Turn of Nut Method) |  |  |  | Date:
Contractor: |  | Contract:
Route: |  | Project:
Item and Location:
Material and Documentation
No. | Items |  | Yes | No | N/A
1 | All materials and documentation meet specifications?
2 | All material parts correct size and shape per shop drawings?
3 | Field welders certification and qualifications comply with specifications?
4 | Welding procedures submitted for review prior to welding?
5 | - HOLD POINT
Structural Steel Erection
No. | Items |  | Yes | No | N/A
10 | Erection sequence per approved erection plan and drawings?
11 | Fit-up pins properly supported to maintain camber?
12 | Specified ratio of pins to bolts checked?
13 | Bearings correct type, dimensions, and configuration per plan?
14 | Ground splices completed and tightened, per Erection Plan, prior to erection?
15 | If required, field welding performed in accordance with specifications?
16 | Shear studs installed per plan?
Anchor Bolt Installation
No. | Items |  | Yes | No | N/A
30 | Anchor Bolts correct type, dimensions and configuration per plan?
31 | Anchor Bolt wells set per plan?
32 | Anchor Bolts set in wells or drilled holes and grouted per specification?
Bolt Pre-Installation
No. | Items |  | Yes | No | N/A
40 | Material properly stored and protected from weather?
41 | Material checked for damage during entire process?
42 | Nuts for coated high-strength bolts lubricated with a visible water-soluble lubricant?
43 | Nuts for un-coated high-strength bolts lubricated with a visible water-soluble lubricant that is oily to touch?
44 | Rotational-Capacity testing device and torque wrenches have up to date calibrations?
45 | Rotational-Capacity testing performed on each assembly lot (bolt, nut, washer) prior to bolt installation?
46 | Field Rotational-Capacity values compared to manufacturer's values?
47 | - HOLD POINT
Comments:
Bolt Installation using Turn-of Nut Method
No. | Items |  | Yes | No | N/A
60 | Joint and all fasteners snug tightened from most rigid part to the free edges?
61 | Bolt tensioning performed only after assemblies have been snug tightened?
62 | Fasteners tightened to at least minimum bolt tension requirements per size and grade?
63 | After snug tightening has each bolt and nut been marked so that the required turn can be verified?
64 | Is the unturned part being prevented from turning?
65 | If impact wrenches used, are they of sufficient capacity to perform the required tightening of each bolt in approximately 10 seconds.
66 | All bolts in joint tightened from most rigid part to the free edges?
67 | Are all bolts being tightened additionally by the applicable nut rotation specified in the requirements?
68 | Installation and tightening of bolt assemblies observed by Engineer?
69 | Inspecting torque wrench and bolt tension calibration device used to verify tightening procedure?
70 | Torque inspection performed on 5 bolt assemblies per lot/per wrench?
71 | Torque verification performed at random on a minimum of 10% of bolts/connection, but no less than 2 bolts/connection?
72 | Fit-up bolts that were damaged or used to pull splices together, and were intended to be used for permanent have been replaced?
Field Coating (Painting)
No. | Items |  | Yes | No | N/A
80 | Field coating in accordance with Section 1081 specifications?
Structural Steel Summary
No. | Items |  | Yes | No | N/A
90 | Were the materials tested at the required frequency?
91 | Did this work meet the project specifications?
Comments:
QC Inspector Print Name: |  | QC Inspector Signature:
Company: