## Memo
Draft Bridge Memorandum
| Job No.: | J5I3000 |  |  | Bridge No.: |  |  | L09624
| County: | Boone-Cooper |  |  | Rte.: | I-70 (Major) over Missouri River
| Final Layout: |  | U.I.P. & Rehab Existing (84'-105'-84')(84'-105'-84')(84'-105'-84')(218.25'-242.5'-218.25') Continuous Composite Plate Girder Spans (550'-550') Continuous Truss Spans (124'-155'-124') Continuous Composite Plate Girder Spans
| Roadway Width: |  | 2 @ 29'-2" plus 2-16" Safety Barrier Curbs & 1-2' Type C Median Barrier Curb
| Alignment: |  | Tangent
| Skew: |  | Square
| Grade: |  | Match existing±
| Loading: |  | HS20-44 (1955), HS20-44 (Alternate Military) (1989 & new construction)
| Beg. Station: |  | Sta. 1474+38.05± (match existing) at Fill Face of End Bent 1
| Traffic Handling: |  | See stage construction attachment for staging. Reduce to one lane each way during expansion joint replacement and painting since no access from under bridge.
| Existing Bridge: |  | Rehab L09624 and use in place.
GENERAL NOTES:
- | Condition Rating: Deck = 6, Superstructure = 5, Substructure = 5
- | AADT 2016 = 36,931 AADT truck = 24% = 8,864
- | AADT 2036 = 66,475 AADT truck = 24% = 15,954
- | Recoat with System H (Gray) as follows: 10' each way from CL expansion joint at Bent 1, 4, 7, 10, 13, 15, & 18. All structural steel in the truss from the top of piers to 16' above the top of slab (no overhead painting, vertical members only).
- | Remove existing expansion device and concrete 1' to fill face and 18" away from front face at bent 1 & 18.
- | Install 3" strip seal expansion joint system at bent 1 & 18.
- | Remove existing expansion device and concrete 3' each way from CL joint at bent 4, 7, & 10.
- | Install finger plate expansion device at bent 4, 7, & 10.
- | Remove existing expansion device and concrete 4' each way from CL joint at bent 13 & 15.
- | Install finger plate expansion device at bent 13 & 15.
- | Remove existing expansion device and concrete 18" each way from CL joint at L4, L8, L12, L16, L19, L19', L16', L12', L8' & L4'.
- | Install 3" strip seal expansion joint system at L4, L8, L12, L16, L19, L19', L16', L12', L8' & L4'.
- | Remove and replace safety barrier curb and type c barrier curb within limits mentioned above for expansion jts.
- | Install thrie beam rail on type c median barrier curb at all open joints to protect traffic from open gap in median barrier curb.
- | Estimate 25 lf of safety barrier curb repair (10' South side near Bent 11) (noted 9/24/2013), (5' South side East of L4') (noted 8/28/2017) and (10' N side near L13) (noted 8/24/2015).
- | Replace navigation lighting system. Include remote monitoring system with access platforms and tie offs. See A0585 for example.
- | Remove Raised Pavement Markers (estimate 160). Includes those on the bridge, bridge approach slabs and roadway concrete approach pavements.
- | Estimate 10,000 deteriorated, loose or missing rivets/bolts to be replaced with high strength bolts. Pack rust separation of plates exceeds 0.5", replace rivet with high strength bolts.
- | Remove pack rust and shim saddle bearings as required at L4, L8, L12, L16, L19, L19', L16', L12', L8' & L4' (9 each L point, total = 90).
- | Provide harness tie off bar on side with saddle bearings of the floor beams of the truss.
- | Reset Pier 15 (span 15-16) bearings.
- | Remove loose and deteriorated concrete and pour beam 6" wider each side and 3' down along edge at bent 4, 7, 10, 13 & 15.
- | Estimate 400 sf of substructure repair (formed). 200 sf - bent 1, 200 sf - bent 18.
- | Replace missing sole plate bolts at Abut 1 & 18 bearings.
- | Clean and heavily seal beam cap at bent 1, 4, 7, 10, 13, 14, 15, and 18 with protective coating - concrete bents and piers (urethane).
- | Repair 5 (half width is 1) floor beams at Pier 7 (Span 6), Bent 4 (Span 3), bent 10 (Span 9).
- | Estimate 15 L or L' locations with interior and exterior vertical gusset plates needing repaired (Interior & exterior 1 unit): L4R Interior and Exterior, L12L Interior & exterior, L14L Interior and exterior, L16R&L Interior and exterior, L18R interior and exterior, L18'R interior & exterior, L16'L&R Interior & exterior, etc.
- | Estimate 10 lateral bracing gussets needing replaced. Cost of rivets replacement included in Rivet Replacement. L3 Center, L11' Center, L7' Center, L3' Center
- | Estimate 15 stringer floorbeam connection repair. L16'-L16' Stringer 9, L15'-L14' @ L14' stringer 9, L14'-L13' @ L13' stringer 9, L13'-L12' @ L12 stringer 9, L11'-Lxx' Stringer 1, L9'-L8' @ L8' Stringer 9, L7'-L6' @ L6' Stringer 9,
- | Estimate 12 stringer stiffeners repairs at floorbeam. L4-L5@ L4 Stringer 9 (2), L8-L9@L8 Stringer 5, L8'-L9'@L8' Stringer 1, L4'-L5'@L4' Stringer 1 & 4,
- | Estimate 20 floorbeam stiffeners repairs: L5' 2nd from L5'L, L12' between stringer 4&5, L12' stringer 5 saddle supports (2), L12' between stringer 5&6, L0 Stringer 9 Stringer Supports (3), L16' between stringer 8&9
- | Estimate 3 stringer splice repairs. L0 stringer 9.
- | Estimate 10 Stringer web/bottom repair: L4L5 Stringer 4@ L4, L12' Stringer 8 & 9
- | Extend slab drains below chords.
- | Apply Methyl Methacrylate (MMA) deck treatment to deck, bridge approach slabs and concrete approach pavement surface. Requires a BSP.
SPECIAL NOTES:
Blue - Changes in Fall/Winter 2016 Estimate Update
Green - Changes in Fall/Winter 2017 Estimate Update
District Contact Mike Dusenberg, TPM (573) 751-7699.
Bridge Division Contact Dean Franke, SPM (573) 526-0246
| Estimated timeline: Early Feb notice to proceed to Friday before Thanksgiving completion date: |  |  | FY'19 Programmed Bridge Amount: |  |  |  |  | 10193000
|  |  |  | FY'19 Programmed Project Amount: |  |  |  |  | 12207000
| Estimated Expansion Joint and Painting Working/Calendar Days for Staging: | [7 empty] | 140/215
| Construction Estimate for FY'19: | [7 empty] | 12585000
Does not include inflation from Planning (3% compounded annually)
| Bridge: | [5 empty] | Date:
Structural Project Manager
| District: | [5 empty] | Date:
Transporation Project Manager
| District: | [5 empty] | Date:
District Bridge Engineer

## Estimate
2018-01-03
Cost Estimate for Rehabilitation of:
I-70 (Major) over Missouri River
County: Boone-Cooper
Bridge No. L09624
Job No. J5I3000
FY'19 Estimate: | [8 empty] | 12585000
Listing of Items | Quantities | [10 empty] | Unit | Cost/ Unit | Item Cost
Removal of Expansion Joint and Adj Concrete | 60.3333 | x | 3 | [6 empty] | = | 181 | lf | 325 | 58825
Bent 4, 7 & 10
Removal of Expansion Joint and Adj Concrete | 60.3333 | x | 2 | [6 empty] | = | 120.6667 | lf | 325 | 39216.6667
Bent 13 & 15
Removal of Expansion Joint and Adj Concrete | 60.3333 | x | 2 | [6 empty] | = | 120.6667 | lf | 325 | 39216.6667
Bent 1 & 18
Removal of Expansion Joint and Adj Concrete | 60.3333 | x | 10 | [6 empty] | = | 603.3333 | lf | 325 | 196083.3333
L4, L8, L12, L16, L19, L19', L16', L12', L8' & L4'
Expansion Device (Finger Plate) | 60.3333 | x | 3 | [6 empty] | = | 181 | lf | 1700 | 307700
Bent 4, 7 & 10
Expansion Device (Finger Plate) | 60.3333 | x | 2 | [6 empty] | = | 120.6667 | lf | 2125 | 256416.6667
Bent 13 & 15
Strip Seal Expansion Joint System | 60.3333 | x | 2 | [6 empty] | = | 120.6667 | lf | 300 | 36200
Bent 1 & 18
Strip Seal Expansion Joint System | 60.3333 | x | 10 | [6 empty] | = | 603.3333 | lf | 300 | 181000
L4, L8, L12, L16, L19, L19', L16', L12', L8' & L4'
Remove and Replace Safety Barrier Curb | 9.3333 | + | 34.6667 | + | 29.5 | + | 56.6667 | + | 25 | = | 155.1667 | lf | 500 | 77583.3333
(includes repairing SBC) | 1&18 |  | 4,7,10 |  | 13&15 |  | Ls&L's |  | Repairs
Remove and Replace Type C Barrier Curb | 4.6667 | + | 17.3333 | + | 14.75 | + | 28.3333 |  |  | = | 65.0833 | lf | 500 | 32541.6667
| 1&18 |  | 4,7,10 |  | 13&15 |  | Ls&L's
Thrie Beam Rail | 100 | + | 192 | + | 144 | + | 520 |  |  | = | 956 | lf | 240 | 229440
=(Gap+10')*2 rows*2 sides*# locations
Class B-2 Concrete - Expansion Joints | [8 empty] | 101.5202 | = | 101.5202 | cy | 2800 | 284256.5706
Bent 1 & 18 | 4.6667 | x | 63 | x | 0.79167 | / | 27 | = | 8.6204
Bent 4, 7 & 10 | 13 | x | 63 | x | 0.79167 | / | 27 | = | 24.0139
Bent 13 & 15 | 8.9583 | x | 63 | x | 0.79167 | / | 27 | = | 16.548
L4, L8, L12, L16, L19, L19', L16', L12', L8' & L4' | 28.3333 | x | 63 | x | 0.79167 | / | 27 | = | 52.338
Reinforcing Steel (Epoxy Coated) | [9 empty] | = | 12182.4245 | lb | 2.4 | 29237.8187
Navigiation Lighting System | [9 empty] | = | 1 | ls | 120000 | 120000
Removal of Raised Pavement Markers | [9 empty] | = | 160 | ea | 150 | 24000
Replace Loose or Missing Rivets | [9 empty] | = | 10000 | ea | 30 | 300000
Shim Saddle Bearings (Rehabilitate Bearings) | [9 empty] | = | 90 | ea | 7000 | 630000
Harness Tie Off @ Saddle Brg Floorbeams | [9 empty] | = | 10 | ea | 2000 | 20000
Rehabilitate Bearings | [9 empty] | = | 3 | ea | 5000 | 15000
Substructure Repair (Formed) | [9 empty] | = | 400 | sf | 140 | 56000
Replacing Sole Plate Bolts | [9 empty] | = | 12 | ea | 200 | 2400
Repair Gusset Plates | [9 empty] | = | 15 | ea | 25000 | 375000
Replace Lateral Gusset Plates | [9 empty] | = | 12 | ea | 5000 | 60000
Slab Drain Extensions | [9 empty] | = | 626 | ea | 250 | 156500
Floor Beam Flange Repair | 108 | x | 21.375 | x | 6 |  |  |  |  | = | 13900 | lb | 15 | 208500
Stringer Floorbeam Connection Repair | [9 empty] | = | 15 | ea | 4000 | 60000
Stringer Stiffeners Repairs | [9 empty] | = | 12 | ea | 500 | 6000
Floorbeam Stiffeners Repairs | [9 empty] | = | 20 | ea | 500 | 10000
Stringer Splice Repair | [9 empty] | = | 3 | ea | 2000 | 6000
Stringer Web/Bottom Repair | [9 empty] | = | 10 | ea | 2500 | 25000
Class B-2 Concrete - Beam Caps | [8 empty] | 313.749 | = | 313.749 | cy | 3200 | 1003996.8764
bent 4 & 7 - sides | 476.667 | x | 1 | x | 4 | / | 27 |  | 70.6173
ends | 28.0555 | x | 1 | x | 4 | / | 27 |  | 4.1564
bent 10 - sides | 602.6667 | x | 1 | x | 2 | / | 27 |  | 44.642
ends | 45.5002 | x | 1 | x | 2 | / | 27 |  | 3.3704
bent 13 & 15 - sides | 1184 | x | 1 | x | 4 | / | 27 |  | 175.4074
ends | 105 | x | 1 | x | 4 | / | 27 |  | 15.5556
Reinforcing Steel (Epoxy Coated) | [9 empty] | = | 47062.3536 | lb | 2.4 | 112949.6486
Methyl Methacrylate (MMA) Deck Treatment | 3128.3438 | x | 58.3333 | / | 9 |  |  |  |  | = | 20276.3047 | sy | 45 | 912433.7126
Stage Conctruction Cost | 5871497.9602 | x | 15% | [6 empty] | = | 1 | ls | 880724.694 | 880724.694
Protective Coating - Concrete Bents & | 1694 | + | 2374 | + | 1300 | + | 6372 | + | 3588 | = | 15328 | sf | 16 | 245248
Piers (Urethane) | bt4&7 |  | bt10 |  | bt13&15 |  | Bt14 |  | Bt1&18
PG 10' each way Expansion Joint Recoat | 133.2671 | tons | [13 empty] | 6997470.6543
Surface Prep. For Recoating Structural Steel | [9 empty] | = | 18000 | sf | 30 | 540000 | 719820 | 5587098.5
Field Application of Inorganic Zinc Primer | [9 empty] | = | 18000 | sf | 4 | 72000
Intermediate Field Coat (System G) | [9 empty] | = | 18000 | sf | 2.995 | 53910
Finish Field Coat (System G) | [9 empty] | = | 18000 | sf | 2.995 | 53910
16' ht Splash Zone-Under Slab Truss Recoat | 2028.852 | tons
Surface Prep. For Recoating Structural Steel | [9 empty] | = | 304300 | sf | 9.995 | 3041478.5 | 4867278.5
Field Application of Inorganic Zinc Primer | [9 empty] | = | 304300 | sf | 2 | 608600
Intermediate Field Coat (System G) | [9 empty] | = | 304300 | sf | 2 | 608600
Finish Field Coat (System G) | [9 empty] | = | 304300 | sf | 2 | 608600
Complete Plate Girder Recoat | 2554.41 | tons
Surface Prep. For Recoating Structural Steel | 344845.35 |  | 17991.0552 | [8 empty] | sf
0.052171
Complete Truss Recoat | 3381.42 | tons
Surface Prep. For Recoating Structural Steel | 507213 | [10 empty] | sf

## Working Days
Br. No. | L09624 | County: | Boone-Cooper |  |  | Date: | 2018-12-11 12:36
Job No. | J5I3000 |  |  |  |  | Name: | Franke
WORKING DAYS:
Bridge Removal: |  |  |  | SF | @ | 1000 | SF/day | =
Prebore: |  |  |  | LF | @ | 130 | LF/day | =
Substructure Excavation: |  |  |  | CY | @ | 69 | CY/day | =
Drive Piling: |  |  |  | LF | @ | 320 | LF/day | =
Intermediate Bent (3 column): |  |  |  | bents | @ | 8 | days/each | =
Rock Sockets: |  |  |  | LF | @ | 18 | LF/day | =
Drilled Shafts: |  |  |  | LF | @ | 25 | LF/day | =
End Bents: |  |  |  | bents | @ | 5 | days/each | =
P/S I-Girder Erection: |  |  |  | spans | @ | 1.5 | days/span | =
Structural Steel Erection: |  |  |  | lbs | @ | 390000 | lbs/day | =
Structural Deck Concrete: |  |  |  | CY | @ | 275 | CY/day | =
P/S Panel Erection: |  |  |  | spans | @ | 1.4 | days/span | =
Reinforcing Steel (Substr): |  |  |  | lbs | @ | 4000 | lbs/day | =
Reinforcing Steel (Super): |  |  |  | lbs | @ | 6200 | lbs/day | =
Total Superstructure (Steel): |  |  |  | spans | @ | 10.2 | days/span | =
Total Superstructure (PSI): |  |  |  | spans | @ | 7.7 | days/span | =
Safety Barrier Curb: |  |  | 220.25 | LF | @ | 17.6471 | LF/day | = | 12.4808 | days
Bridge Approach Slab: |  |  |  | slabs | @ | 4 | days/each | =
Painting: |  |  |  | SF | @ | 730 | SF/day | =
Mill Deck (1/4 "): |  |  |  | SF | @ | 6500 | SF/day | =
Hydro Demolition: |  |  |  | SF | @ | 400 | SF/day | =
Remove Bridge Deck: |  |  |  | SF | @ | 1875 | SF/day | =
Asphalt Overlay: |  |  |  | SF | @ | 8000 | SF/day | =
Low Slump Overlay: |  |  |  | SYD | @ | 1300 | SYD/day | =
Polymer Concrete Overlay: |  |  | 182486.7425 | SF | @ | 12900 | SF/day | = | 14.1463 | days
Expansion Joint Replacement: |  |  | 1025.6667 | LF | @ | 15 | LF/day | = | 68.3778 | days
Replace or Widen Deck: |  |  |  | SF | @ | 450 | SF/day | =
Half - Sole Repair: |  |  |  | SF | @ | 200 | SF/day | =
Full Depth Repair: |  |  |  | SF | @ | 78 | SF/day | =
Slab Edge Repair: |  |  |  | LF | @ | 43 | LF/day | =
Unformed Substr Repair: |  |  |  | SF | @ | 53 | SF/day | =
Unformed Super Repair: |  |  |  | SF | @ | 60 | SF/day | =
Clean and Repaint Steel: |  |  |  | SF | @ | 1800 | SF/day | =
MSE Wall: |  |  |  | SF | @ | 800 | SF/day | =
[8 empty] | Sum = | 95.0049 | days
[7 empty] | Staged Calendar Days = |  | 95 | days
[7 empty] | Staged Working Days = |  | 60 | days

## Painting Area
J5I3000 | Br. No. | L09624
Plate Girder Paint Quantities |  |  | Wide Flange Beam Paint Quantities |  |  | Wide Flange Beam Paint Quantities
| Inches | feet | W21x62 | Inches | feet | W30x108 | Inches | feet
d = | 59.25 | 4.9375 | d = | 20.99 | 1.7492 | d = | 29.83 | 2.4858
tw = | 0.375 | 0.03125 | tw = | 0.4 | 0.033333 | tw = | 0.4 | 0.033333
bf = | 12.375 | 1.0312 | bf = | 8.24 | 0.68667 | bf = | 8.24 | 0.68667
thick bott = | 0.625 | 0.052083 | tf = | 0.615 | 0.05125 | tf = | 0.615 | 0.05125
tf = | 18 | 1.5 | [6 empty] | Use 135 sf per ton.
thick top = | 1.25 | 0.10417
| Web bothsides |  |  | Web bothsides |  |  | Web bothsides
9.875 | ft. |  | 3.2933 | ft. |  | 4.7667 | ft.
| bottom flange (top, bott., and sides) |  |  | bottom flange (top, bott., and sides) |  |  | bottom flange (top, bott., and sides)
2.1354 | ft. |  | 1.4425 | ft. |  | 1.4425 | ft.
| Top flange (bottom and sides) |  |  | Top flange (bottom and sides) |  |  | Top flange (bottom and sides)
1.6771 | ft. |  | 0.75583 | ft. |  | 0.75583 | ft.
Ratio lengths.
| Length of Girder |  |  | Length of Girder |  |  | Length of Girder
60 | ft. |  | 60 | ft. |  | 42.75 | ft.
| Number of Girders |  |  | Number of Girders |  |  | Number of Girders
3 |  |  | 6 |  |  | 6
| Total surface area to be painted |  |  | Total surface area to be painted |  |  | Total surface area to be painted
2463.75 | sq. ft. |  | 1977 | sq. ft. |  | 1786.5225 | sq. ft.
Plate Girder Paint Quantities |  |  | Wide Flange Beam Paint Quantities |  |  | Wide Flange Beam Paint Quantities
| Inches | feet | W21x73 | Inches | feet | W30x116 | Inches | feet
d = | 119 | 9.9167 | d = | 21.24 | 1.77 | d = | 30.01 | 2.5008
tw = | 0.5 | 0.041667 | tw = | 0.455 | 0.037917 | tw = | 0.565 | 0.047083
bf = | 20 | 1.6667 | bf = | 8.295 | 0.69125 | bf = | 10.495 | 0.87458
thick bott = | 1.5 | 0.125 | tf = | 0.74 | 0.061667 | tf = | 0.85 | 0.070833
tf = | 20 | 1.6667
thick top = | 1.5 | 0.125
| Web bothsides |  |  | Web bothsides |  |  | Web bothsides
19.8333 | ft. |  | 3.2933 | ft. |  | 4.7183 | ft.
| bottom flange (top, bott., and sides) |  |  | bottom flange (top, bott., and sides) |  |  | bottom flange (top, bott., and sides)
3.5417 | ft. |  | 1.4679 | ft. |  | 1.8437 | ft.
| Top flange (bottom and sides) |  |  | Top flange (bottom and sides) |  |  | Top flange (bottom and sides)
1.875 | ft. |  | 0.77667 | ft. |  | 0.96917 | ft.
| Length of Girder |  |  | Length of Girder |  |  | Length of Girder
20 | ft. |  | 20 | ft. |  | 42.75 | ft.
| Number of Girders |  |  | Number of Girders |  |  | Number of Girders
3 |  |  | 6 |  |  | 2
| Total surface area to be painted |  |  | Total surface area to be painted |  |  | Total surface area to be painted
1515 | sq. ft. |  | 664.55 | sq. ft. |  | 643.9219 | sq. ft.
Plate Girder Paint Quantities |  |  | Wide Flange Beam Paint Quantities |  |  | Wide Flange Beam Paint Quantities
| Inches | feet | W21x73 | Inches | feet | W30x116 | Inches | feet
d = | 65 | 5.4167 | d = | 21.24 | 1.77 | d = | 30.01 | 2.5008
tw = | 0.375 | 0.03125 | tw = | 0.455 | 0.037917 | tw = | 0.565 | 0.047083
bf = | 16.375 | 1.3646 | bf = | 8.295 | 0.69125 | bf = | 10.495 | 0.87458
thick bott = | 0.75 | 0.0625 | tf = | 0.74 | 0.061667 | tf = | 0.85 | 0.070833
tf = | 20 | 1.6667
thick top = | 1.5 | 0.125
| Web bothsides |  |  | Web bothsides |  |  | Web bothsides
10.8333 | ft. |  | 3.2933 | ft. |  | 4.7183 | ft.
| bottom flange (top, bott., and sides) |  |  | bottom flange (top, bott., and sides) |  |  | bottom flange (top, bott., and sides)
2.8229 | ft. |  | 1.4679 | ft. |  | 1.8437 | ft.
| Top flange (bottom and sides) |  |  | Top flange (bottom and sides) |  |  | Top flange (bottom and sides)
1.8854 | ft. |  | 0.77667 | ft. |  | 0.96917 | ft.
| Length of Girder |  |  | Length of Girder |  |  | Length of Girder
20 | ft. |  | 20 | ft. |  | 42.75 | ft.
| Number of Girders |  |  | Number of Girders |  |  | Number of Girders
3 |  |  | 6 |  |  | 2
| Total surface area to be painted |  |  | Total surface area to be painted |  |  | Total surface area to be painted
932.5 | sq. ft. |  | 664.55 | sq. ft. |  | 643.9219 | sq. ft.
Total
11291.7162 | sq.ft.

## PG Painting Working Days
Bridge No. | L09624 |  |  | Boone-Cooper | County |  |  | Franke |  |  | Date 12/11/2018
Working Days and Estimating Quantities for Recoating Structural Steel (Plate Girder)
Input
|  | Wide Flange Bridge | [5 empty] | Surface Preparation for Recoating = | 18000 | ft^2
|  | Bridge Width = | 63 |  |  |  |  | Inorganic Zinc Primer = | 18000 | ft^2
|  | Tons of steel = | 133.2666 |  |  |  |  | Intermediate Field Coat = | 18000 | ft^2
|  | Girder/Stringer Depth = | 5.0938 |  |  |  |  | Finish Field Coat = | 18000 | ft^2
10.1667
5.6042
|  | Length to be Painted = | 60
20
20
Pay Items
Surface Preparation for Recoating Structural Steel
1) Install Work Platform (if necessary)
|  |  | Length = | 60 | Width = | 63 |  |  | Area = | 3780 | ft^2
|  |  | Length = | 20 | Width = | 63 |  |  | Area = | 1260 | ft^2
|  |  | Length = | 20 | Width = | 63 |  |  | Area = | 1260 | ft^2
[9 empty] | Total Area = | 6300 | ft^2
|  |  |  | Number of platfoms = | 1 |  | Rate = 1/day |  | 1 | Working Days
2) Installing Sand Blasting Containment
|  |  | Length = | 60 | Width = | 63 | Height = | 9.0938 | # sides = | 2 | # ends = | 12
|  |  | Length = | 20 | Width = | 63 | Height = | 14.1667 | # sides = | 2 | # ends = | 4
|  |  | Length = | 20 | Width = | 63 | Height = | 9.6042 | # sides = | 2 | # ends = | 4
|  |  | Needs top ? | No |  | Needs bottom ? | Yes |  | Area = | 11746.125 | ft^2
|  |  | Needs top ? | No |  | Needs bottom ? | Yes |  | Area = | 5396.6667 | ft^2
|  |  | Needs top ? | No |  | Needs bottom ? | Yes |  | Area = | 4064.4167 | ft^2
[9 empty] | Total Area = | 21207.2083 | ft^2
|  |  |  | Base Production Rate = | 1000 | sf/day |  | Rate Change = | 100%
|  |  |  | Production Rate = | 1000 | sf/day |  |  | 21.2072 | Working Days
[9 empty] | 21 | Working Days
3) Disposal of Hazardous Waste
|  |  |  | Waste Fraction = | 0.075 | ton/ton of steel |  |  | Weight = | 9.995 | tons
|  |  |  | Production Rate = | 2 per 15 | tons |  |  | 2 | Working Days
3) SSPC-SP10 Surface Preparation
[9 empty] | Area = | 18000 | ft^2
|  |  |  | Production Rate = | 1000 | sf/day |  |  | 18 | Working Days
[9 empty] | 18 | Working Days
Inorganic Zinc Primer
[9 empty] | Area = | 18000 | ft^2
|  |  |  | Production Rate = | 1800 | sf/day |  |  | 10 | Working Days
[9 empty] | 10 | Working Days
Intermediate Field Coat
[9 empty] | Area = | 18000 | ft^2
|  |  |  | Production Rate = | 1800 | sf/day |  |  | 10 | Working Days
[9 empty] | 10 | Working Days
Finish Field Coat
[9 empty] | Area = | 18000 | ft^2
|  |  |  | Production Rate = | 1800 | sf/day |  |  | 10 | Working Days
[9 empty] | 10 | Working Days
[9 empty] | 0.5*85% of Total Working Days = | 30.6
Note on E15: alderj1: Total Length to be painted
Note on F27: alderj1: Length to be painted, may increase from bent to bent for Safe Span
Note on F28: alderj1: Length to be painted, may increase from bent to bent for Safe Span
Note on F29: alderj1: Length to be painted, may increase from bent to bent for Safe Span
Note on J35: alderj1: Girder/Stringer Depth +4'
Note on N35: alderj1: Based on staging, ends of joint areas, etc.
Note on J36: alderj1: Girder/Stringer Depth +4'
Note on N36: alderj1: Based on staging, ends of joint areas, etc.
Note on J37: alderj1: Girder/Stringer Depth +4'
Note on N37: alderj1: Based on staging, ends of joint areas, etc.
Note on L79: alderj1: Does not include waste disposal

## Truss Painting Working Days
Bridge No. | L09624 |  |  | Boone-Cooper | County |  |  | Franke |  |  | Date 12/11/2018
Working Days and Estimating Quantities for Recoating Structural Steel (Truss)
Input
|  | Wide Flange Bridge | [5 empty] | Surface Preparation for Recoating = | 304300 | ft^2
|  | Bridge Width = | 67.5 |  |  |  |  | Inorganic Zinc Primer = | 304300 | ft^2
|  | Tons of steel = | 2028.84 |  |  |  |  | Intermediate Field Coat = | 304300 | ft^2
|  | Girder/Stringer Depth = | 17.8333 |  |  |  |  | Finish Field Coat = | 304300 | ft^2
|  | Length to be Painted = | 1101.5834
Pay Items
Surface Preparation for Recoating Structural Steel
1) Install Work Platform (if necessary)
|  |  | Length = | 1101.5834 | Width = | 77.5 |  |  | Area = | 85372.7135 | ft^2
|  |  |  | Number of platfoms = | 1 |  | Rate = 1/day |  | 1 | Working Days
2) Installing Sand Blasting Containment
|  |  | Length = | 1101.5834 | Width = | 67.5 | Height = | 21.8333 | # sides = | 2 | # ends = | 2
|  |  | Needs top ? | Yes |  | Needs bottom ? | Yes |  | Area = | 199763.7263 | ft^2
|  |  |  | Base Production Rate = | 1000 | sf/day |  | Rate Change = | 1000%
|  |  |  | Production Rate = | 10000 | sf/day |  |  | 19.9764 | Working Days
[9 empty] | 19.9764 | Working Days
3) Disposal of Hazardous Waste
|  |  |  | Waste Fraction = | 0.075 | ton/ton of steel |  |  | Weight = | 152.163 | tons
|  |  |  | Production Rate = | 2 per 15 | tons |  |  | 22 | Working Days
3) SSPC-SP10 Surface Preparation
[9 empty] | Area = | 304300 | ft^2
|  |  |  | Production Rate = | 10000 | sf/day |  |  | 30.43 | Working Days
[9 empty] | 30.43 | Working Days
Inorganic Zinc Primer
[9 empty] | Area = | 304300 | ft^2
|  |  |  | Production Rate = | 18000 | sf/day |  |  | 16.9056 | Working Days
[9 empty] | 16.9056 | Working Days
Intermediate Field Coat
[9 empty] | Area = | 304300 | ft^2
|  |  |  | Production Rate = | 18000 | sf/day |  |  | 16.9056 | Working Days
[9 empty] | 16.9056 | Working Days
Finish Field Coat
[9 empty] | Area = | 304300 | ft^2
|  |  |  | Production Rate = | 18000 | sf/day |  |  | 16.9056 | Working Days
[9 empty] | 16.9056 | Working Days
[9 empty] | 85% of Total Working Days = | 90.1
Note on E13: alderj1: Total Length to be painted
Note on F23: alderj1: Length to be painted, may increase from bent to bent for Safe Span
Note on J28: alderj1: Girder/Stringer Depth +4'
Note on N28: alderj1: Based on staging, ends of joint areas, etc.
Note on L67: alderj1: Does not include waste disposal