**EXHIBIT IV**

**PERIOD OF SERVICE**

The Consultant shall make submittals in accordance with the schedule described below.

NTP - July 15, 2021

Preliminary Stage Request for Environmental Services by 09/10/21

Preliminary Road Plans Submitted for Review by 09/10/21

Preliminary Road Plans for Approval by 10/10/21

Public Meeting Exhibits by 10/10/21

Bridge Memo by 09/10/21

Request for Soundings by 09/10/21

Right of Way Stage Request for Environmental Services by 10/10/21

Right of Way Plans Submitted for Review by 10/10/21 (if needed)

Right of Way Plans for Approval by 11/01/21 (If needed)

Type Size and Location Bridge Drawings 03/01/22

Final Stage Request for Environmental Services by 08/01/22

100% Review Plans by 09-01-22

Final Signed and Sealed Bridge Plans and Roadway Plans, Job Special Provisions, Final Construction Estimate, Working Day Study, D-12 Form and remaining PS&E documents by October 1, 2022. The anticipated letting is January 2023.

PERIOD OF SERVICE – The total period of service including construction services is expected to be completed by April 1, 2024.