**EXHIBIT IV**

**PERIOD OF SERVICE**

The Consultant shall make submittals in accordance with the schedule described below.

Preliminary Stage Request for Environmental Services by January 14, 2022

Preliminary Road Plans Submitted for Review by February 15, 2022

Preliminary Road Plans for Approval by March 15, 2022

Public Meeting Exhibits by March 15, 2022

Bridge Memo by March 15, 2022

Request for Soundings by March 15, 2022

Right of Way Stage Request for Environmental Services by April 1, 2022

Right of Way Plans Submitted for Review by May 2, 2022 (if needed)

Right of Way Plans for Approval by June 1, 2022 (If needed)

Type Size and Location Bridge Drawings by June 17, 2022

Final Stage Request for Environmental Services by January 2, 2023

100% Review Plans by February 1, 2023

Final Signed and Sealed Bridge Plans and Roadway Plans, Job Special Provisions, Final Construction Estimate, Working Day Study, D-12 Form and remaining PS&E documents by April 3, 2023. The anticipated letting is August 2023.

PERIOD OF SERVICE – The total period of service including construction services is expected to be completed by November 1, 2024.