**EXHIBIT IV**

**PERIOD OF SERVICE**

The Consultant shall make submittals in accordance with the schedule described below.

Complete Bridge Inspection by July 31, 2020

Inspection Findings & Report by August 21, 2020 (The consultant is to notify MoDOT immediately of any critical findings)

Rehabilitation recommendations (Bridge Memo) and estimate by September 25, 2020

Inspection recommendations by September 25, 2020

100% Review Plans December 11, 2020

Final Signed and Sealed Bridge Plans and Roadway Plans, Job Special Provisions, Final Construction Estimate, Working Day Study, D-12 Form and remaining PS&E documents by January 8, 2021.

PERIOD OF SERVICE – The anticipated letting is June 2021. The total period of service including construction services is expected to be completed by September 30, 2023.