**EXHIBIT IV**

**PERIOD OF SERVICE**

The Consultant shall make submittals in accordance with the schedule described below.

NTP by 07/23/21

Preliminary Stage Request for Environmental Services by 09/23/21

Preliminary Road Plans Submitted for Review by 09/23/21

Preliminary Road Plans for Approval by 10/13/21

Public Meeting Exhibits by 10/13/21

Bridge Memo by 09/23/21

Request for Soundings by 09/23/21

Right of Way Stage Request for Environmental Services by 12/01/21

Right of Way Plans Submitted for Review by 12/01/21

Right of Way Plans for Approval by 12/29/21

Type Size and Location Bridge Drawings 12/01/21

Final Stage Request for Environmental Services by 07/13/22

100% Review Plans by 09/09/22

Final Signed and Sealed Bridge Plans and Roadway Plans, Job Special Provisions, Final Construction Estimate, Working Day Study, D-12 Form and remaining PS&E documents by October 7, 2022. Letting is anticipated for Feb. 2023.

PERIOD OF SERVICE – The total period of service including construction services is expected to be completed by December 1, 2024.