**EXHIBIT IV**

**PERIOD OF SERVICE**

The Consultant shall make submittals in accordance with the schedule described below.

Preliminary Stage Request for Environmental Services by 09/01/22

Preliminary Road Plans Submitted for Review by 09/01/22

Preliminary Road Plans for Approval by 09/01/22

Public Meeting Exhibits by 09/01/22

Bridge Memo by 09/01/22

Request for Soundings by 09/01/22

Right of Way Stage Request for Environmental Services by 12/08/22

Right of Way Plans Submitted for Review by 12/01/22

Right of Way Plans for Approval by 12/08/22 (If needed)

Type Size and Location Bridge Drawings 4 weeks after receipt of Foundation Investigation

Final Stage Request for Environmental Services by 08/01/23

100% Review Plans by 08/01/23

Final Signed and Sealed Bridge Plans and Roadway Plans, Job Special Provisions, Final Construction Estimate, Working Day Study, D-12 Form and remaining PS&E documents by October 1, 2023.

PERIOD OF SERVICE – The total period of service including construction services is expected to be completed by December 1, 2025.