EXHIBIT IV

PERIOD OF SERVICE

The Consultant shall make submittals in accordance with the schedule described below.

Preliminary Stage Request for Environmental Services by 10/5/2022

Preliminary Road Plans Submitted for Review by 10/5/22

Preliminary Road Plans for Approval by 10/12/22

Public Meeting Exhibits by 10/19/22

Bridge Memo by 10/19/22

Request for Soundings by 10/19/22

Right of Way Stage Request for Environmental Services by 11/30/22

Right of Way Plans Submitted for Review by 11/30/22

Right of Way Plans for Approval by 12/07/22

Type Size and Location Bridge Drawings 01/04/23

Final Stage Request for Environmental Services by 04/03/23

100% Review Plans by 06/07/23

Final Signed and Sealed Bridge Plans and Roadway Plans, Job Special Provisions, Final Construction Estimate, Working Day Study, D-12 Form and remaining PS&E documents by July 5, 2023.

PERIOD OF SERVICE – The total period of service including construction services is expected to be completed by February 1, 2025.