**EXHIBIT IV**

**PERIOD OF SERVICE**

The Consultant shall make submittals in accordance with the schedule described below.

Preliminary Stage Request for Environmental Services by 06/01/21

Preliminary Road Plans Submitted for Review by 06/01/21

Preliminary Road Plans for Approval by 06/01/21

Public Meeting Exhibits by 06/01/21

Bridge Memo by 07/09/21

Request for Soundings by 07/09/21

Right of Way Stage Request for Environmental Services by 08/09/21

Right of Way Plans Submitted for Review by 08/02/21

Right of Way Plans for Approval by 08/02/21 (If needed)

Type Size and Location Bridge Drawings 10/29/21

Final Stage Request for Environmental Services by 10/29/22

100% Review Plans by 01/07/22

Final Signed and Sealed Bridge Plans and Roadway Plans, Job Special Provisions, Final Construction Estimate, Working Day Study, D-12 Form and remaining PS&E documents by February 1, 2022.

PERIOD OF SERVICE – The total period of service including construction services is expected to be completed by December 1, 2024.